## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-011 - Type 1 Rock Beaching | itp |  |  |  |  | ITP-011 - Type 1 Rock Beaching
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Materials
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Prior to the commencement of work, the Contractor shall nominate the source of the proposed materials, supply specified test results and provide a representative sample for approval by the Superintendent.
label | ○ Rock for Type 1 beaching shall consist of field or quarry rock. The rocks shall be uniform in colour.
label | ○ All rocks shall have a mass of between 20kg and 70kg and at least 60% by number shall be over 40kg. Rocks shall be of such size that the layer of beaching is not less than 225mm thick.
label | REFERENCE DOCUMENTS: 713.03
label | INSPECTION/TEST METHOD: Test certificates, material data sheets and health and safety data sheets
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Submission of Safety Documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: The completed job safety assessment and the Safe Work Method Statement shall be submitted to the Superintendent for review.
label | REFERENCE DOCUMENTS: 713.05
label | INSPECTION/TEST METHOD: Job Safety Sheet, SWMS
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Preparation of Underlying Surface
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Surface compacted and trimmed to design levels. Scours filled with Class 4 crushed rock. No loose or soft spots.
label | REFERENCE DOCUMENTS: Sec713.04
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.2 - Geotextile Placement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Nonwoven geotextile (>250 g/m²) laid evenly, buried 300 mm at edges, overlapped 300–500 mm, no folds or kinks.
label | REFERENCE DOCUMENTS: Sec713.03(b)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.3 - Placement of Type 1 Beaching
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Rocks placed mechanically (≥12 kg), tightly interlocked, gaps ≤60 mm average, surface deviation ≤100 mm over 3 m straight edge.
label | REFERENCE DOCUMENTS: Sec713.05
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.4 - Toe Wall Construction
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Toe walls 600 mm x 600 mm, lined with geotextile, filled with hand-packed rock and smaller stones in voids.
label | REFERENCE DOCUMENTS: Sec713.07
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.5 - Topsoil Filling
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Voids filled to mid-height with topsoil. Where planting is required, topsoil flush with rock surface and adjacent ground.
label | REFERENCE DOCUMENTS: Sec713.05(b)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-012 - Anti-Graffiti Protection | itp |  |  |  |  | ITP-012 - Anti-Graffiti Protection
section | 1 - Anti-Graffiti Protection
checkpoint | 1.1 - Submission of materials and procedures
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Superintendent must review and accept proposed coatings, removers, methods, and equipment. Evidence of product performance and test results (≤24 months old) must be provided.
label | REFERENCE DOCUMENTS: Sec685 5.doc – Clause 685.04
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Approved submission
label | HP
label | RESPONSIBILITY: Contractor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Trial application of coating
label | FREQUENCY: 7 days before full-scale works
label | ACCEPTANCE CRITERIA: Coating must meet performance criteria: adhesion, thickness, appearance, and environmental compliance. Superintendent must approve trial outcome.
label | REFERENCE DOCUMENTS: Sec685 5.doc – Clause 685.11
label | INSPECTION/TEST METHOD: Visual inspection and test panel
label | RECORD OF CONFORMITY: Trial report
label | HP
label | RESPONSIBILITY: Contractor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Surface preparation
label | FREQUENCY: Before coating
label | ACCEPTANCE CRITERIA: Surface must be free of graffiti, shadows, contaminants, and curing membranes. Must meet AS 1627.1 and AS 1627.4 standards.
label | REFERENCE DOCUMENTS: Sec685 5.doc – Clause 685.05
label | INSPECTION/TEST METHOD: Visual inspection, solvent wash
label | RECORD OF CONFORMITY: Preparation checklist
label | WP
label | RESPONSIBILITY: Contractor / Site Supervisor
date | Date Completed:
checkpoint | 1.4 - Environmental condition monitoring
label | FREQUENCY: Every 4 hours during application
label | ACCEPTANCE CRITERIA: Ambient temp: 10–35°C, RH ≤85%, substrate dry and ≥3°C above dew point. No windborne debris or rain spatter.
label | REFERENCE DOCUMENTS: Sec685 5.doc – Clause 685.09
label | INSPECTION/TEST METHOD: Hygrometer / psychrometer readings
label | RECORD OF CONFORMITY: Environmental log
label | IP
label | RESPONSIBILITY: Contractor / Site Supervisor
date | Date Completed:
checkpoint | 1.5 - Application of anti-graffiti coating
label | FREQUENCY: During works
label | ACCEPTANCE CRITERIA: Coating must be smooth, uniform, defect-free, and meet WFT ≥175 µm, DFT ≥100 µm. Must be compatible, UV-resistant, and impermeable to water, CO₂, and acid rain.
label | REFERENCE DOCUMENTS: Sec685 5.doc – Clause 685.07
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: Coating records
label | WP
label | RESPONSIBILITY: Contractor / Site Supervisor
date | Date Completed:
checkpoint | 1.6 - Testing of coating (bond strength, WFT, DFT, penetration)
label | FREQUENCY: Per 50 m²
label | ACCEPTANCE CRITERIA: Bond strength >0.75 MPa (AS 1580.408.5), WFT ≥175 µm (ASTM D4414), DFT ≥100 µm (AS 1580.108.2). Penetration must meet manufacturer specs.
label | REFERENCE DOCUMENTS: Sec685 5.doc – Clause 685.12
label | INSPECTION/TEST METHOD: NATA lab testing
label | RECORD OF CONFORMITY: Test reports
label | TP
label | RESPONSIBILITY: Contractor / NATA Lab
date | Date Completed:
checkpoint | 1.7 - Graffiti removal (maintenance or construction)
label | FREQUENCY: As required (within 24–48 hrs)
label | ACCEPTANCE CRITERIA: No visible markings on coated surfaces. Uncoated surfaces may retain shadows if not intelligible. Sensitive graffiti removed within 24 hrs.
label | REFERENCE DOCUMENTS: Sec685 5.doc – Clause 685.18–19
label | INSPECTION/TEST METHOD: Approved cleaning methods
label | RECORD OF CONFORMITY: Removal report with photos
label | WP
label | RESPONSIBILITY: Contractor / Site Supervisor
date | Date Completed:
checkpoint | 1.8 - Coating repairs and reinstatement
label | FREQUENCY: As needed
label | ACCEPTANCE CRITERIA: Repairs must restore original spec. Causes include yellowing, adhesion loss, colour change, graffiti penetration.
label | REFERENCE DOCUMENTS: Sec685 5.doc – Clause 685.14–15
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: Repair records
label | WP
label | RESPONSIBILITY: Contractor / Superintendent
date | Date Completed:
checkpoint | 1.9 - Final inspection and documentation
label | FREQUENCY: At completion
label | ACCEPTANCE CRITERIA: All records complete. Coating meets spec for appearance, thickness, adhesion, and durability.
label | REFERENCE DOCUMENTS: Sec685 5.doc – Clause 685.13
label | INSPECTION/TEST METHOD: Inspection checklist
label | RECORD OF CONFORMITY: Final report
label | SCP
label | RESPONSIBILITY: Contractor / Superintendent
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-013 - Fencing Installation | itp |  |  |  |  | ITP-013 - Fencing Installation
section | 1 - Preliminary Works
checkpoint | 1.1 - Service locating prior to excavation or post installation
label | FREQUENCY: Before any ground disturbance
label | ACCEPTANCE CRITERIA: All underground services identified and marked; clearance obtained from relevant authorities
label | REFERENCE DOCUMENTS: Dial Before You Dig records, utility maps, project drawings, GPP
label | INSPECTION/TEST METHOD: Visual confirmation of markings; review of service location reports
label | RECORD OF CONFORMITY: Service location report; clearance documentation
label | HP
label | RESPONSIBILITY: Foreman / Contractor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Supply of tubular steel posts and rails
label | FREQUENCY: Each delivery
label | ACCEPTANCE CRITERIA: Steel complies with AS 1074, AS/NZS 1163, AS 1397 or AS 1450; yield strength ≥ 195 MPa
label | REFERENCE DOCUMENTS: Sec707 - Tubular Steel Posts, Rails and Stays
label | INSPECTION/TEST METHOD: Material certification and visual inspection
label | RECORD OF CONFORMITY: Material certificates
label | IP
label | RESPONSIBILITY: Contractor
date | Date Completed:
checkpoint | 1.3 - Galvanizing of steel components
label | FREQUENCY: Each batch
label | ACCEPTANCE CRITERIA: Hot dipped galvanized to AS/NZS 4680 or pre-galvanized to AS 1397 Z275
label | REFERENCE DOCUMENTS: Sec707 - Tubular Steel Posts, Rails and Stays
label | INSPECTION/TEST METHOD: Visual inspection and coating thickness verification
label | RECORD OF CONFORMITY: Galvanizing certificate
label | IP
label | RESPONSIBILITY: Contractor
date | Date Completed:
checkpoint | 1.4 - Repair of damaged galvanized coating
label | FREQUENCY: As required
label | ACCEPTANCE CRITERIA: Repaired using organic zinc-rich primer to AS 3750.9
label | REFERENCE DOCUMENTS: Sec707 - Tubular Steel Posts, Rails and Stays
label | INSPECTION/TEST METHOD: Visual inspection and primer application check
label | RECORD OF CONFORMITY: Repair log
label | IP
label | RESPONSIBILITY: Contractor
date | Date Completed:
section | 2 - Installation
checkpoint | 2.1 - Installation of posts in concrete footings
label | FREQUENCY: Each installation
label | ACCEPTANCE CRITERIA: Footings comply with N20 concrete grade and specified dimensions
label | REFERENCE DOCUMENTS: Sec707 - Steel Post and Welded Mesh Fences
label | INSPECTION/TEST METHOD: Site inspection and measurement
label | RECORD OF CONFORMITY: Installation checklist
label | TP
label | RESPONSIBILITY: Contractor
date | Date Completed:
checkpoint | 2.2 - Attachment of welded mesh panels
label | FREQUENCY: Each installation
label | ACCEPTANCE CRITERIA: Panels securely fixed with galvanized fittings
label | REFERENCE DOCUMENTS: Sec707 - Steel Post and Welded Mesh Fences
label | INSPECTION/TEST METHOD: Visual inspection and fitting verification
label | RECORD OF CONFORMITY: Inspection report
label | IP
label | RESPONSIBILITY: Contractor
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Submission of Certificate of Compliance
label | FREQUENCY: Prior to use
label | ACCEPTANCE CRITERIA: Certificate includes relevant test reports and product certification
label | REFERENCE DOCUMENTS: Sec707 - Certificate of Compliance
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Certificate of Compliance
label | IP
label | RESPONSIBILITY: Contractor
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-014 - Linemarking Works | itp |  |  |  |  | ITP-014 - Linemarking Works
section | 1 - Construction Works
checkpoint | 1.1 - Redundant Linemarking Removal
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Where removal of unsuitable pavement marking is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
label | REFERENCE DOCUMENTS: Vicroads Spec.721.A12
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent / Contractor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Surface Preperation
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Surface clean, dry, and dust free before application
label | REFERENCE DOCUMENTS: Vicroads Spec.721.A06
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer / Foreman
date | Date Completed:
checkpoint | 1.3 - Linemarking and RRPM set out
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless an exemption has been granted in writing by the Superintendent
label | REFERENCE DOCUMENTS: Vicroads Spec.721.B05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer/Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Linemarking Installation
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Thickness per spec (≤2.0mm for thermoplastic), reflectivity to AS 1742.
label | REFERENCE DOCUMENTS: Vicroads Spec.720.07
label | INSPECTION/TEST METHOD: Visual inspectioon, dry film thickness check, reflectivity.
label | RECORD OF CONFORMITY: Thickness guage, luminance/reflectivity test records.
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - RRPM installation
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Correct colour, spacing, aligned with edges/centrelines.
label | REFERENCE DOCUMENTS: Relevant EMP
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: RRPM placement log with spacings and colour coding noted.
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Completion insoection - Linemarking & RRPMs
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Works complete, complient, free from defects, overspray or misaligned markings.
label | REFERENCE DOCUMENTS: Relevant EMP
label | INSPECTION/TEST METHOD: Joint inspections with superintendent
label | RECORD OF CONFORMITY: Final sign off form, defect rectification log if neededn
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-015 - Guardfence Installation | itp |  |  |  |  | ITP-015 - Guardfence Installation Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
label | REFERENCE DOCUMENTS: Design Drawings & Drawings Register
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Materials
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All materials are to be used must be on VicRoads current accepted products list (RDN06-04) and confirm with the detailed design.
label | ○ The contractor shall submit to the Superintendent all test certificates related to the supply of steel for the works at least 14 days prior to commencement of installation.
label | REFERENCE DOCUMENTS: VR Section 708.04 & 708.05
label | INSPECTION/TEST METHOD: HP
label | RECORD OF CONFORMITY: ITP Signed, Certificate of Materials
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Identification of Services
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure any locations have been identified and marked on site. Ensure any approvals are in place with service providers prior to commencing install.
label | REFERENCE DOCUMENTS: DBYD
label | INSPECTION/TEST METHOD: Witness Point
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Setout
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Contractor to confirm with the superintendent the required location and length of all guard fence alignments.
label | REFERENCE DOCUMENTS: Design Drawings, VR Section 708.08
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/MRPV Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Installation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Guard fence system to be installed in accordance with design drawings, manufacturer guidelines, and within tolerances set out in VicRoads Standard Section 708.07 (d).
label | REFERENCE DOCUMENTS: Design Drawings, Manufacturer Guidelines, VR Section 708.07.
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.5 - End Treatments
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed in accordance with design drawings, manufacturer guidelines, and specifications.
label | REFERENCE DOCUMENTS: Design Drawings, Manufacturer Guidelines, VR Section 708.07.
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.6 - Installation of Delineators
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Contractor to supply and fasten delineators on left hand side (red) and right-hand side (yellow).
label | REFERENCE DOCUMENTS: VR Section 708.07
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
section | 3 - Testing and Quality Control
checkpoint | 3.1 - Submission of Certificate of Compliance (CoC)
label | FREQUENCY: Upon completion of install
label | ACCEPTANCE CRITERIA: Contractor to submit the CoC to the Superintended from guard fence supplier.
label | REFERENCE DOCUMENTS: VR Section 708
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: ITP Signed
label | TP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 3.2 - Submission of Material Test Certificate
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Contractor to submit test certificate to superintendent from guard fence supplier.
label | REFERENCE DOCUMENTS: VR Section 708
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: ITP Signed
label | TP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-016 - Road Signage Installation | itp |  |  |  |  | ITP-016 - Road Signage Installation
section | 1 - Preliminary Works
checkpoint | 1.1 - Inductions
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the CRG Site.
label | REFERENCE DOCUMENTS: PMP Inductions Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction card
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | HP*
label | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
date | Date Completed:
checkpoint | 1.3 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: IFC Project Drawings/ Drawing Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest revision IFC drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: EMP, Site induction
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Traffic Management (When required)
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Approved TMP and MOA
label | REFERENCE DOCUMENTS: Applicable TMP no.:
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Approved TMP & MOA
label | AP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.1 - Service Proving
label | FREQUENCY: Prior to commencing install
label | ACCEPTANCE CRITERIA: All underground services must be located, proven and clearly marked prior to any excavations, stripping, clearing and grubbing or any other type of ground penetration including boring for off-structure barrier piles and driving barrier posts.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.700.1, GPP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer / Foreman
date | Date Completed:
section | 2 - Roadside Signage Install
checkpoint | 2.1 - Set out posts and foundations
label | FREQUENCY: Prior to commencing install
label | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.714.06
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Consent to proceed by Superintendent OR written exemption granted, This ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Material compliance
label | FREQUENCY: Prior to commencing install
label | ACCEPTANCE CRITERIA: All road Signing must comply with the Technical References including the requirements of section 860 of the VicRoads Standard Specification Sections for Roadworks and Bridgeworks.
label | REFERENCE DOCUMENTS: VicRoads Specification 860
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Material compliance, This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Installation method
label | FREQUENCY: Once per lot
label | ACCEPTANCE CRITERIA: The sign installation shall be as described in the sign schedule and as shown on the contract drawings.
label | REFERENCE DOCUMENTS: VicRoads Specification 714.04 & 07
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Installation tolerances
label | FREQUENCY: After completion of works
label | ACCEPTANCE CRITERIA: Verify signs were installed to tolerances stated in VicRoads Sec. 714.05
label | REFERENCE DOCUMENTS: VicRoads Specification 714.05
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Photos, This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-017 - Landscaping | itp |  |  |  |  | ITP-017 - Landscaping
section | 1 - Preliminary Works
checkpoint | 1.1 - Supply of plant stock and materials
label | FREQUENCY: Each delivery
label | ACCEPTANCE CRITERIA: Complies with AS 2303 and VR 720
label | REFERENCE DOCUMENTS: Sec720.03 & Sec720.04
label | INSPECTION/TEST METHOD: Visual inspection; certification review
label | RECORD OF CONFORMITY: Inspections, samples & records as per 720.03, 720.04
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.2 - Site ripping, topsoil application, and cultivation verification
label | FREQUENCY: Before mulching or planting
label | ACCEPTANCE CRITERIA: Ripping depth, topsoil depth, and cultivation meet specifications outlined in table 720.071
label | REFERENCE DOCUMENTS: Sec720.07(b)-(e)
label | INSPECTION/TEST METHOD: Site inspection; visual inspection
label | RECORD OF CONFORMITY: Superintendent signature
label | HP, WP
label | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Planting of trees and shrubs
label | FREQUENCY: Each planting event
label | ACCEPTANCE CRITERIA: Planting holes, staking, and watering meet specification
label | REFERENCE DOCUMENTS: Sec720.09
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Photographic evidence
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Grassing with Type 1 and Type 2 seed
label | FREQUENCY: Each sowing event
label | ACCEPTANCE CRITERIA: Seed mix, sowing rate, and fertilising meet specification
label | REFERENCE DOCUMENTS: Sec720.10
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: Photographic evidence
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Landscape maintenance
label | FREQUENCY: Ongoing during defect liability period
label | ACCEPTANCE CRITERIA: Accepted maintenance program, joint inspections carried out and plant performance is in accordance with Sec720.11
label | REFERENCE DOCUMENTS: Sec720.11
label | INSPECTION/TEST METHOD: Routine inspections; performance verification
label | RECORD OF CONFORMITY: Maintenance program; quarterly joint inspections
label | IP, WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-022 - Bridge Deck Waterproofing | itp |  |  |  |  | ITP-022 - Bridge Deck Waterproofing
section | 1 - Preliminary Works
checkpoint | 1.1 - Material Conformity
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Waterproofing works shall not take place until the Contractor's proposed materials and procedures and surface preparation in accordance with clause 691.08 have been reviewed and accepted by the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Spec.691.04
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Work Method Statement, ITPs, Test Plans
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: The Contractor shall not proceed with the trial system application or the permanent waterproofing membrane system installation works until the WMS and ITPs have been reviewed and approved by the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Spec.691.25
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Trial Application
label | FREQUENCY: Prior to full scale waterproofing works
label | ACCEPTANCE CRITERIA: The Contractor shall not proceed with the full scale waterproofing works until the trial waterproofing membrane application has been carried out and the outcomes reviewed and approved by the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Spec.691.16
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Application
label | FREQUENCY: During application
label | ACCEPTANCE CRITERIA: No spray application of liquid applied membrane shall be carried out within ten (10) metres of buildings, footpaths, roadways, pedestrians or vehicles without protective measures or methods being used which shall be submitted to the Superintendent for approval, a minimum of two working days in advance of the proposed works.
label | REFERENCE DOCUMENTS: VicRoads Spec.691.26
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-020 - Construction of Bridge Expansion Joints | itp |  |  |  |  | ITP-020 - Construction of Bridge Expansion Joints
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Engineer/ Works Supervisor
date | Date Completed:
checkpoint | 1.2 - Materials
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: The Contractor shall submit proposals for joints and their installation (including items (b) to (f) listed below) to the Superintendent for review within four weeks of acceptance of tender
label | ○ The Contractor shall supply all expansion joint components including joints, seals, inserts, anchorages, cover plates, waterproofing membrane, drainage system, bedding mortar, nosing, edging and all adhesives and sealants required for the installation of the joint system in conformity with the supplier’s recommendations
label | REFERENCE DOCUMENTS: Design Drawings, VR Section 660
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Engineer/ Works Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Alternative Designs
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: If an alternative bridge expansion joint is proposed it shall be designed in accordance with Bridge Technical Note 1999 002 Design of deck joints for road bridges, in conjunction with the requirements of the AS 5100, the Australian Standard for bridge design.
label | ○ The Contractor shall submit proposals for joints and their installation (including items (b) to (f) listed in 660.03) to the Superintendent for review within four weeks of acceptance of tender.
label | REFERENCE DOCUMENTS: VR Section 660.03
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Engineer/ Works Supervisor
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Joint Installation
label | FREQUENCY: Prior to install
label | ACCEPTANCE CRITERIA: Expansion joint gaps shall be designed and dimensioned for installation at a mean temperature of 20C.
label | ○ In the event that the ambient temperature differs from 20C by more than 5C, it may be necessary to vary the joint gap. The Contractor shall seek a direction from the Superintendent and shall vary the joint-gap if required
label | REFERENCE DOCUMENTS: VR Section 660
label | INSPECTION/TEST METHOD: Temperature reading taken
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/Superintendent
date | Date Completed:
checkpoint | 2.2 - Installation Tolerances
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The following tolerances shall apply to joint installation:
label | (a) joint gap +-3 mm
label | (b) deviation from plan alignment 5 mm maximum over the total length of the joint
label | (c) the top surface of the joint shall be level with the adjacent road surface with a tolerance of 0 to -2 mm when measured with a 2.5 m straight edge at 90º to the joint
label | REFERENCE DOCUMENTS: VR Section 660.04
label | INSPECTION/TEST METHOD: Visual Inspection / measurement taken
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Supervisor
date | Date Completed:
checkpoint | 2.3 - Pre-pour inspection
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Prior to casting deck concrete, the Contractor shall ensure that there is no conflict between the joint anchors, the deck reinforcement and any embedment. Where conflict does occur, the Contractor shall submit proposals for resolving the conflict to the Superintendent.
label | ○ Ensure the completion of the Inspection Test Checklist (ITC) by the designated Precast Concrete Surveillance Officer.
label | REFERENCE DOCUMENTS: VR Section 660.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, ITC Complete
label | HP*
label | RESPONSIBILITY: Project Engineer/ Supervisor
date | Date Completed:
checkpoint | 2.4 - Post Concreting Inspection
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: After concreting and prior to installation of the joint seal, the vertical face of the concrete under the full length of the joint shall be inspected for the presence of voids and other imperfections. If voids are discovered, the Contractor shall remove the affected section of the joint to enable a full inspection of the concrete and shall submit proposals for repair to the Superintendent.
label | ○ Following completion of the joint assembly and tensioning of all anchor bolts, the full length of the joint shall be tested by tapping with a hammer. Should any part of the joint exhibit a hollow-ring or movement, the affected length shall be removed and re-bedded and all bolts replaced and re-tensioned. If the concrete under the joint is found to have voids or other imperfections or any of the anchor bolts are not properly restrained, the Contractor shall submit proposals for repair to the Superintendent.
label | REFERENCE DOCUMENTS: VR Section 660.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Supervisor / Contractor
date | Date Completed:
checkpoint | 2.5 - Tensioining Anchor Bolts
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Not later than two weeks prior to installation of the bridge joint, the Contractor shall submit proposals for tightening of anchor bolts to the Superintendent.
label | ○ The Contractor shall supply a copy of the torque-wrench calibration certificate to the Superintendent on request.
label | ○ Anchor bolt tensioning records shall be maintained by the Contractor and supplied to the Superintendent on completion of installation.
label | ○ If the required tension cannot be achieved, the Contractor shall submit proposals to the Superintendent for rectification of the defect.
label | REFERENCE DOCUMENTS: VR Section 660.04
label | INSPECTION/TEST METHOD: Data Record
label | RECORD OF CONFORMITY: ITP Signed, Record of Data
label | HP
label | RESPONSIBILITY: Project Engineer/ Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Compression Seals, Inserts and membranes
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Compression seals, inserts and membranes shall be installed in one continuous piece for the full length of the joint including footpaths and barriers.
label | ○ If seals are bonded to the nosing, the surface shall be prepared and primed and the adhesives placed in accordance with the supplier’s recommendations.
label | ○ Completed joints shall be watertight.
label | REFERENCE DOCUMENTS: VR Section 660.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Supervisor / Superintendent
date | Date Completed:
checkpoint | 2.7 - Trafficking of Joints During Construction
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: If the joint or any of its component parts is damaged during construction, the Contractor shall repair the damage to the satisfaction of the Superintendent or replace the joint.
label | REFERENCE DOCUMENTS: VR Section 660.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Supervisor
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-021 - Fabrication of Super-T Beam | itp |  |  |  |  | ITP-021 - Fabrication of Super-T Beam
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Engineer/ Works Supervisor
date | Date Completed:
checkpoint | 1.2 - Materials
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure correct concrete mix being used in accordance with design drawings and specifications.
label | ○ Approved Mix: V75V26AL
label | ○ Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS.
label | ○ The Contractor shall submit the following for the material in each coil of wire or strand:
label | — test certificates for tensile testing
label | — load-extension graphs together with:
label | — the manufacturer's certificate of compliance of the tendon material with the Australian Standard a stress-relaxation test certificate for material taken from the same production facility and of the same type of material as that proposed for use in the works (stress relaxation-test certificates for similar tendons produced within the calendar year prior to the proposed use will be accepted) to the Superintendent at least seven days prior to the delivery of the coil or lot to its place of use.
label | REFERENCE DOCUMENTS: Design Drawings, VR Section 620
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Material Data Sheets.
label | HP*
label | RESPONSIBILITY: Engineer/ Works Supervisor
date | Date Completed:
checkpoint | 1.3 - Calibration of Prestressing Equipment
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: The Contractor shall maintain current calibration certificates conforming to the requirements of AS 2193 Grade B for the jack and pressure gauges or other force measuring devices. Jacks and pressure gauges and other devices shall be calibrated and used as a single unit. Calibration to AS 2193 shall be carried out by a laboratory that is NATA-accredited for that method, and at the appropriate force range.
label | REFERENCE DOCUMENTS: VR Section 622.06
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed, Calibration Certificates
label | HP*
label | RESPONSIBILITY: Engineer/ Works Supervisor
date | Date Completed:
checkpoint | 1.4 - Submission of proposed method of transfer of prestress
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure submission of the details of the proposed method of transfer of prestress to the Superintendent for review.
label | REFERENCE DOCUMENTS: VR Section 622.08
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Notification of stressing operations
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: The Superintendent shall be given seven days notice of stressing operations.
label | ○ All stressing operations shall take place in the presence of the designated Precast Concrete Surveillance Officer.
label | REFERENCE DOCUMENTS: VR Section 622.06
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Forms
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Forms shall be manufacutred from steel, except where otherwise approved by the Superintendent.
label | ○ The formwork shall be constucted to as to produce a product in accordance with the design drawings, and with the surface finish and tolerances specified in Section 610.
label | ○ Casting bed to be inspected by designated Precast Concrete Surveillance Officer.
label | REFERENCE DOCUMENTS: Design Drawings , VR Section 620, 610.
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.2 - Stressing operations
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All stressing operations shall take place in the presence of the designated Precast Concrete Surveillance Officer.
label | REFERENCE DOCUMENTS: VR Section 622.06
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Supervisor
date | Date Completed:
checkpoint | 2.3 - Pre-pour inspection
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure the completion of the Inspection Test Checklist (ITC) by the designated Precast Concrete Surveillance Officer.
label | REFERENCE DOCUMENTS: VR Section 622.06
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, ITC Complete
label | HP*
label | RESPONSIBILITY: Project Engineer/ Supervisor
date | Date Completed:
checkpoint | 2.4 - Data to be recorded
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure the following data is recorded and forwarded to the Superintendent prior to delivery of the pre-stressed units to the site:
label | ○ ID No. of each unit
label | ○ ID No. of prestressing equipment
label | ○ Calibration certificates for prestressing equipment
label | ○ ID No. for each tendon
label | ○ Sag take-up force:
label | ○ Elongation at take-up force:
label | ○ Obtained elongation at completion of tensioning:
label | ○ Obtained tendon force at completion of tensioning:
label | ○ Elongation after release of jack:
label | ○ Tendon pull-in:
label | ○ Compressive strength of concrete at time of transfer of prestress:
label | ○ Steam curing charts
label | ○ Hog measure following transfer of prestress:
label | REFERENCE DOCUMENTS: VR Section 622.09
label | INSPECTION/TEST METHOD: Data Record
label | RECORD OF CONFORMITY: ITP Signed, Record of Data
label | HP
label | RESPONSIBILITY: Project Engineer/ Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Projecting reinforcement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure projecting reinforcement is in accordance with that shown on the design drawings and is in good condition.
label | REFERENCE DOCUMENTS: VR Section 620.03
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.6 - Marking
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure the identification number, date of casting, the manufacturuers name or registered mark and the maximum mass shall be marked on every precast unit.
label | REFERENCE DOCUMENTS: VR Section 620.06
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed / Certificate of Compliance - Formwork Inspection
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.7 - Handling & Storage
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The units shall be supported on bearers clear of the ground. Bearers shall support the units over their full width and be placed perpendicular to the longitudinal axis of the unit.
label | REFERENCE DOCUMENTS: VR Section 620.07
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.8 - Transporting
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Units shall not be transported from the precast yard until specified 28 day concrete compressive strength has been achieved, and not before 7 days after casting.
label | ○ No beam shall be transported and erected if it has a bow in excess of 1 in 400 of the length or 75mm whichever is the lesser. Should the bow at any time exceed the maximum allowable limit steps shall be taken to ensure the safety of the unit throughout the journey.
label | REFERENCE DOCUMENTS: VR Section 610.14
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed, Concrete Test Reports
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP