## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-311-STR-Elastomeric Bearings (Supply & Installation)
ITP Description: |  | Elastomeric Bearings (Supply & Installation)
Discipline (e.g. CIV/STR/RAIL: |  | 311-STR
Revision Number: |  | 1
Revision Date: |  | 2025-08-12
ITP created by: |  | Manwel Kalyana
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Hopkins only
Inspection & Test Plan - Elastomeric Bearings (Supply & Installation)
[9 empty] | Revision: | 1
[9 empty] | Date: | 2025-08-12
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 610 November 2018 VicRoads Section 610 June 2019 VicRoads Section 620 May 2009 VicRoads Section 622 November 2018 VicRoads Section 652 June 2010 VicRoads Section 656 June 2010 VicRoads Section 653 April 2024 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries
2.1 | Galvanised Bearing Plates | IFC Drawings 620.05 AS5100.4 AS/NZS4680 | Steel bearing plates (top, bottom and tapered attachment plate) are to be manufactured to the requrements of the IFC Drawings and AS5100.4 and galvanised to AS/NZS4680: Tolerances: Length/width = +2mm, -1mm Or; Diameter = +2mm, -1mm Twist = the lesser of 1% or 1.5mm Galvanised coating thickness for material >6mm: Average = 600gm/m² or 85µm Localised minimum = 500gm/m² or 70µm Attach: Dimensional Records Attach: Galvaniser's Certificate of Compliance | Document Review | Where applicable, once, for each component | IP | SE/PE/SPE | This ITP
2.2 | Epoxy Bedding Mortar Product Selection | IFC Drawings Product TDS | Product to be selected based on the following criteria: i. dual component, thixotropic epoxy resin or adhesive ii. CHARACTERISTIC COMPRESSIVE STRENGTH OF BEARING PEDESTAL MATERIAL TO BE 50 MPa MIN AT 28 DAYS. equal to or greater than substrate Iii. have no minimum thickness requirement Enter: Teambinder Material Approval number [free text box] | Document Review | Where applicable, once, for each product, prior to use | IP | SE/PE/SPE | This ITP
2 | Preliminaries - (Continued)
2.3 | Elastomeric Bearings | IFC Drawings AS5100.4 ATS 5520 | Elastomeric bearings are to be manufactured to the requirements of the IFC Drawings and AS5100.4. Testing: Each bearing tested under compression Batch tested for shear stiffness Enter: Teambinder Material Approval number [free text box] | Document Review | Where applicable, once, for each component | HP | Nominated Authority | ConQA Hold Point Release
3 | Pre-installation Activities
3.1 | Crosshead / Pedestal Tolerances | Survey As-builts / Survey Report | Re-check that the As-built dimensional tolerances comply with the requirements below: Reduced level ±2.5mm Variation from grade across the width of individual pedestals shall not exceed 1 in 200 Deviation from flat surface ±1mm | Document Review | Each element | IP | PE/SE/SPE | This ITP
4 | Installation Activities
4.1 | Bottom Bearing Plate Installation | IFC Drawings | Bottom bearing plate to be dry-fit into the correct location and orientation as shown on the IFC Drawings. Mix the epoxy bedding mortar as per the manufacturer's TDS and apply a 1mm thick layer (approximate) evenly to the full extent of the plate. Bolt the plate to the pedestal to a torque setting of approximately 175Nm (60Nm hilti tds). Record: The bearing plate ID onto the Red-line Drawings or Survey Report | Measure Visual | Where applicable, each bearing plate 4 days prior to loading | IP | Surveyor SE/PE/SPE | This ITP
4.2 | Elastomeric Bearing Placement | IFC Drawings | Place the elastomeric bearings to the survey marks to achieve compliance with the IFC Drawings and tolerances. Record: The elastomeric bearing ID onto the Red-line Drawings or Survey Report | Measure Visual | Where applicable, each bearing location | IP | Surveyor SE/PE/SPE | This ITP
5 | Post-installation Activities
5.1 | As-built Survey | IFC Drawings 610.46 (a), Table 610.462 (November 2018) 610.47 (a) Table 610.472 (March/June 2019) | Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element. Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP
5.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /