## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-311-STR-HOP-Elastomeric Bearings (Supply & Installation) | itp |  |  |  |  | ITP-311-STR-HOP-Elastomeric Bearings (Supply & Installation) Rev 1
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-311-STR-Elastomeric Bearings (Supply & Installation)
label | ITP Description: Elastomeric Bearings (Supply & Installation)
label | Discipline (e.g. CIV/STR/RAIL): 311-STR
label | Revision Number: 1
label | Revision Date: 12/08/2025
label | ITP created by: Manwel Kalyana
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 610 November 2018
label | ○ VicRoads Section 610 June 2019
label | ○ VicRoads Section 620 May 2009
label | ○ VicRoads Section 622 November 2018
label | ○ VicRoads Section 652 June 2010
label | ○ VicRoads Section 656 June 2010
label | ○ VicRoads Section 653 April 2024
section | 2. Preliminaries
checkpoint | 2.1 - Galvanised Bearing Plates
label | Reference - IFC Drawings 620.05, AS5100.4, AS/NZS4680
label | Acceptance Criteria - Steel bearing plates (top, bottom and tapered attachment plate) are to be manufactured to the requrements of the IFC Drawings and AS5100.4 and galvanised to AS/NZS4680:
label | ○ Tolerances:
label | — Length/width = +2mm, -1mm Or;
label | — Diameter = +2mm, -1mm
label | — Twist = the lesser of 1% or 1.5mm
label | ○ Galvanised coating thickness for material >6mm:
label | — Average = 600gm/m² or 85µm
label | — Localised minimum = 500gm/m² or 70µm
label | ○ Attach: Dimensional Records
label | ○ Attach: Galvaniser's Certificate of Compliance
label | Method - Document Review
label | Frequency - Where applicable, once, for each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 2.2 - Epoxy Bedding Mortar Product Selection
label | Reference - IFC Drawings, Product TDS
label | Acceptance Criteria - Product to be selected based on the following criteria:
label | i. dual component, thixotropic epoxy resin or adhesive
label | ii. CHARACTERISTIC COMPRESSIVE STRENGTH OF BEARING PEDESTAL MATERIAL TO BE 50 MPa MIN AT 28 DAYS. equal to or greater than substrate
label | iii. have no minimum thickness requirement
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Where applicable, once, for each product, prior to use
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 2.3 - Elastomeric Bearings
label | Reference - IFC Drawings AS5100.4, ATS 5520
label | Acceptance Criteria - Elastomeric bearings are to be manufactured to the requirements of the IFC Drawings and AS5100.4.
label | ○ Testing:
label | — Each bearing tested under compression
label | — Batch tested for shear stiffness
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Where applicable, once, for each component
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Pre-installation Activities
checkpoint | 3.1 - Crosshead / Pedestal Tolerances
label | Reference - Survey As-builts / Survey Report
label | Acceptance Criteria - Re-check that the As-built dimensional tolerances comply with the requirements below:
label | ○ Reduced level ±2.5mm
label | ○ Variation from grade across the width of individual pedestals shall not exceed 1 in 200
label | ○ Deviation from flat surface ±1mm
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - PE/SE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Installation Activities
checkpoint | 4.1 - Bottom Bearing Plate Installation
label | Reference - IFC Drawings
label | Acceptance Criteria - Bottom bearing plate to be dry-fit into the correct location and orientation as shown on the IFC Drawings.
label | ○ Mix the epoxy bedding mortar as per the manufacturer's TDS and apply a 1mm thick layer (approximate) evenly to the full extent of the plate.
label | ○ Bolt the plate to the pedestal to a torque setting of approximately 175Nm (60Nm hilti tds).
label | ○ Record: The bearing plate ID onto the Red-line Drawings or Survey Report
label | Method - Measure, Visual
label | Frequency - Where applicable, each bearing plate 4 days prior to loading
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Elastomeric Bearing Placement
label | Reference - IFC Drawings
label | Acceptance Criteria - Place the elastomeric bearings to the survey marks to achieve compliance with the IFC Drawings and tolerances.
label | ○ Record: The elastomeric bearing ID onto the Red-line Drawings or Survey Report
label | Method - Measure, Visual
label | Frequency - Where applicable, each bearing location
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Post-installation Activities
checkpoint | 5.1 - As-built Survey
label | Reference - IFC Drawings
label | ○ 610.46 (a), Table 610.462 (November 2018)
label | ○ 610.47 (a), Table 610.472 (March/June 2019)
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | ○ Attach: Survey As-builts / Survey Report
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP