## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
07764559-bcd8-45b7-ae87-bf889540aaf0 | checklist | ITP - Batter Hinge Extender Rev 0 | itp | ITP - Batter Hinge Extender
e8fd842e-c4a3-4d7d-a043-6718800dbc5e | section | 1.0. Aggregate Acceptance Testing
fc9c93d2-664b-4c89-9424-e56849840e8b | checkpoint | 1.01 - NZTA M04
0843ce5e-564a-5011-95e4-b654d64fe4c6 | note | Detail of Activity / Test - Crushing Resistance
96d767e0-8670-53c3-98f1-35cdd5b244fc | note | Action (Hold, Monitor, Witness) - H
a559fda8-8fcc-51d6-b6b2-4366f3846bba | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
721e7364-2365-5c9a-8553-db4f9cdd7d65 | note | Inspection / Test method - NZS4407:2.4.7
b55fbbbe-5ed1-54ff-825c-a6abe7a01fdd | note | Acceptance Criteria - > 130KN
5600f934-50be-5b2a-a1b5-c1b677e136f7 | note | Record documents (QCP - Quality Control Portal) - IANZ report
6eee25ab-8b22-51a7-883f-8ece9490a0aa | note | Responsibility - Contractor
54e88820-905a-5cdf-bbdb-3da1fffd4d5d | note | QA / Site Engineer - A
4703659e-8687-5b3d-9636-f99e4b30a42c | note | Eng. Rep / NZTA - I
5d8fe8f8-e170-5375-a1af-49ff2e83295f | note | Contractor - R
85edfbf5-eb54-4bfe-86ef-d1e2a73dfb5a | signoff | AUTHORITY HOLDPOINT
cf3faaec-7000-495d-8274-d2bbb95d9596 | checkpoint | 1.02 - NZTA M04
a6bc2ba5-3c20-5213-bce8-32cfb4b62c4b | note | Detail of Activity / Test - Particle size distribution
9b99021d-3a25-5dec-9d3a-ee84f068733b | note | Action (Hold, Monitor, Witness) - H
1d512770-d1bb-5fda-8e7d-67bd80544ee9 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
ea0a1890-c556-580a-bbac-afcb3c1ce5ff | note | Inspection / Test method - NZS4407:2.4.7
c061f12a-4d27-5339-b648-c3704819c089 | note | Acceptance Criteria - As per NZTA M04 Specfication
e07947e8-5399-5300-92ed-918749c13894 | note | Record documents (QCP - Quality Control Portal) - IANZ report
5e13ac6b-fb3c-5593-ab48-b7d344d4982f | note | Responsibility - Contractor
0e348d44-2f1c-5478-becf-745c4af60627 | note | QA / Site Engineer - A
566a3900-df04-50cd-8828-a43aad3e68bb | note | Eng. Rep / NZTA - I
545ee719-5946-54db-9b16-28a8679b6506 | note | Contractor - R
269b6155-eaf0-4c7b-9127-039b044032a8 | signoff | AUTHORITY HOLDPOINT
88df86cb-e3bf-45b0-9b20-9c5a6b7b42ef | section | 2.0. Construction
a2f58387-1c0f-415c-9f2a-eb0084bc4ec1 | checkpoint | 2.01 - Mark out earthwork extents
016d1f15-1180-56f9-846b-cf4845d00e28 | note | Detail of Activity / Test - Set out and approve extent of earthworks
45e0c044-691d-51e4-8d9c-a7c100e2a4d7 | note | Action (Hold, Monitor, Witness) - M
c94b1f3f-7690-55d9-a22f-2d4ec7747aa5 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to earthworks
b34819ed-c41c-53e8-8e22-5ad827c3334e | note | Inspection / Test method - Visual / Photo
0aeedd64-9dc7-533e-9a1c-d8da19e8067a | note | Acceptance Criteria - QA/Site Engineers Approval
5550513f-871c-5042-8699-dde7b2756507 | note | Record documents (QCP - Quality Control Portal) - Checksheet
119f942a-60e7-505f-b6e7-699755f7e053 | note | Responsibility - Contractor
45f24a22-5430-529d-a0ed-6c7f2449500c | note | QA / Site Engineer - A
f9d59091-da04-5768-ac34-d65d85e37d75 | note | Eng. Rep / NZTA - I
f1b68982-0f07-509d-875c-4e56f22dbc12 | note | Contractor - R
9eec95c1-2779-4a5a-8598-5e91805c41b7 | checkpoint | 2.02 - Earthworks
874508f6-6976-5c1a-bf24-2f0a18ee5ca7 | note | Detail of Activity / Test - Excavate to a depth required in the design drawing
d00a6626-bd01-5396-be3b-88a80ee4e6c4 | note | Action (Hold, Monitor, Witness) - M
59403aa8-3e3b-5f43-b117-0cfba6a6ab64 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where hinge extender is required
b42a1488-5ab1-5534-be5a-ae528396f21c | note | Inspection / Test method - Visual / Photo
8080906e-ce1e-5340-b9c3-5aca6bf5f7d0 | note | Acceptance Criteria - QA/Site Engineers Approval
fa462151-a007-56f9-ba43-7b7173543ebd | note | Record documents (QCP - Quality Control Portal) - Photo
d50463eb-2ba7-5b8d-8bf2-8e5bd73a0703 | note | Responsibility - Contractor
c95c6a69-38f3-5532-bbe2-a7f6386241d9 | note | QA / Site Engineer - A
4ba23c89-c330-5410-b80c-94514fd90ab0 | note | Eng. Rep / NZTA - I
962c8d12-41da-5de5-aee0-bd648a3bb768 | note | Contractor - R
438f7c6c-555b-4662-b121-48b518395ff5 | checkpoint | 2.03 - Post Installation
0d06e472-3151-5152-affa-aae0fd10f3d6 | note | Detail of Activity / Test - EZY-Guard LDS Z-Post 2000mm long at 1.0m C/C spacing or NU-Guard High Tensile Posts 1900mm at 1.0m C/C spacing
e842ccf5-13f3-54f9-ae5c-9e6ad1e2fc06 | note | Action (Hold, Monitor, Witness) - M
56d92ef8-8227-5fcc-a908-1f6c447fc129 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where hinge extender is required
631461f1-8922-541a-aa3c-9fdc10244309 | note | Inspection / Test method - Visual / Photo
41c73408-14c0-5c82-ae65-feb5653ae4b8 | note | Acceptance Criteria - As Per Design Drawing
2c1f29a0-0ba6-5f49-8e47-bce664930290 | note | Record documents (QCP - Quality Control Portal) - Photo
aa24c361-a060-5776-a71b-5ae64bd31417 | note | Responsibility - Contractor
4ec84342-b18b-5e79-bbd2-c858b6a46166 | note | QA / Site Engineer - A
b3879a04-dc08-52ef-9bf5-6e1f0c37a383 | note | Eng. Rep / NZTA - I
63b865c7-7181-575a-884b-be5dc329d3dd | note | Contractor - R
22e6c51d-315d-4ffe-a743-d1626aaab941 | checkpoint | 2.04 - Timber Board Installation
0d2ef65b-d537-517d-a4cb-9a8dee5a7920 | note | Detail of Activity / Test - Install 2 to 3 No. 250mm X 50mm H5 Timber Boards fixed with galvanised M12 bolt and square washers
094f0a35-605d-51e5-a5ad-6a12af9dd33e | note | Action (Hold, Monitor, Witness) - H
95a1e395-6066-5a25-92b7-90796f651b4b | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where shoulder support is required
daeebb5c-5114-5978-aef5-a4fb953e297a | note | Inspection / Test method - Visual / Photo
4f0d28d4-cafc-5fa5-a20d-6cc04b203c97 | note | Acceptance Criteria - As Per Design Drawing
ec7bc3be-149b-58d1-a610-236a360fd540 | note | Record documents (QCP - Quality Control Portal) - Photo
b6ed505d-d148-5561-9e81-09356a92a990 | note | Responsibility - Contractor
21ff3a90-883b-5cac-944f-803a3a56b7ca | note | Project Specific Notes / Instructions - To Ensure a minimum of 150mm of the bottom timber board buried in the embankment
8fa7a1bb-edad-5d85-aa9e-e3f0ea1de116 | note | QA / Site Engineer - A
01ffa600-a3a4-5d29-9aa5-53dc1719e7b4 | note | Eng. Rep / NZTA - I
47106fab-9ca8-5463-ab3a-a0baa8469380 | note | Contractor - R
04a3fe4e-5996-48c0-9286-73f40a2e73aa | signoff | AUTHORITY HOLDPOINT
a6684218-23d9-42e3-8a62-8dc18121388d | checkpoint | 2.05 - AP40 Placement
13d0863d-5401-5f2c-aa57-1d0b0284511e | note | Detail of Activity / Test - Backfill and compact using M4 AP40
05d7f887-a1b4-53ff-922e-2b68e577dade | note | Action (Hold, Monitor, Witness) - H
83b4292c-a620-5667-b66b-9d1474cd4e48 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Test Every 10m
d0db9760-07a8-5dbb-bafc-5e5c4a15cd90 | note | Inspection / Test method - Clegg
f2f150e8-2850-5bcc-af91-e3ac5d6930df | note | Acceptance Criteria - Clegg Results >30
f0c6e4e8-682c-5ce1-890f-a0125220894e | note | Record documents (QCP - Quality Control Portal) - Checksheet/Photo
685077ba-cdd9-57bf-bc2c-027bc9caeb0c | note | Responsibility - Contractor
91f66bfd-5ae3-5501-a187-425db25f1e2b | note | QA / Site Engineer - A
4cbfab56-b1cc-519c-941b-8d698ee6147f | note | Eng. Rep / NZTA - I
30bf6d43-00a3-5cca-9b96-c7d4bc1afd4e | note | Contractor - R
653acfb2-92ff-4ba9-9bbd-e6b48370a0ef | signoff | AUTHORITY HOLDPOINT
25f8068e-b2cb-4ddd-a321-ca5757ccbb38 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
579fbaea-8fa8-56a8-9e69-c49d7139fe51 | textbox | Contractor's Rep Name:
52d85b79-0378-5d93-8748-4ca78fcd3271 | textbox | Engineer's Rep. Name:
3fd5ebad-58b5-5837-88ce-0bfb293ab051 | date | Date:
ea04b478-1d73-4f5a-b586-9e9a6c9fcea3 | signoff | Add Signature
19eadae8-8802-5b0e-96b4-40aab5769d57 | checklist | ITP - Chipseal Rev 0 | itp | ITP - Chipseal
de92f433-8d95-5167-8ab1-a4a100c606b5 | section | Design
16beec8f-7019-5452-b6a4-9a6c35eae987 | checkpoint | 1 - Treatment Selection
8c8594da-6af8-5f58-ac8b-47786c4a2d04 | note | Verification Activity - Physical / Site video/photographic record
363258c0-aa1d-539c-b37b-8cb853b851c7 | note | Methods or Reference - Asset Team - Base Preservation
4605c89f-a749-5eb0-8e15-b1899d96f3d9 | note | Frequency - Annually Pre-reseal
0690ea7e-7d71-58ff-a5cc-df717e41231f | note | Acceptance Criteria - Documented approval from at time of Tender -Team/Client
ad9ca390-cec5-526f-97fe-8da5c922e867 | note | Hold / Witness Point - Mandatory HOLD POINT - Client Approval
e0ad7bbf-75fb-5ae2-bef0-ee1bd76cdb92 | note | Records - Approved Seal Designs
04e2df52-d24e-59ac-9339-5d0aba9c964c | note | Responsible Person - Sealing Contract Manager / Engineer
c3f89b74-5c7c-56aa-a13f-c33590939a21 | signoff | AUTHORITY HOLDPOINT
7e196db8-4281-57be-a81c-a731beeb180f | checkpoint | 2 - Chipseal Design
21cc6101-c692-5b4a-ab48-48ea98e33d80 | note | Verification Activity - Peer review by Authorised Seal Design Approver
f79ca6ff-d241-5e3e-b4c5-b73e48345a7e | note | Methods or Reference - Chipsealing in NZ
f61c2fcf-6b67-503c-8fd8-f43c54bab3dc | note | Frequency - One per design prior to commencing onsite
d6fc83d3-15f6-5631-8b3d-ee8513d1eac7 | note | Acceptance Criteria - Design meets requirements of P17
33f7bfc6-4035-5500-b475-022f399b75b8 | note | Hold / Witness Point - Mandatory HOLD POINT - Seal Design peer Reviwer - Client Approval
d4ab7a59-00d3-56c2-96ad-3d16f4f8384a | note | Records - Peer Reviewed Seal Designs
a118de6c-c1d7-5c54-abbc-01dc3ac1e2cf | note | Responsible Person - Sealing Contract Manager / Engineer
cbc886b2-b76c-5db1-8c2b-06c62cc4ffdc | signoff | AUTHORITY HOLDPOINT
1cd929e2-7426-50b9-af5c-db5d7482256c | section | Materials Testing
c2341a9e-7932-5208-afb5-e453eb711307 | checkpoint | 1 - Size (Grades 2-5) & Shape (Grades 2-4)
a9880745-584d-5cec-9fca-0e8bd2611dbd | note | Verification Activity - Lab Test
e0239544-b439-510c-9a6c-248f9527d84d | note | Methods or Reference - NZTA M/6
9cd469b4-e036-5989-b33f-1298280a42b0 | note | Frequency - 1/500m3
3d7986b0-d0f4-58cb-b0fa-4ebad950154a | note | Acceptance Criteria - Size (ald mm)
b404e1f9-0260-531a-84e7-45ce0ed4b2ba | note | ○ G2 9.5-12.0
d7923a91-8d98-5f66-906d-f059e935686a | note | ○ G3 7.5-10.0
1dd0f860-23dd-5ad5-a079-3d690da1b28b | note | ○ G4 5.5-8.0
ad733c59-9580-57ba-a34b-2f49af676bbc | note | ○ G5 Report
3d1fd3d2-123e-58f4-b3f2-df416b27714d | note | Hold / Witness Point - Witness Point
bd024640-102f-52b6-9a23-8ef6f96a750f | note | Records - IANZ Lab Reports
f740777d-ef62-5280-a659-f270652f5311 | note | Responsible Person - Sealing Contract Manager / Engineer
2e45d16c-b134-5de5-8a48-753edce46f26 | checkpoint | 2 - Size (Grades 2-5) & Shape (Grades 2-4)
3de44f12-cbac-5427-bd29-41bc0f4743c8 | note | Verification Activity - Lab Test
ad98f400-d4d7-5583-a3c7-f5681c24e66a | note | Methods or Reference - NZTA M/6
b57f5d99-d090-5903-964e-58782d40124e | note | Frequency - 1/500m3
46df09f2-f527-5840-96f2-a484a68964c8 | note | Acceptance Criteria - Shape
f5c6521c-9638-5d2b-bd12-36c96763e6b5 | note | ○ AGD/ALD Ratio G2,3,4 = 2.25 max
46978e06-8d81-58b4-ba19-6dbe19ea748d | note | ○ G2,3,4 = min 98% with 2+ broken faces
d8704148-4f83-5773-b7be-6a58ca0772ca | note | Hold / Witness Point - Witness Point
a84e7a4f-5b04-524f-9d8c-258288fb22fc | note | Records - IANZ Lab Reports
f42e08f6-d6c4-5b04-a87c-685a065d4a01 | note | Responsible Person - Sealing Contract Manager / Engineer
d92eb445-325a-5c56-8099-b52939d4c05e | checkpoint | 3 - Cleanliness (Grades 2-6)
09ff3d80-7d9d-5ea6-acba-cdfa74f16d76 | note | Verification Activity - Lab Test
a473ae1a-da03-534e-90a4-c7dc1dfa66f1 | note | Methods or Reference - NZTA M/6
8a5ce8d2-851e-500c-9dda-ef6a4f0c563c | note | Frequency - 1/500m3
45f4bc29-c7e2-5e23-8aee-3ae0f0448c2e | note | Acceptance Criteria - Cleanness value
3a3c2ded-7885-54ac-b57b-6bb91da5a6ff | note | ○ G2 = 89
dca0f9f6-7cb0-503d-894d-595b672347d8 | note | ○ G3 = 87
7eb294fd-7951-5352-ab78-f8a70f3c4737 | note | ○ G4 = 85
ee7da877-ed1b-5293-a104-0b60d3017b7d | note | ○ G5 & G6 Report only
32c208ab-72e8-519b-8159-a7961a435015 | note | Hold / Witness Point - Witness Point
3943d478-9ad9-5dd5-a0dd-700fa4513387 | note | Records - IANZ Lab Reports
4af6a67d-223c-578a-b36e-6c956b0d4475 | note | Responsible Person - Sealing Contract Manager / Engineer
907a5b34-d7fc-5451-80d8-e0970eefa3c4 | checkpoint | 4 - Compatibility (Multi Layered seals)
bd5bce0e-8797-5fdc-b9ab-5c0d43be4591 | note | Verification Activity - Comparison Of Chip ALD
dfeb114f-a2a9-5e23-a130-4bff113b4249 | note | Methods or Reference - Chipsealing in New Zealand NZTA (NZTA 2005)
fc7cd369-2f0d-5eaf-9302-2ceed29606ba | note | Frequency - 11.5
f9c507c3-e302-573d-ba85-acebae16bc02 | note | Acceptance Criteria - Two Coat Seal Aggregate Compatibility
2c37808e-8e72-5cdb-88a9-1fdbd99da1c0 | note | – – – – – – – – – – – – – –
081e78ff-06f7-5198-947f-4bff79a7021d | note | Upper Limit (x ¦ y) ¦¦¦ Lower Limit (x ¦ y)
0a54da32-2235-5670-8909-ff73bd22d109 | note | – – – – – – – – – – – – – –
ecda9c22-e0a1-5c01-aba7-dacf6d484fff | note | 0 ¦ -0.44 ¦¦¦ 0 ¦ -1.42
6e9e3a66-4010-5719-b9c5-0310628ad8d1 | note | 1 ¦ 0.27 ¦¦¦ 1 ¦ -0.84
65148c6d-3532-5070-ba53-3ed2b57f0f01 | note | 2 ¦ 0.98 ¦¦¦ 2 ¦ -0.26
aeb3b653-2b25-58da-8549-aa2a155eab2e | note | 3 ¦ 1.69 ¦¦¦ 3 ¦ 0.32
77feabca-708c-5aa0-a63d-82004922add2 | note | 4 ¦ 2.4 ¦¦¦ 4 ¦ 0.9
fd46e692-362e-5ece-b394-623b2bda6dfe | note | 5 ¦ 3.11 ¦¦¦ 5 ¦ 1.48
1160d91c-0d90-5388-b81a-9e678972d155 | note | 6 ¦ 3.82 ¦¦¦ 6 ¦ 2.06
ed48bc2d-de29-5586-8455-b0246653b5b4 | note | 7 ¦ 4.53 ¦¦¦ 7 ¦ 2.64
ee77e960-1fa3-5f09-a32c-a01b2e5640f1 | note | 8 ¦ 5.24 ¦¦¦ 8 ¦ 3.22
e45eb816-93f9-5936-9a4f-041e5d350a66 | note | 9 ¦ 5.95 ¦¦¦ 9 ¦ 3.8
24612e24-878c-57de-bb82-cad06d178015 | note | 10 ¦ 6.66 ¦¦¦ 10 ¦ 4.38
06dba8ff-aaba-517f-9ae6-f1c879764d6b | note | 11 ¦ 7.37 ¦¦¦ 11 ¦ 4.96
058f4422-6f0d-5010-9c41-61d0548850ab | note | 12 ¦ 8.08 ¦¦¦ 12 ¦ 5.54
abac5f86-b634-51f3-b7c0-f519e6816540 | note | 13 ¦ 8.79 ¦¦¦ 13 ¦ 6.12
e8b690c3-3b62-5c6f-8794-c9a0dc4a644a | note | 14 ¦ 9.5 ¦¦¦ 14 ¦ 6.7
13f6237e-705a-584a-9869-155ce0e9685b | note | 15 ¦ 10.21 ¦¦¦ 15 ¦ 7.28
712135b3-bd1c-5cf7-bcba-7c9dbceba12c | note | 16 ¦ 10.92 ¦¦¦ 16 ¦ 7.86
38bd2d9c-351a-59e0-9fba-1a3bddebe84a | note | – – – – – – – – – – – – – –
8404b4ab-08b4-5c79-8a3d-2aad39fc122a | note | Compatibility Point
3859bcdf-02e1-599b-a4b4-6b4fbf96e4b7 | note | x ¦ y
7890d083-d731-5891-a1b8-a8548f0f0e93 | note | 11.5 ¦ 7.2
f5a5d6da-8777-5f1d-adc2-9a33b3a7c828 | note | – – – – – – – – – – – – – –
b3ede0ef-57f3-5468-b613-0db9749a0eef | note | Hold / Witness Point - Witness Point
6929ceaf-0bf3-526a-bdd6-1cf77d537299 | note | Records - IANZ Lab Reports
13c53e10-c070-5e11-a7d0-79627aa02655 | note | Responsible Person - Sealing Contract Manager / Engineer
31462998-ec2a-558c-bdb1-2f69bde3a2d8 | checkpoint | 5 - Compatibility (Multi Layered seals)
b40f7402-74ba-5ae9-83c1-887b47a23a87 | note | Verification Activity - Comparison Of Chip ALD
aad88e1a-edc3-515c-a9c6-f754c07b924c | note | Methods or Reference - Chipsealing in New Zealand NZTA (NZTA 2005)
0837712b-73ee-5483-bada-328886379305 | note | Frequency - 7.2
fcd561db-4bf0-5fc5-ab86-36f126ce6fa8 | note | Acceptance Criteria - Two Coat Seal Aggregate Compatibility
79cf5fe2-ba07-52ed-8c52-1046d63a4904 | note | – – – – – – – – – – – – – –
0ef4686d-e0a1-5bce-b096-9334cc60d8e2 | note | Upper Limit (x ¦ y) ¦¦¦ Lower Limit (x ¦ y)
0518db59-a21d-5455-a861-40a27a0453ef | note | – – – – – – – – – – – – – –
a4bcff6d-12be-5548-b414-285999586f67 | note | 0 ¦ -0.44 ¦¦¦ 0 ¦ -1.42
1e45f48a-60ce-5cbf-9a03-47534beac279 | note | 1 ¦ 0.27 ¦¦¦ 1 ¦ -0.84
eecce50d-3bca-52b7-a2fb-40ddaee2e607 | note | 2 ¦ 0.98 ¦¦¦ 2 ¦ -0.26
db00ebef-e224-5347-b504-9b2ea7f9f2ed | note | 3 ¦ 1.69 ¦¦¦ 3 ¦ 0.32
028a0cb4-9e71-5726-9222-1385f77c32a8 | note | 4 ¦ 2.4 ¦¦¦ 4 ¦ 0.9
7da4dbf6-2a9d-527d-a263-2ecebba2fe5e | note | 5 ¦ 3.11 ¦¦¦ 5 ¦ 1.48
380c82a7-eb96-5b45-b023-3fb78036e714 | note | 6 ¦ 3.82 ¦¦¦ 6 ¦ 2.06
cafaf48f-c911-5a14-9b9b-69421f3d90bf | note | 7 ¦ 4.53 ¦¦¦ 7 ¦ 2.64
63e087d8-66e9-50ae-b626-85b55a4d1cb3 | note | 8 ¦ 5.24 ¦¦¦ 8 ¦ 3.22
de99cbb8-c8a5-558c-914e-dfe4f6b7f5b5 | note | 9 ¦ 5.95 ¦¦¦ 9 ¦ 3.8
1103e6ef-6b66-5c1e-838a-ecfa0ca5699f | note | 10 ¦ 6.66 ¦¦¦ 10 ¦ 4.38
6fca420f-a37b-5cda-bf94-ad32dfc1b8eb | note | 11 ¦ 7.37 ¦¦¦ 11 ¦ 4.96
f1fb8533-1e61-5737-8c56-60bb5b1172d9 | note | 12 ¦ 8.08 ¦¦¦ 12 ¦ 5.54
7bfcc63e-560b-5af2-8e0e-e28b1039f7b2 | note | 13 ¦ 8.79 ¦¦¦ 13 ¦ 6.12
6ba5341b-2779-58f9-b5ec-1b88d62c21f2 | note | 14 ¦ 9.5 ¦¦¦ 14 ¦ 6.7
073fa69d-93c3-5873-9744-7bab2a4734e7 | note | 15 ¦ 10.21 ¦¦¦ 15 ¦ 7.28
4117fae7-882a-5772-9d95-c07e6e06c0a3 | note | 16 ¦ 10.92 ¦¦¦ 16 ¦ 7.86
6bbf656f-e45b-5541-836a-22bf853fee58 | note | – – – – – – – – – – – – – –
c6c1963b-7ac8-5926-a890-764ce8ad88f8 | note | Compatibility Point
ff5f8dfb-fb7b-52ed-af07-ddface52152d | note | x ¦ y
d49ad839-0ad8-5da7-a8ca-a331cccefb0c | note | 11.5 ¦ 7.2
698e3af3-883c-5494-b632-bc4a72f6d934 | note | – – – – – – – – – – – – – –
7174a18c-03a9-5574-9de5-27648beb13dc | note | Hold / Witness Point - Witness Point
b6dc63cb-2b8e-55f0-b262-773f57d45921 | note | Records - IANZ Lab Reports
135adfcf-d7de-5536-9029-c7237117979e | note | Responsible Person - Sealing Contract Manager / Engineer
197916eb-c62d-5c09-afcc-234b5ea9a454 | checkpoint | 6 - Bitumen Distributor
96920bed-b19e-5c60-8792-1123aad4988b | note | Verification Activity - IANZ Lab E/2 Results
3f879b55-4a9e-528e-8d20-f2bac0ead35c | note | Methods or Reference - Code of Compliance
63931585-ad11-589f-8f53-d60d60f3be3b | note | Frequency - Annual
102d69b4-0977-5512-820b-193d999e0a58 | note | Acceptance Criteria - Speed Test(+-3% over 100m), Dipstick Test (+-50L over 2000L), Matt Test (app rate within 0.10L/m2, longitudinal within 10%, thirds within 5%, transverse within 20%)
4bfb7e84-93b9-5cd5-9e76-8b4a8a561254 | note | Hold / Witness Point - Mandatory HOLD POINT - Client - Engineer Witness
11cd3b06-b42f-515e-add6-78c691aace19 | note | Records - RNZ E2 Certificate
f3c36f82-0013-5fff-8415-cd717a0845db | note | Responsible Person - Sealing Contract Manager / Engineer
d2a391b0-ca14-54ee-946c-212cd3aa3543 | signoff | AUTHORITY HOLDPOINT
43831901-43f4-51fe-be20-6899f082301d | checkpoint | 7 - Emulsion/PME Testing
3ff533ac-99b1-5ec9-b0e0-f1d44d43ddd1 | note | Verification Activity - Lab Testing
833f99d8-74b3-5d28-bdd1-ac8ba2707664 | note | Methods or Reference - Manufacture Specification
587c773f-24e2-53f1-bf10-957cced09eec | note | Frequency - Per Emulsion/Bitumen Production Batch
94e6497e-66eb-5726-bc23-a561262a423d | note | Acceptance Criteria - Bitumen Content, ITM 11-01, Viscosity, ITM 10-02, PH ITM-08-02
6e12188d-76b6-50ff-868c-9e2a23d72dea | note | Hold / Witness Point - Witness Point
0d1f3ca5-c998-5645-8b6d-012a6c5f7f6d | note | Records - IANZ Lab Reports
06b33136-ea2f-5b58-b325-161ab7e1b6c9 | note | Responsible Person - Road Science
a68b9206-ecbd-59f0-bdfb-03c526d95604 | section | Surface Inspection
97229735-4410-5505-a0f4-0d3d6d2cf0fb | checkpoint | 1 - Surface Texture - Measurement
30992215-6fb8-5829-9e30-e309637c2ea0 | note | Verification Activity - Sandcircle Measurement
975447bb-1fb7-51d9-880d-00334a3bd720 | note | Methods or Reference - NZTA T/3
1d55f0bf-b2be-5846-9553-f9420ade3074 | note | Frequency - At time of Seal Inspection
22dd72a9-5722-5204-b616-f6f218677460 | note | Acceptance Criteria - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture
cf7d8cb7-2288-5434-bc68-e5ae8455829d | note | Hold / Witness Point - Witness Point
a50e24d3-e404-5b10-8798-f093aa718d95 | note | Records - Sandcircle Data
6e286e95-7ef3-5c51-aa0e-886a754f056a | note | Responsible Person - Sealing Contract Manager / Engineer
149a5682-8fa1-5d06-b5a0-af5241fef7da | checkpoint | 2 - Surface Texture - Measurement
4c0e8f22-b5c9-5616-bd73-f66238f596de | note | Verification Activity - ARRB Hawkeye or
412d7379-8070-53b9-a467-53dec1c26b2a | note | Methods or Reference - NZTA T/3
a7ca3c4c-3427-5f43-82e6-64a9cfee8a8e | note | Frequency - At time of Seal Inspection
7624b646-b51f-57ab-9a11-0db722d94256 | note | Acceptance Criteria - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture
a4a7e926-04d6-5efc-98cb-281be8649653 | note | Hold / Witness Point - Witness Point
2543414f-5540-5633-933f-94b5e27783d5 | note | Records - Hawkeye Data
0f64c36d-e024-5600-a2a4-404e09bd41ec | note | Responsible Person - Sealing Contract Manager / Engineer
81fac8d1-0cb2-5a1e-a159-e38fb21ab569 | checkpoint | 3 - Surface Texture - Measurement
ed320e9e-5aa0-5a3e-a6a9-b205234b6ff1 | note | Verification Activity - NZTA HSD
7b7cfdca-7dbb-56fd-a6cf-7922800cc5f7 | note | Methods or Reference - NZTA T/3
6549abc7-226c-5f50-a7ee-2255be93b0da | note | Frequency - At time of Seal Inspection
65642d1f-ecfe-50ff-934a-c6915fd1d4fb | note | Acceptance Criteria - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture
e317a46b-ad46-5628-8bd8-063daa683bd9 | note | Hold / Witness Point - Witness Point
475ca499-6980-5b17-8b0f-102c5cfee0f8 | note | Records - High Speed Data
db8477fd-9005-5c08-a19e-d49f9788b06d | note | Responsible Person - Sealing Contract Manager / Engineer
e1db09d7-5cf0-599d-be08-f3892ebb7418 | checkpoint | 4 - Pre Seal Survey
6054e86d-39af-5c17-af2f-56ee861a7202 | note | Verification Activity - Downer Survey or MS Forms Pre Reseal Inspection
9ae8e63b-ac4c-5d9c-94b9-760e2d4b5352 | note | Methods or Reference - Downer Survey or MS Forms Pre Reseal Inspection
26475c83-67cf-5c8f-93f6-4c2c92d1eccb | note | Frequency - At time of Seal Inspection
c12a34b7-a74d-52aa-9736-b5576ddfe198 | note | Acceptance Criteria - Record & any noted issues / Client
81f33da8-a042-51a7-adba-78531e788a1b | note | Hold / Witness Point - Witness Point
b119a889-951d-5105-97dc-61db2f33c502 | note | Records - Lucidity
8c072e1a-d35a-5f6b-9978-c49736d0da60 | note | Responsible Person - Sealing Contract Manager / Engineer
14322989-9711-5c35-83f8-492907b2e88e | checkpoint | 5 - Construction Compliance testing
0863a61e-1c40-52f7-b933-3d09f9d79f06 | note | Frequency - 24 hours in advance of seal construction commencement
c09b6912-9f90-50bb-b7c6-d7c80ad9f6ee | note | Acceptance Criteria - Confirmation from renewals manager all testing has met requirements
049dc639-e617-5bc5-bb05-a7fe98bbb1db | note | Hold / Witness Point - Hold Point
1f47d3bf-281d-5df9-b4f0-9e228a420eec | note | Records - Email Confirmation
35c1d9d8-8231-5766-ae6e-d8c2387af9bb | note | Responsible Person - Sealing Contract Manager / Engineer
a6df6356-5359-53c2-9c49-2b71c5b6a5fa | signoff | AUTHORITY HOLDPOINT
07c0a4ad-653e-531f-b0db-b53a026bf4bf | section | Seal Construction
00e8d642-36e6-5f2e-b664-55b5a501809b | checkpoint | 1 - Go/No Go Survey
bca26e88-6896-5edf-adf5-fd36ed05f748 | note | Verification Activity - Visual, Zeus, Iris
f7f26fa1-1cf9-5ef3-ac6b-45ae98948ae4 | note | Methods or Reference - Downer Survey Sealing Go / No Go, Road Science Zeus app & Downer Iris app
deb625d5-a6ee-5e3f-aef1-94b2f8a72037 | note | Frequency - Prior to sealing on each site
53ba1b38-58fb-5863-873b-e06beec3ff65 | note | Acceptance Criteria - Pass on Go / No Go, Marginal & discussion with Contract Manager or written approval from Rehab Manager
beb83ee0-3da5-5984-8a14-a6055749d4dc | note | Hold / Witness Point - Witness Point
31879bb6-da9b-5b0a-88a9-9bc2d0a2cd37 | note | Records - Lucidity
677c3fbc-19b3-50c0-ad44-7abede5df2dd | note | Responsible Person - Supervisor / Foreperson / QA
7ffead08-ae2f-551e-b369-30029ae1292a | checkpoint | 2 - Pavement Markings/RRPMs
463046a3-6332-5dc4-83ba-796bf26e236f | note | Verification Activity - Tagging of existing Pavement Markings, Removal of RRPMs
d94df56f-3fca-5526-8eeb-a3a52f4bec30 | note | Methods or Reference - Pavement Marking Set Out Sheet, CBP
814fecbb-1e33-5c24-ab64-2f26fd0208f7 | note | Frequency - Prior to sealing on each site
187fac4c-b001-5a07-8dc2-2bc07cb9269d | note | Acceptance Criteria - All raised pavement markers to be removed (1st & 2nd Coat Seal surfaces excluded) and existing line marking "tagged". Check for any new markings required
b29772df-1b5f-5b3c-a89f-d8ca19eeee48 | note | Hold / Witness Point - Witness Point
902dbefe-48f8-58d2-b56a-fdb1b0c8f66d | note | Records - None
05025bbf-acff-53f5-aeeb-b019491c5c88 | note | Responsible Person - Foreperson / QA
dd7abef7-6dad-5ced-92c8-dca328ac4451 | checkpoint | 3 - Road Furniture & Sumps protected
eb22f242-5bf7-594d-8983-77eece26a63b | note | Verification Activity - Visual Inspection
c2fd0fb9-048f-510b-a629-44b8b6095476 | note | Methods or Reference - Crew Breifing Plan / Visual
ae2db8b4-3a9a-5889-863c-3e1a8da27c0f | note | Frequency - Prior to sealing on each site
e85868d2-3bc2-5a20-8a3c-28607eccdcd5 | note | Acceptance Criteria - Protect all road furniture in accordance with Crew Breifing Plan. Fabric & protect all sumps.
665c14ac-8e2e-5372-8f43-ac9c7fa9e458 | note | Hold / Witness Point - Witness Point
18a48f72-c264-5aa2-9ae4-ca778b8b81ed | note | Records - None
c2027490-11d9-5b9c-a5e1-0215a35d40fb | note | Responsible Person - Foreperson
4af2be6e-bd26-5ab4-b723-465b7754aa5b | checkpoint | 4 - Surface Condition/Temp
f5a5f4a1-0b0c-5d74-a463-2fac7720acf5 | note | Verification Activity - Physical / Visual Inspection
01bd7a2b-377f-5b77-a8ad-9db868be5ac5 | note | Methods or Reference - Visual / NZTA T/3
910162ec-32ce-57d2-b7bf-67e76bb2ff77 | note | Frequency - Prior to sealing on each site
aa981376-f513-5b60-bccc-0e50b6b28332 | note | Acceptance Criteria - Surface area shall be dry and free from any loose chip, dust, dirt, vegetation. Temperature recorded on site prior to sealing commencing
34166aff-9c0f-5f9c-9f0d-4763587885a8 | note | Hold / Witness Point - Witness Point
10b1aa85-c671-5a1f-9f13-47fba4dbe015 | note | Records - None
e0ed8289-8561-58b9-9875-f0f99ba6785a | note | Responsible Person - Foreperson / QA
6ec6d590-fde4-53b1-9e45-5769aef2bbc8 | checkpoint | 5 - Stockpiles
bad51d86-6373-55dc-9fc4-a42ab9bca83f | note | Verification Activity - Visual Inspection
37f32ab2-937d-5e62-8013-95931193c779 | note | Methods or Reference - CBP
c2c7a996-8eb0-558d-b25b-d5c905709b99 | note | Frequency - Each Stockpile
4c02514a-1c09-59f4-b9ac-4ac8d37f18a4 | note | Acceptance Criteria - Correct Source, Grade and quantity. Uniquely Identified.
0b70f602-a431-5d21-9a48-950440957a82 | note | Hold / Witness Point - Witness Point
dd23e5bf-8d44-51e2-b656-bed408d678eb | note | Records - Sealing Data Docket
c7c4a8c9-eeec-5321-a8f0-3b9b15adcc44 | note | Responsible Person - Foreperson
029df437-5a43-5ec6-a015-3f8ab307090c | checkpoint | 6 - Spraying
9ffc90e7-5936-57ca-8767-4a9ead7fc198 | note | Verification Activity - Paper Start and Finish all runs
eee19341-2ad7-5290-9597-579d57319390 | note | Methods or Reference - Spray Runs
36822b6a-9e05-5c98-b4a5-cead6cc73ae8 | note | Frequency - All Runs
4a9b844c-13d9-5b2a-950e-167e1b45f6bd | note | Acceptance Criteria - Mark out start / Finish
ba3cf6b8-2606-58e4-953a-3fdfbcadf8d6 | note | Hold / Witness Point - Witness Point
f87da80e-0748-5d43-8429-92b9f4f92848 | note | Responsible Person - Sealing Contract Engineer / QA
e2d1ac1a-afad-5598-a739-d1bdd95d1491 | checkpoint | 7 - Sealing
476ca91b-2ffb-5d8c-a0cf-d4e98a94547c | note | Verification Activity - Longitudinal Joints out side of wheel tracks
d56ad1a4-d9f7-5a7e-8dd8-9c83b0db61d1 | note | Methods or Reference - Spray Runs
e5d61f24-417e-5855-96e3-7c7ff7a89b76 | note | Frequency - All Runs
4359f1dd-24b6-5c4b-96e6-cc84fc34cf68 | note | Acceptance Criteria - Mark out lane lines by construction team
8ffe9fd2-f2aa-50c1-bd43-ccea9b2eb643 | note | Hold / Witness Point - Witness Point
3f07445d-637a-50ba-91e7-66e6dd3cbf88 | note | Responsible Person - Sealing Contract Engineer / QA
52dde67c-5c28-5ee0-9cec-dbe4b0c62826 | checkpoint | 8 - Binder Application Rate
ead0f5c2-870c-510e-9826-8068a3cc84e7 | note | Verification Activity - Tank Level dips prior to and after spray run
1be6d777-7cf9-5c2c-bb32-be2864b646e1 | note | Methods or Reference - Dipstick
47dae73e-99fc-52cd-93a0-3034f11fe030 | note | Frequency - At Beginning of the day After 1st spray run of site After last spray run of site At end of tank prior to loading
2049d227-5cff-5809-a0b1-046d63e09973 | note | Acceptance Criteria - Quantities used to be within the desired tolerance of design Spray Rate
b73642c4-c0ae-5ba6-bf5a-8f89a7f9d434 | note | Hold / Witness Point - Mandatory HOLD POINT
13c5a645-e666-5276-b6f6-196e6e6c9a6d | note | Records - Spray Sheets
f84ce3d4-9971-5af3-964d-287817b1f64b | note | Responsible Person - QA
71a59df1-1e07-525d-96a3-fab3c8738ac7 | signoff | AUTHORITY HOLDPOINT
9255ac83-7da0-5149-b350-b4198aae2c9e | checkpoint | 9 - Chip Spread Rate
777b56db-3b3b-5cab-8956-4fe7ea72fa88 | note | Verification Activity - Visual
2e0239d0-2fc2-582b-8462-1dd63a3d8787 | note | Methods or Reference - Crew Briefing Plan/Visual
028ae5eb-989e-5c40-a780-e78b7c043b16 | note | Frequency - On going whilst seal being constructed
0e932287-8755-5dce-8bf3-c332e0e786f4 | note | Acceptance Criteria - Chip is applied in accordance with the appropriate coverage as specified in the Crew Briefing Plan
83b7acb4-5641-5481-9514-2623c8affb49 | note | Hold / Witness Point - Witness Point
0096e38f-ff07-59e9-82ff-a3fc9fbff7ea | note | Records - Data Docket
f3e23a70-4481-5655-922f-ff3707261478 | note | Responsible Person - QA/Foreperson
3554adfa-efd4-580a-af84-1ced7492e089 | checkpoint | 10 - Removal of Surplus Chip
49577832-d5c9-5791-9f88-b08967e63a5b | note | Verification Activity - Physical / Visual
15500140-14dc-51eb-8740-582ee5c25187 | note | Methods or Reference - Front Mounted Broom / Suction Truck, Downer Survey or MS Forms Post Seal Inspection
75881ae6-972d-5dbe-b21a-11beade9590a | note | Frequency - At conclusion of positive traffication within 48 hours
4d8fcd80-e4c9-5e55-8a6c-fe88978263fb | note | Acceptance Criteria - All sump and road furniture protection removed. Meets requirements of P/17 Table 2.
d9a1aab0-0398-5125-af55-ebb71de19d4a | note | Hold / Witness Point - Witness Point
58d042ae-4da8-5a33-990c-8ea6ebf09769 | note | Records - Post Seal Inspection
562d297e-ed14-551a-9619-b71612608589 | note | Responsible Person - Sealing Contract Engineer / QA
eeeb3404-d9dd-5127-8727-25e782887735 | section | Post Seal Construction
8ff292a5-e74c-563e-bc64-1a3f84d7a66b | checkpoint | 1 - Post Seal Traffic Management
244ce85d-fbba-5024-9846-bddd853817bd | note | Verification Activity - Physical / Visual
dbcc3c7c-91b7-55db-98c5-df6ec47389ef | note | Methods or Reference - As per TMP
5039ed17-12d1-5474-b02d-4d310838160e | note | Frequency - Full length and width of carriageway
a3b82f8c-d0c8-58d8-9b94-4e24dd609387 | note | Acceptance Criteria - Minimum of 48 hours under normal traffic flow. If rain forecast within 48 hours, traffication recommences until clear weather window of at least 48 hours
71e5db67-c562-50fe-8665-dd628c906f8d | note | Hold / Witness Point - Hold Point
dee97c17-2077-507b-976d-5abac7b2545a | note | Records - Zeus or suitable recorded weather data
3351725b-5018-5821-8a00-05dc56fbfa44 | note | Responsible Person - Sealing Contract Manager / Engineer
ca1e4a5d-ef92-588a-8337-eb91710ac3cd | signoff | AUTHORITY HOLDPOINT
2d1fb8cd-fa24-5802-96ee-1dad52b9914f | checkpoint | 2 - Post Seal Inspection
19529b50-9753-5c38-82c5-9d79a1bfb01f | note | Verification Activity - On Site Visual
9a2f8c38-c468-57ae-8fff-9a6c342f7859 | note | Methods or Reference - Lucidity Post Seal Inpsection
8429ca27-78bd-513c-a810-21408c2d3b60 | note | Frequency - After sealing is complete
f6b50d8d-bd73-5fa8-a810-94b9bf2091a2 | note | Acceptance Criteria - Engineers requirements. Any defects identified, repairs programmed and costs estimated
bce1dd4e-62d7-555b-9282-a1afb8b177a7 | note | Hold / Witness Point - Witness Point
21845532-91bf-5fee-9ec5-fb8b3980044c | note | Records - Post Seal Inpsection
fd5ce92b-ef45-5b38-a697-baa8769bd2f6 | note | Responsible Person - Sealing Contract Engineer / Manager / QA
619aff3e-1d69-597d-b461-874087fbe0aa | checkpoint | 3 - Asbuilts and RAMM data
2074b931-7750-5889-a8cf-f8c7fda4fe35 | note | Verification Activity - RAMM Update Sheet
61547549-c397-5b32-af88-7365b50f42cf | note | Methods or Reference - RAMM Database
9f0947aa-9ff7-54e0-a8a2-7a93f85ee5db | note | Frequency - After sealing is complete
0f90bb80-6222-5e87-baab-e396bf03817d | note | Acceptance Criteria - RAMM update sheet 100% complete and accurate, note data provided for RAMM update to be uploaded by others. As Built Drawing Complete.
afedc4fa-85a1-5b4f-9af4-d22c193cc451 | note | Hold / Witness Point - Witness Point
893491fc-5cb9-502b-a279-b7ebe81ebbf7 | note | Records - As built information / RAMM Update Sheet
28e609c3-0912-5412-b4e3-86391093b747 | note | Responsible Person - Sealing Contract Manager/ QA/QE
65da45e6-fe89-5f07-bd89-3689037c4393 | checkpoint | Quality Record Close Out:
317778d0-32ac-53f6-8c18-fbc44dec9644 | textbox | Name:
c945fbe5-2849-55a9-aa57-62966428ad60 | date | Date:
02487113-a0d4-50b0-8176-3b37d69fe6b0 | signoff | Add Signature
14e0dc44-1481-534d-956b-383650624467 | checklist | ITP - Culvert Construction Rev 0 | itp | ITP - Culvert Construction
18625714-ce94-5597-8f08-06d796c0bb28 | section | 1.0. AGGREGATE AND PIPE / ACCEPTANCE TESTING
fa55c305-6395-5ddd-8d6b-ec292230bc6d | checkpoint | 1.01 - Bedding Material
274cc01f-a219-5dc6-8280-74f8872b9fdc | note | Detail of Activity / Test - Well graded GAP 7 will be used and tested for Grading, Linear Shrinkage, Weathering Index, Crushing resistance, Maximum and Minimum Dry Densities
80a95df4-dda7-5089-99db-d11d7038ebc8 | note | Action (Hold, Monitor, Witness) - H
ed1df31b-8d78-51e3-9243-dfd1b03c3eb1 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
48060952-5acf-5b0e-a1c7-b6d4ba435cad | note | Inspection / Test method - Test Report
224dab66-3f19-54d1-b091-8bcb81373b76 | note | Acceptance Criteria - Compliant With AS/NZS 3725:2007
3b7b0a25-af10-5bbf-914e-775be647de9b | note | Record documents (QCP - Quality Control Portal) - IANZ report
f53c622a-c976-5cc3-bb5e-a7d60f56aae7 | note | Responsibility - Contractor
f3d899c1-dee0-583c-b12e-dd8e800acb81 | note | Designer / PTG - A
acdd5b6d-9d56-5fde-a590-50e12271bc48 | note | Eng. Rep / NZTA - I
78588d6f-e962-598f-a191-08c88736a466 | note | Contractor - R
4d700e7a-6f5e-56e1-8fb1-948b2ca0bd93 | signoff | AUTHORITY HOLDPOINT
ebe994d3-5ad3-54f7-b87c-b949d2f19b6d | checkpoint | 1.02 - BackFill Material
3670d518-1c9b-5aef-9589-31019b787a2d | note | Detail of Activity / Test - Material Type
5ee7f0f6-4efb-57b5-b719-cfeebb6a21e3 | note | Action (Hold, Monitor, Witness) - H
ddd7f23e-1f8c-55c1-88bf-a5b55b13c84c | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
b00c9cfe-7b49-551d-95a3-7f4061f4a954 | note | Inspection / Test method - Test Report
24bfcb1c-4949-5545-af66-ebf41f405e36 | note | Acceptance Criteria - Compliant with TNZ F/1:1997
69e57144-c777-5a7b-80a7-403cdb80f7b2 | note | Record documents (QCP - Quality Control Portal) - IANZ report
5793c692-783b-5e81-9c45-817741cd31ff | note | Responsibility - Contractor
ca4a1601-4019-5d21-b8df-127ed5f9cb04 | note | Designer / PTG - A
91dc2dc1-50f7-5df2-9707-236a85fde6fb | note | Eng. Rep / NZTA - I
ff9c4c44-b106-5d3a-b531-c1c91e2b79c2 | note | Contractor - R
3456ccca-32df-50f7-88f5-8c34610cc23e | signoff | AUTHORITY HOLDPOINT
ea747ca3-7237-5fc5-89e7-94118cd678e5 | checkpoint | 1.03 - Culvert Pipe
9f64c6cd-a681-5756-8602-716b56645e6a | note | Detail of Activity / Test - Concrete pipes and fittings shall comply with the requirements of AS/NZS 4058:2007 for concrete pipes
3978ab77-4145-5be2-bb6d-633ff40dc424 | note | Action (Hold, Monitor, Witness) - H
7d720220-5c9c-5093-a936-6cac074c1c35 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
90302b29-8591-5bd9-a101-1e81bdb2a989 | note | Inspection / Test method - Data Sheets
8f5db4cb-dfa5-5df0-9ee4-58c4b3865d36 | note | Acceptance Criteria - Compliance with TNZ F3
64f64446-d5ac-5cdd-a14f-46c69ec4ecff | note | Record documents (QCP - Quality Control Portal) - Supplier QA Report
d4eb7b15-f084-5df4-b3ab-3d5dc2cdcd41 | note | Responsibility - Contractor
6c47e60b-d0bc-5893-9bd3-82df09db7a9e | note | Designer / PTG - A
ad9b15a5-e8e4-5b5c-b16f-b8d4a3f4b0ac | note | Eng. Rep / NZTA - I
5cace5c4-024e-5e85-bd6e-4694f8a43e0c | note | Contractor - R
e401f0da-1592-5fb9-810d-64b3987c4b83 | signoff | AUTHORITY HOLDPOINT
66fccb42-ae79-5a0c-aefa-446b55d7525f | section | 2.0. CONSTRUCTION
d506a0a6-20eb-5ce3-ac3a-80a3d213aa27 | checkpoint | 2.01 - Setout
99fc3061-1cd6-59b1-ad68-faaa507c4e89 | note | Detail of Activity / Test - Culverts to be placed in line with existing culvert
4a33bc2f-7f2f-5a96-bd1e-44f349a0abff | note | Action (Hold, Monitor, Witness) - M
df151ec4-ab05-51bd-834c-d308fe846f76 | note | Minimum Test Frequency (Lot = 1 day’s production) - Prior to Commencement
f36d5900-c24d-51e6-8c74-3c42cc725126 | note | Inspection / Test method - Survey
766add28-287f-5dbe-aa45-0f1ec31b0cf9 | note | Acceptance Criteria - Engineers Approval
2db1fa5c-f96a-56e4-a921-c7f6e5001015 | note | Record documents (QCP - Quality Control Portal) - Checksheet
d50e1790-679e-5631-b252-944fcfedbf72 | note | Responsibility - Engineers Representative
7bc9910c-dc6e-5d77-87e2-951ff5a9aac2 | note | Designer / PTG - A
ee7b2235-c889-528f-95c9-e3349353ccd7 | note | Eng. Rep / NZTA - I
4ce420a1-f71f-5548-989c-5792d6864e6a | note | Contractor - R
8352e650-7c90-5039-bd99-344f6425d84a | checkpoint | 2.02 - Excavation
949ee649-a890-5ba1-8e3a-159feda59873 | note | Detail of Activity / Test - Excavtion of Trench should be within tolerances.
1ad636ed-f2b4-5ba1-acf0-dd5072e70bc5 | note | Action (Hold, Monitor, Witness) - M
66bbc3b3-f0e4-5af0-bea7-4af6ededbf7f | note | Minimum Test Frequency (Lot = 1 day’s production) - For each site where Culvert is Required is required
e9faeaac-8ca1-52b1-b06e-20fac6fe5ac1 | note | Inspection / Test method - Visual / Photo
2ef7a0bb-2646-5d5e-8c36-3b2014f5134b | note | Acceptance Criteria - Trench width should wide enough to allow for adequate compaction. Trench should be excavated to the depth of the bottom of the existing culvert.
cde4aab6-3d17-56d1-979a-d179076ea3ab | note | Record documents (QCP - Quality Control Portal) - Checksheet
3331bd0e-a32e-5fa4-b697-02564b174437 | note | Responsibility - Contractor
63de8fba-ddb8-55b7-a8c7-b0c6daf35a80 | note | Designer / PTG - A
90536545-3993-5689-ac48-245592fb2016 | note | Eng. Rep / NZTA - I
288da077-25f1-540e-9278-af71d663a591 | note | Contractor - R
872315cb-ca2b-5728-96e3-50ddf0a81514 | checkpoint | 2.03 - Pipe bedding and haunch zone inspection
d3def7f5-fde5-5c7f-ba40-f5b5dfc9e669 | note | Detail of Activity / Test - Bedding Material
175f1849-3b9d-5b33-b163-b27f7f6e02f3 | note | Action (Hold, Monitor, Witness) - H
89c379a0-1961-50c4-a851-b78b9c5610e2 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per trench length
a0e3c8c9-0ee5-50b4-a973-95e59a5e6249 | note | Inspection / Test method - Visual / Photo
931ec0a3-c14c-59b7-898f-767bb94f70a4 | note | Acceptance Criteria - The Engineer shall complete a Visual Inspection to NZTA F/3: 2010 each strength length on Pipe bedding and haunch zone
c78b838b-c79f-5eca-b5dc-9ed45107cae6 | note | Record documents (QCP - Quality Control Portal) - Checksheet
0df00d4a-111d-5f65-87b2-11595576a85a | note | Responsibility - Contractor
290547f7-4aab-5b26-b49a-0d66deac11ae | note | Designer / PTG - A
8f34cc01-baa1-5803-8ac0-2ee68bc36853 | note | Eng. Rep / NZTA - I
3453f212-6a36-5755-a3b1-e44de5882995 | note | Contractor - R
5a315429-f662-55e1-964b-9dfcc5cbd0d1 | signoff | AUTHORITY HOLDPOINT
f4628ffd-926c-5379-88ef-ccdff68c8459 | checkpoint | 2.04 - Pipe bedding and haunch zone Density Testing
cd75bf8a-24bf-50af-b95a-0765dd3a7daa | note | Detail of Activity / Test - Pipe surround material shall be placed and compacted over the full width of the trench to a finished minimum thickness of 150mm above the crown of the pipes.
7d3e8f4e-7bc6-54ad-84cb-06d912bbef65 | note | Action (Hold, Monitor, Witness) - I
8d3eb213-09cc-5345-b7c4-846e100d25b4 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 15m trench length Minimum of 2 tests between pits/manholes
dbb4ebce-3258-52b8-8a45-da46b335321f | note | Inspection / Test method - NDM / Clegg Report
618efc91-b134-5c74-840d-387fd6a8707e | note | Acceptance Criteria - The pipe bedding and haunching zone shall be compacted to a MDD of 90%
944d054c-fc1b-56b4-a4e8-9a7f127b990d | note | Record documents (QCP - Quality Control Portal) - Checksheet
99275967-9f40-503e-8aef-0c54ff3f59f5 | note | Responsibility - Contractor
d0e099fd-c673-5124-8b69-8211d6f6056a | note | Designer / PTG - A
03edf42b-097a-51ea-9983-55510d18bd47 | note | Eng. Rep / NZTA - I
e87c0aba-2aad-58ac-b35f-8a5f31e11dbb | note | Contractor - R
46552687-0a11-57c5-be78-f338fb8a96a0 | checkpoint | 2.05 - Pipe laying
97fb43dd-c92f-55c7-9e75-5a67c52c21cc | note | Detail of Activity / Test - Pipe To be placed to Line
7021bda3-38c4-593d-b69e-b5328aec9dfb | note | ○ Pipe to be place to grade
02c5ffc9-6fcd-5161-aaab-7803a4693e73 | note | Action (Hold, Monitor, Witness) - M
a0c2b61d-be88-57ff-b06e-eeeb29e25660 | note | Minimum Test Frequency (Lot = 1 day’s production) - Test Each Pipe as it placed
5e03ab23-f014-502c-8a0a-cb03c19650fd | note | Inspection / Test method - Pipe Laser and other approved equipment
4896864f-aee3-5bad-8a58-2dc8a0d100ee | note | Acceptance Criteria - Placed to correct line and level as per IFC Drawings
0ba420a6-9d61-5cfd-af4f-9b3fcb0e83d9 | note | Record documents (QCP - Quality Control Portal) - Surevy Records
682a9fbf-6f74-5c3c-9365-ccf29aac9359 | note | Responsibility - Contractor
f6e388f6-3bc7-51fd-a6e3-e87ede78c852 | note | Designer / PTG - A
33bb5641-481e-5008-90ba-2e5370a72b3d | note | Eng. Rep / NZTA - I
ab8b048a-4c1d-5d99-be86-056b6cd07834 | note | Contractor - R
a1263578-0502-550b-8680-9cb290c5df7d | checkpoint | 2.06 - Side zones Density Testing
c3c84241-517a-5179-9c86-b50c94c505d1 | note | Detail of Activity / Test - Pipe surround material shall be placed and compacted over the full width of the trench to a finished minimum thickness of 150mm above the crown of the pipes.
5158245e-0d07-52c9-ba05-e1d869de9e84 | note | Action (Hold, Monitor, Witness) - I
0e0e9852-8893-5679-8b5c-b0323f2e69cb | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per backfill layer per 15m trench length. Minimum of 2 tests backfill layer per trench between pits/manholes
ab90fe13-5dc8-5213-840f-ad830eaa2b81 | note | Inspection / Test method - NDM / Clegg Report
370d3751-db4f-5f30-97a4-f32328a15a5d | note | Acceptance Criteria - The Side zones shall be compacted to a MDD of 90%
5e06e224-392b-5932-a65d-18836292e0fa | note | Record documents (QCP - Quality Control Portal) - NDM/Clegg Report
9ea94d46-35c0-5f62-94eb-f3f8eba0eb47 | note | Responsibility - Contractor
51dd3da1-aadf-5417-8d46-9aa8f5bb0edf | note | Designer / PTG - A
3daafa42-093b-542e-9159-3d1524537e7a | note | Eng. Rep / NZTA - I
2f81f114-514c-5d1b-90ef-cbb026d3c529 | note | Contractor - R
61e9422f-ebcc-5092-a12f-b0c6a6ba6002 | checkpoint | 2.07 - Compaction above Pipe
da72903d-1f63-58b3-a111-98c57832c46a | note | Detail of Activity / Test - Only hand operated compaction tools shall be used until the backfill has achieved a depth of 300mm above the crown of the pipe.
b7b55e52-e73d-5ea4-83a4-e7c90bdcbcb4 | note | Action (Hold, Monitor, Witness) - I
6eddbb2b-102e-57b8-8af2-37338f18c87f | note | Minimum Test Frequency (Lot = 1 day’s production) - During Works
d0bbaa46-afe0-594e-bede-473a86252a80 | note | Inspection / Test method - Site Records
590d490a-5e5e-5817-85e1-1294a37acf4d | note | Acceptance Criteria - Visual/Measurement
defa67ab-3c1c-5560-9336-ea02a290db18 | note | Record documents (QCP - Quality Control Portal) - Checksheet
a5daa003-55b5-507f-9bf1-db0f54f2c50a | note | Responsibility - Contractor
7f2bd0bc-0c22-53b7-93b9-9e1436949f62 | note | Designer / PTG - A
55d5e1a3-d339-5c4d-8e9a-68f2fc80c56b | note | Eng. Rep / NZTA - I
0c74c0cd-7a55-5777-b575-93da37b2f83c | note | Contractor - R
a4dcecbf-8db9-5bd6-9a86-5b68ea5478e8 | checkpoint | 2.08 - Pipe overlay zone inspection
3032df66-28d5-5ea1-97b6-66a705c88152 | note | Detail of Activity / Test - The Engineer shall complete a Visual Inspection to NZTA F/3: 2010 each strength length on Pipe overlay zone
32965920-ae24-5fe3-b683-19b7a6695560 | note | Action (Hold, Monitor, Witness) - H
b2849ae6-d327-5eda-8aa4-6ce7016f1212 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per trench length (Between Chambers)
365ba9a5-eb92-54b5-9580-586a0a9d988e | note | Inspection / Test method - Engineers Record
9402d3e2-2dcc-521e-a4f0-b9fc6b8583ef | note | Acceptance Criteria - Visual Inspection
52e93c91-7729-5d7d-bd20-b354793e1b09 | note | Record documents (QCP - Quality Control Portal) - Engineers Record
f27cf259-b1c7-5c22-8b76-05f72d8e4040 | note | Responsibility - Contractor
57e00910-adcd-5062-b564-8641783bbced | note | Designer / PTG - A
3f149d7b-d440-54a2-9198-5f4a378c8534 | note | Eng. Rep / NZTA - I
b15c6fad-70d0-59ed-b3f4-d1cc9ed9ccbb | note | Contractor - R
072808eb-ea1c-55d4-b1ba-55198552b9f8 | signoff | AUTHORITY HOLDPOINT
e46fd6e7-1009-50f8-b6c2-7307d132d4d2 | checkpoint | 2.09 - Pipe Overlay Zone Density Testing
f81dc8a3-55d0-52e1-b179-df49ae869340 | note | Detail of Activity / Test - Backfill material shall be built up in layers not exceeding 200mm. The Pipe overlay zone shall be compacted to a MDD of 90%
fa7607d3-2b23-57de-874c-259edef1128c | note | Action (Hold, Monitor, Witness) - I
bfb43e06-7d0e-5ad0-ada1-0980e927ab87 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 15m trench length Minimum of 2 tests between pits/manholes
aa75941a-89ea-5418-bd9d-fef642225c50 | note | Inspection / Test method - NDM / Clegg
0d1ba029-72a7-5801-a5b6-7d5a09a99087 | note | Acceptance Criteria - NDM/Clegg
a050e280-f481-5486-aabe-9fb9252c61be | note | Record documents (QCP - Quality Control Portal) - NDM/Clegg Report
72040962-5dc5-503c-a774-9362d66333ee | note | Responsibility - Contractor
ae311105-723f-5475-8276-bb16617f3159 | note | Designer / PTG - A
bc927965-50dd-5954-8108-2f75f59a6fa8 | note | Eng. Rep / NZTA - I
b03ae02e-9132-5e4c-94b3-b8803b9f61d2 | note | Contractor - R
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
2d617896-f105-5a9a-9a8e-eb27a600cce2 | textbox | Contractor's Rep Name:
dca3646a-8ee6-5cad-ab9b-58eb8beccfbe | textbox | Engineer's Rep. Name:
7205de62-b750-50d0-9564-bfdd05b79b88 | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
62960d88-348f-4f45-992d-31268e2685b2 | checklist | ITP - Dig-out Rev 0 | itp | ITP - Dig-out
bfc697ce-f8b7-4eb4-8a20-482bd3b10035 | section | 1.0 Pavement Repair (Digout)
096edeab-79d8-474f-ba3c-da4bdd444fb0 | checkpoint | 1.01 - Scala
7277ce76-ff04-594d-b003-c5bac0e42aea | note | Detail of Activity / Test - Determine the depth of excavation
30dc5528-8b1c-5e79-ad65-39a0ca1cc05b | note | Action (Hold, Monitor, Witness) - M
e611c666-7bdd-5f2c-bc75-79a36fe84ec3 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where digout is required
2f98c613-5986-5337-8833-34819512b242 | note | Inspection / Test method - Measure / Photo
27f95fd2-c607-5560-b553-565c7634c6a0 | note | Acceptance Criteria - Site Engineers Approval
9e8a79b2-171c-53d5-9b78-f04b74e1e6a4 | note | Record documents (QCP - Quality Control Portal) - Checksheet
8fd8f9d4-4df2-57b1-a428-ff8465a23c37 | note | Responsibility - Contractor
8df8dc35-4a0e-54ef-8051-e7307432720e | note | Project Specific Notes / Instructions -
244ac0e4-be5b-56f9-aa47-317a6e03590f | note | Site Engineer - A
801fee59-2713-5222-b1e4-51ec46b5a85c | note | Eng. Rep / NZTA - I
ea1b1091-84d1-55b4-a79b-a3bdf2fcea72 | note | Contractor - R
34534ed7-d431-4a07-b07d-b681af84b94b | checkpoint | 1.02 - Excavation
8203d385-0679-50b9-9bea-ccbe6fff0861 | note | Detail of Activity / Test - Excavate existing pavement from finish road level (FRL) and depth will vary from scala result
028831b7-887a-5e49-9ca4-0f54d7cf1043 | note | Action (Hold, Monitor, Witness) - M
15fed6bd-9c1a-53d9-bb8d-cdd293174bfb | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where digout is required
34d9da90-142b-5a57-acc4-c9dbc15c206d | note | Inspection / Test method - Measure / Photo
78c3d791-d054-5baf-83da-8eba6556d4c2 | note | Acceptance Criteria - Site Engineers Approval
69e13425-a75d-526c-b27e-ca0a88affa23 | note | Record documents (QCP - Quality Control Portal) - Checksheet
f0f0f4d1-32b0-5c3c-b419-d8a74062555f | note | Responsibility - Contractor
1b4169fe-b475-5d5a-9909-71eb04feb763 | note | Project Specific Notes / Instructions -
b353158d-20bd-56e7-997a-df399ad01ddd | note | Site Engineer - A
76857ee6-d3c4-5e6c-a03f-81cbbc9800c6 | note | Eng. Rep / NZTA - I
c2e158e0-5f6c-5285-99d1-c90e56142ef1 | note | Contractor - R
d05b7c51-29ac-4261-96d2-18acf340ba3e | checkpoint | 1.03 - Geogrid
92f7da21-b0ad-52ed-9d94-94f8563bc113 | note | Detail of Activity / Test - Geogrid maybe installed to reduce the digout depth
094edaa0-c956-52fc-bdf5-c9c9ed43d7c5 | note | Action (Hold, Monitor, Witness) - M
530ccd10-dd63-5ade-b03f-c1af1c2d4003 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where digout is required
4428aed9-f13e-5f7f-b3b5-61d1c70a6bac | note | Inspection / Test method - Photo
8f2542c3-fabd-569f-9e75-ad353fd8fa76 | note | Acceptance Criteria - Site Engineers Approval
418c0886-d7e0-559c-8e09-d3dc9c2adb36 | note | Record documents (QCP - Quality Control Portal) - Checksheet
33f8854c-7e0e-585e-8f47-10503194611f | note | Responsibility - Contractor
af70a807-973e-53d8-a900-44da771aca57 | note | Project Specific Notes / Instructions -
b24f4e92-2d1a-5d03-be09-ffa435629e76 | note | Site Engineer - A
5fed0014-2a97-5ee7-88cf-fed0c05d91b6 | note | Eng. Rep / NZTA - I
1d1195bc-928d-54b7-b455-193fab355495 | note | Contractor - R
d1df1a5a-62f2-4581-94ce-ca0173a3e0f5 | checkpoint | 1.04 - Backfilling Thickness
69362c18-51fc-56de-9a25-d644b81b772d | note | Detail of Activity / Test - Layer thickness is not to exceed 100mm (compacted), cloth will be installed prior to backfilling and AP40 to be used.
e37088fd-7e29-5806-9f75-6208adf5b542 | note | Action (Hold, Monitor, Witness) - M
cf4fe7ce-5650-5785-8650-9956734b5c47 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Varies from the depth of excavation
dfeb748b-70df-5cc6-897c-211e3422cd47 | note | Inspection / Test method - Measure / Photo
bc04e8cf-12ac-5ef4-b6b5-b9ad066629b6 | note | Acceptance Criteria - Site Engineers Approval
6d6a0f50-2d78-592a-ad03-e8ea814a432a | note | Record documents (QCP - Quality Control Portal) - Checksheet
adb0d86a-ec15-5a9c-93bd-e63f5c0b2347 | note | Responsibility - Contractor
5f77c771-8d0c-52e0-aecc-59d8d4b37c8a | note | Project Specific Notes / Instructions -
320779d8-ef89-51e4-89ca-4439cd4288d6 | note | Site Engineer - A
a50818b6-3f6b-51ed-8f6e-ce34d0fdc72b | note | Eng. Rep / NZTA - I
3f0f6b3f-4e0a-5045-8821-c9b922aa585c | note | Contractor - R
28351c88-b978-48dd-bc43-3eb2bef1ab40 | checkpoint | 1.05 - Compaction Requirements
a03ce139-7dbd-52ba-af35-81d583f8f010 | note | Detail of Activity / Test - Clegg Impact Value using
bdc5afa3-b1f6-584a-9642-996460722dbf | note | Action (Hold, Monitor, Witness) - H
50635c36-41fa-54a0-b9db-6c647c49987c | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Every 100mm depth compacted
20c182c2-8429-5444-b50e-309ec28e3f02 | note | Inspection / Test method - Measure
1d4b218c-8745-53fb-aacd-fdd5cdc94964 | note | Acceptance Criteria - Clegg Impact Value (CIV) ≥ 30 if NDM is not available on site
31d79e02-c3e3-55d5-9a04-a350f9a9b9af | note | Record documents (QCP - Quality Control Portal) - Carried out by competant operator, record results on digout Checksheet
95da5007-25de-5909-8e49-3ec30b90dab4 | note | Responsibility - Contractor
9b48d1ab-fc6e-5dff-8b74-b3aab761d0ff | note | Project Specific Notes / Instructions -
9c79b85b-88e4-5945-bcfd-b35140810b01 | note | Site Engineer - A
18228ba5-4f4e-5b42-a17c-8425b8457af6 | note | Eng. Rep / NZTA - I
97e6f2b2-3c02-5821-9fc5-713ca356f33e | note | Contractor - R
a0a27575-de74-4e97-a919-d5132b9c4227 | signoff | AUTHORITY HOLDPOINT
f3e8f80b-1258-4404-b15d-a71e6e536955 | checkpoint | 1.06 - Finished Level
34403f2f-1ac4-5469-894c-54adb6c361d6 | note | Detail of Activity / Test - Ensure the finished level of subgrade is flush with existing surfacing and there are no depressions that could hold water.
d139d392-711c-5d1b-a9a2-76bdead70f3f | note | Action (Hold, Monitor, Witness) - M
5d64e193-db58-5f95-a981-a6453471ee2e | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where digout is required
7a5305f0-840d-568b-846b-9c7c0b237cba | note | Inspection / Test method - Visual / Photo
34856082-dd26-58f2-aad9-003cd0c90935 | note | Acceptance Criteria - Site Engineers Approval
1be9d37b-e48a-596d-88d0-899cc53dc611 | note | Record documents (QCP - Quality Control Portal) - Checksheet
11d86a04-3543-5661-b3c5-d5b807376261 | note | Responsibility - Contractor
3189da0e-a3da-503c-b6da-555571aa8828 | note | Project Specific Notes / Instructions -
c1739d1a-5d42-5d30-95f1-68fa48c1bb25 | note | Site Engineer - A
6b0b89bd-538d-5bbb-9444-4d9c41dd161e | note | Eng. Rep / NZTA - I
b30550d7-6869-59ff-9678-f123f4292509 | note | Contractor - R
bc916954-6a4e-4f7a-966a-6d25eacfb735 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
a990c8fe-64f0-57f2-a984-35afd647a485 | textbox | Contractor's Rep Name:
6cf8bde1-23c7-5a95-affe-a14e1f4b409b | textbox | Engineer's Rep. Name:
34a120b4-38c6-5027-8fa5-29fec82a1e6d | date | Date:
f0b3db43-193a-4a65-9eed-5e7047c74ad4 | signoff | Add Signature
a9c3f9ed-5013-4e14-927a-5cff3e03fafe | checklist | ITP - Entranceway Culvert Construction Rev 0 | itp | ITP - Entranceway Culvert Construction
7cd9c452-3a1d-4e2b-b199-353c13399a7a | section | 1.0 AGGREGATE AND PIPE / ACCEPTANCE TESTING
973a0fb0-7302-47f4-bf76-3dd5c818fffe | checkpoint | 1.01 - Bedding Material
e67b668e-55dd-59c6-a167-37572d86b746 | note | Detail of Activity / Test - Well graded GAP 7 will be used and tested for Grading, Linear Shrinkage, Weathering Index, Crushing resistance, Maximum and Minimum Dry Densities
13e5b326-d278-5b44-a8f5-8932de341fda | note | Action (Hold, Monitor, Witness) - H
dcf5c52c-a420-5ca9-9be1-b24c60123c83 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
89891977-be74-5c03-acec-194066366d55 | note | Inspection / Test method - Test Report
0791b8ac-faf7-5332-a2d2-ad78c8a9b783 | note | Acceptance Criteria - Compliant With AS/NZS 3725:2007
c50cc778-f313-56c5-bdc3-e852ad221a64 | note | Record documents (QCP - Quality Control Portal) - IANZ report
83af71da-05cc-50c0-97de-383a6fa31701 | note | Responsibility - Contractor
4e4cccf5-79cb-57fe-8ef6-f54862004c1e | note | Site Engineer - A
2357db29-9a42-5a4e-afdb-13320921554a | note | Eng. Rep / NZTA - I
1de7d93b-b514-533f-b42b-571d5421132e | note | Contractor - R
9ae13aa5-b45e-468f-98b7-a95643d1ca0d | signoff | AUTHORITY HOLDPOINT
95da942c-423e-4b93-8f2f-558b5c078f51 | checkpoint | 1.02 - BackFill Material
6582ab4d-1a76-56d1-a738-a6a2a42c7f3a | note | Detail of Activity / Test - Material Type
db2e068b-93ea-55c5-9a9c-c37f522a302b | note | Action (Hold, Monitor, Witness) - H
92175edd-cf29-5023-b103-569913b941c1 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
a4424d27-3047-53a2-806a-5a691a0a598c | note | Inspection / Test method - Test Report
16569766-061f-5e57-b9f0-99ff48c2e39f | note | Acceptance Criteria - Compliant with TNZ F/1:1997
9ada5006-94da-5e76-935f-072fb5da536e | note | Record documents (QCP - Quality Control Portal) - IANZ report
f759b9c9-8967-51ce-9994-d6a884797a53 | note | Responsibility - Contractor
83a9b447-3113-551f-99c0-1c070f6c86d7 | note | Site Engineer - A
d5dc3731-57cb-5464-a31c-d663f9f8e0e5 | note | Eng. Rep / NZTA - I
757c6526-d2a5-52bf-9c31-94bd99944db5 | note | Contractor - R
c3734fc4-9dc6-461c-acc1-cee870700771 | signoff | AUTHORITY HOLDPOINT
d6b35da0-e02c-403e-b3d8-a1175f2803ae | checkpoint | 1.03 - Culvert Pipe
63058d07-88ff-5be9-ba4f-c1b8962d9854 | note | Detail of Activity / Test - Concrete pipes and fittings shall comply with the requirements of AS/NZS 4058:2007 for concrete pipes
12aa98d5-c517-52a3-b6bd-36e227cb36fd | note | Action (Hold, Monitor, Witness) - H
a81e17bc-2f38-521b-aa17-d37ed0e46711 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
ec0c6681-7145-5c02-98ab-659bc830b5d1 | note | Inspection / Test method - Data Sheets
928d2c9f-1d23-5b7d-8f1a-a6219d2db69b | note | Acceptance Criteria - Compliance with TNZ F3
2b672e0d-f619-506f-b6cf-09894be190ee | note | Record documents (QCP - Quality Control Portal) - Supplier QA Report
3c66b0e8-7596-596c-8aef-fc7125abeb24 | note | Responsibility - Contractor
76f9dbc8-3958-588c-ada1-032667f88196 | note | Site Engineer - A
bfd3acaf-bd74-58b1-b7db-3a24e6735192 | note | Eng. Rep / NZTA - I
48e24af4-dfef-5ac2-a1b7-25d169ca6e73 | note | Contractor - R
c8a77040-494d-49b7-a814-c19bcf2bf905 | signoff | AUTHORITY HOLDPOINT
a03c0744-0574-4578-9917-8a7082104ab1 | section | 2.0 CONSTRUCTION
ab8a245c-c2f3-43eb-9b84-5ec8b8f88077 | checkpoint | 2.01 - Setout
8fc463cf-8a42-5aa9-9744-dbf863f8da4c | note | Detail of Activity / Test - Culverts to be placed in line with existing culvert
8d67159c-d728-50b1-b32e-19e57a94eb31 | note | Action (Hold, Monitor, Witness) - M
6fc7a28e-d5ea-5572-8379-064d32135a37 | note | Minimum Test Frequency (Lot = 1 day’s production) - Prior to Commencement
210d9367-f814-51e1-b0bb-bcee9d730183 | note | Inspection / Test method - Survey
476b9244-7fd6-59b0-b34f-d7fa72ba5991 | note | Acceptance Criteria - Engineers Approval
e317f9b8-ecf7-52be-a070-8e8899d7822b | note | Record documents (QCP - Quality Control Portal) - Checksheet
5e3f17e2-c770-5520-bc5b-b6238a6c0ed3 | note | Responsibility - Engineers Representative
ec173adb-9ff4-5eba-8fef-4f3318904a3b | note | Site Engineer - A
dda00c33-3653-59b3-b005-91f3d5ba0a08 | note | Eng. Rep / NZTA - I
1808582e-476e-5a89-b00d-56cf2170a068 | note | Contractor - R
9aaa9cbb-696e-4014-bcee-fd54fd76a937 | checkpoint | 2.02 - Excavation
9032c677-9e63-536b-8009-b9d96c879494 | note | Detail of Activity / Test - Excavtion of Trench should be within tolerances.
e050084c-c99d-5150-9dec-2efc83eb151e | note | Action (Hold, Monitor, Witness) - M
e227faf1-09f1-5b8f-8f65-6e02d0a68304 | note | Minimum Test Frequency (Lot = 1 day’s production) - For each site where Culvert is Required is required
a5ecb2c8-82f7-5cbb-bf0d-3b926302e5d9 | note | Inspection / Test method - Visual / Photo
89a11589-53a9-5215-b55a-cfb7a6b3ac0a | note | Acceptance Criteria - Trench width should wide enough to allow for adequate compaction. Trench should be excavated to the depth of the bottom of the existing culvert.
7fc1378c-a95f-5175-b982-1297fe25a8cd | note | Record documents (QCP - Quality Control Portal) - Checksheet
b2b26234-c7f2-59c0-a1dc-49d9247fb0f6 | note | Responsibility - Contractor
cc908c92-042f-5713-9f80-c1d0f91a0494 | note | Site Engineer - A
6472e02e-170c-500d-ada9-7ef10e0b436c | note | Eng. Rep / NZTA - I
17a93324-088c-5183-9a96-ed60bbe8c839 | note | Contractor - R
4d682299-5da0-4739-9013-7e9487903006 | checkpoint | 2.03 - Pipe bedding and haunch zone inspection
991f5dfd-7235-5ff5-a20d-2d69a0c7a947 | note | Detail of Activity / Test - Bedding Material
61f79681-0430-5297-8192-80853ac8b086 | note | Action (Hold, Monitor, Witness) - H
fbcd09fd-ce4d-51c6-90d1-5eed1c56f28a | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per trench length
ae173ef5-5c92-52c5-89dc-4678a35b6050 | note | Inspection / Test method - Visual / Photo
95d78a3e-cb88-5c89-9d59-6f3b93628ee7 | note | Acceptance Criteria - The Engineer shall complete a Visual Inspection to NZTA F/3: 2010 each strength length on Pipe bedding and haunch zone
56f0281d-6ab2-5b08-967a-1d250a7442c7 | note | Record documents (QCP - Quality Control Portal) - Checksheet
0e85c594-7e29-57c0-b52d-ec190e674f1a | note | Responsibility - Contractor
e481310a-fb62-5703-b7ec-4d9deb1e3bc2 | note | Site Engineer - A
db409aab-7a1c-560e-9444-92fa085566e4 | note | Eng. Rep / NZTA - I
9ea20092-475d-59df-89d0-0d91de2aa96c | note | Contractor - R
7f0d1602-6a22-4bd6-b0b6-7be85836b6d6 | signoff | AUTHORITY HOLDPOINT
5b774c33-0779-44d9-8c84-77bbdaf41441 | checkpoint | 2.04 - Pipe bedding and haunch zone Density Testing
68af21e8-59da-50b0-b82e-ec041996c7cf | note | Detail of Activity / Test - Pipe surround material shall be placed and compacted over the full width of the trench to a finished minimum thickness of 150mm above the crown of the pipes.
69e4c274-5166-58e0-95f1-2d15f7cbaf4d | note | Action (Hold, Monitor, Witness) - I
0cd1795e-ca65-5030-9677-ce26f34076e2 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 15m trench length Minimum of 2 tests between pits/manholes
ce61b99e-ce1c-5b38-aff1-b0777b687574 | note | Inspection / Test method - Clegg Report
f211f1e8-e757-5161-937c-20ae4b5b4af3 | note | Acceptance Criteria - The pipe bedding and haunching zone shall be compacted to 20 CIV
4f00db1d-9039-5198-a1f8-7cc94dbbab25 | note | Record documents (QCP - Quality Control Portal) - Checksheet
ea7f316d-6724-5b39-98d0-4909f8b20390 | note | Responsibility - Contractor
f64387e7-d295-5571-882c-41085ae0002c | note | Site Engineer - A
2ed28889-1412-5ff4-828f-de1885816e53 | note | Eng. Rep / NZTA - I
d2e36367-c947-568f-b08b-d4efd45d3601 | note | Contractor - R
adbb51c5-9651-4377-a0ae-fd5deb7c3626 | checkpoint | 2.05 - Pipe laying
84e2f68a-8f21-50be-9cdc-07c497d5d72e | note | Detail of Activity / Test - Pipe To be placed to Line. Pipe to be place to grade.
66f9a35a-53ce-5850-b98a-abf929ddcee0 | note | Action (Hold, Monitor, Witness) - M
2e82bf61-acaa-5fbd-8cf3-40b494e0bc94 | note | Minimum Test Frequency (Lot = 1 day’s production) - Test Each Pipe as it placed
cbe0d7ea-645d-503e-be8f-a53cab6736c1 | note | Inspection / Test method - Pipe Laser and other approved equipment
5b7ab9aa-8b34-566f-bcc6-f350640fe726 | note | Acceptance Criteria - Placed to correct line and level as per IFC Drawings
1eb536be-7172-5765-b165-f42bd713aaac | note | Record documents (QCP - Quality Control Portal) - Surevy Records
3f274b6f-4e32-51e1-a52c-5d121aa7bd12 | note | Responsibility - Contractor
8801753a-9ec0-5beb-8bf7-0eeb38b92457 | note | Site Engineer - A
4863ba38-21c6-5fa3-b9cc-361fb759773c | note | Eng. Rep / NZTA - I
8ea4c463-76bb-54a8-b7bb-0541ba8ae055 | note | Contractor - R
959b330e-fdb1-4d2a-a789-4accc678d803 | checkpoint | 2.06 - Side zones Density Testing
47f3b02a-0165-5fc2-9a27-4735e6990ef4 | note | Detail of Activity / Test - Pipe surround material shall be placed and compacted over the full width of the trench to a finished minimum thickness of 150mm above the crown of the pipes.
78641cb6-515c-500e-ba26-167392339b22 | note | Action (Hold, Monitor, Witness) - I
47b20fa9-5343-5d77-bb6a-a5d288332bf2 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per backfill layer per 15m trench length. Minimum of 2 tests backfill layer per trench between pits/manholes
b8dad07d-b2b1-5172-83d1-484be932a41c | note | Inspection / Test method - Clegg Report
5cc99985-2a61-59d8-88c2-d408b95a418f | note | Acceptance Criteria - The Side zones shall be compacted to
7e80572d-6e7a-5047-9b0c-6274c7e9715a | note | Record documents (QCP - Quality Control Portal) - Clegg Report
d19ca8ef-caf8-58f2-a10a-a7fd007dfc8f | note | Responsibility - Contractor
8e745c62-5030-5b00-a386-dd4f8d61a0f3 | note | Site Engineer - A
eefb7188-a59f-5704-8295-3a503c579abc | note | Eng. Rep / NZTA - I
6160fd16-0968-5cd8-a7eb-c4c7acd62680 | note | Contractor - R
cbe944e5-49f0-491f-9104-973d72d7bfaa | checkpoint | 2.07 - Compaction above Pipe
625172d8-892a-557e-9e74-8077edb500c1 | note | Detail of Activity / Test - Only hand operated compaction tools shall be used until the backfill has achieved a depth of 300mm above the crown of the pipe.
d49d47bf-2786-58ea-a19e-d0064322e5f6 | note | Action (Hold, Monitor, Witness) - I
7f1346f7-b23b-5114-baad-2037a64c97b0 | note | Minimum Test Frequency (Lot = 1 day’s production) - During Works
b0e9d6df-e16c-57a7-862f-ff1bedee6fb3 | note | Inspection / Test method - Site Records
8e77db7b-89f5-56ac-bf14-342d1b0c3901 | note | Acceptance Criteria - Visual/Measurement
2dbb0cf5-cf35-531e-bb48-3a4d6170d6a5 | note | Record documents (QCP - Quality Control Portal) - Checksheet
0ca54830-c442-52d1-9faa-dd25edc5fa3c | note | Responsibility - Contractor
53e5b00a-154a-56ad-9005-fc767ec331df | note | Site Engineer - A
9d2b0a8b-757f-5f7f-bcf7-3d2e57e8348c | note | Eng. Rep / NZTA - I
d8278863-6941-5085-9c36-07a76bf3367f | note | Contractor - R
6c8fe86a-563d-4b6e-88f0-7e3c0c714c71 | checkpoint | 2.08 - Pipe overlay zone inspection
38653f60-bbd4-5c52-803f-eee252cd6c63 | note | Detail of Activity / Test - The Engineer shall complete a Visual Inspection to NZTA F/3: 2010 each strength length on Pipe overlay zone
54de3b72-048c-5565-abb4-a7457d4b6b67 | note | Action (Hold, Monitor, Witness) - H
7fbb23a2-8600-591a-90fb-f0d49360fd5f | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per trench length (Between Chambers)
e28263a1-9c53-518c-a06f-d23a1e1ac23c | note | Inspection / Test method - Engineers Record
3754257c-e7e4-5ede-8dfd-74e219366da1 | note | Acceptance Criteria - Visual Inspection
05ba82b1-6206-536a-83f7-d03eb7a28462 | note | Record documents (QCP - Quality Control Portal) - Engineers Record
0b9f8ac6-704e-5b44-813b-ea7350b46171 | note | Responsibility - Contractor
e5870d53-b00a-568f-900e-1ead75a93f47 | note | Site Engineer - A
3f4b2619-21f0-5af7-8c39-85cff36e6e82 | note | Eng. Rep / NZTA - I
2a69ad33-1c22-552b-af27-7f9bd5c30060 | note | Contractor - R
8615b806-d553-4895-88f6-147efefa0200 | signoff | AUTHORITY HOLDPOINT
c6906680-af67-4dbd-a8a4-577c883389fc | checkpoint | 2.09 - Pipe Overlay Zone Density Testing
435793f1-aafb-599e-82cf-782da30df387 | note | Detail of Activity / Test - Backfill material shall be built up in layers not exceeding 200mm. The Pipe overlay zone shall be compacted to a MDD of 90%
c0e83ae2-b611-56bc-b473-bbf03006f6b4 | note | Action (Hold, Monitor, Witness) - I
138b1cb6-1bc2-5bc0-8ecd-300bb0cc4415 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 15m trench length Minimum of 2 tests between pits/manholes
c94749a7-2c02-5c6d-8a3e-31bbc601a9ff | note | Inspection / Test method - Clegg
30062dac-9450-5f15-8938-4bfbeefdf46c | note | Acceptance Criteria - 30 CIV
91735a8f-a732-516b-b00c-05d7a8bc94a4 | note | Record documents (QCP - Quality Control Portal) - Clegg Report
25ea1c9e-8aaf-5dd1-aa00-e7ae3f9fd11a | note | Responsibility - Contractor
59b5db9c-92be-582c-983f-d677f9f134c1 | note | Site Engineer - A
0785e68f-0f63-5926-892a-c7393bb976f2 | note | Eng. Rep / NZTA - I
5496c9cc-c1d3-55b7-95d5-3e46cbff9343 | note | Contractor - R
8011cfd9-513a-4a5d-bc44-fe5f5c6c4813 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
3d47b767-72ed-5e81-b235-b5fa46e5b57b | textbox | Contractor's Rep Name:
369d6a9b-f51c-5256-90f8-ca2bd523c6d2 | textbox | Engineer's Rep. Name:
36d7bbba-c1bf-5c35-add0-a74938baf7fa | date | Date:
df2f4a1b-7925-456c-8f40-460e399d1dbd | signoff | Add Signature
10dd382c-f6f8-5ffa-b464-ddfbbb1bf28c | checklist | ITP - Entranceway Rev 0 | itp | ITP - Entranceway
c698dab8-acda-52b7-987b-2acecfeccfcf | section | 1.0. AGGREGATE ACCEPTANCE TESTING
7f75c0bf-94bb-5d2d-8aa5-43911e3260ba | checkpoint | 1.01 - NZTA M04
7383fada-66a6-59a2-8388-f7f9ec125b6b | note | Detail of Activity / Test - Crushing Resistance
a970e88a-3396-5032-bee2-15cb7b6f8f42 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
384537ff-f11e-56ee-b20c-cf6267115c0e | note | Inspection / Test method - NZS4407:2.4.7
682cd5b8-7f79-5fc4-8be0-2528d3f5eaba | note | Acceptance Criteria - > 130KN
14ef7184-0d6c-5046-bef6-f3affcb97cd9 | note | Record documents (QCP - Quality Control Portal) - IANZ report
a20ff025-9224-5e5b-be3d-bc3989d227b9 | note | Responsibility - Contractor
63ff2a4b-003f-53df-9254-5f7fea3c3db6 | note | Designer - A
a639f66e-1d19-534b-a3b3-c0263506c209 | note | Eng. Rep / NZTA - I
b2ea6146-1ada-5838-af47-301ec9592c69 | note | Contractor - R
1d15ff46-5f4f-5e5a-abb2-ce4a9d764b0d | checkpoint | 1.02 - NZTA M04
c79cc3d2-efaa-57a4-9c10-5a02826c412c | note | Detail of Activity / Test - Particle size distribution
52b0e159-0b32-5767-ba25-bb5075fcf860 | note | Action (Hold, Monitor, Witness) - H
b21bb7e4-b14e-5d8c-a866-97936e846815 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
94cd806a-60e8-54c9-ae3d-7a717a41f84d | note | Inspection / Test method - NZS4407:2.4.7
e8fd52c5-1a65-5565-8ef0-0eac7bb0a21e | note | Acceptance Criteria - As per NZTA M04 Specfication
22be14b5-e0c3-5917-aeb6-f8137f4849ef | note | Record documents (QCP - Quality Control Portal) - IANZ report
413dead7-777e-5487-8986-e508b66253ce | note | Responsibility - Contractor
62371b09-4024-556a-8581-79d3c1df01d6 | note | Designer - A
e16be062-4d34-566d-b63f-0f3d85f30ecb | note | Eng. Rep / NZTA - I
85253e45-3002-5ce8-bfe3-79636aa5bc70 | note | Contractor - R
5ecb0763-95b6-5726-8494-66d0c2f95ad6 | signoff | AUTHORITY HOLDPOINT
66fccb42-ae79-5a0c-aefa-446b55d7525f | section | 2.0. CONSTRUCTION
5b802e8c-ba68-5859-b05d-d1617c42a80d | checkpoint | 2.01 - Earthworks
384dda4c-367a-5365-9e61-1103c66c463f | note | Detail of Activity / Test - Scarify Existing Entrance way Surface
6d425b3a-2462-5133-b452-9e6f7b66693c | note | Action (Hold, Monitor, Witness) - M
7291392f-6cde-50f3-a66d-3e1d3a4e9c1f | note | Minimum Test Frequency (Lot = 1 day’s production) - As per design drawings
d26c0fc4-59ac-51b2-a20f-0f24128b1c92 | note | Inspection / Test method - Visual / Photo
f072246b-064a-5ae9-9749-cb0b1fc1a253 | note | Acceptance Criteria - Site Engineers Approval
4687f810-dde0-55af-95e5-cdcc2ad0bc54 | note | Record documents (QCP - Quality Control Portal) - Checksheet
80d7c0fc-74ae-59b3-9f3e-735de7e72a9e | note | Responsibility - Contractor
6e1d4103-705a-5f6b-8be7-65b2648ccaf2 | note | Designer - A
f402900d-8d7f-596b-8ec9-932caaa5dafe | note | Eng. Rep / NZTA - I
c7f55712-3b7e-51f8-99ab-4d22d51c482c | note | Contractor - R
5a35f15b-c3be-52d4-926a-1e55e27bf6bd | checkpoint | 2.02 - M4 Placement
7038fdaf-c644-59e1-88ce-efeb9bb5b250 | note | Detail of Activity / Test - M4 Placed in Accordance with Design Drawing and Survey
015018be-1eed-58ea-b6e0-b41db42f7191 | note | Action (Hold, Monitor, Witness) - M
528b1e70-951d-5922-8d3c-0b3a815b548c | note | Minimum Test Frequency (Lot = 1 day’s production) - As per design drawings
08f5678e-b3b8-5d92-831f-371d463d3672 | note | Inspection / Test method - Visual / Photo
30fd34a7-6acf-5744-be76-2b5949672a15 | note | Acceptance Criteria - Survey Record
524bb368-80eb-51c6-8871-9f7db11a7e46 | note | Record documents (QCP - Quality Control Portal) - Checksheet
701cec4b-a716-5b41-b3c3-f4ce9ab56889 | note | Responsibility - Contractor
42407029-6710-579f-9a63-4dc63894f835 | note | Designer - A
cc4b52d2-9420-54bb-81c0-c750b052b264 | note | Eng. Rep / NZTA - I
33261346-75ec-5aa2-8050-d3d96ff98ce4 | note | Contractor - R
58907c6f-a246-58ba-bcd0-6d4f16118aaf | checkpoint | 2.03 - M4 Compaction
2c32c6c9-f915-5474-a23a-71a6777152de | note | Detail of Activity / Test - Compact in Layers no greater than 150mm.
411340bd-5ec8-5bac-b38a-4678c6224960 | note | Action (Hold, Monitor, Witness) - H
83887f74-6a78-51b7-885b-d2f7edf29efa | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test Per 10m2
2762f174-735c-5092-8c27-ce29342bb9fd | note | Inspection / Test method - Clegg
fa418ebd-47df-5dfb-aa5c-d784e7d89c9d | note | Acceptance Criteria - CIV >30
4c890fa0-860f-5317-9352-07a29d7d97f2 | note | Record documents (QCP - Quality Control Portal) - Checksheet
1c315567-a1c1-53ee-8273-14debdd0d2ee | note | Responsibility - Contractor
2de03c0e-4f59-5481-b5fb-d7595feb89fa | note | Designer - I
6770546c-cab0-56e7-be87-6a6728fa27ec | note | Eng. Rep / NZTA - A
edf17f6e-3cb1-5289-afad-6663e71976da | note | Contractor - R
f75311a3-057c-5382-9faf-d9309f11a4fc | signoff | AUTHORITY HOLDPOINT
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
948a54d9-9bcc-5839-a3ed-5febcea6b702 | textbox | Contractor's Rep Name:
785288aa-426a-504f-a1f1-f07cf4745c49 | textbox | Engineer's Rep. Name:
0cba0e96-4f4c-576a-8472-d3e27d74f72b | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
04ddb398-4e2a-4627-9bb5-d83e9ea014c1 | checklist | ITP - Entranceway. Rev 0 |  | ITP - Entranceway Version
2e6f12e9-aa5e-40fb-b3c9-1cf90bb1eb74 | section | 1.0. AGGREGATE ACCEPTANCE TESTING
aaa74b25-80e8-445e-a36a-9e573ceaaf7d | checkpoint | 1.01 - NZTA M04
b12f784f-27f2-5f93-a586-8d8224408b9b | note | Detail of Activity / Test - Crushing Resistance
2b14ebf9-4851-5438-9fb0-06eb7872ed99 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
51cbee16-ef50-532f-976e-f7f6728a0775 | note | Inspection / Test method - NZS4407:2.4.7
73377e52-8f6a-5fc3-b208-fcfd1a59a942 | note | Acceptance Criteria - > 130KN
c2c2347d-06aa-5cab-85d8-1f99ffcc5c33 | note | Record documents (QCP - Quality Control Portal - IANZ report
52dab1ec-b8dd-5e58-b229-6b3243552ebd | note | Responsibility - Contractor
61d3cf91-5f0e-5529-be2f-94ea4aedd8ec | note | Checked by R = Responsible, I, Informed, A = Approve (Designer) - A
a4d021c2-39b2-5186-a4cd-3ef2416102b5 | note | Checked by R = Responsible, I, Informed, A = Approve (Eng. Rep / NZTA) - I
c74098dc-918c-5c74-80bd-7d41483d5138 | note | Checked by R = Responsible, I, Informed, A = Approve (Contractor) - R
6f7fb107-f448-461c-86e0-871034f49aae | checkpoint | 1.02 - NZTA M04
a058bf46-6972-5f14-b925-ff05706a636e | note | Detail of Activity / Test - Particle size distribution
caa4b396-6dba-5bf6-85f6-ef813e9df757 | note | Action (Hold, Monitor, Witness) - H
93aca286-be5e-5d8a-a8be-959a634575ec | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
5629bb8d-263e-5c06-82a5-1d99fff952f8 | note | Inspection / Test method - NZS4407:2.4.7
db8c33b9-0ca6-5839-91f4-2e4dc0561dca | note | Acceptance Criteria - As per NZTA M04 Specification
5b393119-ca10-5c19-baf5-b99a9128daa9 | note | Record documents (QCP - Quality Control Portal - IANZ report
360638e7-f3cf-58ca-a799-209bba09d715 | note | Responsibility - Contractor
2d5547c9-c7e5-5cba-8aac-43b77178a506 | note | Checked by R = Responsible, I, Informed, A = Approve (Designer) - A
a16f75fa-c474-540e-b684-04d520a8bc56 | note | Checked by R = Responsible, I, Informed, A = Approve (Eng. Rep / NZTA) - I
3533eb5d-0369-5e69-98ec-3c916ce25d41 | note | Checked by R = Responsible, I, Informed, A = Approve (Contractor) - R
17a77787-e3a3-43da-b1f9-ab9562819836 | signoff | AUTHORITY HOLDPOINT
060dacff-211a-4a57-ad9f-54d3678fb522 | section | 2.0 CONSTRUCTION
9243a796-06ea-4756-81ae-27c671a636cb | checkpoint | 2.01 - Earthworks
e78c7f06-1b60-546d-8dae-3d42fba71977 | note | Detail of Activity / Test - Scarify Existing Entrance way Surface
6e14e82b-ee34-5ca2-8a68-7609572fac0d | note | Action (Hold, Monitor, Witness) - M
1744e851-8d1a-5bf2-a3d0-181d0137feff | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - As per design drawings
4cee43ba-ea31-5e95-8f41-09271b799797 | note | Inspection / Test method - Visual / Photo
d198d991-018e-57a7-9072-d70279c72058 | note | Acceptance Criteria - Site Engineers Approval
b50a2523-1f5d-553e-a261-00fe64bd7f57 | note | Record documents (QCP - Quality Control Portal - Checksheet
7784d5a0-178f-5129-9962-b3219c7497b2 | note | Responsibility - Contractor
0897608f-57a8-5fab-a9f5-8fb771973d70 | note | Checked by R = Responsible, I, Informed, A = Approve (Designer) - A
8afb2975-fffb-5db0-bcdb-13bbcd6de110 | note | Checked by R = Responsible, I, Informed, A = Approve (Eng. Rep / NZTA) - I
c155218e-c924-5a09-ae37-64b05dc33896 | note | Checked by R = Responsible, I, Informed, A = Approve (Contractor) - R
d4f22d74-d345-4cec-aa21-67ce0d8d2fd0 | checkpoint | 2.02 - M4 Placement
614d1b45-a218-5257-a57e-5c0a4ebe068f | note | Detail of Activity / Test - M4 Placed in Accordance with Design Drawing and Survey
5d895570-7d7b-505f-af80-eb59b2ca8eb5 | note | Action (Hold, Monitor, Witness) - M
c9dd17e1-9746-527b-b1c7-22bf38f2c2c5 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - As per design drawings
d840b7f1-1f35-59f8-b47f-78beb54ebdc1 | note | Inspection / Test method - Visual / Photo
ad313221-e334-5390-8147-cf793c23953d | note | Acceptance Criteria - Survey Record
c65f7f7f-db49-5e2a-af73-a046f36b17eb | note | Record documents (QCP - Quality Control Portal - Checksheet
ae69cb23-32de-548f-89fd-bd24b8b4a62d | note | Responsibility - Contractor
16afa52d-950d-5967-9dac-dd2913c3068e | note | Checked by R = Responsible, I, Informed, A = Approve (Designer) - A
811d41aa-cde6-543d-ab53-17ead81492fd | note | Checked by R = Responsible, I, Informed, A = Approve (Eng. Rep / NZTA) - I
fa9b27a0-93f4-5603-8c50-895bc528357d | note | Checked by R = Responsible, I, Informed, A = Approve (Contractor) - R
8756938a-b9b0-4ed0-831b-ca0db9572854 | checkpoint | 2.03 - M4 Compaction
84bbd6d4-aac0-5ada-88dc-3e04a8712db3 | note | Detail of Activity / Test - Compact in Layers no greater than 150mm.
56361816-ebef-5ac5-90d7-a5ebd6cb876e | note | Action (Hold, Monitor, Witness) - H
915e1d65-dffa-5d2f-ab2e-a8701acd05fd | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test Per 10m2
cd58f84f-c129-579d-bf78-de939711e4a0 | note | Inspection / Test method - Clegg
5527139e-5fe9-5790-a433-698c4f8ed3f1 | note | Acceptance Criteria - CIV >30
db91e3d3-7c6a-5ae9-ba75-7dc449907926 | note | Record documents (QCP - Quality Control Portal - Checksheet
503044fa-186f-598f-8a45-789b8542fec6 | note | Responsibility - Contractor
5a811bd9-5320-5911-b76a-164f0cdd43df | note | Checked by R = Responsible, I, Informed, A = Approve (Designer) - I
57d002ff-c9e7-5b40-a6ae-0d013a852385 | note | Checked by R = Responsible, I, Informed, A = Approve (Eng. Rep / NZTA) - A
eee2fd91-6c7d-5a08-adb2-ee19ce540110 | note | Checked by R = Responsible, I, Informed, A = Approve (Contractor) - R
de69cb3d-f7e7-4c76-80ab-f7f81314323a | signoff | AUTHORITY HOLDPOINT
3ce7416b-3d72-4ef1-880c-ff33ab4e6ea6 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
70496ade-d789-5031-8d80-d09f34bc297b | textbox | Contractor's Rep Name:
af35e47b-a011-595f-8830-2c9b4c8f0ab1 | textbox | Engineer's Rep. Name:
8d999b64-32de-46bc-ab4e-05a1759e238a | signoff | Add Signature
246dc7c2-6b71-4e3e-bba5-9d38923a0087 | checklist | ITP - Foam Bitumen Stabilisation - FBS operation Rev C | itp | ITP - Foam Bitumen Stabilisation - FBS operation
a00bc9d8-64c1-4999-a7de-5aabf464b308 | section | 3.0. BITUMEN STABILISATION OPERATION
b9554871-3e0e-44d8-a817-58a9f97c4ad3 | checkpoint | 3.01 - Stabilising Agents
28c8b1f4-ccdd-5822-8343-f896385c198c | note | Detail of Activity / Test - Lime (if applicable - check PI delete otherwise)
bb1209fc-95a3-52fb-a2ec-19a79e21579c | note | Action (Hold, Monitor, Witness) - M
2b77b00c-d030-5dc1-be4e-ac50bc57bf0b | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Batch
a634de0b-6d0b-5486-b8e3-dee8e22e1cf2 | note | Inspection / Test method - TNZ M/15
0e079211-1179-54c6-ae38-5adc3300e467 | note | Acceptance Criteria - Conform to Specification
5d7d76a5-9bb7-5b0b-b94a-7a8662d34b6a | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
c02180c3-7a2f-5d4b-ac37-6221b4c09a08 | note | Responsibility - Stabilising Contractor
6b6efc60-79ed-58cf-9731-79dd48a206ec | note | Eng. Rep - I
4b6031cc-ef8f-592c-983b-8016e5a99ca3 | note | Contractor - R
780f8eb5-2838-46e0-9a04-4aac35402456 | checkpoint | 3.02 - Stabilising Agents
f334de20-963e-5edd-aa90-55da7753873a | note | Detail of Activity / Test - Cement, GP
f6310bfb-8243-5a40-b3bf-fe0e768cb788 | note | Action (Hold, Monitor, Witness) - M
d78986c6-18af-5668-83e3-32fffa706449 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Batch
0c50f017-6604-5231-9dcc-d8b52c25a889 | note | Inspection / Test method - NZS 3122
07c3b6aa-3601-5c64-882d-6191e59c2d93 | note | Acceptance Criteria - Conform to Specification
23225786-257c-56c0-87a6-ad7df870ced4 | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
7b9772db-9ed0-5801-ab17-75dc424e2ef6 | note | Responsibility - Stabilising Contractor
a659dda3-4f08-5d12-ad97-1b6fd85c992b | note | Eng. Rep - I
e044bbdd-fff8-5a4a-9c28-26780560fd7c | note | Contractor - R
36812c63-f570-4cdb-961a-33975432d57e | checkpoint | 3.03 - Stabilising Agents
0f21f7fe-31a4-598f-9d34-c013e50ce3dd | note | Detail of Activity / Test - Bitumen (130/150)
ee32f64f-5aa0-5150-9bc7-ca281216e3e6 | note | Action (Hold, Monitor, Witness) - M
5df72389-7814-5707-ad2a-3e0838b3bbdb | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Batch
d66f6ad6-22cd-5bfa-b0a4-885d189c7a9e | note | Inspection / Test method - M/1
415d103b-0d54-515a-b093-f988758792b7 | note | Acceptance Criteria - Conform to Specification
9cd85b2f-7d7a-567e-84b4-c98a97d5bc19 | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
0c1a0551-5e72-581b-b707-456b05317aca | note | Responsibility - Stabilising Contractor
1b971870-4d57-52b1-82ec-2cc599efa8c5 | note | Eng. Rep - I
72ba31e7-f62a-5ffb-aeee-3ea5bcac2595 | note | Contractor - R
5a203069-24cd-4c0e-953e-f39c6bce0855 | checkpoint | 3.04 - Weather conditions
7e579a10-d3e4-5a4f-b104-bce88533311f | note | Detail of Activity / Test - Material behind stabiliser
a273ca59-b657-5e2d-99f5-3b63a289eb38 | note | Action (Hold, Monitor, Witness) - M
b90376da-5b62-5bc7-8ec0-423e68cb0439 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading
dea90754-69c4-5708-be7b-e75238a567df | note | Inspection / Test method - Measurement
37a0bf1b-6da2-5820-af38-e71ea11804df | note | Acceptance Criteria - Material after stabilisation:
2fac2761-784d-54d9-a1b0-539df18a096e | note | ○ BE: > 20°C, FB: > 20°C
5362c40c-3b8b-574a-b905-23238f9a1317 | note | ○ and Ambient: >5 deg.C
82516172-6e0c-5b72-9735-d5d31da4485f | note | Record documents (QCP - Quality Control Portal) - Daily work Log
224470a0-f34d-5b3f-a740-6377bf77ceda | note | Responsibility - Stabilsing Contractor
b12a8ea8-6d7e-5854-ba89-fab284694ffb | note | Eng. Rep - I
64ac91b0-7d67-5fdc-bfb4-1a45b3411c28 | note | Contractor - R
2047664e-9aca-4c57-9519-a61637f9ad47 | checkpoint | 3.05 - Weather conditions
831b984b-e8cb-5b02-997a-259a9993c8d4 | note | Detail of Activity / Test - Wind
4e1f9e21-5462-50c5-8935-14f8812376a5 | note | Action (Hold, Monitor, Witness) - M
c1cfaf0b-b96b-5ac6-a866-f70896dc074f | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading cement or lime
056e8197-5db4-5bd1-b44a-f80c90bd3a6a | note | Inspection / Test method - Local weather stations
3e80ca24-e1c1-5259-ac8d-f1cd1147fef8 | note | Acceptance Criteria - Wind speed < 25 km/hr
44f1e3af-fe26-5d67-aa3b-8bee16664b69 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
b4619f13-54d6-5267-be7f-165f1a041fa3 | note | Responsibility - Stabilsing Contractor
b2722816-6658-5f08-a08f-524d0f3846f4 | note | Eng. Rep - I
b2dc844b-8c24-567f-b3b9-0a6f0bac34be | note | Contractor - R
ccd0bb94-7cc2-4a4e-bf47-7003cb40ddad | checkpoint | 3.06 - Weather conditions
1d63f752-c237-525d-8f49-609bef22fe85 | note | Detail of Activity / Test - Rain
d3260bf3-6279-5bc4-abce-6b8e0499ffea | note | Action (Hold, Monitor, Witness) - M
36a2b23a-835e-5845-a571-04a967bfdda3 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading cement or lime
b296b2e0-a543-5ed5-859e-7d13fd250f9e | note | Inspection / Test method - Local weather stations
c77a3daa-cd72-5b02-b5dc-5659d0382d55 | note | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
664e4099-5181-56b0-926e-ec0e40b477ce | note | Record documents (QCP - Quality Control Portal) - Daily work Log
ed001f9f-a06e-5eca-ab59-d68ed294d9e2 | note | Responsibility - Stabilsing Contractor
a693df82-0d8a-5ad4-87ce-237556589e9c | note | Eng. Rep - I
3083d2da-9745-552d-b7ea-9efbfd91e0d0 | note | Contractor - R
5bd34be4-813c-4730-a9a5-a19b331fff82 | checkpoint | 3.07 - Spreading of powdered stabilising agent (Cement / Lime)
697d3e79-20ca-59a7-a23e-aa844161edef | note | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
693fd1fb-ad99-5107-9f51-09732c905d4f | note | Action (Hold, Monitor, Witness) - M
fe4d2e05-026b-5f05-beb8-188cc65dc864 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 400 m2, every 150m for a 2.4m width
bc9834ba-de54-5ffc-ba7b-9825f24d14bb | note | Inspection / Test method - Weigh mat or tray
68495d89-558d-5508-ac55-865ea3590669 | note | Acceptance Criteria - ± 0.5kg/m2 of specified rate
88e1a4d0-89cb-51a3-a277-253a9ad9c699 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
2b04c315-ec4e-5951-8bcc-c2b20d97ae44 | note | Responsibility - Stabilising Contractor
0a538539-1fcc-5aff-a54e-b37c4fc11223 | note | Eng. Rep - I
c36e0d2a-30b1-570a-9d19-576acafbb7fb | note | Contractor - R
f9562f44-22f9-4a67-a193-6d9ae36c7083 | checkpoint | 3.08 - Spreading of powdered stabilising agent (Cement / Lime)
d3f08a8a-98c5-5f34-8f61-bf72577c8dd3 | note | Detail of Activity / Test - Compare area spread with weight used for each spreader load
162fd237-4e9c-5536-bfa2-388fe1356567 | note | Action (Hold, Monitor, Witness) - M
1119ab10-4cdb-5884-a87e-0d28b564c89f | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going measurement by computer/load cells
d12cb9f3-bafd-5c76-b6a1-e52115a6633b | note | Inspection / Test method - Measurement each run
a9cb2ff6-7cb5-5a51-9c0d-34d7b1a3e4b4 | note | Acceptance Criteria - ± 2.5% of specified rate
b1528d8d-1742-5c43-984e-caf127a1d873 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
7045ca02-0a38-568d-8bbc-f83ed23fb47a | note | Responsibility - Stabilising Contractor
9e52a72b-3c0e-5229-9ced-ae29f6b44bd9 | note | Eng. Rep - I
1914345c-9572-50ba-9a9e-64ee9ae3946c | note | Contractor - R
2ba0a1f3-75c0-4b4f-9e2e-1837238615b4 | checkpoint | 3.09 - Injection of bituminous stabilising agent (FBS or BE)
5bd340c3-34de-52a3-b701-2978cf4055d8 | note | Detail of Activity / Test - Flow meter and operator's display readings
ccb22d88-2004-5002-8589-6dcb91046e4e | note | Action (Hold, Monitor, Witness) - M
4e0f3803-67af-57c2-a738-8dcca681a3cb | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Continous monitoring by the operator and the grounds person
cbabbb1f-32f8-5517-8bdb-501b9efb0c2f | note | Inspection / Test method - Visual display reading
da3f4036-a9c5-516f-b8b2-48c1cc70703c | note | Acceptance Criteria - ± 5% of specified rate
1de6954d-e2c1-5596-8f26-8a50d63fc81e | note | Record documents (QCP - Quality Control Portal) - N/A
1ef71ffe-7bc2-545d-9973-41942273d345 | note | Responsibility - Stabilising Contractor
bbda99be-e794-5e7c-b3d8-1adb04505c05 | note | Eng. Rep - I
a3e614fd-7296-517f-a517-ee75a26cca6e | note | Contractor - R
9f29339e-a4af-4197-95f4-b4419d69bb79 | checkpoint | 3.10 - Injection of bituminous stabilising agent (FBS or BE)
b9cbcafa-3cad-550e-b562-b5d13ae85396 | note | Detail of Activity / Test - Compare tonnes used (from the stabiiser's PCU) with the measured area
43427e48-a5a7-5530-a84e-a22f33d40eee | note | Action (Hold, Monitor, Witness) - M
00d69b8c-f2bf-527b-b72b-1c380c02b528 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Record usage from PCU at the end of each run
262bdee6-b426-5180-981e-d7fae5baa7eb | note | Inspection / Test method - Record readings at the end of each run
874f49e2-1130-594e-a1fe-4cb1502500ae | note | Acceptance Criteria - ± 3% of specified rate
a9948cf9-cecd-5493-ab89-fcdaf513162d | note | Record documents (QCP - Quality Control Portal) - Daily work Log
5544dd5b-1bde-526e-91fb-92223f798bcf | note | Responsibility - Stabilising Contractor
a21e4bef-12c9-5c5d-8440-2d9b8efa1103 | note | Eng. Rep - I
e1e66f59-d145-56e6-ae02-fbc99fd393fd | note | Contractor - R
a2cd3db0-b06a-43d8-9c92-26b906a56e2f | checkpoint | 3.11 - Injection of bituminous stabilising agent (FBS or BE)
5f0496e9-91eb-5a4c-b793-a64cf51250c3 | note | Detail of Activity / Test - Compare tonnes used (from delivery docket) with measured area
9a51d772-c94b-5c24-af6e-0ae00d48324c | note | Action (Hold, Monitor, Witness) - M
172fbd54-06c7-55dd-93c6-c3d5b8670685 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each bitumen tanker load
6cc83ef4-9400-5b13-84f4-8169c635668f | note | Inspection / Test method - Dip bitumen tanker before and after
85ed1592-11fd-5813-9d24-50c3afb64c6c | note | Acceptance Criteria - ± 2.5% of specified rate
4c741690-5880-5495-ac6a-e9ab4b0673ce | note | Record documents (QCP - Quality Control Portal) - Daily work Log
8f70108e-343d-5abb-ab92-8d0a275a38b7 | note | Responsibility - Stabilising Contractor
341b719f-afb5-5b56-a6b5-4ea0b7f7a844 | note | Eng. Rep - I
3cc7b669-9fca-5203-931e-42bbb46dddc8 | note | Contractor - R
89306521-c9fc-4b32-9efa-f22007a50ae5 | checkpoint | 3.12 - Injection & Mixing of Water
84e4bb5a-4cf0-5904-b96c-7620460a8f47 | note | Detail of Activity / Test - In-situ Stabilisation process
f8ae02c9-76c3-5d29-9ac3-95917401b6c7 | note | Action (Hold, Monitor, Witness) - M
9699bd91-130d-553d-b49b-09875dfcb54a | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going visual assessment
226d1129-0af3-5bab-9dbd-1143d88d9cbe | note | Inspection / Test method - Visual and hand squeeze test
e9734ce2-fba9-5a79-92a3-461b08727138 | note | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
2a008858-faf4-51fa-ad02-63eff3d298e4 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
9add2c40-e4ca-57f1-882a-15cb83e4842a | note | Responsibility - Stabilising Contractor
2d386a6e-f20a-5262-b8d1-cd928e6fad52 | note | Eng. Rep - I
60a6ab33-0ebc-5133-a936-1763e50fca47 | note | Contractor - R
fc8c47a4-5828-456f-91e0-4716c8ed0b09 | checkpoint | 3.13 - Depth of stabilisation
dbf7c3f9-bbdd-5a7b-b92d-3c13676cadde | note | Detail of Activity / Test - Depth of stabilisation
156d2a71-7d3d-53b4-bb27-529de4e74a26 | note | Action (Hold, Monitor, Witness) - M
bb5a0917-6a0b-526b-adc3-361c03065b9f | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Every 200m
13d28c80-574d-5d6c-a7a9-f285743b344b | note | Inspection / Test method - Measurement
504e00ce-0569-55d2-bf95-1989bc43b10e | note | Acceptance Criteria - +15mm / -5mm from specified depth
455d9f29-1833-59c6-89d2-751a16bc92a6 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
39fa017d-73fd-5117-9fda-b1598f0b5615 | note | Responsibility - Stabilising Contractor
de99bc27-435c-5fda-a29b-05055b5b60de | note | Eng. Rep - I
6c8b4048-d84d-56e4-88d4-d0a81f975652 | note | Contractor - R
e73acfe4-47d7-4bf4-a493-9839ae7bdab4 | checkpoint | 3.14 - FBS material
353cc034-b81a-5aac-a248-484a2b8c83b2 | note | Detail of Activity / Test - Stabilised material strength - ITS
6cbd1743-58d8-5211-9ec7-b1feaad17c15 | note | Action (Hold, Monitor, Witness) - M
3cb9969c-40d0-588f-9fc2-bc69e2f2a850 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 3 soaked ITS + 3 dry ITS per Lot or when the material changes
932bb398-5e77-5a9e-9d39-0f118a1d5d68 | note | Inspection / Test method - NZTA T/19N: 2020
43bf7a33-82b4-5c51-bf5c-4f2b7cab82a2 | note | Acceptance Criteria - Testing at 1mm/min:
70426f25-f2d4-57f3-8a57-e48c2244c2f8 | note | ○ BSM Dry ITS: 150 kPa to 400 kPa
197c5a3a-5541-5569-b825-814b0bcd8bde | note | ○ BSM Soaked ITS: 120 kPa to 350 kPa
bfbf3463-2b10-58a1-be43-21725905842d | note | Testing at 50.8mm/min:
3ba0d148-fd7c-5498-b718-8296564bb283 | note | ○ BSM Dry ITS: 180 kPa to 450 kPa
5acd52da-af7d-5f62-ab2a-4c5b8468f076 | note | ○ BSM Soaked ITS: 150 kPa to 420 kPa
441eac45-fcd9-5be3-8f98-40414b277b50 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
e0019cc9-9d7d-558c-a9ff-7dfbfccb8998 | note | Responsibility - Stabilising Contractor
233519c1-1844-5279-8231-57a8f989a042 | note | Project Specific Notes / Instructions - ITS briquettes to be produced on site if travel time to lab > 30 minutes.
c047ec83-ca6b-5b29-97b4-552b2073c84c | note | Designer - I
9e8098a9-4f8c-57f9-b0ce-c19bbaf805ab | note | Eng. Rep - A
9f9651d0-ce04-5baa-9fa8-663398b38c1f | note | Contractor - R
23d3ad71-1dd5-4041-8992-85de2c825a3a | checkpoint | 3.15 - Compaction
46f9a038-48b6-509b-83f9-04cd8a4a3545 | note | Detail of Activity / Test - Plateau Density Test
90a84b18-4b25-5601-be31-b8e0926adf20 | note | Action (Hold, Monitor, Witness) - H
8da9194c-3f7c-573d-ba5d-e87b16dbdf35 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
1fdc82b6-cb67-5c91-baea-db046c2e1c04 | note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
a7daada6-6e13-5f0e-8547-1547a3145777 | note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
32688bfb-957c-55ab-b5e3-8a1f494063ad | note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
8529de75-2bbb-546f-89e3-f7802fb59b60 | note | ○ IANZ report when processed
10ecc23e-4ce5-5bfb-a70a-30c719c3446a | note | Responsibility - Stabilising Contractor
0bd5d9cd-b639-5857-9790-1d9fd4a8f516 | note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
b9351c54-ab1c-505c-9471-79fd567a3788 | note | Designer - I
472efac6-1cb9-5e17-9b0b-197c5168c59d | note | Eng. Rep - A
1e0ea94c-ef8a-504f-95f4-bf301ba75ba9 | note | Contractor - R
a83681f8-8148-4337-b049-b1a50945533f | signoff | AUTHORITY HOLDPOINT
15ce93c2-90b3-4038-a43c-9c4f05b4fbbc | checkpoint | 3.16 - Compaction
c7f81284-90eb-5cab-8614-0fd38c182a5b | note | Detail of Activity / Test - Maximum Dry Density
d5a5f7f8-161f-5a73-8489-7cf3ae1d70c5 | note | Action (Hold, Monitor, Witness) - M
21dab51b-58db-592c-937a-6403ed68a5bb | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
4569f9d9-f774-52c4-abbf-2a00b89fb1a8 | note | Inspection / Test method - NZS 4402.4.1.3
52b5dcf8-9ed9-57fe-ace2-48dd113f0aec | note | Acceptance Criteria - For analysis of DoC
3167eb28-d524-57b3-9403-c969687be1ae | note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
a1d882a1-ee1f-5776-aa37-feb0ae300d56 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
daee2f23-d7c4-5539-9b71-072efcc96457 | note | Responsibility - Stabilising Contractor
140d5f0a-ea2a-52c5-a4b8-4d6176ae459b | note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
6fa1009b-e28f-5a2a-bdfa-aacf7b94ccf4 | note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
0cfe27fe-99b8-5947-9c9f-47fab93eb607 | note | Designer - I
3401ca7d-32af-584f-957a-8c1a94cb0536 | note | Eng. Rep - A
9a30ce88-5d95-58a6-a734-5b8729c549bc | note | Contractor - R
3f9afa40-6ff1-4dc5-b066-d0567255223b | checkpoint | 3.17 - Compaction
8c5eeb3f-96d2-5a15-80a8-6643cce752bc | note | Detail of Activity / Test - Degree of Compaction (DoC)
efe7408f-daaf-52ee-b8f1-553ef17415ba | note | Action (Hold, Monitor, Witness) - H
20e9132b-4c52-5be2-9b1d-4add3f341f79 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per 1,000m2
87dd3133-2dd6-545d-a196-dd8db9a509b8 | note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
5767676a-e510-530f-82f1-913d81329626 | note | Acceptance Criteria - Average DoC ≥ 98%, Minimum DoC ≥ 95%
0579656c-20de-58a7-a0d2-452103deb9ee | note | Record documents (QCP - Quality Control Portal) - IANZ Report
b86711d9-a508-5273-90f2-4d012245c7df | note | Responsibility - Stabilising Contractor
d9ad18c9-47c0-5d6d-b423-7102f8c4e063 | note | Designer - I
b4ccb1c8-e1d4-5345-9ab1-e28b6eb153a5 | note | Eng. Rep - A
3e10bab7-d57a-55d2-8edf-c07df1d9d3db | note | Contractor - R
42bc4a54-a945-4a39-a670-e1a0eeff665f | signoff | AUTHORITY HOLDPOINT
7d01ca1a-5e5c-45e9-a68a-6778abc5f89c | checkpoint | 3.18 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
7cd8e5f9-55f0-5701-a970-370b49a19872 | note | Detail of Activity / Test - Clegg Impact Value
3337e0f9-24b8-5f75-ab94-1e4355e202a7 | note | Action (Hold, Monitor, Witness) - H
9aa90ec1-e6f4-552f-ba71-ab9a21615b6f | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per 1000m2
194233fb-5a5f-5529-9c5d-6b266e49efad | note | Acceptance Criteria - CIV ≥ 50
5eceaf0e-bca1-5d6a-9f8e-bfceb8f638d3 | note | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
59896bab-3276-5145-a3b5-b2c1f5c6c23b | note | Responsibility - Stabilising Contractor
b4f83107-4505-518c-9f7e-f55c862a8059 | note | Designer - I
7e543bc4-fe4b-5d9d-91d8-7226370e56ba | note | Eng. Rep - A
30d716fb-297a-58c2-a1fd-4a0b10b2b478 | note | Contractor - R
2f6f8fab-df21-4676-81b4-ce6f0306a10b | signoff | AUTHORITY HOLDPOINT
69bcce42-1552-4010-b932-21ca99d0465e | checkpoint | 3.19 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
bc40d76d-a28d-555a-ad2d-790df7b33152 | note | Detail of Activity / Test - Degree of Saturation, DOS
e2f25132-e922-555c-9f10-a074e32fba70 | note | Action (Hold, Monitor, Witness) - M
3aef154d-c96b-59e7-a9a6-5fb19250f680 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per 1000m2
100e2bc6-53c0-5dcd-a54b-42dfec71e4bf | note | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
774cff89-85f8-57b8-ad2b-99a2991dfd3b | note | Acceptance Criteria - aim for DOS ≤ 80%
d67de038-9bd3-5a3d-a836-1bd63d5fcc60 | note | Record documents (QCP - Quality Control Portal) - IANZ report
b3259b2b-c02f-5db6-bbed-8ed41a45acda | note | Responsibility - Contractor
f577c75f-21da-574b-ac28-4a690ac7c7cd | note | Project Specific Notes / Instructions - Report only
633a597b-a50d-5fb4-b479-75242b44b648 | note | Designer - I
b129b522-be66-56d3-a3ca-7a86dbdd7b0a | note | Eng. Rep - A
af3cea94-73c1-554c-b5a6-9243274b39a0 | note | Contractor - R
bbde201d-d3a2-4a2f-a316-e74601cec7d3 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
d7f999d5-6a32-5958-80cc-4b091055c3bf | textbox | Contractor's Rep Name:
39cf7b87-f3a8-593d-b5b6-fa022aafb62f | textbox | Engineer's Rep. Name:
f3572542-dda1-57e8-8b45-49775c1c5971 | date | Date:
de5e79f7-208f-4efc-a06a-3aefb7a6e452 | signoff | Add Signature
50401ff0-8c9f-4820-b65d-98536bbcc58b | checklist | ITP - Foam Bitumen Stabilisation - Material testing Rev C | itp | ITP - Foam Bitumen Stabilisation - Material testing
1214eaff-9533-472f-b0b6-375c9e03616c | section | 1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING / DESIGN and DRAWINGS
c4d2d047-358d-44f7-91e7-15bf2fd1b557 | checkpoint | 1.01 - AP40 Basecourse Aggregates used for overlay (if applicable)
939f549b-7f20-52a7-a42d-c7eebcdc307a | note | Notes:
7560a98f-ed33-5bf4-aab9-2ac5d25da359 | note | H = Hold point up to approval of Optimisation Testing
0cfe4bbd-25ff-5ee1-99a3-120c273f2bf4 | note | M = Monitor during production
92293821-7498-50bd-8e26-472cc2102a6d | note | Detail of Activity / Test - Crushing Resistance
0e306a85-0b5b-53ca-bb7f-0756b3194292 | note | Action (Hold, Monitor, Witness) - H
c7e0578f-bc7e-5111-84e9-50fe60e50de3 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 10,000 m3
6a679069-058a-5d13-852c-3ed8a1ee9bcc | note | Inspection / Test method - NZS4407:3.10
cadf50c6-1bbd-5405-bac9-4db1febe544c | note | Acceptance Criteria - < 10% passing 2.36mm sieve at 130kN
bcf37de1-a224-5030-a658-142eaea28209 | note | Record documents (QCP - Quality Control Portal) - IANZ report
d9af233a-f185-518c-b463-d8a240b366b6 | note | Responsibility - Contractor
ed24ddc3-114a-55bd-8344-b5d39eae9b72 | note | Designer - A
16e7d4fd-dfc3-5c57-bbf8-01021fac9a22 | note | Eng. Rep - I
43548e03-58d5-537f-9d7a-d4b874b370b4 | note | Contractor - R
fc8bcc7e-c6c1-45ab-a22a-8350a7fedb76 | signoff | AUTHORITY HOLDPOINT
0d7c8279-2a45-414d-809d-888e687dbcea | checkpoint | 1.02 - AP40 Basecourse Aggregates used for overlay (if applicable)
895f0db6-2c97-58aa-a353-f7c527f5abcc | note | Notes:
98a6737c-2e70-5213-a9e4-6abd787725dd | note | H = Hold point up to approval of Optimisation Testing
730a15df-aad0-5629-b787-025a1513336a | note | M = Monitor during production
cdbf705a-096e-59d5-aa70-bf5477702c24 | note | Detail of Activity / Test - Weathering Quality Index
2323594f-a3e6-5b2e-a915-659c29647454 | note | Action (Hold, Monitor, Witness) - H
9c800a2d-6e37-5384-b9d9-9c6554a3b6b2 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 10,000 m3
5bb5e559-2a58-5882-871a-8b70907cacb1 | note | Inspection / Test method - NZS4407:3.11
2fa8826f-e522-536a-8622-3bca83a9fc09 | note | Acceptance Criteria - AA, AB, AC, BA, BB, CA
c1cb5f36-5dbf-5598-9097-59e159c7529e | note | Record documents (QCP - Quality Control Portal) - IANZ Report
8baaeee8-12f1-54b7-9715-4832a9ac477d | note | Responsibility - Contractor
7c2ef797-32f4-5039-9520-5a2d980447e7 | note | Designer - A
87548dc5-364e-50c3-b79c-3bc476ccf902 | note | Eng. Rep - I
b2385d57-dc91-57c7-934e-67bad19181d2 | note | Contractor - R
d2867377-70d3-41e5-a94e-6ad4575d1fe7 | signoff | AUTHORITY HOLDPOINT
cdc61f0c-1d6f-4f3a-aa66-0e5be07010d9 | checkpoint | 1.03 - AP40 Basecourse Aggregates used for overlay (if applicable)
440a26e5-a89e-5c54-b6c8-5505eeeb86b7 | note | Notes:
cb35a1b9-ca42-5092-bc8f-0ad2a96ca20b | note | H = Hold point up to approval of Optimisation Testing
c3496765-679c-5904-b461-06004842267b | note | M = Monitor during production
76153490-be3d-5bd0-b7b5-a3513e5852ae | note | Detail of Activity / Test - Calfornia Bearing Ratio (CBR)
096bc2ce-47b5-5b77-bc5c-a0888784b5a2 | note | Action (Hold, Monitor, Witness) - H
795125ac-ee58-5340-aa2f-f454b151e363 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 10,000 m3
a72967f8-47ff-5848-b9d0-2f4506331116 | note | Inspection / Test method - NZS4402:4.1.3, NZS4407:3.15
b12322ed-6468-5616-ab95-78b7c8936859 | note | Acceptance Criteria - Compaceted using NZ Vibe Hammer 4-day soaked CBR ≥ 80%
727ea729-6f17-551f-9abc-f2c9480d9fe6 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
b27e44c5-93cd-541a-b6a8-283bd9349d62 | note | Responsibility - Contractor
a1ca5142-63cd-50b9-8d84-32d6f06d56c0 | note | Designer - A
82a53c19-4676-528c-9766-b50acdd8be63 | note | Eng. Rep - I
01c8caaa-519d-5608-9d44-ad3a36d975ec | note | Contractor - R
b346a439-285d-481a-8530-40c4cdb2f87e | signoff | AUTHORITY HOLDPOINT
7f29f024-94c6-4e82-8102-707b7226e0fd | checkpoint | 1.04 - AP40 Basecourse Aggregates used for overlay (if applicable)
aca50c22-278f-5abe-ac82-e3c03cc534fa | note | Notes:
d6070808-16f9-513f-80e2-8f3f1fbff1d2 | note | H = Hold point up to approval of Optimisation Testing
bb8395d9-9f71-55ad-8736-a26055a05709 | note | M = Monitor during production
7e224a64-2505-5ce4-8129-521afb812cc2 | note | Detail of Activity / Test - Quality of Fines, either PI or SE or CI
38d8f41c-8e00-5949-a6fb-88d83f5c5e5c | note | Action (Hold, Monitor, Witness) - H
1959f9a0-d734-570e-a832-969cc2d62a12 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m3
8ff226dd-d859-5c41-bdc4-6c56b718e349 | note | Inspection / Test method - NZS4407:3.4 - PI, NZS4407:3.5 - CI
784fb4c8-e86c-52df-b4e4-7165ef06b4a5 | note | Acceptance Criteria - PI ≤ 5, CI ≤ 3
0708e6d8-4935-5fa5-a7d0-f6bae8abc123 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
66d08137-21d6-5b02-a4c5-1e1a96f0b940 | note | Responsibility - Contractor
7626a4ac-74fc-58dc-84b2-d1a5cd74d699 | note | Project Specific Notes / Instructions - NZTA M04: 2024
f256fb4e-a9e0-5e5a-b8d5-56947f140ceb | note | ○ AP40 - Class 2
694cc505-5729-5930-86ff-902dbbac98ae | note | ○ PI and CI applies
fdb75ecb-825b-5fab-8752-0840a1c2302f | note | Designer - A
c918fbe9-2b6a-56db-8e67-59721c32b224 | note | Eng. Rep - I
5766a89e-48c9-58e3-a9c9-ddf5ab833525 | note | Contractor - R
2ddf9c84-0292-45ad-9a12-9eb7163fe6cd | signoff | AUTHORITY HOLDPOINT
2878c0ef-fd86-45d3-ac94-a0bbbb935513 | checkpoint | 1.05 - AP40 Basecourse Aggregates used for overlay (if applicable)
c7d3739c-63e2-562b-a767-278c11f6cf2e | note | Notes:
c8cff791-48c7-5e09-8942-a04233884ed2 | note | H = Hold point up to approval of Optimisation Testing
0be373a2-1213-5c86-aed1-f318ec496801 | note | M = Monitor during production
c47f7fc2-5bc0-5062-a1d7-235d9e9b5a34 | note | Detail of Activity / Test - Broken Faces Content
63b8fd5a-b682-5e0b-b09b-28c2e253a4c4 | note | Action (Hold, Monitor, Witness) - H
6d67cd1f-7c0b-5fae-8416-126f1588697d | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m3
e9b11a6c-4ac5-5bd1-b549-7276f80ec7b9 | note | Inspection / Test method - NZS4407:3.14
275c8fa7-15c8-5106-92c0-395d07f9ca9a | note | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
6f1190bf-454e-5d71-906f-3a8a9b3d74bb | note | Record documents (QCP - Quality Control Portal) - IANZ Report
6fa1e6a3-e7ff-54ab-a432-9d8f97277ed0 | note | Responsibility - Contractor
94dd9fc9-1b2a-5ade-aadb-5744c0a6a572 | note | Project Specific Notes / Instructions - Waived if aggregate is from crushed hard rock quarry
dfae59af-3a76-5c7e-80e1-ba9c541ae2ba | note | Designer - A
3a562568-f8e2-5ac9-9331-562a8c0476ae | note | Eng. Rep - I
340ab2d3-7d05-597f-8bcc-6f468b36f17e | note | Contractor - R
cfa26299-7bbb-4323-9cb6-f45a39982dcc | signoff | AUTHORITY HOLDPOINT
b33218e2-df73-4008-b123-36534e075830 | checkpoint | 1.06 - AP40 Basecourse Aggregates used for overlay (if applicable)
ebf62e88-7bbc-5b3d-bdef-300583251691 | note | Notes:
7536c786-8f40-57d4-971c-1b29d0fb864f | note | H = Hold point up to approval of Optimisation Testing
1b720de0-a6cb-5630-a830-8985ab240259 | note | M = Monitor during production
25c927a0-6aaa-5907-aafb-159897f752af | note | Detail of Activity / Test - Particle Size Distribution
6c6f7ab2-99d5-5318-90ca-c274bf51efa8 | note | Action (Hold, Monitor, Witness) - H
9b3ed8b5-b727-5661-9592-6760e7b80714 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m3
36c15bac-92d7-52e8-b31f-b72f15fb9737 | note | Inspection / Test method - NZS4407:3.8.1
4680a386-f3e4-5e1d-8b99-aea05b6d4fae | note | Acceptance Criteria - NZTA M04:2024-Class 2
afb24762-6e8b-598c-9868-35ced0f0fe68 | note | ○ Class 2 in Table 12 for PSD
fff9e455-3d88-5b70-868c-4ea3b5da30eb | note | ○ Table 13 for shape control
e5f878c2-2225-5472-82ef-40fbe4942d4c | note | Record documents (QCP - Quality Control Portal) - IANZ report
fec35cc8-3d44-535e-b971-d2ae25a154d9 | note | Responsibility - Contractor
b15c96d2-1d3d-5fb2-abbf-fa573e26709b | note | Designer - A
fb5424b4-5e3b-5f3a-acc1-d75470e5c139 | note | Eng. Rep - I
1929a8b5-f17d-5fe9-b303-baf7f6f9a806 | note | Contractor - R
098e12e1-6f76-4071-a99f-628bf52504f1 | signoff | AUTHORITY HOLDPOINT
7d7c449d-9541-4ff3-b525-310312a85b27 | checkpoint | 1.07 - Optimisation of Stabilising Agent(s)
bed86e4f-5e79-5a12-a08e-ddb8efcf186a | note | Detail of Activity / Test - Blend Particle Size Distribution
0eaaaae5-471b-5558-a2aa-56bf51080bf0 | note | Action (Hold, Monitor, Witness) - H
576de383-8810-58c4-a25d-605486703223 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m3
4737c4ed-6491-5fc0-80a8-75932dbb4d4d | note | Inspection / Test method - NZS4407:3.8.1
81e106e7-047a-55e2-a0fd-c1efd60818fd | note | Acceptance Criteria - Check if average of existing (from TPs) and any overlay will meet the ideal FBS / BE grading.
89c20d38-4775-5be1-ad28-acc17c04248d | note | Record documents (QCP - Quality Control Portal) - Report using IANZ Reports for AP40 and TP PSDs
5768b334-7978-5b33-96e7-d95913249376 | note | Responsibility - Designer
815661cc-e810-509c-918e-e93fff7a150e | note | Project Specific Notes / Instructions - Designer to advise if "average" blend is acceptable.
5b6363a0-559d-5c7e-929e-19f06555785d | note | Designer - R
6356b73d-4cc5-5976-8a28-cf564b0526ef | note | Eng. Rep - A
0afb1952-3d9e-5abc-abce-17bcc25c8aa9 | note | Contractor - I
8ccdeb42-b843-404f-a94e-b8613fef5362 | signoff | AUTHORITY HOLDPOINT
4c353865-6967-49e7-af6d-4f04369c1e33 | checkpoint | 1.08 - Optimisation of Stabilising Agent(s)
4f3e3cab-fdc9-54bb-874f-c7d96e297025 | note | Detail of Activity / Test - Indirect Tensile Strength, ITS
4f1dd96b-28d2-5cf7-aaa5-f6b30990711a | note | Action (Hold, Monitor, Witness) - H
426f9883-8b38-5ab6-ad92-f19b11dbe08c | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Optimisation test per aggregate type
d8e5c13c-2967-5ad6-bc14-140cfc6ffd3c | note | Inspection / Test method - NZTA T/19: 2020
97b9c791-16f1-55b7-8c50-7ed685ec26bf | note | Acceptance Criteria - Testing at 1mm/min:
222c40aa-5d72-5260-a3c1-13794963986b | note | ○ BSM Dry ITS: 175 kPa to 400 kPa
68d93378-ecee-5994-8b7f-d288285d378c | note | ○ BSM Soaked ITS: 150 kPa to 350 kPa
273ff0d3-e20e-5595-bb3c-d743f13cb8c8 | note | Testing at 50.8mm/min:
bcd74be3-6a31-5545-b8ba-c219eaf2a5b6 | note | ○ BSM Dry ITS: 210 kPa to 480 kPa
cdf1a1d6-b25e-5a12-b2ef-4092272465df | note | ○ BSM Soaked ITS: 180 kPa to 450 kPa
9feefa5c-e4f1-5e25-a492-7a9c8f5f17cf | note | Record documents (QCP - Quality Control Portal) - IANZ Report
511f93f7-b88a-54a6-8005-468278c23184 | note | Responsibility - Designer
d21b4a0a-b17a-5ec0-888a-dc3e5d5cf663 | note | Project Specific Notes / Instructions - Designer to advise on binder content(s)
6aee3ad3-95d9-5c50-98a6-e8d2bd701780 | note | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
a3fc34a1-8063-586d-b31f-e306b38e7b44 | note | Designer - R
d7ccd279-aea8-5f74-86e7-b914b1442145 | note | Eng. Rep - A
90834bb3-96d1-51bc-9420-87b996194946 | note | Contractor - I
e837076f-9bc1-4d26-a321-a9bfac2d8db5 | signoff | AUTHORITY HOLDPOINT
124f8e3d-4a71-456a-9ee8-622afbc5eccb | checkpoint | 1.09 - Optimisation of Stabilising Agent(s)
05246fe3-e914-5857-ba53-f6ae682347af | note | Detail of Activity / Test - Unconfined Compressive Strength, UCS
2fab2d3c-03b7-5f55-a411-1617a9a694ce | note | Action (Hold, Monitor, Witness) - H
f5a39290-8152-59e1-90b9-7977bf8ac6a7 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Optimisation test per aggregate type
0998e7fc-14f5-5a1d-94aa-a012db38a1b0 | note | Inspection / Test method - CCNZ / NPTG / CETANZ Industry Guide
f7d8635f-2fa5-5d61-8677-f3a2edddefd3 | note | Acceptance Criteria - UCS limits set by the design engineeer
6a2915cc-4806-5cf8-9266-915aba734ddb | note | Record documents (QCP - Quality Control Portal) - IANZ Report
a7cf3bb6-8eff-5789-b197-c7bea04700f2 | note | Responsibility - Designer
bec5805b-89a7-5ac2-9d9d-9693bd578370 | note | Project Specific Notes / Instructions - Designer to advise on binder content(s)
280d772b-5429-568f-a626-dc4809862ab3 | note | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
6f44d415-6afe-5291-a756-ea0ea9151b42 | note | Designer - R
ca4cb921-081b-5b1a-af48-9684a48e61e4 | note | Eng. Rep - A
f3e6c33a-a138-5486-853a-bc0add60d579 | note | Contractor - I
83859a60-bb3a-4cdc-a1e8-745192428fe4 | signoff | AUTHORITY HOLDPOINT
ffb0ced8-0e8d-466e-9a08-4b78b241828c | checkpoint | 1.10 - Optimisation of Stabilising Agent(s)
9e84e6e0-ccd0-52d1-a5ce-d906f9cf3298 | note | Detail of Activity / Test - Modified Maximum Dry Density
711b467c-9ef2-5af7-88bf-70b290ce35cf | note | Action (Hold, Monitor, Witness) - H
4927a30b-1256-5f85-b556-fa4d6bf7e65e | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Single Point DD vs WC during optimisation test
0f49d600-06da-5aed-ac1a-793557086651 | note | Inspection / Test method - NZS 4402.4.1.3
902c502f-a006-53a5-a771-81018abfa759 | note | Acceptance Criteria - To determine target density
d8a2e625-a307-50d2-ba3c-179044f42d8f | note | Record documents (QCP - Quality Control Portal) - IANZ Report
13d0a1ab-74f5-51d3-947e-dd78f4ae0e41 | note | Responsibility - Designer
0f01399b-e889-5b39-b877-8dc838a824c3 | note | Project Specific Notes / Instructions - Required before Stabilisation comences
1ad38360-aebf-57a7-911c-47d977364a33 | note | Designer - R
a3f8d428-2098-5a18-bbd8-5a61b8b1e872 | note | Eng. Rep - A
b23fa9ca-24f2-52e6-aa46-a767bfd93150 | note | Contractor - I
c095f327-6a4f-4ee6-95ea-cd4d50dd6d8b | signoff | AUTHORITY HOLDPOINT
f14b2b03-4f38-45f0-8457-873d010bd52d | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
264a6c63-4cbb-51cd-9dcb-5f88c4314a6e | textbox | Contractor's Rep Name:
fdecc137-1322-5f43-a964-19c140aad8b6 | textbox | Engineer's Rep. Name:
850dc2ad-0b32-55ec-8834-07feff92d686 | date | Date:
d5058f4e-82b1-41e8-9c44-2409802e94ee | signoff | Add Signature
66866723-e3d6-4680-b3e5-688524abfb9c | checklist | ITP - Foam Bitumen Stabilisation - Post FBS testing Rev C | itp | ITP - Foam Bitumen Stabilisation - Post FBS testing
6fa23a9e-5a06-43a8-9e76-c8710d17e289 | section | 4.0. Testing and Sgnoff
be4e881e-1fd5-4c4c-bd2e-65ef3d00c639 | checkpoint | 4.01 - Finished Pavement
46ad5448-7474-5b73-98c9-e0b81a25fd43 | note | Detail of Activity / Test - Crossfall
e61e2521-cbbd-5469-aa5a-1e1d2a288380 | note | Action (Hold, Monitor, Witness) - H
6a8b6468-8ed6-5a55-aed8-c399a8af5902 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
b273bbc7-132f-5f28-8d7b-29de1838c3d0 | note | Inspection / Test method - Measurement
6adb61cd-62a5-5c04-b02c-26fa4cd6db8b | note | Acceptance Criteria - ± 0.5% of specified crossfall measure, 2m apart
b2d34e13-3185-55e4-9db8-9ceb2fa98e94 | note | Record documents (QCP - Quality Control Portal) - Survey
3949bcb4-bd3c-54fd-bb77-4c2d48be5007 | note | Responsibility - Stabilising Contractor
28b6dccf-e587-504d-b299-03d685179f7b | note | Eng. Rep - A
d47d2b6f-a76b-5d23-82ba-a0bf5052d6e2 | note | Contractor - R
bb43c77c-39e2-404a-83a0-313784600d01 | signoff | AUTHORITY HOLDPOINT
e017371c-78e0-498a-8f36-ac91a2af1438 | checkpoint | 4.02 - Finished Pavement
f7098ac0-b668-5c88-ac71-c319de29101c | note | Detail of Activity / Test - Stabilised width
a4046b22-41ac-5fe1-b722-644375da3c2b | note | Action (Hold, Monitor, Witness) - H
d9430be2-a0b0-5f6b-af2a-44042f83f91e | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 every 20m
74813c65-0fd1-5962-b138-154a3e28b5a5 | note | Inspection / Test method - Measurement
d81a556d-d5ce-5b04-a807-d64dedebfef4 | note | Acceptance Criteria - -20mm, +100mm
cdbb09c4-9471-5fb1-b8b2-9cec94b34a8a | note | Record documents (QCP - Quality Control Portal) - Survey
6c8df082-ae55-548c-bd6c-cce5e4661776 | note | Responsibility - Stabilising Contractor
d3dff643-919a-59de-bb4c-64a04287d46d | note | Eng. Rep - A
53d495a6-7612-5f98-8786-49c3103d53b8 | note | Contractor - R
d6fdd515-fb4f-47f3-96bc-0caaabd5ce47 | signoff | AUTHORITY HOLDPOINT
d080dfd2-a076-4d27-9e93-a580117bb750 | checkpoint | 4.03 - Finished Pavement
bbbb9354-e0bd-5229-b5f6-d9bef0175f4c | note | Detail of Activity / Test - Surface Shape
e9de1007-0c0d-5811-8a13-6fa7da07a4b1 | note | Action (Hold, Monitor, Witness) - H
3749b0af-23e1-53a8-9337-adece439a34f | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
b2dbca5c-3b34-5897-b561-3388a43687e9 | note | Inspection / Test method - Measurement
2ff606cd-1e65-5404-9b8a-3ba10c362cd1 | note | Acceptance Criteria - < 10mm using 3m straight edge
45e09a88-b26a-545a-96e6-b9ff050185bb | note | Record documents (QCP - Quality Control Portal) - Survey
7a211355-bf1e-5383-8915-ed03d04bc975 | note | Responsibility - Stabilising Contractor
b8c3c37f-29e7-5325-a631-775b7c616b7f | note | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
a8951c34-5b3e-5b9b-ba0f-b1061c147989 | note | Eng. Rep - A
e5cbaf61-c240-54ed-9710-3af110a8f873 | note | Contractor - R
599cec15-a4f8-456f-890b-3524c257e9fc | signoff | AUTHORITY HOLDPOINT
55a3317e-35e6-44e1-b326-164452eb97cc | checkpoint | 4.04 - Finished Pavement
8d1b49dc-feb2-5993-9317-482defa9126e | note | Detail of Activity / Test - Surface Levels
0bc24c71-398b-55d5-a54d-31b070113497 | note | Action (Hold, Monitor, Witness) - H
8f02b8af-a4e7-501f-9859-f271fa5109b0 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
723d37db-d1f4-5ec7-8703-5d53720166c6 | note | Inspection / Test method - Measurement
03041029-b74e-5ce2-bc3e-400e6b5a5c70 | note | Acceptance Criteria - -5mm, +15mm
016dd6bc-8b35-56cc-a0e9-e9630cd9f8c2 | note | Record documents (QCP - Quality Control Portal) - Survey
8eab5569-f5a2-5db7-9ba5-774f2da65330 | note | Responsibility - Stabilising Contractor
be0880bd-65a8-5658-82e1-1bcab8f8fe5d | note | Eng. Rep - A
b54ed1c3-05d1-59ae-8e41-3341a9b14852 | note | Contractor - R
4faf4109-490f-4714-ae84-67d252c80148 | signoff | AUTHORITY HOLDPOINT
e1a541c1-3586-4925-b1f9-263bc09709f2 | checkpoint | 4.05 - Finished Pavement
555c440c-f37d-5474-b263-a22d0d736138 | note | Detail of Activity / Test - Surface Finish
54ad0dc6-bacd-56ed-8d88-8fcebde1c9c3 | note | Action (Hold, Monitor, Witness) - H
c9c0402b-d4d6-54b7-85f8-7966e247e069 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Lot
af7eeda3-4cc7-5a6d-9e13-d8de2b2c1f90 | note | Inspection / Test method - Visual
8e567845-9fe5-5278-83fa-354a8ee862a8 | note | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate
2c81a5b3-1267-508a-9008-07f93b709559 | note | 2. Smaller aggregate held in place by fine material
7baae317-574e-5d90-a87c-ef523635a8ec | note | 3. matrix does not displace under normal trafficking and/or sweeping
ac1b8212-cc00-5ec2-b559-bc08cbed1af2 | note | Record documents (QCP - Quality Control Portal) - Survey
acf95bcf-6430-5057-b2bb-fb1fc607149d | note | Responsibility - Stabilising Contractor
5266a37a-0a8b-5a67-9aa6-0c2d12af4560 | note | Project Specific Notes / Instructions - ER to be present at pre-seal inspection
93bcdaae-57e3-5409-89c5-ab649cb2d07a | note | Eng. Rep - A
8e9f3023-b330-5946-af7b-5b03f3edca5e | note | Contractor - R
ac52939e-7acb-45d0-b43b-599a81ac6b02 | signoff | AUTHORITY HOLDPOINT
1b7bddca-bef2-4034-9237-8554ae7ee4e5 | checkpoint | 4.06 - Finished Pavement
37d3c052-9173-5953-94cd-4e81a916c15b | note | Detail of Activity / Test - Roughness
1c151a54-c241-5b5f-9303-c236b61caeb4 | note | Action (Hold, Monitor, Witness) - H
5d61b939-d890-5926-827f-b7bec78eec78 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Before Sealing
0e16214c-c287-552a-8849-1248a0bedaa1 | note | Inspection / Test method - TNZ TM 7003 v1
790c35cc-3a71-5694-b302-d162a0f69094 | note | Acceptance Criteria - 100m rolling average ≤ 75 counts/km
e3c7a991-3caf-5759-bdfa-ea46805ef3f7 | note | Record documents (QCP - Quality Control Portal) - Test Certificate
6c31b2b4-3fc0-5bb9-bb81-730cd64c0dbd | note | Responsibility - Contractor
616dc034-c8c8-5a09-86d5-249461879a15 | note | Eng. Rep - A
0d967df5-bcaa-5101-b929-a91780c8f57a | note | Contractor - R
6d305d5e-700a-47ae-916f-62f31800b0ed | signoff | AUTHORITY HOLDPOINT
5d0301a6-470d-492b-9e64-2681aa3bcca3 | checkpoint | 4.07 - Pavement Layer Signoff
d337e6e4-9bbc-5475-9d72-f4a4bf7a6d07 | note | Detail of Activity / Test - Assessment of all test results for conformity
f766d944-7953-507d-995d-db69fe5759f8 | note | Action (Hold, Monitor, Witness) - H
774b7735-13aa-566c-8b67-1fc2706726f4 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each Lot
501eb58f-54b6-585d-82b6-63e827740a57 | note | Inspection / Test method - Site Inspection
052d6f03-ea74-557a-b364-ca31bad3f914 | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
2ae54b16-d0a3-533c-a2af-fc573250721d | note | Record documents (QCP - Quality Control Portal) - NCR
94b9e781-1cf5-58e4-949e-e9c4d2b771c5 | note | Responsibility - Engineers Representative
05f13293-3b7a-4ae8-bfec-1cf9a1b2be1d | signoff | AUTHORITY HOLDPOINT
d0cfc70a-c013-451a-9a50-2d37a153af14 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
896b73af-5dcd-5949-96fb-9818d1affea1 | textbox | Contractor's Rep Name:
b7f5da01-ad6e-5b59-883e-b6db6508fa07 | textbox | Engineer's Rep. Name:
f8fe48ec-862b-585d-a90c-725906c57ec8 | date | Date:
a9e3c242-eeba-4260-8021-9053059e4bd5 | signoff | Add Signature
5c3ec20e-3f84-4bef-92cf-d1d49bda1fb2 | checklist | ITP - Foam Bitumen Stabilisation - Pre Treatments Rev C | itp | ITP - Foam Bitumen Stabilisation - Pre Treatments
b5380e82-7ea2-43f9-9cf1-e3e33c4693b1 | section | 2.0. BEFORE BITUMEN STABILISATION STARTS
fc5a4667-6af6-4155-b643-7c27310d3064 | checkpoint | 2.01 - Setout section
b7469805-4d2d-5688-b1c2-ac7dc36cf157 | note | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
e724fc98-a3cd-5be9-9b0c-267d845cf819 | note | Action (Hold, Monitor, Witness) - H
6d79dfa4-f884-5541-a77a-8fc8b9bd1aae | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to each section
87ef72cf-2925-570c-9dcf-5b14bf8a84b6 | note | Inspection / Test method - Survey
d1b0ce30-8573-52d3-8386-713bd8239800 | note | Acceptance Criteria - Document existing furniture
1aa192fe-6cc8-5ee2-b323-b47be9784e4f | note | Record documents (QCP - Quality Control Portal) - Electronic survey files
fc2f52e7-c16e-55d9-a62a-53e065adacd3 | note | Responsibility - Contractor
9ec84cce-fe78-5efb-ab57-1e13a5ab66b4 | note | Eng. Rep - I
7b121d1a-fcf3-553a-94b8-14cc6c9f0f82 | note | Contractor - R
c2cbd3a7-5e8b-4ca0-83a3-7fe870dc31ba | signoff | AUTHORITY HOLDPOINT
27b67008-3b42-40f0-a584-381bfc9ec55d | checkpoint | 2.02 - Pre-hoe, shape and proof roll
1a33fdc7-b426-5544-943b-ae7d3da94a72 | note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
f1b7b2ea-c8ce-56aa-8f17-a7ce62c9f405 | note | Action (Hold, Monitor, Witness) - H
c5821353-42c7-54cb-9f23-e7e9deac0b08 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to stabilisation per section
fa387cf4-552f-5095-9640-9b2894b34f9a | note | Inspection / Test method - Use grader's machine control and inspect shape
70508a94-ce95-5d84-828a-2be4ffda606c | note | Record documents (QCP - Quality Control Portal) - N/A
09fd418c-7356-549d-8ed6-5fd35d5afdea | note | Responsibility - Stabilising Contractor
fda5d0b8-d342-5fa6-a369-3938d12aac04 | note | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
ba171a3d-4ee8-50bf-825f-08f9a92d3583 | note | Eng. Rep - A
d8a80e99-bbcd-5346-9212-c09f3113f77e | note | Contractor - R
153e22f6-8332-4b5f-8ef6-164b57d847d0 | signoff | AUTHORITY HOLDPOINT
99764d25-1bc5-4ee4-8eac-200f107a4eb6 | checkpoint | 2.03 - Pre-hoe, shape and proof roll
7e7244cb-29dd-5271-87ab-8eeaf538db0b | note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
ab334fdf-e593-538b-9bce-ab93d8153b82 | note | Action (Hold, Monitor, Witness) - H
8af1194d-4a39-592c-a9a6-d8bd85129e56 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to stabilisation per section
6e14ef5c-0158-54c9-8e49-28e4593cca90 | note | Inspection / Test method - Visual check or Vibratory Roller's response meter
b6297ab8-c5f6-5cd8-82ff-8b23cfe1eb43 | note | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
2dc434f3-9644-511f-91c2-92a986086842 | note | Responsibility - Stabiliisng Contractor
20763f7e-1f40-569c-8cc2-e6ed866a5182 | note | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
7fe1a52c-9ba6-5ab0-b4fd-f8cb25d76034 | note | Eng. Rep - A
12f25bd5-3890-5116-80ce-57ed8b1cf47c | note | Contractor - R
b0347f78-412b-4a28-bfd3-45818549bfff | signoff | AUTHORITY HOLDPOINT
bb116b83-3e20-44e6-a2b9-71d5d4de447a | checkpoint | 2.04 - Compaction
058499d2-be7f-5b01-9ea2-af4ff46c5874 | note | Detail of Activity / Test - Plateau Density Test
75aa1f03-8d4d-52c8-b5ee-40b6298b46f3 | note | Action (Hold, Monitor, Witness) - H
d4751b14-aa88-5829-afbe-556528e51199 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
d49f8c39-72bd-5f51-8c6f-2a1891d4d089 | note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
ac60ac3c-7330-5527-9da5-d226d63b0bd3 | note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
2f7d7c07-1d7e-550f-b460-b95b4acc33a8 | note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
6450f46c-b1c6-5f98-ad2b-c325eb217762 | note | ○ IANZ report when processed
87bef643-8269-5062-929c-c74583eaa879 | note | Responsibility - Stabilising Contractor
046b2466-037f-562d-848e-7383192569e5 | note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
7ac7a66f-50a4-5c7f-89dd-24d7d2d5d8bf | note | Designer - I
bcaeb408-5c93-5ff7-8977-f4336aa67cdc | note | Eng. Rep - A
5941c94e-d642-59b2-a4ad-53c9a4c7ce2c | note | Contractor - R
d3bc96d8-73d8-4cfb-8ea2-52821e351822 | signoff | AUTHORITY HOLDPOINT
c10aec6c-2b5b-412e-a647-bfc63ee16f10 | checkpoint | 2.05 - Compaction
901435da-41cb-523d-963d-705a3b8063a9 | note | Detail of Activity / Test - Maximum Dry Density
b061050b-7434-5188-b556-818ebfb82388 | note | Action (Hold, Monitor, Witness) - M
5cac288d-9b8f-5551-8486-d0857c7cee12 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
21801d26-1e34-52d2-9fe4-753db1354c5e | note | Inspection / Test method - NZS 4402.4.1.3
bc6d77f9-2a20-583a-8a77-37f04050e0ac | note | Acceptance Criteria - For analysis of DoC
df535908-0605-5135-9f59-1ee9853ead46 | note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
e02909d4-7fe6-5d65-b7c1-2cd730384df3 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
6da2f203-8631-560c-a79b-07df86d38458 | note | Responsibility - Stabilising Contractor
d50877a6-c186-5104-bc67-f4cdb7e1807f | note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
6b6977d0-5412-539d-b0a7-4bfbc8848bc2 | note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
f26b344b-6a96-5b92-9f5c-38990138b396 | note | Designer - I
0d87ed54-5817-5330-87c8-b2d6f17f04e7 | note | Eng. Rep - A
201e2e87-3c8e-56d6-aae2-79e7a5693e87 | note | Contractor - R
1ceca5d7-3c2d-461b-936b-f25e0fdd9ad7 | checkpoint | 2.06 - Compaction
bf61e0aa-8c32-5224-bb3b-d59c189fcc6d | note | Detail of Activity / Test - Degree of Compaction (DoC)
3d71ddbe-abc3-5eb7-96e7-9a19cd506f37 | note | Action (Hold, Monitor, Witness) - H
7de0b9cf-65d1-521c-805c-4c1b7b3b2471 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per 1,000m2
4b7ac3fd-5ed9-5c29-be5b-c04e4d404463 | note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
f8152922-8603-5b46-b269-27adb71591b0 | note | Acceptance Criteria - Average DoC ≥ 95%, Minimum DoC ≥ 92%
1fc14b82-1c04-5cb6-a20c-46422e9014be | note | Record documents (QCP - Quality Control Portal) - IANZ Report
507979e9-19fa-5fff-aacc-33085d19abee | note | Responsibility - Stabilising Contractor
17381022-6206-5f0a-a079-46bc59b6ff05 | note | Designer - I
5fbee23f-f138-5ba7-8cfa-b2222c955975 | note | Eng. Rep - A
d1be43e6-511e-534d-88ef-fa55fb79f734 | note | Contractor - R
898fe605-3296-4d54-94cc-cae663c28e43 | signoff | AUTHORITY HOLDPOINT
6bf12dc1-6647-4bda-9ec0-13c4d2445c68 | checkpoint | 2.07 - Overlay and check levels
8923d334-d910-5e42-bb6a-34a2f4def70e | note | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
ffb8b7f6-3e8a-5d69-be7c-5aade7a14c87 | note | Action (Hold, Monitor, Witness) - H
eb450803-e054-5eba-86a7-f39bb7229336 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to stabilisation per section
b800b703-c2e4-5248-872c-86e59ba9b4f2 | note | Inspection / Test method - Survey
87457d51-bacc-58b8-9afb-f576c0bd082f | note | Acceptance Criteria - As per NZTA Z/16
225536c8-03d8-5ecc-b29d-2bf16f16d15a | note | Record documents (QCP - Quality Control Portal) - Check with Grader and visual inspection
c593bfeb-8b16-5594-a073-f168d2628f01 | note | Responsibility - Stabilising Contractor with Main Contractor
ba34c5c1-6006-5c4e-bef4-2783f004ece4 | note | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to):
5b4cc416-89e3-5a61-892c-88f667c3d685 | note | – overlay aggregate quality / consistency
5bc33a54-86b2-5f1e-9278-5d6224f2c40e | note | – moisture content
7231f15a-2317-5de3-a22a-1ec79f39b14b | note | – any concerns with shape and tie in
380969e7-5837-5d34-bbad-5d2dccc711bf | note | – etc.
48eede4b-6cfd-57dd-b8e4-14f45872dcf5 | note | Eng. Rep - I
645469d6-fa15-591a-872b-eb63ee1c74ed | note | Contractor - R
129867dc-0b95-40f6-86d6-b51aa80378ae | signoff | AUTHORITY HOLDPOINT
dece3019-bde1-4321-9231-cedd7a8b66b9 | checkpoint | 2.08 - Production Plan
521feea3-a803-59c7-859d-dee41bea4adb | note | Detail of Activity / Test - Plan showing cut lines and sequencing of works
ccf083d1-d138-5afc-9a67-f45ba0495a69 | note | Action (Hold, Monitor, Witness) - M
e4d579f1-2d77-56b2-a5ad-6b9c29a782e0 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to each section
cfc164ff-c29a-543e-823a-ecb59fbeefe0 | note | Inspection / Test method - Daily Report
afd81382-4a7e-59f1-ad3d-7f70e31bfdc4 | note | Acceptance Criteria - Points covered in NZTA B/5
119e766d-05ae-5ffc-9a05-bdb23e617546 | note | Record documents (QCP - Quality Control Portal) - Daily Production Plan
9f37db90-cb9f-52c9-b4e2-253cf35768e1 | note | Responsibility - Stabilising Contractor
387bb612-5d94-544b-90e9-a875fdccf7a8 | note | Eng. Rep - I
936415f3-bcc7-5ead-8c88-16cd13f3e590 | note | Contractor - R
6c0708eb-f46f-4385-9d0b-39267adaca6d | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
c34b8ce0-3d61-544e-8c75-834a27e89cf5 | textbox | Contractor's Rep Name:
4f59ee66-2f61-53b1-bf3a-e5fd6e5e4671 | textbox | Engineer's Rep. Name:
35138d07-1c71-5210-86a8-ba8ffc6540a9 | date | Date:
edd9ccc1-984f-4551-8bdf-d2aa5a2495f8 | signoff | Add Signature
cb00c33f-d8e2-40f5-bdc9-212ab93eebbb | checklist | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - FBS Rev B | itp | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - FBS
d8ef6521-879e-4d25-a8ca-f219b0cba94d | section | 3.0. BITUMEN STABILISATION OPERATION
300678dc-be5d-4458-9307-45d413bcb864 | checkpoint | 3.01 - Stabilising Agents
7b170038-bb70-5b1a-b084-fb7fc15f5a0d | note | Detail of Activity / Test - Lime (if applicable - check PI delete otherwise)
0c7986a4-72ad-592e-88d0-815571f023ec | note | Action (Hold, Monitor, Witness) - M
0e7286f1-e551-5a79-a654-f398e9eafa64 | note | Minimum Test Frequency - Per Batch
9b85c672-a926-50e2-b30a-dfbb6c49d1f7 | note | Inspection / Test method - TNZ M/15
765917b3-52a7-51e3-855a-294185b56bfd | note | Acceptance Criteria - Conform to Specification
ff06a786-381c-56b1-b349-8131389b5d74 | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
e79a0344-b583-51c9-8b45-2c235f858a7b | note | Responsibility - Stabilising Contractor
345022ad-9cb8-5ab5-b39f-01dce5fd877e | note | Designer -
af6d9fb2-2a3e-5471-9e91-7610b1df4ea7 | note | Eng. Rep - I
df048ed3-030d-5007-abb1-8b0590f9cd70 | note | Contractor - R
fa2b539f-ca18-4324-96a4-752373b43667 | checkpoint | 3.02 - Stabilising Agents
3a5ab8ad-289b-53e6-944d-06efc708dc79 | note | Detail of Activity / Test - Cement, GP
9a21d9df-7666-5b29-a037-ff5cf9e008f2 | note | Action (Hold, Monitor, Witness) - M
190a5196-6f13-5f4f-856d-9b8d67b39923 | note | Minimum Test Frequency - Per Batch
32ed7bfb-4c22-5e8c-b0f0-3cde43c2cb50 | note | Inspection / Test method - NZS 3122
aa167323-6a7d-5781-bf2d-e0263c3a2d2b | note | Acceptance Criteria - Conform to Specification
4c4adb36-8da2-5f6f-b91d-4655ed17a9e0 | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
075bd061-0d18-576c-8f6e-d27dbc904b3c | note | Responsibility - Stabilising Contractor
dd2aa021-42b3-5206-80db-1bf9fd9f8222 | note | Designer -
87d9f3f2-f9a2-525d-b537-b26486036c8f | note | Eng. Rep - I
faeb97a4-e5a1-5fc0-bebc-a128ca64b49f | note | Contractor - R
776294c9-64df-4a85-a4d5-f54887b765b0 | checkpoint | 3.03 - Stabilising Agents
0f01e20b-38b1-5046-86e0-2894bdb5c1fe | note | Detail of Activity / Test - Bitumen (130/150)
8a1e7aa8-d720-5907-898e-139c0c811b18 | note | Action (Hold, Monitor, Witness) - M
ca11a5b7-a155-5721-a150-34b6ccafe869 | note | Minimum Test Frequency - Per Batch
94ed4fed-7216-54f0-91a7-a1d6ec0cec28 | note | Inspection / Test method - M/1
c640dd2c-73c3-5545-a3fd-d95af039ab37 | note | Acceptance Criteria - Conform to Specification
76d5f00c-4c27-5a39-9f2d-c7d579a24bba | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
c4f68861-faca-5a6f-a0fa-fe413d9cfc69 | note | Responsibility - Stabilising Contractor
ae8f8a0c-6561-53e8-8645-a14a7dc29ac6 | note | Designer -
84e09dee-2db8-5591-a718-ff32a4e3fe8b | note | Eng. Rep - I
73c91c28-f3b7-5a5f-8d95-ce33b40b92bf | note | Contractor - R
678b213b-a6fa-421b-b320-15fbcd65d6bf | checkpoint | 3.04 - Weather conditions
673501bb-f801-5100-9331-90ef3b1d2978 | note | Detail of Activity / Test - Material behind stabiliser
2f231e77-2996-5df6-aef4-69e59a7b5669 | note | Action (Hold, Monitor, Witness) - M
e55f3cc8-4b60-5e87-8399-ccc30aaff79e | note | Minimum Test Frequency - Prior to spreading
713d2c20-2fdb-5805-a873-0c651eb8b694 | note | Inspection / Test method - Measurement
68989f55-6a17-5a03-9de3-f64e35a0210b | note | Acceptance Criteria - Material after stabilisation:
fcaede72-4cfd-517b-8f23-d144caeafb3e | note | ○ BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C
0b47cf0d-695a-58ce-b578-bf16b70ec639 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
3dd888fd-234e-5419-8372-356745954d72 | note | Responsibility - Stabilsing Contractor
c40cf100-3079-5dd0-aa29-ebc553ac2e49 | note | Designer -
f0b5fbce-32c6-5bb9-865e-bdae74ec9df5 | note | Eng. Rep - I
3225b6c9-e4d1-5a8f-ae48-cc625362984c | note | Contractor - R
5c7cc53e-f663-4c87-8fe3-9bb6f541c508 | checkpoint | 3.05 - Weather conditions
f7cd9bcf-5cb3-5944-bd42-40336296274a | note | Detail of Activity / Test - Wind
0007adf5-b9d2-57f6-a9d7-b98afdf02b0b | note | Action (Hold, Monitor, Witness) - M
7dbd22a6-3689-5167-ab62-fc7e42d40a30 | note | Minimum Test Frequency - Prior to spreading cement or lime
00624b8a-bc75-51be-a7a3-8e807022f883 | note | Inspection / Test method - Local weather stations
95563aca-78e7-540e-8055-c8c62e07a677 | note | Acceptance Criteria - Wind speed < 25 km/hr
1b1ad197-5bed-5b7c-8127-5fc802d012dd | note | Record documents (QCP - Quality Control Portal) - Daily work Log
2e6d26bb-617c-5e53-89df-9b24e8592bcc | note | Responsibility - Stabilsing Contractor
126823c4-3eaa-5382-a6cf-6b44bac4f286 | note | Designer -
f6ff4da3-2306-58cf-be22-7350e1440fa6 | note | Eng. Rep - I
08478bfb-47f6-5c3d-83ad-45206d9eb6c2 | note | Contractor - R
46bc8ca9-bd9a-44d4-8193-e7d6e79fcb04 | checkpoint | 3.06 - Weather conditions
c8976fc8-4a07-508c-8e3a-a6d3ec00cfdd | note | Detail of Activity / Test - Rain
1abcbe2e-a646-577b-9132-f3df4242ef2e | note | Action (Hold, Monitor, Witness) - M
2640dbe6-905a-50bf-b2f9-63ccc540a822 | note | Minimum Test Frequency - Prior to spreading cement or lime
765da351-2312-5e0d-8a07-8a61d5ac4e98 | note | Inspection / Test method - Local weather stations
183adf0d-bae1-57bf-b595-b7482a5cf498 | note | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
a57dbf40-5197-586a-b917-11e564497229 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
a5f4501f-7c59-5ce6-8eee-677c85a4a0da | note | Responsibility - Stabilsing Contractor
e5ada5b9-c189-5046-8240-794b8ac4b27f | note | Designer -
20ad339f-e471-5f66-b764-786c7e56729d | note | Eng. Rep - I
9b39e0f0-0e6c-5f8e-878f-df44d24fc0a7 | note | Contractor - R
431fa874-f2fc-4636-b32a-5811d8db4516 | checkpoint | 3.07 - Spreading of powdered stabilising agent (Cement / Lime)
ec973ca8-2332-52f1-9ec9-7ff79f2f35b6 | note | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
8a8fb0bb-63d6-5063-a904-f31948bb376e | note | Action (Hold, Monitor, Witness) - M
38c85354-25f9-5666-b974-b39b61cd8f4b | note | Minimum Test Frequency - every 400 m2
f1100932-f506-576f-9613-928cd1e2a4e4 | note | ○ every 150m for a 2.4m width
45e0cb21-9d17-51a6-b6ef-02be569652e8 | note | Inspection / Test method - Weigh mat or tray
032e5784-c0cf-523b-9ecd-cbcdea625b17 | note | Acceptance Criteria - ± 0.5kg/m2 of specified rate
4f1dd546-33db-5492-856b-df29681b2a0f | note | Record documents (QCP - Quality Control Portal) - Daily work Log
d3f7eeb4-40e3-5d54-8745-05a3ab956a92 | note | Responsibility - Stabilising Contractor
94c05036-ae3f-5bc7-982e-3baea4161f15 | note | Designer -
33fc58e4-001f-5ff2-b224-4b03aa6100ca | note | Eng. Rep - I
c3910f24-a58c-5f08-b8ae-cc48aea46677 | note | Contractor - R
13da3fc0-d9d6-440a-aae2-10c8adc392ef | checkpoint | 3.08 - Spreading of powdered stabilising agent (Cement / Lime)
69ee29b5-89c8-51cb-aa14-3a9eba23124e | note | Detail of Activity / Test - Compare area spread with weight used for each spreader load
4c05d370-4f44-5e41-a9cb-b8f56322c9a1 | note | Action (Hold, Monitor, Witness) - M
824934b9-e78a-528f-b026-af694eec4cae | note | Minimum Test Frequency - On-going measurement by computer/load cells
5e2e3791-7019-58b0-b629-601bfeb45bee | note | Inspection / Test method - Measurement each run
26b1e2fd-2632-5ea5-b9ac-d0d02dff7008 | note | Acceptance Criteria - ± 2.5% of specified rate
d667831f-f287-5ecc-b573-db706105a9bf | note | Record documents (QCP - Quality Control Portal) - Daily work Log
203e4243-4be0-584d-9c72-0e5ca20b6102 | note | Responsibility - Stabilising Contractor
5d7e66de-839d-5147-9cd5-7d540a601fe2 | note | Designer -
87d9c396-5f0b-5ccf-9a1d-18e6cfce43a2 | note | Eng. Rep - I
fc41935f-c38f-54b5-a5ee-fff957b43dd9 | note | Contractor - R
6e352b39-75d7-4e73-94c7-2384c865ec6a | checkpoint | 3.09 - Injection of bituminous stabilising agent (FBS or BE)
80a66f69-bd2c-53ab-b872-8db097eae54c | note | Detail of Activity / Test - Flow meter and operator's display readings
08d4d7ac-b3bb-5c2a-8ed6-2b814be07b43 | note | Action (Hold, Monitor, Witness) - M
376d8475-b394-5178-94da-69606a3280d5 | note | Minimum Test Frequency - Continous monitoring by the operator and the grounds person
7acbcb79-1382-5324-8ed1-0da489cb4ef5 | note | Inspection / Test method - Visual display reading
65201396-bd65-5809-91bb-72e93f9a7ecc | note | Acceptance Criteria - ± 5% of specified rate
338b675f-7cf3-544f-b64a-8c3b9e76119d | note | Record documents (QCP - Quality Control Portal) - N/A
a57a308e-a570-5c31-8e1d-5f28776d20e1 | note | Responsibility - Stabilising Contractor
99b11250-168f-59d6-a153-ccf05d22a56e | note | Designer -
72e93935-e6ad-535b-92dc-f626b29d1087 | note | Eng. Rep - I
ee1f34d8-14ed-5142-bd2d-80f31c540696 | note | Contractor - R
eef99401-f8e5-4d5b-a0f5-ec179790ca5a | checkpoint | 3.10 - Injection of bituminous stabilising agent (FBS or BE)
9e03074f-be8c-51b3-9ccc-68824b6aa9d4 | note | Detail of Activity / Test - Compare tonnes used (from the stabiiser's PCU) with the measured area
5e3ed324-3350-526c-9d4b-4c7e79411f2a | note | Action (Hold, Monitor, Witness) - M
36a5e2cd-5a87-5a23-bc5b-5f4ef2468a4e | note | Minimum Test Frequency - Record usage from PCU at the end of each run
4f62b893-99f0-5e38-a9cc-8478593f4bfc | note | Inspection / Test method - Record readings at the end of each run
664ab4f6-b801-5c43-ac27-4913d61f32fa | note | Acceptance Criteria - ± 3% of specified rate
f96a6822-ba9f-50e7-b1e3-96416032d09b | note | Record documents (QCP - Quality Control Portal) - Daily work Log
95aea2b8-6651-57d5-9ad2-4ed945710b7c | note | Responsibility - Stabilising Contractor
7946edcb-856a-59ff-850c-7bebfc4ca9a7 | note | Designer -
e21fe23b-b623-5997-b238-141981fb0ded | note | Eng. Rep - I
7484c209-0182-53ce-b384-b9a879b5bd04 | note | Contractor - R
870f663b-ff6e-4b1f-970c-00deb9971e70 | checkpoint | 3.11 - Injection of bituminous stabilising agent (FBS or BE)
59a9ceee-95ab-59e6-8ec9-86c8be6b3b07 | note | Detail of Activity / Test - Compare tonnes used (from delivery docket) with measured area
9d561315-b77b-5cf4-9602-c83d9e4a434a | note | Action (Hold, Monitor, Witness) - M
52f7bc6d-2dfd-5c9c-b5d2-9449b5c93b3f | note | Minimum Test Frequency - For each bitumen tanker load
3b191d38-90be-5291-9ec1-40e72d463727 | note | Inspection / Test method - Dip bitumen tanker before and after
cb163d06-e7ab-574c-843e-bfb0d281cae4 | note | Acceptance Criteria - ± 2.5% of specified rate
61cd63fb-af6f-5eff-a915-9f73ec3e19c6 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
1aec19db-ae4a-5890-92a4-b1300cab33f8 | note | Responsibility - Stabilising Contractor
b8f21546-25c3-5eef-8cc6-7798928bf6b8 | note | Designer -
f4cfa13d-85ba-54d9-8b26-a49766dacf48 | note | Eng. Rep - I
f9cdf248-6493-5fda-b29d-82d333b6d7c1 | note | Contractor - R
2657bc9f-7cc9-41b4-98a7-ef62164b4d52 | checkpoint | 3.12 - Injection & Mixing of Water
364626a4-87a6-51c9-98de-80acf519457a | note | Detail of Activity / Test - In-situ Stabilisation process
37d9c6e2-3d4d-5eef-a873-5eea3c83d824 | note | Action (Hold, Monitor, Witness) - M
2e49cb39-1d8b-5110-aea6-4d4ce9149707 | note | Minimum Test Frequency - On-going visual assessment
ec67b07d-21d7-5e5d-b78c-126368097246 | note | Inspection / Test method - Visual and hand squeeze test
3488c196-691b-563c-98c7-13a7c61ba05c | note | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
76485777-fbb0-5257-8f74-52abea6e6de5 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
b9b1032f-2743-59c9-af1b-3680eb6de815 | note | Responsibility - Stabilising Contractor
0714fd78-e6bc-505d-be6c-f676be78cdc8 | note | Designer -
0f4fe2b5-61dd-5cd5-ab52-2debbbb58f80 | note | Eng. Rep - I
84150439-1baf-580a-9980-a4836cb3e130 | note | Contractor - R
131bbfa0-1a5a-4c76-8188-fe0f10a9a6ed | checkpoint | 3.13 - Depth of stabilisation
684feebb-6f13-539d-be07-5c485c7c13f0 | note | Detail of Activity / Test - Depth of stabilisation
5753db85-4f1a-571a-8779-728562178829 | note | Action (Hold, Monitor, Witness) - M
d15bb0fa-92c9-5751-8768-e4b856304057 | note | Minimum Test Frequency - Every 200m
7e7b9024-a6ed-5853-b981-7de1314e144f | note | Inspection / Test method - Measurement
e7e98ef1-6f53-5938-97be-90de519f336f | note | Acceptance Criteria - +15mm / -5mm from specified depth
65f0c92c-bdd1-5d7d-9e0a-4ca6e9578972 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
62930853-3ac9-568e-a696-26c08b3bcf17 | note | Responsibility - Stabilising Contractor
7846a892-dcaa-5b4c-a19a-1cad4520d5a0 | note | Designer -
43d1f80c-1412-523f-b198-11f503cbb9b2 | note | Eng. Rep - I
40934b68-9656-5273-bb26-a77a033c11ef | note | Contractor - R
6f29ca26-9bd9-40d4-8c2c-623f74c3545d | checkpoint | 3.14 - FBS material
3c5400b5-b6bc-53cc-8ca9-bf7a9b4c30bd | note | Detail of Activity / Test - Stabilised material strength - ITS
62dd85bb-ed21-513a-b4b4-bfed1d4f34dd | note | Action (Hold, Monitor, Witness) - M
250fa7e1-9af4-5536-acd6-75865e5dccea | note | Minimum Test Frequency - 3 soaked ITS + 3 dry ITS per Lot or when the material changes
b05b7ac1-4111-5c99-9c72-28c6013324d5 | note | Inspection / Test method - NZTA T/19N: 2020
650e8247-f461-5429-9e40-dde904cbeb40 | note | Acceptance Criteria - Testing at 1mm/min:
c4ad9a2d-c480-5151-9f36-515f193e7636 | note | ○ BSM Dry ITS: 150 kPa to 400 kPa
e5a5bebb-6c34-556f-b03b-9bb9ed3c2ce2 | note | ○ BSM Soaked ITS: 120 kPa to 350 kPa
6b86a787-d8c1-538c-a92a-df2f52634331 | note | Testing at 50.8mm/min:
fe55f2cc-ae92-5e98-999c-fe37e6598133 | note | ○ BSM Dry ITS: 180 kPa to 450 kPa
2e2dc7df-590c-5af8-acab-c8a7258f08f7 | note | ○ BSM Soaked ITS: 150 kPa to 420 kPa
0ebb3a0f-7097-5867-8b6b-cae9feefc570 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
7584af84-8d9e-570a-917e-02c0e8e7ad99 | note | Responsibility - Stabilising Contractor
d4ca534f-b956-58df-b4ec-9fe1baa9a174 | note | Project Specific Notes / Instructions - ITS briquettes to be produced on site if travel time to lab > 30 minutes.
4333fdc1-dcec-53c3-bbc6-e6412dcca425 | note | Designer - I
9417c5e5-1bda-5d71-a90b-4369cf226344 | note | Eng. Rep - A
38e34eff-fe0a-58e8-8e5f-a06c99aa63c3 | note | Contractor - R
82af3bce-00d2-40a4-93f7-a1024f1e9428 | checkpoint | 3.15 - Compaction
71ad2461-ba7e-52c0-bfbf-3913ad32e6f6 | note | Detail of Activity / Test - Plateau Density Test
0d26d21c-d02c-5242-a259-45d562fb4ee1 | note | Action (Hold, Monitor, Witness) - H
51090804-507a-5c8f-a7d3-4fc788abd05e | note | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
141a41ba-c681-5a45-a097-9f648b9b8850 | note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
2a69971c-c854-5060-a945-5d3f437f81e4 | note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
65d40f0c-0c24-5985-8cdd-851cfc4c8244 | note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
221ccbe6-ccc9-591e-84ea-36e479c5f78c | note | ○ IANZ report when processed
3b5fe2f6-7225-574b-b023-db1a5e28b41c | note | Responsibility - Stabilising Contractor
fb7cd940-f61f-5d51-8e0b-f048f79f1345 | note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
9e939af5-c786-5894-b0d9-4ab375675b15 | note | Designer - I
da5be10c-0731-5d67-9e96-c10802830c0a | note | Eng. Rep - A
33fc4bb0-5580-5f00-b882-4d901518d57d | note | Contractor - R
eecc1077-6c58-447c-84b2-f929cfa33a31 | signoff | AUTHORITY HOLDPOINT
5114b78e-d8de-4f5d-a6c9-8462e7bb793e | checkpoint | 3.16 - Compaction
75bd4811-1b5e-522d-a0ee-69766bba8b16 | note | Detail of Activity / Test - Maximum Dry Density
7b96987f-6ed6-5f39-bebd-071c29ebe0a3 | note | Action (Hold, Monitor, Witness) - M
d32c72cd-9aa8-56ec-8750-6e6d5f9afb87 | note | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
858ab6d9-28f4-55fc-9f47-bb7f679283b1 | note | Inspection / Test method - NZS 4402.4.1.3
9e90a469-6f86-5eb4-ba01-6f018ca6e045 | note | Acceptance Criteria - For analysis of DoC
4b1d2e1a-3791-5ec9-bfd2-7aed0c5e1271 | note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
9cd47372-fbbc-524b-9db1-d56ed8d9f5f3 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
54dda18d-012a-5bcd-be74-43979c5d5006 | note | Responsibility - Stabilising Contractor
2630d42f-1bc7-53e2-9278-3c5ca7ecbee5 | note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
520c5eeb-c4d0-5062-a0d6-a8bdd0529f68 | note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
2a7be574-8c8c-5da8-b8af-36d5e1ff13a0 | note | Designer - I
c674dd6f-a79e-5b05-a9b6-e5948571ebe7 | note | Eng. Rep - A
4394b227-c939-512d-a6ec-e313a4921b1a | note | Contractor - R
d4b36688-a0ae-4a74-bee5-454d7f5bc6f0 | checkpoint | 3.17 - Compaction
920c0204-29ae-55e1-816d-7c4cfd9ea3b0 | note | Detail of Activity / Test - Degree of Compaction (DoC)
74cded30-3424-57bd-b8c1-c03a6aa9f558 | note | Action (Hold, Monitor, Witness) - H
010e233b-3733-54cf-ae6b-c0d6aabda295 | note | Minimum Test Frequency - 5 per 1,000m2
9e70d432-7191-5c9a-91f4-43a47e94c84d | note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
de990b5c-e40d-5703-86d0-734327700ad8 | note | Acceptance Criteria - Average DoC ≥ 98%
bcb0d54e-5401-54ca-8ab0-86eca4da7edb | note | ○ Minimum DoC ≥ 95%
8a511aa2-fe57-5a41-bced-db88162326aa | note | Record documents (QCP - Quality Control Portal) - IANZ Report
bb64a9e8-f5c3-5323-95df-fdb9a432e858 | note | Responsibility - Stabilising Contractor
4ab4807d-a46d-5c58-9d9c-34189572d55a | note | Designer - I
1a480cd1-b62c-5d03-8027-fbd2917c6321 | note | Eng. Rep - A
c5a83294-40d7-5d71-a02c-1527060faa2d | note | Contractor - R
d55cecd1-1453-452b-b729-8825b656bb75 | signoff | AUTHORITY HOLDPOINT
23137da4-62ae-47ab-822c-80e471fdedc4 | checkpoint | 3.18 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
98af9cb1-3178-5a4a-8f48-861e780276c6 | note | Detail of Activity / Test - Clegg Impact Value
52d5306d-44ba-5b80-891a-9a2e006e2b4a | note | Action (Hold, Monitor, Witness) - H
f571df61-6c3c-5d2d-b3fb-1ac8d83aec31 | note | Minimum Test Frequency - 5 per 1000m2
3c139de4-3414-5f00-848f-12e040697897 | note | Acceptance Criteria - CIV ≥ 50
39f3e454-7ba2-5ebe-b7e9-9d75befb0418 | note | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
1ceffda6-16cb-59e8-9b02-8d120b94dab7 | note | Responsibility - Stabilising Contractor
6602fc72-e6d8-558d-937d-b44832007dbe | note | Designer - I
35cc424e-afa4-5f44-973f-baa5e2ce009b | note | Eng. Rep - A
eda4eb11-20c2-59c5-8e1d-1f72dd7a6031 | note | Contractor - R
a394fb02-0299-49b8-909f-6301cd3ee93e | signoff | AUTHORITY HOLDPOINT
8cbdb261-7992-4a01-b98c-acfd4799e247 | checkpoint | 3.19 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
ffcf1cbe-05d2-5f7b-b41d-77537d9f1d73 | note | Detail of Activity / Test - Degree of Saturation, DOS
5ab91b91-eee2-5802-813f-bd95b74a1724 | note | Action (Hold, Monitor, Witness) - M
b6de0756-8b40-5b93-8042-92ee89223143 | note | Minimum Test Frequency - 5 per 1000m2
61cb77b2-43a6-52ac-a134-89068936ee96 | note | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
c6cbe3b8-0195-5d34-b37f-5c7ebcd37f9b | note | Acceptance Criteria - aim for DOS ≤ 80%
a0ade02a-5aa3-5cdd-9255-8ec4e706bca5 | note | Record documents (QCP - Quality Control Portal) - IANZ report
b08b39b6-b03b-5ae1-adcf-79ae41cbfda3 | note | Responsibility - Contractor
5cda9f0a-6440-5831-a062-5f65f32c3dce | note | Project Specific Notes / Instructions - Report only
26021cc6-b582-5218-8a53-b6fcc8c6ddf2 | note | Designer - I
b0e1ab3d-f151-5a4b-8748-9d9b625aaaa9 | note | Eng. Rep - A
2101dd0b-6fe6-51d4-8b3b-fa455a11262f | note | Contractor - R
2e1a76a4-8136-4708-9035-344d54465224 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
b20461d5-575c-55d7-86ed-94d61ffcc7da | textbox | Contractor's Rep Name:
1c91b8d6-d8de-534a-a30c-d94134463e2a | textbox | Engineer's Rep. Name:
8a25b29d-7533-5183-bb94-708f6456dbdb | date | Date:
34223289-a477-4015-b1e1-cf4658964dbd | signoff | Add Signature
3dfac74e-f517-49e8-99fb-1feb1ad50208 | checklist | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Material Testing Rev B | itp | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Material Testing
5c57a86e-8841-4d0d-83e1-4f6b50f3afcf | section | 1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING / DESIGN and DRAWINGS
5cbdd1c5-7c36-4c87-8680-40ddbd7ef27f | checkpoint | 1.01 - AP40 Basecourse Aggregates used for overlay (if applicable)
48017c8a-642a-5821-ab1b-8ab7fc45e4d4 | note | Notes:
f35c3142-971f-583c-b536-c5ec27ebccc4 | note | H = Hold point up to approval of Optimisation Testing
e462968c-05c1-5019-bcb5-cac800498a84 | note | M = Monitor during production
328ef5e7-9435-5348-bd66-ff1bcc1ab1c2 | note | Detail of Activity / Test - Crushing Resistance
b437c9d7-e7d4-56c9-8783-79ded052e0d9 | note | Action (Hold, Monitor, Witness) - H
ef60a537-6a26-5e20-8258-0230b96560f6 | note | Minimum Test Frequency - 1 per 10,000 m3
d73563d6-8a2d-56c4-8c12-c9ecdbd9c2b6 | note | Inspection / Test method - NZS4407:3.10
a7cb7961-413a-5ac1-ab4f-ad23616099e3 | note | Acceptance Criteria - < 10% passing 2.36mm sieve at 130kN
ce9768c5-4037-57f7-837e-19ed086cd680 | note | Record documents (QCP - Quality Control Portal) - IANZ report
ff248f98-7836-5212-80c4-006d6bb612d9 | note | Responsibility - Contractor
b0dcbd22-a086-5b38-948b-f63aed346f83 | note | Designer - A
f6103d3e-d71a-5d11-8a6c-62a1f5ead984 | note | Eng. Rep - I
cdfb57fc-040b-5066-8e5b-3ab01627e38e | note | Contractor - R
4abee1b7-b7c8-45de-899f-70da1e38d0f2 | signoff | AUTHORITY HOLDPOINT
5321a5c5-4351-4c15-a472-85ec7f7dd383 | checkpoint | 1.02 - AP40 Basecourse Aggregates used for overlay (if applicable)
90089326-5b0a-5fc4-abfa-0ac877a47dc7 | note | Notes:
8623cb8e-9d3b-53df-a501-3a0d692d1664 | note | H = Hold point up to approval of Optimisation Testing
f0013354-66d7-55bc-9be2-782139bc2ff7 | note | M = Monitor during production
eb0582de-a309-575c-a4f8-a0956ca8e1f2 | note | Detail of Activity / Test - Weathering Quality Index
51fb5635-ee72-558a-b24a-83afff5f3745 | note | Action (Hold, Monitor, Witness) - H
5ec79528-f975-5825-93ea-5b84dcbe6abc | note | Minimum Test Frequency - 1 per 10,000 m3
93256229-7f0e-554e-a70f-90c2458ebc6f | note | Inspection / Test method - NZS4407:3.11
d0b81b33-5dc5-5b95-b0c4-b5cd53236212 | note | Acceptance Criteria - AA, AB, AC, BA, BB, CA
2437dc4e-cedd-576d-900c-3fff2a08ce4d | note | Record documents (QCP - Quality Control Portal) - IANZ Report
d48f4a53-b9df-5f18-8450-85f44b4a4aec | note | Responsibility - Contractor
e4d30dc9-66b4-5762-824f-634eba3e15f9 | note | Designer - A
f25371e2-307a-5e4e-bc89-42d122c185b3 | note | Eng. Rep - I
5f45d956-afb7-50c1-bbb3-786500f9a590 | note | Contractor - R
f1b1d7ba-9aaf-4757-9bb3-011f905f47f3 | signoff | AUTHORITY HOLDPOINT
36cefb35-d465-4b3a-bd37-369ca9003f72 | checkpoint | 1.03 - AP40 Basecourse Aggregates used for overlay (if applicable)
8669be36-98ce-5807-ae2a-83da217fdfb8 | note | Notes:
6abe7959-9d03-5313-b411-f6d1992d2ca5 | note | H = Hold point up to approval of Optimisation Testing
1ec032ba-8599-501a-a4d6-77938f0ce70d | note | M = Monitor during production
3398bc85-78a7-5a5e-b746-9e702b65db2d | note | Detail of Activity / Test - Calfornia Bearing Ratio (CBR)
3f187061-b665-591d-8fd3-d9955f35a46c | note | Action (Hold, Monitor, Witness) - H
392d25d5-a839-5181-89cf-9f75599c2120 | note | Minimum Test Frequency - 1 per 10,000 m3
067727ae-39eb-5ce8-9b92-e578b43508cc | note | Inspection / Test method - NZS4402:4.1.3, NZS4407:3.15
38a3bbaf-75d0-5457-97db-c7cbfa5225d6 | note | Acceptance Criteria - Compacted using NZ Vibe Hammer
c717eb43-8f76-5e2b-9247-d7979a301aff | note | ○ 4-day soaked CBR ≥ 80%
c97e7b2c-b65d-518c-aff5-0d0d32cab3bd | note | Record documents (QCP - Quality Control Portal) - IANZ Report
e35fc8ff-72d0-5d1c-afbd-b02b134c3855 | note | Responsibility - Contractor
94a2e85d-3b71-52fc-b1cf-587bf95585c8 | note | Designer - A
bb3a5ba0-0ff0-55e9-8ae6-ff35005d3b7d | note | Eng. Rep - I
a259c717-503e-5235-938b-b1f8a67743a0 | note | Contractor - R
4a34497a-fb61-4d5d-8a98-fc197a59465f | signoff | AUTHORITY HOLDPOINT
54132683-783d-45a5-a3b7-c1b7ab4b45fc | checkpoint | 1.04 - AP40 Basecourse Aggregates used for overlay (if applicable)
44a6fa02-7c39-5f26-9975-36aeaf551fef | note | Notes:
903ce6f5-12ff-53d6-bdb4-bb017969ef4f | note | H = Hold point up to approval of Optimisation Testing
1ff50a37-e1e9-5f76-9ede-6d2afd577558 | note | M = Monitor during production
9e3daaf9-f61b-5db2-ac45-d145941b3d9b | note | Detail of Activity / Test - Quality of Fines, either PI or SE or CI
89876e8d-6226-58d6-9434-f6a76532e6b7 | note | Action (Hold, Monitor, Witness) - H
97fd00f5-6202-5420-a6bc-f837ec1a312c | note | Minimum Test Frequency - 1 per 1,000 m3
a9bd55ee-aeff-57b8-953d-3a29d45dc67b | note | Inspection / Test method - NZS4407:3.4 - PI, NZS4407:3.5 - CI
158b3623-a278-5a4a-ac18-2038f95a037e | note | Acceptance Criteria - PI ≤ 5
48e9f913-1aab-51ab-8042-b17dde46f18a | note | ○ CI ≤ 3
95036e8d-8a77-5a18-8c62-c78e73344196 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
ca35b2f1-2be5-57e2-9e78-884fb890ae60 | note | Responsibility - Contractor
fbbfed19-c100-5f23-8036-29a0cbba41af | note | Project Specific Notes / Instructions - NZTA M04: 2024
f1ab15de-9eac-547b-8729-9ca1eace060c | note | ○ AP40 - Class 2
87a87406-fbed-50bf-9e2b-057acce16673 | note | ○ PI and CI applies
3274a8bb-306b-54ec-9014-5781ff523445 | note | Designer - A
78beef82-84a1-5a3e-beeb-49c232ba77d9 | note | Eng. Rep - I
5dc382c7-3f9d-5c93-8279-06a08e75880f | note | Contractor - R
3bee49b6-ba79-452d-8f5d-3ade9f352b73 | signoff | AUTHORITY HOLDPOINT
3e3720ca-edb7-4086-bb99-5b73f6c874dc | checkpoint | 1.05 - AP40 Basecourse Aggregates used for overlay (if applicable)
9682cf54-bfdf-5938-a871-c05c0c3222df | note | Notes:
79f24023-d21f-5a19-9d79-969179086071 | note | H = Hold point up to approval of Optimisation Testing
188f9847-9127-589f-850a-f7f252d96221 | note | M = Monitor during production
6dd9b448-cf4d-54d3-a16c-835e09754dc3 | note | Detail of Activity / Test - Broken Faces Content
45bcb205-7d1c-5ea7-9f76-3d55e3588e49 | note | Action (Hold, Monitor, Witness) - H
2627185b-1a00-523a-b81c-e57f98af39ea | note | Minimum Test Frequency - 1 per 1,000 m3
df424d99-4761-5ea4-96b2-a53d5343c497 | note | Inspection / Test method - NZS4407:3.14
92ed48b8-c996-551b-b04a-086a178df94e | note | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
a5d5b0e6-2cf6-5dac-9b11-62a308f5b72b | note | Record documents (QCP - Quality Control Portal) - IANZ Report
543a10f8-fc26-531b-8a82-39adde0d860d | note | Responsibility - Contractor
785efb8b-1c94-5d00-b1da-60e0b072c472 | note | Project Specific Notes / Instructions - Waived if aggregate is from crushed hard rock quarry
7a6399df-c946-5e17-b491-b498a8e98eb1 | note | Designer - A
b822cb39-b74a-5f83-861f-cd15cdd564ad | note | Eng. Rep - I
6f04a6dc-c9c3-5207-83dc-a8102037fc02 | note | Contractor - R
b0960d1a-d860-4a73-ae08-7b9fa092fbb5 | signoff | AUTHORITY HOLDPOINT
6518ba89-7482-49fb-bf7a-3b69038756c9 | checkpoint | 1.06 - AP40 Basecourse Aggregates used for overlay (if applicable)
c8829cf8-50d5-5d86-8ca1-33d833320618 | note | Notes:
3fb6c50a-e320-5390-86fb-ad463ae3bde3 | note | H = Hold point up to approval of Optimisation Testing
08112104-9ac4-5ceb-9f7f-02cec8af4670 | note | M = Monitor during production
e2649ff3-7e2a-538a-9c08-3541f312fc00 | note | Detail of Activity / Test - Particle Size Distribution
f5d661f0-86fd-5dbe-8902-851187acfd4a | note | Action (Hold, Monitor, Witness) - H
17eb4d53-d57b-5a83-acb5-e44b2ddd384b | note | Minimum Test Frequency - 1 per 1,000 m3
38034cd6-d0d3-5aee-97a1-bf59aae7f162 | note | Inspection / Test method - NZS4407:3.8.1
d176e142-418f-568b-a53b-5acc086ec822 | note | Acceptance Criteria - NZTA M04:2024-Class 2
735b1fe4-c3bb-5ec5-a0ea-c5b7433fd787 | note | ○ Class 2 in Table 12 for PSD
fe004cf8-efa2-5b6d-a382-d8b74c6fbe57 | note | ○ Table 13 for shape control
b4533d68-e4ef-505a-b60b-75a6def0f5a3 | note | Record documents (QCP - Quality Control Portal) - IANZ report
55a93b77-1633-5523-83e3-a9545b40023a | note | Responsibility - Contractor
1b5c2df4-a739-51e1-a0a8-c7f6ab00e259 | note | Designer - A
71d1edb1-18bd-5f3e-90e1-7b3ebf699e29 | note | Eng. Rep - I
cd540e89-6762-5fb7-8b7d-3afcfb2c9790 | note | Contractor - R
9d749840-9bc8-45c4-89c8-ed614059c8b8 | signoff | AUTHORITY HOLDPOINT
2165838c-2fe1-4119-8404-5f5595e17778 | checkpoint | 1.07 - Optimisation of Stabilising Agent(s)
f6eb4174-6b68-5391-a745-4a460df963b1 | note | Detail of Activity / Test - Blend Particle Size Distribution
da3a9004-8c0a-51e1-afe4-94303afe379e | note | Action (Hold, Monitor, Witness) - H
84083575-08e6-5644-9b92-18a5c1f12f8c | note | Minimum Test Frequency - 1 per 1,000 m3
b15492b2-7e60-55ec-9afb-e89aed5fb81d | note | Inspection / Test method - NZS4407:3.8.1
c4c63bc1-b08d-5048-a2e7-2b63a1b234c2 | note | Acceptance Criteria - Check if average of existing (from TPs) and any overlay will meet the ideal FBS / BE grading.
a5dbe4b5-8196-51d6-bb55-9bfd3abd7a9b | note | Record documents (QCP - Quality Control Portal) - Report using IANZ Reports for AP40 and TP PSDs
90ea92bf-c34d-597d-b7c4-c453a9f53636 | note | Responsibility - Designer
d51f0fff-89be-50d2-aae9-d877af3b1809 | note | Project Specific Notes / Instructions - Designer to advise if "average" blend is acceptable.
568da662-d3d8-5f90-8995-483b2069d9bf | note | Designer - R
c2b3edfb-f050-5c06-9565-dc887ae2de40 | note | Eng. Rep - A
dc5e04c8-f953-59c0-bcd4-ade1bd31580a | note | Contractor - I
d39c7761-46a4-443d-abeb-0bd353d33772 | signoff | AUTHORITY HOLDPOINT
c391065e-4f78-41c0-864c-8b99d4a290e9 | checkpoint | 1.08 - Optimisation of Stabilising Agent(s)
bb19fcf3-7a58-5b7c-be8c-1f0391d76928 | note | Detail of Activity / Test - Indirect Tensile Strength, ITS
b93e4e71-8c38-5195-92e9-05a1ad566cb0 | note | Action (Hold, Monitor, Witness) - H
3ec32c82-bb17-5c17-ad88-77a24cc00e33 | note | Minimum Test Frequency - 1 Optimisation test per aggregate type
983e5d12-e0ff-59cc-bc56-3a96aadb7d12 | note | Inspection / Test method - NZTA T/19: 2020
ca93ae43-5dc5-5649-81fb-d5ccdc7160b0 | note | Acceptance Criteria - Testing at 1mm/min:
535bf00b-6a2a-5bdb-b259-5ed95f2b452c | note | ○ BSM Dry ITS: 175 kPa to 400 kPa
643d1790-5774-50b0-a972-bdb29934821b | note | ○ BSM Soaked ITS: 150 kPa to 350 kPa
258ab4eb-c4b9-55d2-a525-73b5f6c197bb | note | Testing at 50.8mm/min:
b22f999c-4520-5836-8fad-dfca452d6091 | note | ○ BSM Dry ITS: 210 kPa to 480 kPa
14651ab0-5a91-5663-938c-ac2c23d9624e | note | ○ BSM Soaked ITS: 180 kPa to 450 kPa
c696d72f-482d-57ec-b3cf-7414e2817846 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
7b4894b5-3d69-53ae-a467-ac2b394b8c41 | note | Responsibility - Designer
9728557a-d20c-5389-a431-079e57bf412a | note | Project Specific Notes / Instructions - Designer to advise on binder content(s)
0da38a93-4524-5a98-9c6e-7966fc886cab | note | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
90d9049a-2307-5337-86e5-a9e2354b2c29 | note | Designer - R
445a7ccb-a346-5fa0-a0c5-dbc4277a0c10 | note | Eng. Rep - A
591d0e8c-958c-5905-90cc-f43fed82327e | note | Contractor - I
38ceff28-74cd-46b0-ac85-5f4c4248aaa8 | signoff | AUTHORITY HOLDPOINT
7a14ab84-a5b9-43de-8cbc-83839817af9d | checkpoint | 1.09 - Optimisation of Stabilising Agent(s)
9695242e-c04d-5bc6-97ae-6ac776d174bd | note | Detail of Activity / Test - Unconfined Compressive Strength, UCS
1e734099-dab6-5bfb-b281-09c3244da8f4 | note | Action (Hold, Monitor, Witness) - H
e7bcd50e-19f6-58fc-8d1c-348fd82ca334 | note | Minimum Test Frequency - 1 Optimisation test per aggregate type
ef3df4cc-6cd5-51d9-b6b4-3c969895790a | note | Inspection / Test method - CCNZ / NPTG / CETANZ Industry Guide
fdbf3878-7cf4-55c3-b9f7-6d4851ba3fd7 | note | Acceptance Criteria - UCS limits set by the design engineeer
27edb2ad-3015-58fd-ace5-409c3a46f7b5 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
cb2898bb-56e1-502c-80e8-3f43dd02f446 | note | Responsibility - Designer
40e13313-1e73-5975-b1ea-665b64a14b48 | note | Project Specific Notes / Instructions - Designer to advise on binder content(s)
29c797e0-512f-5c80-adc3-8b6734020f84 | note | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
6a9f90d0-9a92-5646-88a9-45de72629494 | note | Designer - R
6608c6eb-aefe-5ab3-92cd-3fd25899b4e7 | note | Eng. Rep - A
1e2a3138-c886-5af0-a2d9-46e6d1051d3f | note | Contractor - I
33b1cbe8-343c-4634-af95-3e1634bcc56f | signoff | AUTHORITY HOLDPOINT
b6fede76-0840-4249-b91f-dd2f59a9df72 | checkpoint | 1.10 - Optimisation of Stabilising Agent(s)
5a14aa38-1e3c-593f-9a29-5fd6e35fb722 | note | Detail of Activity / Test - Modified Maximum Dry Density
6e2d31b9-89d9-588d-b254-751293c2720e | note | Action (Hold, Monitor, Witness) - H
eb86512e-1658-530e-af44-9eb54183ab8f | note | Minimum Test Frequency - Single Point DD vs WC during optimisation test
05474044-72cd-5522-8146-6569c2234b4e | note | Inspection / Test method - NZS 4402.4.1.3
1204e4f2-4c05-5eff-9823-7dd571040798 | note | Acceptance Criteria - To determine target density
0481dd19-f8ce-501e-bd5a-884e2355664c | note | Record documents (QCP - Quality Control Portal) - IANZ Report
5a27fcb9-7c28-56e7-be74-373d1cf167e3 | note | Responsibility - Designer
683a96d8-31f0-5bee-bde9-15148dd598c5 | note | Project Specific Notes / Instructions - Required before Stabilisation comences
2e939b88-49b5-52df-9776-d4f50e08accb | note | Designer - R
03bd13ce-9189-5b33-b4d2-8e21326aa921 | note | Eng. Rep - A
0efeee38-e0d6-53e0-bd32-e2be8f1bfe1e | note | Contractor - I
0beae8b4-8a9c-4873-8064-0813302a4138 | signoff | AUTHORITY HOLDPOINT
86630885-2f1d-495c-95ef-28622a492c3a | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
68d9a070-de49-5a87-9491-11860f3a299e | textbox | Contractor's Rep Name:
492b4316-947d-5189-93b6-712427c06cd0 | textbox | Engineer's Rep. Name:
ce25f072-a0bd-520c-8fc2-df7ed2a27df6 | date | Date:
99a62c46-5f8b-4663-a3a5-0247bbef24e7 | signoff | Add Signature
a8f1c727-5578-4ac3-b0c0-d3f260414126 | checklist | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Post Construction Rev B | itp | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Post Construction
6e8df426-08fe-49ba-954b-a3c62119c477 | section | 4.0. Testing and Sgnoff
1d2a75d5-95c4-4aee-80e4-17dca4fdcec9 | checkpoint | 4.01 - Finished Pavement
3ce31e48-58e7-5b2c-bace-005aca6d3dc1 | note | Detail of Activity / Test - Crossfall
f2b1f50e-d1ac-5d49-87e7-b5237fb54656 | note | Action (Hold, Monitor, Witness) - H
13fe3972-c2dd-5f8d-930f-da2b76765fc9 | note | Minimum Test Frequency - every 20m
bf4e20ec-ad87-5561-9499-75581cb1f36b | note | Inspection / Test method - Measurement
739d749f-d64e-5c1c-9657-3a1efe355880 | note | Acceptance Criteria - ± 0.5% of specified crossfall measure
039bdeb1-8bb8-5cb5-8f75-de8e2b9c70ba | note | ○ 2m apart
89b6da4e-4cef-5730-8d9b-36d95e775ff8 | note | Record documents (QCP - Quality Control Portal) - Survey
390cf557-dac1-5c03-8186-af2ba19eda4a | note | Responsibility - Stabilising Contractor
74f930b4-1619-542d-912b-3c71ca58b71b | note | Designer -
cdc3a208-df1c-57b9-aef6-cf6e244f6541 | note | Eng. Rep - A
5437b68e-35de-55b8-baf2-f3cffd4f175a | note | Contractor - R
abd5e623-130f-4441-9606-1de3d9990525 | signoff | AUTHORITY HOLDPOINT
8456f9c0-ac4d-4e4f-8d3f-0997d804688c | checkpoint | 4.02 - Finished Pavement
ff951fb2-4547-5d92-9ad1-01e21449fb32 | note | Detail of Activity / Test - Stabilised width
6ded0675-aa7a-5623-ae75-537d654d50c3 | note | Action (Hold, Monitor, Witness) - H
56d41611-a303-5738-9b14-5bce2f693d62 | note | Minimum Test Frequency - 1 every 20m
2ef1df87-abd0-5d9f-98d4-8e5bfb79b680 | note | Inspection / Test method - Measurement
240a8c1c-ce77-534e-a5a2-e242e12e3abf | note | Acceptance Criteria - -20mm, +100mm
26194227-5eef-5dba-a1a5-2450a31ad213 | note | Record documents (QCP - Quality Control Portal) - Survey
4d25217c-d5b9-5dec-a4f7-b61f2571ffa6 | note | Responsibility - Stabilising Contractor
1439b29d-5121-5b02-8673-215d645ec8ab | note | Designer -
2b2ebde6-7cf4-55b6-87fc-0ade79d73e53 | note | Eng. Rep - A
451f355f-20ef-585a-a6e1-a7816fdff9fe | note | Contractor - R
3d4bc6a8-4a5c-4034-b9a2-f23d70174ec0 | signoff | AUTHORITY HOLDPOINT
452b8196-b750-408b-b740-dd59ce69e96e | checkpoint | 4.03 - Finished Pavement
46ea3332-5a95-5fd2-afb2-995c1e82a1d8 | note | Detail of Activity / Test - Surface Shape
f94281e7-96f5-5c66-b6e0-780af14347ac | note | Action (Hold, Monitor, Witness) - H
b5ca814e-6090-5b1d-9783-449b0b209e6a | note | Minimum Test Frequency - every 20m
e11ae886-82b8-511c-8f79-5e13e3c2cf35 | note | Inspection / Test method - Measurement
1168e5f3-eb06-5b62-83e2-c687ac198884 | note | Acceptance Criteria - < 10mm using 3m straight edge
72f26be9-e85f-5f8e-93c9-f84bd3c1392b | note | Record documents (QCP - Quality Control Portal) - Survey
d14fdfa2-d084-5a84-b4e5-12e7060b9ea8 | note | Responsibility - Stabilising Contractor
832ad969-aff5-570f-9525-ef082b121542 | note | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
b5ccdd50-3b5d-5823-99f7-fa19cac17eb2 | note | Designer -
c8e2d2fe-0693-5569-9954-67a1e39bc5eb | note | Eng. Rep - A
b29996b4-7f90-56aa-bd6b-764a82569ffc | note | Contractor - R
0bdf281d-e052-41ea-9a4a-5724df90c819 | signoff | AUTHORITY HOLDPOINT
6a75b2f2-3821-4c9d-ae64-b12dafe8a5d5 | checkpoint | 4.04 - Finished Pavement
eda98795-047b-5323-a455-3c28fb8a2a0c | note | Detail of Activity / Test - Surface Levels
a5637b1e-c300-5479-ad99-79b5858ae629 | note | Action (Hold, Monitor, Witness) - H
4ced63b6-d415-5df9-b529-0b8c4fe8da4c | note | Minimum Test Frequency - every 20m
d7238d88-0608-5854-9598-de77f575916f | note | Inspection / Test method - Measurement
20687d3d-a9ac-56f4-8027-0826d0c020f6 | note | Acceptance Criteria - -5mm, +15mm
25813049-98b7-594d-8a7c-25b55b6e5e8a | note | Record documents (QCP - Quality Control Portal) - Survey
41192371-8db9-59e9-92bf-6e093dd0fbd1 | note | Responsibility - Stabilising Contractor
7f91271a-4458-5d9f-be5b-605305a84968 | note | Designer -
14eef2db-49a3-5935-9c62-0689b8d75aac | note | Eng. Rep - A
28901b2c-0132-5337-8565-be47ad58ddf6 | note | Contractor - R
ee5f4b25-de31-460d-a0da-c89d7e34a6af | signoff | AUTHORITY HOLDPOINT
731b284d-948a-44ef-910e-94c2bb398928 | checkpoint | 4.05 - Finished Pavement
218319bf-130a-5464-b9fb-df80c1108ce8 | note | Detail of Activity / Test - Surface Finish
ae5dd566-9b64-52af-ac6b-e956e62a0a4d | note | Action (Hold, Monitor, Witness) - H
7e57a6ba-709e-54ab-bc9e-75d22cf05efd | note | Minimum Test Frequency - Per Lot
20e122a2-6d37-548c-86b2-617957b415f5 | note | Inspection / Test method - Visual
5112ad36-6250-5763-a132-66cdcee168ec | note | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate
3ad31a0c-1246-5263-beb9-840f74564d5e | note | 2. Smaller aggregate held in place by fine material
17b4d8d3-414b-55c2-b552-e3fb813e20be | note | 3. matrix does not displace under normal trafficking and/or sweeping
dcf516cc-f80a-5a1e-ab35-28e069362c9d | note | Record documents (QCP - Quality Control Portal) - Survey
7fa1cec3-62b1-56af-bef6-335996f2ac25 | note | Responsibility - Stabilising Contractor
48743bf1-60a4-5493-8004-388bdc59f98f | note | Project Specific Notes / Instructions - ER to be present at pre-seal inspection
fb16f045-9c6a-55a9-bf0a-79d115d894f2 | note | Designer -
1d43da0b-a4b2-51d0-87ea-8468074b5c6e | note | Eng. Rep - A
cea52502-1327-59fc-a9eb-197edcf72db0 | note | Contractor - R
6f29a733-3cbb-49fc-beb9-c871b453f500 | signoff | AUTHORITY HOLDPOINT
f4e27aca-191b-4f09-84c2-8479bbe1acf2 | checkpoint | 4.06 - Finished Pavement
fc0996ae-454f-5973-81a1-9b28e93c3806 | note | Detail of Activity / Test - Roughness
303480d6-844c-54a7-96e2-01c3704a1b29 | note | Action (Hold, Monitor, Witness) - H
8cdacb59-4f97-5702-96ce-2e009c5f0b41 | note | Minimum Test Frequency - Before Sealing
d0da6633-2dbe-59d7-81b0-6d7683741ae4 | note | Inspection / Test method - TNZ TM 7003 v1
b3ddb200-29ce-504a-8fe3-d404804842ca | note | Acceptance Criteria - 100m rolling average ≤ 75 counts/km
501a82bf-7955-5c8c-80e2-937dec741884 | note | Record documents (QCP - Quality Control Portal) - Test Certificate
32b7e25c-86d4-509c-a453-3ab560f0c144 | note | Responsibility - Contractor
894cc346-5857-55e2-bf96-8d9ee371040e | note | Designer -
42efd9f2-ad5a-56d2-92b2-4f53112453b5 | note | Eng. Rep - A
80e7efd9-60c1-5b5f-8a13-a2638921ff0a | note | Contractor - R
0488aacb-f83f-4c12-ad6d-7f4dd831c223 | signoff | AUTHORITY HOLDPOINT
ddeca87d-c438-4174-88ff-83c0b4050d6d | checkpoint | 4.07 - Pavement Layer Signoff
7ab5fb5f-0bf2-5e28-86f1-5017ed70c427 | note | Detail of Activity / Test - Assessment of all test results for conformity
f5b0d073-574d-5716-a951-5068a229bf83 | note | Action (Hold, Monitor, Witness) - H
9b74750c-0cee-5ce4-ac0e-f5029fff838f | note | Minimum Test Frequency - Each Lot
5a2edc09-bae7-53a2-bf66-843b12c39087 | note | Inspection / Test method - Site Inspection
d5831d43-1cbc-56d9-b984-e055dc5af889 | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
06315187-678d-5ffb-b69c-1bb91330dfe6 | note | Record documents (QCP - Quality Control Portal) - NCR
c856adad-6522-511c-b919-408250d7d936 | note | Responsibility - Engineers Representative
c1e2239a-6399-5654-97c8-e371e2e704c8 | note | Designer -
c985a5f1-c4a2-5644-af60-16d161cb4b8c | note | Eng. Rep -
1e8f40fe-e33e-4a78-a2b6-526e20206c8d | signoff | AUTHORITY HOLDPOINT
7f2be5cd-becd-43b2-8b50-d5ce8e8517a9 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
18a151c2-4659-528e-a3fa-1ab4bad0f4d8 | textbox | Contractor's Rep Name:
d473aec9-c2e7-5014-b297-3c0433c9abbc | textbox | Engineer's Rep. Name:
36dbf01b-1f3a-538f-94ee-2cd6790c1756 | date | Date:
28d89cf0-055a-41aa-960f-17cae2f0c84f | signoff | Add Signature
ce4be921-9c9e-4b5b-a732-3dff9559a423 | checklist | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Pre Construction Works Rev B | itp | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Pre Construction Works
f3dd1379-8985-4d82-a25d-3cb52bdf7f1b | section | 2.0. BEFORE BITUMEN STABILISATION STARTS
c6c9d99a-f167-4951-b0fa-69fb6b2c15f8 | checkpoint | 2.01 - Setout section
b46f278c-a9e1-5306-9700-7430cd82c3dc | note | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
6ab1316c-191d-599f-ad30-11f0d650e2c6 | note | ○ Refer to Project Specific Notes
87b87c83-34c0-5925-a02b-2bd32c81accc | note | Action (Hold, Monitor, Witness) - H
facc8a32-ccf5-56c0-bd28-e1b063ba0699 | note | Minimum Test Frequency - Prior to each section
048d3b6c-9c64-55e9-bca2-8bc0ec32c1fb | note | Inspection / Test method - Survey
ed9e4512-b5fa-5db8-a255-eff580402a9a | note | Acceptance Criteria - Document existing furniture
065a52d5-e2a6-587e-946b-44b014eae5cc | note | Record documents (QCP - Quality Control Portal) - Electronic survey files
5ff814d4-5e6e-5576-8f63-a9d21220d20b | note | Responsibility - Contractor & Stabilising Contractor
5481d321-bb3b-5bc6-9d71-5bd8a747017e | note | Project Specific Notes / Instructions - Note that the two transition ends of the site will require a digout as per the digout table on DWG#T2W-802-007.
9a49e666-03fe-57b9-81ec-b620cacbf7cc | note | ○ Extent of these as follows:
ab939834-1100-54b2-b361-f580ef88c20b | note | – RP 4235 to RP 4270
1b130a86-13c4-505b-9d3f-01704f01a809 | note | – RP 7580 to RP 7640
f49ddc80-6fe4-5630-830c-e4d6aaa4dcd7 | note | Designer -
cf479ea1-bbf4-5c13-82fe-d1e1cbea8d22 | note | Eng. Rep -
e2929d87-160d-5f22-b85e-ec92344a6f2e | note | Contractor - R
8863bb1e-7d4a-4a0a-ac11-4f7de31bea58 | signoff | AUTHORITY HOLDPOINT
8f2e8b07-8e75-428e-9fa4-3d3b69fb8f50 | checkpoint | 2.02 - Pre-hoe entire area, then shape and proof roll
7d7acc1a-b099-5aa7-b844-470439ea2a4d | note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site specific methodology statement and/or IFC drawings and proof roll while compacting
7e6e2425-f813-528c-8fd8-f11ac6996228 | note | Action (Hold, Monitor, Witness) - H
786b8772-bdba-5b40-bee8-1a73fe848c0e | note | Minimum Test Frequency - Prior to stabilisation per section
05565e9f-5eee-5c47-ab6b-de8816d510f0 | note | Inspection / Test method - Use grader's machine control and inspect shape
bde7c822-b52f-5e66-a090-f6383c27bbac | note | Record documents (QCP - Quality Control Portal) - N/A
c3cd00ab-e779-5e7c-a9c7-ef7f973fa47b | note | Responsibility - Stabilising Contractor
631b1bbb-d2fa-5b29-9741-d31fd814949b | note | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
e7c62076-398a-5b44-adf1-78f15b6c33dd | note | Designer -
b0afb73e-d1e4-57a4-8edd-ec8c5e0fec90 | note | Eng. Rep -
7a058c9d-34a4-550e-af12-25873dcf0b75 | note | Contractor - R
d2b8fd16-9abb-459c-bac7-d66ea70160e5 | signoff | AUTHORITY HOLDPOINT
0f2d1761-6d10-40ad-812c-8e6a75471b27 | checkpoint | 2.03 - Pre-hoe entire area, then shape and proof roll
ebe4d82e-9685-5f7e-ab4d-62e2df2e59bf | note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site specific methodology statement and/or IFC drawings and proof roll while compacting
ea092708-95a0-5112-8261-dc55fbd9982a | note | Action (Hold, Monitor, Witness) - H
fface762-fb02-5135-885d-462bff4612f5 | note | Minimum Test Frequency - Prior to stabilisation per section
03332862-9735-5e2d-933e-0ab19e643238 | note | Inspection / Test method - Visual check or Vibratory Roller's response meter
8359458e-e76e-5a6b-a8a9-fde630f3e863 | note | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
71b8d945-a3b2-52e6-a31d-d5b06a534687 | note | Responsibility - Stabilising Contractor
fa4a8b9b-ac03-59a7-b83d-7668f718d094 | note | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
a9834c08-88a2-502f-836a-8be9de224b21 | note | Designer -
b29d1a1a-28f5-563b-9505-7ab04dca2c74 | note | Eng. Rep -
b55fc3c7-7cd4-5020-835e-e6a17bc9424e | note | Contractor - R
05c76662-008b-4369-942a-e7ec24811023 | signoff | AUTHORITY HOLDPOINT
113ce325-3bac-4079-9fa1-9f39065fcc4f | checkpoint | 2.04 - Spreading of Cement (for modified subbase) (2.24t/m3 x 0.19m x 1.5% = 6.4 kg/m2)
13b1dab9-0586-5bc5-a4f2-7582d6473e12 | note | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
4b8941d5-516d-5ae1-888f-bc6613f28cba | note | Action (Hold, Monitor, Witness) - M
acee1b95-209c-53df-99e6-55b6f7e34cb5 | note | Minimum Test Frequency - every 400 m2
c40ddf3d-cf8d-5880-86fc-3b6c569f42e0 | note | ○ every 150m for a 2.4m width
cff3201e-c124-5cb2-8824-897e065f6749 | note | Inspection / Test method - Weigh mat or tray
a2acc0eb-3d4a-5efc-b137-30ef54b1e9e5 | note | Acceptance Criteria - ± 0.5kg/m2 of specified rate
74272e0b-65e5-51cd-9ab4-42c3929562c8 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
223d8b1a-21c0-58d8-b70e-2764230637df | note | Responsibility - Stabilising Contractor
1e5256fd-1e3a-5de7-9134-7ea6b59fe3c4 | note | Designer -
c5603a88-fad8-54b2-8967-cc9f57ded180 | note | Eng. Rep -
61d5b77c-7915-54d5-8adc-e889d34bc343 | note | Contractor - R
9ae6f34e-e8fa-44b7-bfd9-fb9a50b40a4a | checkpoint | 2.05 - Spreading of Cement (for modified subbase) (2.24t/m3 x 0.19m x 1.5% = 6.4 kg/m2)
e4b1692c-4541-58ab-8729-55c4d318a910 | note | Detail of Activity / Test - Compare area spread with weight used for each spreader load
b6841006-535f-53b0-af27-2191efcc30b8 | note | Action (Hold, Monitor, Witness) - M
43b46e56-652f-5f2f-95b5-64c23f69e573 | note | Minimum Test Frequency - On-going measurement by computer/load cells
12bedbf4-93ec-57ad-9e9a-04d05757c209 | note | Inspection / Test method - Measurement each run
1bbc2c20-2edd-5bf8-985c-076e1e6ae67f | note | Acceptance Criteria - ± 2.5% of specified rate
6a5d2749-d203-5c2b-9810-97b48c08b725 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
c371f619-e57b-549e-b89a-f8b7e06afa17 | note | Responsibility - Stabilising Contractor
e6f33726-d4a7-5319-926f-1f64f9e96185 | note | Designer -
bf622fab-a808-5465-ad93-57ee75b60b62 | note | Eng. Rep -
b9bf540f-1fa1-5665-9579-bf5d525b7b85 | note | Contractor - R
62fb1d05-92bc-4710-82f0-983943dc2993 | checkpoint | 2.06 - Compaction of Modified Subbase
a2a44c98-af9b-5094-a88b-d1f6334ccbec | note | Detail of Activity / Test - Plateau Density Test
e6bf2408-9a78-54e2-b81b-35a4f320be69 | note | Action (Hold, Monitor, Witness) - H
21160d3b-97a7-5c86-8b6a-a95d623f880b | note | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
fc2b8548-8d0d-5c2e-ba23-e9738ad17418 | note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
4b5ba1ae-41a9-5ae8-a6c2-5a950b4891e3 | note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve MDD
a3782973-52d8-5122-8592-7f2fd0e2d6c1 | note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed
3072d352-ae16-5475-9919-8c60af5e2f69 | note | Responsibility - Stabilising Contractor
563416f6-266c-51f2-bb3b-55799ea780cd | note | Project Specific Notes / Instructions - If MDD can't be achieved then the PDT- MDD must be approved by the ER
0b255778-5c98-5b27-92c7-3e99814b0b17 | note | Designer - I
f250bccd-4039-55ff-b865-fcbc71dff30e | note | Eng. Rep - A
5823cf83-5af8-54c7-abba-9418dd716a00 | note | Contractor - R
9bbae5dc-198e-42ea-906e-468f9468441b | signoff | AUTHORITY HOLDPOINT
ed7235d2-2dbe-4456-98f9-2505c29ee5c0 | checkpoint | 2.07 - Compaction of Modified Subbase
1c0c468d-b947-567f-aebf-2e4bc2808faf | note | Detail of Activity / Test - Maximum Dry Density
b658f163-8ac0-5942-89cc-0a00cb838eef | note | Action (Hold, Monitor, Witness) - M
2caae0da-e8de-5ab8-b1c7-f9fe47f13d90 | note | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
cc665a8b-2526-5d4b-8112-14f6ea40feee | note | Inspection / Test method - NZS 4402.4.1.3
5ac168c3-9e39-5007-9e89-ea779371c8fb | note | Acceptance Criteria - For analysis of DoC
efe5baad-3b8e-55ba-8e49-d6478dc81996 | note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
5e1b7cc0-da7b-5436-91bf-180126789bbb | note | Record documents (QCP - Quality Control Portal) - IANZ Report
2a6da78d-c7d2-5a00-a65f-e1afa054dee9 | note | Responsibility - Stabilising Contractor
a4e2dd09-08ea-50e0-8545-e39772b994c3 | note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
8c2d27a2-1d41-53c5-a104-0dcb5edbf871 | note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
471724cb-fcbc-5885-ab37-971c688443bf | note | Designer - I
11e6fbb7-d74f-5969-86c3-882ed18116dd | note | Eng. Rep - A
44b79c6f-b225-5aa9-bd7d-9a9a4b20441f | note | Contractor - R
63230614-2875-4708-9ddf-4afea5c1bb33 | checkpoint | 2.08 - Compaction of Modified Subbase
33e3c47c-cd0a-5b47-b982-5af11a6c4450 | note | Detail of Activity / Test - Degree of Compaction (DoC)
27cb0274-dd49-5c30-892b-6882f47f5f94 | note | Action (Hold, Monitor, Witness) - H
24b0fbc2-c8bc-5cea-8e0e-da319ead285d | note | Minimum Test Frequency - 5 per 1,000m2
6a14046a-6a3a-507d-a65c-f9b571adac3e | note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
e2048e79-d711-53a2-9be3-860b3077214c | note | Acceptance Criteria - Average DoC ≥ 95%
e73ddf53-136b-5c89-aadb-dc2631e70121 | note | ○ Minimum DoC ≥ 92%
8ca6bc7f-d10f-5c48-818e-a04edc076bd5 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
a62578bf-0030-5828-8758-ff04e5858c1b | note | Responsibility - Stabilising Contractor
2f1a3933-9d7e-56ae-b361-d41f4f84a0de | note | Designer - I
261942ae-a1cf-5215-94f8-fb94fc1c4951 | note | Eng. Rep - A
4c2f4c2c-9103-5575-b8dc-56c0070690e2 | note | Contractor - R
2e8d91a6-93b1-492c-b107-3b7dfb6cbeae | signoff | AUTHORITY HOLDPOINT
44ef52d9-4693-4fbe-8005-e5201b282418 | checkpoint | 2.09 - Overlay and check levels
52190e47-36c2-5cd7-ac0f-efee7c1a9a3f | note | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
aa41dda7-435d-5570-a32b-8bd6015c24de | note | Action (Hold, Monitor, Witness) - H
38f507a3-532f-5cc1-84e6-01359cc40b84 | note | Minimum Test Frequency - Prior to stabilisation per section
c61f21fc-ed29-5bdf-853b-2b9a156ce169 | note | Inspection / Test method - Survey
70a6cbc8-0160-5cb4-9824-9c795011ab27 | note | Acceptance Criteria - Subbase + 15 / - 5
fe0d4f03-faaf-533f-b3c7-38cb0cd78dfc | note | Record documents (QCP - Quality Control Portal) - Surveyor
9b48ed11-bc85-58c6-8480-df26ba511c1a | note | Responsibility - Stabilising Contractor with Main Contractor
dfc7ca59-aba0-521c-91e2-087d34620690 | note | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to):
0d9b7b72-bfa4-5721-853b-c7a79e72f99d | note | – overlay aggregate quality / consistency
f91945e2-1120-5863-b5a6-efbb8a57bc8c | note | – moisture content
353a277b-fc96-5165-94a3-17917b1d923a | note | – any concerns with shape and tie in
fc3bc6d6-2216-5d41-967a-b5f71596838a | note | – etc.
e359d6f0-817c-587a-978c-721a9f5b4306 | note | Designer - I
a51b6c84-d437-5ec7-bbcb-54b2c7e6dc6f | note | Eng. Rep - A
3c87b6ab-650a-5f8c-84d5-ab6786a325de | note | Contractor - R
e70c558e-84e9-4120-a58f-9bd1c17e0b2e | signoff | AUTHORITY HOLDPOINT
2095555d-3e71-4374-8260-22157291fc02 | checkpoint | 2.10 - Production Plan
a8a3cadf-7fb2-5fb5-8c36-1b7b51d3f8a1 | note | Detail of Activity / Test - Plan showing cut lines and sequencing of works
642c7731-6073-5079-9b2e-b644e0f6aa36 | note | Action (Hold, Monitor, Witness) - M
78aea5ae-bde5-5c04-ae90-01c20c7ba212 | note | Minimum Test Frequency - Prior to each section
5d81bb95-12df-5741-9cb0-e573e0b45db2 | note | Inspection / Test method - Daily Report
535c3dbd-6b58-5a33-8ddb-8f84e7d57fc1 | note | Acceptance Criteria - Points covered in NZTA B/5
db6d4102-fdaa-55a6-9f00-254158910daa | note | Record documents (QCP - Quality Control Portal) - Daily Production Plan
50a87352-b899-5af6-8edf-b63b175bca41 | note | Responsibility - Stabilising Contractor
0f981757-1c18-5349-86fe-960e599eacdb | note | Designer - I
1d621fa4-26a4-5e40-97ad-4075dfe41328 | note | Eng. Rep - A
6d389af8-ceb0-5278-a58f-dd5217ad813d | note | Contractor - R
f2712b7e-dd87-4dbc-87b0-be10ee3e31cf | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
ebaf65a2-8200-5429-a223-ef6b3e1f0da4 | textbox | Contractor's Rep Name:
2a951d92-9de0-5513-803c-10253696541a | textbox | Engineer's Rep. Name:
6f030bc0-59a5-553e-98b1-5b96d7e4a201 | date | Date:
789fa673-c517-4011-8d78-78bca859f72b | signoff | Add Signature
bcb41f72-6cd8-41ae-a1b5-92325b6e642d | checklist | ITP - Guardrail Lift Existing Rev 0 | itp | ITP - Guardrail Lift Existing
08b7cae3-84c6-485d-9243-6999f25ea6ad | section | 1.0. GUARDRAIL HARDWARE ACCEPTANCE
9b01a8ea-8f47-4da6-98bc-723c4a9a2b16 | checkpoint | 1.01 - Guardrail Hardware
4c15d983-2e53-5a81-a342-b0393d3ab3d2 | note | Detail of Activity / Test - Compliant with Standards
402aa324-7aa9-5ab8-b402-0614b26bbc75 | note | Action (Hold, Monitor, Witness) - H
a77cc545-f1a6-51a9-ac1b-23a4c4f939b5 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
a271736e-fe42-523a-adc2-c8b7d6cc82bf | note | Inspection / Test method - Visual / Photo
66c5920f-5f17-53e4-b4d4-a96718fc263e | note | Acceptance Criteria - AS/NZS3845
511ce22f-5f1f-5500-8c3a-b680baef4dbc | note | Record documents (QCP - Quality Control Portal) - Data Sheet
b5ae60b8-711f-5e44-91a3-47849030c1b4 | note | Responsibility - Contractor
068a71b3-48b7-504f-918f-ca3280f20a84 | note | Site Engineer - A
3c300144-6415-5d39-b970-b987e2c919d9 | note | Eng. Rep / NZTA - I
c9a76db9-fdd8-5faf-804e-6bb2df0ffa4e | note | Contractor - R
470f162e-8fe4-477b-98aa-52b6096f7077 | signoff | AUTHORITY HOLDPOINT
a91fa2e1-a89f-4cbe-a0d7-ccedcd572cef | checkpoint | 1.02 - Guardrail Hardware
cd7c88a4-920d-570e-b8cd-16840e9e77ac | note | Detail of Activity / Test - MASH Tested
3c04bdf9-ed10-578f-8714-e45831e819e6 | note | Action (Hold, Monitor, Witness) - H
b2b0cd5c-e6a8-56be-9277-147dfecd29f9 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
5c3a4d99-be3e-5ca5-9ea8-f50cf8c141ed | note | Inspection / Test method - Visual / Photo
c8921760-b337-55eb-9d5f-adf036ec2caf | note | Acceptance Criteria - AS/NZS3845
c64903f1-624a-53e9-97cd-4393a37715ef | note | Record documents (QCP - Quality Control Portal) - Data Sheet
2e018b2a-e763-5ef4-8bde-b51b9413d3a0 | note | Responsibility - Contractor
75a75afc-0794-52a7-9e66-b46e514bd0c4 | note | Site Engineer - A
38d747e1-b52f-57a9-a1b9-232404fd604a | note | Eng. Rep / NZTA - I
539741d8-3ae9-52e6-b576-c4135dddd92b | note | Contractor - R
09d5d05f-73eb-4e1a-9445-cdd6d6af3a12 | signoff | AUTHORITY HOLDPOINT
148d8273-c5bb-4b5c-a0da-751eacee69ab | checkpoint | 1.03 - Labelling
b1788a75-6dca-5f5f-bc40-e7b9e2683f88 | note | Detail of Activity / Test - All components labelled with AS/NZS3845
a9d1e287-a383-589e-9932-7b933d3eb347 | note | Action (Hold, Monitor, Witness) - H
7c6aa273-09aa-50df-be2c-8ba5a58b3432 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
083bce5b-8170-5afb-b8c9-8a681b491b39 | note | Inspection / Test method - Visual / Photo
18a04a1a-2b22-565d-b2cd-54afedef3836 | note | Acceptance Criteria - AS/NZS3845
fa24a46e-82f8-585b-99c8-6785c43411ac | note | Record documents (QCP - Quality Control Portal) - Data Sheet
333c355c-e693-578a-93fc-6d83fa02da6e | note | Responsibility - Contractor
3c6bb802-1700-5a4e-b357-cd2c33c9fd05 | note | Site Engineer - A
0aba9598-b431-54d1-89eb-03543de2a42b | note | Eng. Rep / NZTA - I
dffc8cec-834e-512b-951b-2437ae1ed0d3 | note | Contractor - R
78ba5ad7-1abb-4c80-b064-21f529609031 | signoff | AUTHORITY HOLDPOINT
c2174f06-bf8c-4f85-9fbe-ffcdc29ab088 | section | 2.0. CONSTRUCTION
e83a25a2-9187-4306-aaf3-e4526332084f | checkpoint | 2.01 - Remove Splice Bolts
02d33b54-a74b-5708-a6af-9abd0e1dfa43 | note | Detail of Activity / Test - Unbolt M16x32 Splice Bolts at splice joint eaither end of the W-Beam rail
b9be46e7-fccf-5585-94f6-ac808ae1212c | note | Action (Hold, Monitor, Witness) - M
2746936a-0961-5aa2-affe-f10b8e0e44f5 | note | Minimum Test Frequency (Lot = 1 day’s production) - All Splice BoltsBolts
9576adf4-1b8e-5d66-bbdb-e3a9ee4378b3 | note | Inspection / Test method - Visual / Photo
067a7cf9-7b6c-5876-a5d8-85bcde71481f | note | Acceptance Criteria - Site Engineers Approval
e488c3f6-b51f-5e90-ba8d-09a75e534d74 | note | Record documents (QCP - Quality Control Portal) - Checksheet
0631f5b4-c20d-588b-acda-b330fb554e70 | note | Responsibility - Contractor
dbf7ba18-8a0c-5a2c-bae5-833e4571a5a5 | note | Site Engineer - A
2794b0b2-3f92-5859-a684-f34db9befe94 | note | Eng. Rep / NZTA - I
b14fe45b-8d3b-5028-beb1-6b8395d7a881 | note | Contractor - R
d28cf51f-2932-4949-aa3f-0299d41fb28b | checkpoint | 2.02 - Remove Carriage Bolts
740b8d58-ca37-5cae-a880-076ff4277548 | note | Detail of Activity / Test - Unbolt each carriage bolt on W-Beam rail.
91f23079-fd18-52a8-8b2f-1fbb9d67f3c3 | note | Action (Hold, Monitor, Witness) - M
79e3d8bf-d101-5c3a-a8cc-8e7b5787c395 | note | Minimum Test Frequency (Lot = 1 day’s production) - All Carriage Bolts
fd2e30b2-ad4d-5c9e-b60a-02b20f7cd748 | note | Inspection / Test method - Visual / Photo
a96fc6ac-3093-5679-ad34-a331ea0dbaf8 | note | Acceptance Criteria - Site Engineers Approval
5a97e06f-1560-59ae-adab-6593119e0403 | note | Record documents (QCP - Quality Control Portal) - Checksheet
8ac01d84-ecc4-5924-b3bb-757087ca69b4 | note | Responsibility - Contractor
53c64276-c371-5816-aaa1-80718fce2958 | note | Site Engineer - A
2aac06c9-4e7d-53f7-b109-5dab55bf9a32 | note | Eng. Rep / NZTA - I
af8e5bab-f582-5381-a559-1e238631bc3f | note | Contractor - R
c98406c3-3fe5-49c2-95af-1a8363f99f93 | checkpoint | 2.03 - Replace Carriage
d0fff893-4e9a-5991-aa7e-10e4bc23b592 | note | Detail of Activity / Test - Remove existing Carriage form Post and replace with Ezy-Lift Carriage
013277a2-39e8-56f2-8800-af2239ace420 | note | Action (Hold, Monitor, Witness) - M
eff76848-5138-5751-998a-0bda18bef737 | note | Minimum Test Frequency (Lot = 1 day’s production) - All Carriages
b6e7ea67-6cfb-5f45-a8db-b025b115989d | note | Inspection / Test method - Visual / Photo
3bddaa16-6c8b-5e39-857a-a99acbfd0027 | note | Acceptance Criteria - Site Engineers Approval
cd54005e-a0ae-5516-829e-4e2768276b04 | note | Record documents (QCP - Quality Control Portal) - Checksheet
770efe51-789e-53a7-a303-930d115d0bc7 | note | Responsibility - Contractor
26330b0c-a29f-58eb-8005-565a5a25f7be | note | Site Engineer - A
ea04caeb-1cb9-5de9-85ec-6c5b232d9cd7 | note | Eng. Rep / NZTA - I
458858b6-5a10-51a3-890d-59ca5881421d | note | Contractor - R
f8dcdb99-577a-427e-8a02-48559b4de990 | checkpoint | 2.04 - Bolt Carriage
5ca9f5ff-968c-5e1e-9d04-f9f2c566e5b9 | note | Detail of Activity / Test - Reinstall Carriage Bolts and Washers Tight
4a261330-a693-51ab-9897-d63b014c1c90 | note | Action (Hold, Monitor, Witness) - M
4a959c17-d50f-5948-889b-cb287ab6ea41 | note | Minimum Test Frequency (Lot = 1 day’s production) - All Carriage Bolts
45514a54-3f79-548d-acdf-75340eec33e8 | note | Inspection / Test method - Visual / Photo
19f39a29-820b-5bcc-b22b-e776903721e9 | note | Acceptance Criteria - Site Engineers Approval
f7dbd140-faf2-5ee3-bccc-01d3af009989 | note | Record documents (QCP - Quality Control Portal) - Checksheet
e44bbf74-6fde-5036-9ff1-3c69e9e24882 | note | Responsibility - Contractor
d3b11100-9d99-5284-a563-f3872bc90744 | note | Site Engineer - A
cfa6f849-5021-5d8f-9d50-0cefd12732ea | note | Eng. Rep / NZTA - I
5502e90c-9c98-5775-8f1f-5d5fef9de399 | note | Contractor - R
9434f4aa-c8ab-4585-a7aa-ddee7c6c8d4f | checkpoint | 2.05 - Determine Height of Guardrail above new pavement
318f6a1e-68cf-5e4d-b1dd-039fd2249fe4 | note | Detail of Activity / Test - Top of W-Beam 787mm Above Finished Road Level
64de7d0d-ef48-534b-b036-453b47aebb28 | note | Action (Hold, Monitor, Witness) - M
3bfe3a0c-8365-5471-98d8-31a99bdc5537 | note | Minimum Test Frequency (Lot = 1 day’s production) - At Every Post
2b4c9dfb-8213-575e-925a-bfe1f8d2c3ba | note | Inspection / Test method - Measure
ae6b2fe9-0318-5a11-8118-ed702d2f324b | note | Acceptance Criteria - Site Engineers Approval
9d54a54d-c067-55b5-ad81-b5fd0bcd1adf | note | Record documents (QCP - Quality Control Portal) - Measurement Sheet
994e04b5-b772-5118-be1e-ca703ad3a88d | note | Responsibility - Contractor
38377aae-d32e-53dc-aad3-6b3ae51c76dc | note | Site Engineer - A
9b62e071-0c38-53f1-81b5-23a255dfee64 | note | Eng. Rep / NZTA - I
e3f76c4d-c396-5a7d-93a3-9b5c3e13b62e | note | Contractor - R
f37c177f-e0ce-4101-bf4d-d8cfe36921cf | checkpoint | 2.06 - Install Cariages Carriages
fc627623-8df0-55df-a8ff-25b71dd5dba9 | note | Detail of Activity / Test - Install New Carriages at Correct Height to Achieve 787mm above road level
5966b505-bea3-57a8-abeb-299168880874 | note | Action (Hold, Monitor, Witness) - H
240b00ca-ebb5-5565-a3c7-50f3f618c1e8 | note | Minimum Test Frequency (Lot = 1 day’s production) - At Every Post
5b499c6c-f6f1-5723-9c50-9926d5e90c83 | note | Inspection / Test method - Measure
607e4598-6d02-5731-9c8c-7c58e36d4cc1 | note | Acceptance Criteria - Site Engineers Approval
9653dd25-2e24-56da-b565-92a1f263bf24 | note | Record documents (QCP - Quality Control Portal) - Measurement Sheet
2949fdf1-a6bb-5611-b004-8bafce9c6afe | note | Responsibility - Contractor
2d398980-4681-5302-a7bd-836fbaefcaf9 | note | Site Engineer - I
8acd6548-3537-5fdc-93dd-48ff4df10019 | note | Eng. Rep / NZTA - A
eef2000c-6337-5520-b61b-854d62f67d3e | note | Contractor - R
5b8d6a18-e02e-4dfb-a051-e016f42e6226 | signoff | AUTHORITY HOLDPOINT
d818d943-569d-49e6-963f-d6c1c20b9204 | checkpoint | 2.07 - Install W-Beam Rails
4d5ae037-74b4-5079-a4f8-9e34190e9861 | note | Detail of Activity / Test - Reinstall W-Beam Rails to Exy Lift Carriage using M16x30mm Bolts and 75x45mm Square washers at each post
6c4ee185-3cd7-5b42-b895-2533392c5e14 | note | Action (Hold, Monitor, Witness) - M
269b71f2-c793-5b34-80fb-1daa5b237549 | note | Minimum Test Frequency (Lot = 1 day’s production) - At Every Post
bf3b3831-9f64-5627-ab1e-cfe2f0b29e7d | note | Inspection / Test method - Visual / Photo
26563336-ae76-52e5-a829-ea5c2617539a | note | Acceptance Criteria - Site Engineers Approval
75e77394-f82c-5965-a9e5-c0e74c78d373 | note | Record documents (QCP - Quality Control Portal) - Checksheet
f3446151-8862-5d02-91cb-bb1ac3aecfb8 | note | Responsibility - Contractor
c1ef6466-3e17-57ea-9df5-6e4f7d80dde3 | note | Site Engineer - A
dae53882-2b8f-55d3-8531-0a113b57af5c | note | Eng. Rep / NZTA - I
d127b347-433e-5ee1-9aba-298130841ec5 | note | Contractor - R
7eb3f664-4b7c-4cc7-a269-e11f1dcc3ddf | checkpoint | 2.08 - Overlap Rails
450eed39-3531-57c8-add6-3e84c8a0bfed | note | Detail of Activity / Test - Overlap Rails during installation to there is no leading edge facing traffic
f69c924e-f7de-5a15-9b50-f1bfa25df4cb | note | Action (Hold, Monitor, Witness) - M
59894d7d-485a-5011-bc78-739f76a0d9a5 | note | Minimum Test Frequency (Lot = 1 day’s production) - Every W-Beam Rail Joint
ae0789a0-cd55-5a64-be2c-e1ef56f4bfa4 | note | Inspection / Test method - Visual / Photo
f2bda3c6-7f9b-5604-ad3e-07172113e5b7 | note | Acceptance Criteria - Site Engineers Approval
712640fc-ce88-5224-95e0-47251d6da73c | note | Record documents (QCP - Quality Control Portal) - Checksheet
01ea0ca0-5f0a-5a54-bfad-1e5dbe962e45 | note | Responsibility - Contractor
86f3c19b-2362-552b-b553-92c098b62004 | note | Site Engineer - A
395c01ba-36e4-5b51-960a-da87b1fc4a25 | note | Eng. Rep / NZTA - I
328d8ec1-f7ed-576a-8924-20b147521160 | note | Contractor - R
545f6004-8f3a-4cc9-b37e-299e19931141 | checkpoint | 2.09 - Splice Bolt Installation
dea6760a-1ac7-554e-ae25-32c886e1b93e | note | Detail of Activity / Test - Install Splice bolts at every 2nd post using M16m32mm splves bolts and oversized nuts. 8 Bolts required per Splice connection
cec07cbc-a548-5395-a6bb-b6ea16844042 | note | Action (Hold, Monitor, Witness) - M
0b511ee2-a98a-53e8-9149-3c67f65dab02 | note | Minimum Test Frequency (Lot = 1 day’s production) - Every 2nd Post
8cad5854-bbd7-59b8-9219-455a8829f453 | note | Inspection / Test method - Visual / Photo
51ba4a78-b999-581c-9c33-d7ca41c88a06 | note | Acceptance Criteria - Site Engineers Approval
e843f480-7243-52e7-a181-b09e95c3ddf1 | note | Record documents (QCP - Quality Control Portal) - Checksheet
dec86220-b237-500c-8ffa-6e42d2649d82 | note | Responsibility - Contractor
ba495798-2196-55a1-a913-90e00bd3584f | note | Site Engineer - A
03710017-5df3-508b-a133-7a1f1b9ec418 | note | Eng. Rep / NZTA - I
e3d5b38e-d061-5857-b075-cfbb2beecc35 | note | Contractor - R
ff680d71-4571-4d77-bb59-f158fcf65e84 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
7b01c437-edee-5936-ae71-68d63aef4b84 | textbox | Contractor's Rep Name:
f5838026-8259-58c5-afc4-1a27942b0903 | textbox | Engineer's Rep. Name:
7a99ed5d-29e9-5649-b1e0-b663ec35e1eb | date | Date:
12894926-2346-4788-a274-f73c994574a9 | signoff | Add Signature
00780191-066c-5e2e-9012-e63ca78ba88b | checklist | ITP - Kerb and Channel Rev 0 | itp | ITP - Kerb and Channel
509f0569-c076-5048-adab-15a6a5981826 | section | 1.0. AGGREGATE AND CONCRETE TESTING
b1d1e2eb-02f6-59d6-9011-519eaead095e | checkpoint | 1.01 - Concrete
c28dba65-dbc6-5e52-89c0-9fb7ea64c649 | note | Detail of Activity / Test - Concrete Supply
5f12d43f-3dff-5c08-bfa1-2342d2edc07d | note | Action (Hold, Monitor, Witness) - H
2351f1e3-82c8-5225-b768-59d4b42c8b08 | note | Minimum Test Frequency - 1 Test per material per source
7641424e-9196-54bf-821f-27c62b241939 | note | Inspection / Test method - NZS4407:3.10
056e1e39-2a06-5e9d-afc0-c56e3c60cdef | note | Acceptance Criteria - 20Mpa Minmum Strength after 28 Day
3041d1b1-8824-5b4a-baf8-3578504b58e5 | note | Record documents (QCP - Quality Control Portal) - IANZ report
27ebaebf-6d5f-5ff9-94f2-58e217253a84 | note | Responsibility - Contractor
e07f0d09-1ff5-5105-863d-c81c012b1b2d | note | Designer - A
29226a34-2ce8-5c8b-a1ce-fc2ae13a409e | note | Eng. Rep / NZTA - I
0eaa195f-a12a-5d36-83eb-424df7bd7c58 | note | Contractor - R
e04fca8e-fc03-5a11-b09a-1742b6945054 | signoff | AUTHORITY HOLDPOINT
1d15ff46-5f4f-5e5a-abb2-ce4a9d764b0d | checkpoint | 1.02 - NZTA M04
f4ab533c-1954-53c5-93d0-3e6b74e0b758 | note | Detail of Activity / Test - Crushing Resistance
cb00372a-cfba-5ff6-b291-ef5171be99fe | note | Minimum Test Frequency - 1 Test per material per source
4db60482-e034-57aa-87a0-2d97e68bc313 | note | Inspection / Test method - NZS4407:2.4.7
4ce8848b-6a40-53c9-81e2-8936d6eedafd | note | Acceptance Criteria - > 130KN
52179bef-1b1e-5132-9c57-b15233c67c6c | note | Record documents (QCP - Quality Control Portal) - IANZ report
5e81b707-77b3-5400-9d04-f3c5edf1fec3 | note | Responsibility - Contractor
cca007ec-b3ed-5851-99f0-e840665257ca | note | Designer - A
bd5b413a-d3ea-5e5e-89a4-2f809ff2a745 | note | Eng. Rep / NZTA - I
bb322f82-90fa-55ef-8ed0-51e3a4677e57 | note | Contractor - R
4e96cf6a-d797-5ecc-9a3c-3106b6e3024c | checkpoint | 1.03 - NZTA M04
98e8f66f-9c88-5d84-9e9e-2bc26eca8cc8 | note | Detail of Activity / Test - Particle size distribution
a55fab7b-aa80-513a-9d44-f56d17d327d4 | note | Action (Hold, Monitor, Witness) - H
06612d8b-7922-5bae-88ec-ad70233077ed | note | Minimum Test Frequency - 1 Test per material per source
0d0e10a4-140b-52af-828a-f6897761ea5f | note | Inspection / Test method - NZS4407:2.4.7
e2e280fb-e315-526c-bdec-77cc1e93288f | note | Acceptance Criteria - As per NZTA M04 Specfication
632af8fd-4fa4-53ef-bbc9-2c80ac647cc3 | note | Record documents (QCP - Quality Control Portal) - IANZ report
53c4cc40-2b74-50d5-911b-c5f09e6cc645 | note | Responsibility - Contractor
de152650-e28c-5911-8c0c-e1595f940ff2 | note | Designer - A
b29ecef5-52be-521d-be40-843ff5ba9fa2 | note | Eng. Rep / NZTA - I
58b11fa7-b2aa-52fd-9d11-05f30f5cae34 | note | Contractor - R
7c0871fe-df88-5bac-b26a-696c6e714f8e | signoff | AUTHORITY HOLDPOINT
56110d7c-4078-588c-9b46-3a22f13f0775 | section | 2.0. CONSTUCTION
5b802e8c-ba68-5859-b05d-d1617c42a80d | checkpoint | 2.01 - Earthworks
31780bbb-abb0-5b51-90fa-3992953f49dc | note | Detail of Activity / Test - Cut to Waste Existing Kerb and Channel
5c3124cd-c33b-53e9-baba-cc5de0eab82c | note | Action (Hold, Monitor, Witness) - M
f2e00d79-2fc3-58a1-81cd-f8633e8164b6 | note | Minimum Test Frequency - As per IFC drawings
b4521da3-d58e-5acf-9c69-99dac85808bd | note | Inspection / Test method - Visual / Photo
532fe4a3-0840-58a0-a9fb-eb9220469b0e | note | Acceptance Criteria - Site Engineers Approval
0baab63a-7ccf-5fd9-a3d6-f58ff3959e41 | note | Record documents (QCP - Quality Control Portal) - Checksheet
633c9b59-f2a0-5d05-821b-b731176e5989 | note | Responsibility - Contractor
09ac1f10-e8dc-5aed-9f14-64540d73d20a | note | Designer - A
3bbe3dff-ba77-540e-baf7-a40ed238e4f0 | note | Eng. Rep / NZTA - I
7b9487b4-a878-504f-ac73-3ae61da7047c | note | Contractor - R
a280ad99-12fa-5570-b050-dcd5a50cb77f | checkpoint | 2.02 - Prepare Subgrade
5152414b-b2f5-5232-b128-3b60c79cc8a6 | note | Detail of Activity / Test - Subgrade further compacted or excavate the unsuitable material and replace
6b333cae-6cb0-5dfb-a6ec-3486575f3146 | note | Action (Hold, Monitor, Witness) - M
d6d09cd5-c181-512c-9fe4-3f816cfc57d7 | note | Minimum Test Frequency - Test Every 10m
ad8c76ae-aaa5-52d3-8590-a71eafb7d211 | note | Inspection / Test method - Visual / Photo
8e4deab2-8dbb-52ae-8967-31f7318b0489 | note | Acceptance Criteria - Clegg Result >15
24729b58-04b7-566a-bbaa-d475abf12fb0 | note | Record documents (QCP - Quality Control Portal) - Checksheet
5553241d-5988-57f0-b520-facad70fd49d | note | Responsibility - Contractor
3c677786-259a-5ccc-acd9-dae2add4874a | note | Designer - A
44c7348c-8f4a-57a8-9fcb-e8e9de5964b0 | note | Eng. Rep / NZTA - I
270b20e4-c90e-56c2-9f35-d60b3f5c5ac8 | note | Contractor - R
23ea1f12-ea41-5e68-9ef7-0aa7a5ca45c2 | checkpoint | 2.03 - M4 Palcement
e930e4e7-e60b-5cdd-8dd6-7929e36f0b00 | note | Detail of Activity / Test - Compacted layer of GAP40 as required to adjust height of new K&C shall be placed over subgrade. (75mm Min)
67fbe963-46c0-5eac-9bba-de301fe7e56a | note | Action (Hold, Monitor, Witness) - H
5c98f86e-3ab6-5605-8418-05ec76a996bf | note | Minimum Test Frequency - Test Every 10m
c2b78627-cee3-51d2-bae7-71b3a040416c | note | Inspection / Test method - Clegg Test
7c94625a-28cd-5827-b209-cc2d6a66d064 | note | Acceptance Criteria - Clegg Result >30
bb54384a-3abe-5caf-8003-c7c2e176967f | note | Record documents (QCP - Quality Control Portal) - Checksheet
056043cf-c2eb-50dc-9a87-687092a36ae2 | note | Responsibility - Contractor
12147659-47fd-5fa9-befb-756659d510dd | note | Designer - I
ba2ef4ea-4e67-5430-b9df-9d75bf1aa80f | note | Eng. Rep / NZTA - A
423d42b5-d442-5ed0-9323-f883a49633f9 | note | Contractor - R
736a4ee5-c79a-5237-b8c7-bc1cd9eafa73 | signoff | AUTHORITY HOLDPOINT
d594ae3b-2e51-50cd-ad83-a9fcd934fc5a | checkpoint | 2.04 - Kerb and Channel Placement, Line and Level
331465c0-e040-5992-b3df-50d1cba9972a | note | Detail of Activity / Test - Construction of Kerb as per profile setout in IFC drawing
6c244b7a-4746-56ef-bb36-0bf6ad4eae3e | note | Action (Hold, Monitor, Witness) - M
ce4d77bb-f258-53fc-a5a9-4b59a2d43635 | note | Minimum Test Frequency - Throughout the activity
9d0cf89d-6b16-5084-8b61-220d5c3d7738 | note | Inspection / Test method - Meausre off Survey Pegs
c30b0585-385d-53f5-ba92-dd8db5b35cb5 | note | Acceptance Criteria - Check Sheet of Survey Pegs Versus Actual
8328c7b2-928b-5eb9-8adc-9f9339a43ad9 | note | Record documents (QCP - Quality Control Portal) - Checksheet
5ff24f96-f738-5815-8681-baf77732bfe6 | note | Responsibility - Contractor
ad9fd77f-9315-5780-875c-f33472bee601 | note | Designer - A
dfde453d-1cc5-5129-b72d-d52850109bf0 | note | Eng. Rep / NZTA - I
1d8957da-0904-56c3-a938-229dbd7ea404 | note | Contractor - R
fec9ede7-1a16-5aed-83c8-51bd3f8b3a95 | checkpoint | 2.05 - Contraction/Expansion Joints
5163d854-182e-5029-906e-78cdccf48483 | note | Detail of Activity / Test - Maximum spacing of 3m and minimum 50mm deep
172215c3-8d26-5308-9a2d-b79507a4df41 | note | Action (Hold, Monitor, Witness) - M
5cfaa435-fb95-535c-8220-8df1fceee4e8 | note | Minimum Test Frequency - Once
f5723d9d-a969-5a31-a22e-4d89e055789a | note | Inspection / Test method - Visual / Photo
f691f8a6-c050-53bf-9b1a-48994da3eb9b | note | Acceptance Criteria - Measure Cut Spacings
79232ae0-6bfd-50c2-977c-a13c231a483d | note | Record documents (QCP - Quality Control Portal) - Checksheet
2f07e8da-b154-5d4c-bcf2-3d0a32b8002f | note | Responsibility - Contractor
b1a8bf03-b862-5b66-86bd-c2e2167fa507 | note | Designer - A
98425e34-65fc-5ea1-94c0-50e9794bf192 | note | Eng. Rep / NZTA - I
775220d6-84d8-506a-a55a-600ea569039d | note | Contractor - R
8bb2a965-3780-566e-af0d-380d18f586fe | checkpoint | 2.06 - Curing of Concrete
d0f86cdf-a10f-5ff4-a961-bd3fcc055cad | note | Detail of Activity / Test - Curing period shall not be less than 1 day OR 36 hours
2ced8da0-95cc-56bf-a8fa-e1435a3b3f28 | note | Action (Hold, Monitor, Witness) - M
db7433eb-0cfa-5107-91b4-6cfcc2b67e7f | note | Minimum Test Frequency - Throughout the activity
bacb5928-9a52-5ac5-a141-a3c7342dc032 | note | Inspection / Test method - Visual / Photo
e0745b69-e3ef-5376-8521-91709ed8326b | note | Acceptance Criteria - Visual Inspection
4e93f544-166f-568e-815f-b931cb93e4af | note | Record documents (QCP - Quality Control Portal) - Checksheet
4fff75df-2ca5-55ab-a253-ca2e12eac5ec | note | Responsibility - Contractor
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
def521a5-19bc-57be-92d7-dbc032333c2a | textbox | Contractor's Rep Name:
2553d783-fc64-52ee-8c82-d2fb5be12e4f | textbox | Engineer's Rep. Name:
5264cd35-dfb2-525b-ab33-0067722a9d78 | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
c7fe751a-2260-5c04-816e-cef7b8234e2b | checklist | ITP - M10 Dense Graded Asphalt - Construction Rev 0 | itp | ITP - M10 Dense Graded Asphalt - Construction
e37f64ad-2e1d-5892-9ad5-ee339d5a3957 | section | 2.0. MANUFACTURE OF ASPHALT
9ed5d845-4845-59b1-8427-9a3acc3b9c38 | checkpoint | 2.1 - Temperatures
fae9ae64-57f2-5b89-a0d1-780a7c7fd8d9 | note | Detail of Activity / Test - Mixing of aggregates and bitumen
ea7c0296-d795-5896-a32b-d15a49d6fc5b | note | Action (Hold, Monitor, Witness) - M
32a2f120-7805-569c-9005-0f68dfafb7b5 | note | Minimum Test Frequency (Lot = 1 day’s production) - Constant monitoring of temperature by calibrated euipment
bd119174-f434-54ae-8a27-8cc41b1c8780 | note | Inspection / Test method - Plant temperature probes
2226442e-9ff8-5ca7-985b-26bd851bd38b | note | Acceptance Criteria - PG64H binder Mixing range 160 - 170°C
1e91dc54-4a79-5b9c-86eb-5da86ab21792 | note | ○ PG64 V/E (Flexiplus Bind) binder mixing range: 170 to 190 deg.C
ea397109-35cf-5863-86de-89ad16898fa7 | note | ○ NZTA M10: 2020 states max. 185 deg.C
bd5514ad-ffca-534a-916b-22cefb87ff46 | note | Record documents (QCP - Quality Control Portal) - Plant site diary
93b1835b-44e5-53ab-b92c-fe7e68b0bc8d | note | Responsibility - Asphalt Manufacturer
ffb410b7-f3e1-5a8f-a526-c055dd3cf242 | note | Designer - I
5d587eec-90ca-53a8-b3ad-c16f8248fe35 | note | Eng. Rep / NZTA - I
74bf321a-7ba3-51ed-affb-fc3112c35314 | note | Contractor - R
371b495f-cbbd-51d8-98fd-3096d0f2d646 | checkpoint | 2.2 - Production Asphalt
feff0614-d3c5-5371-a2d6-7ea5452838e3 | note | Detail of Activity / Test - Particle Size Distribution
728ce3fc-48ce-5f53-9667-e7a064be8a53 | note | Action (Hold, Monitor, Witness) - M
65562595-9c98-5a01-b4c7-6b2697e5ef4c | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
9f36ac89-14d9-5b05-99a9-ecb5dc05f40e | note | Inspection / Test method - NZS 4407, Test 3.8.1
380fec6f-a9ac-5d08-8109-f49791c66838 | note | Acceptance Criteria - NZTA M10: 2020, Refer to Table 5.3
fe40dcd9-e966-5d37-8a98-2935ec5a3208 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
e9c93a36-de9b-50fb-844e-5c8596fa8c7f | note | Responsibility - Asphalt Manufacturer
4b997074-a0ea-53a7-b4fd-2ec921cbcea1 | note | Designer - I
54a7bb85-c9ae-5cb4-bcd2-b0146a996b70 | note | Eng. Rep / NZTA - I
22e44766-0cfd-5253-8b22-ac968701ad95 | note | Contractor - R
da6c9329-532a-54f2-9369-db8989f73e9b | checkpoint | 2.3 - Production Asphalt
eb140f69-d427-543f-849f-9e33a90d178e | note | Detail of Activity / Test - Binder Content
15104e22-7489-5a22-af92-495054c41705 | note | Action (Hold, Monitor, Witness) - M
ef0e845e-0b10-5a84-abc7-60c3ca1547ea | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
5366d195-9c51-576e-839f-ad30e5df0c3e | note | Acceptance Criteria - NZTA M10: 2020
47462373-222b-54fe-b18b-835ee9d343e3 | note | ○ Individual Test Result: ± 0.5
d1bec60b-bf3b-5469-b398-32b4e201ee5a | note | ○ Mean of Three Test Results: ± 0.3
b0d10a0c-1e70-5a4c-9009-15c7e22ff864 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
c3a2b53b-68b4-5841-8d4d-2662c75ebbac | note | Responsibility - Asphalt Manufacturer
e8a2d00f-b4d4-589e-86a3-1a9d486e25a1 | note | Designer - I
23a12374-0783-5032-9b05-e75205daaefd | note | Eng. Rep / NZTA - I
2831c5c7-3ffd-5b5e-88ce-d6f854cef597 | note | Contractor - R
d005f834-a3b6-51b4-8e32-d7fbf27a8fbb | checkpoint | 2.4 - Production Asphalt
e027be64-69e3-5cb9-8845-55393b668d54 | note | Detail of Activity / Test - Max. Specific Gravity (MSG) of mix
eaec6aab-3b19-5f92-aae3-f1a18ee78553 | note | Action (Hold, Monitor, Witness) - M
27d644e7-787a-5058-b794-c01458acb84e | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 600t at asphalt plant
d540f63d-9d9d-5eb3-abb6-878f67666ae2 | note | Acceptance Criteria - Report
b229d81d-8198-5172-9b2a-f5e85940a79f | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
1675fa07-178c-591d-a54e-52ef1c3ab4db | note | Responsibility - Asphalt Manufacturer
3ef83d4e-7f54-568c-b1d3-8d6d568c654f | note | Designer - I
83619bd0-706c-5092-a689-b4797a2c97f4 | note | Eng. Rep / NZTA - I
b6e7558d-85fa-537a-a096-10d632f9da55 | note | Contractor - R
9680cc3b-0b4b-5394-9dff-da10e33d09d1 | checkpoint | 2.5 - Production Asphalt
e52c4d01-eef3-5f5b-91c9-eee5582b7ed2 | note | Detail of Activity / Test - Air Voids at lab design compaction
c8cf73be-84c2-58d2-9f7c-b0c973d8a1de | note | Action (Hold, Monitor, Witness) - M
aa785332-7be9-5e39-8233-a05f84ea7531 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 600t at asphalt plant
1aeb6e18-4b07-54db-bead-8d132d2ca916 | note | Acceptance Criteria - NZTA M10: 2020:
37356146-3ac7-581d-9d7e-df6edacb5e1d | note | ○ Individual Test Results: +2.0, -1.0
4af93e03-eac2-5de6-92be-fff11db973a1 | note | ○ Mean of Three Test Results: +1.2, -0.6
803ed502-35bf-5526-b02c-59b87d58d47f | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
4feafdde-919e-5039-a5df-e82f01624101 | note | Responsibility - Asphalt Manufacturer
46c231da-87fc-5617-8a68-7b0638d314fa | note | Designer - I
87e9026c-b892-5a01-9fce-adb5f4598c9b | note | Eng. Rep / NZTA - I
46522c14-f2b9-5816-aa5f-ec62cc4800ca | note | Contractor - R
4ee242ad-877a-59da-9474-f2ca98f5c556 | section | 3.0. PLACING AND FINISHING
fa3cebdc-265b-5a4a-b405-b1aa87d1625a | checkpoint | 3.1 - Milling
786ca795-29f0-5eca-8770-974cba15c1f8 | note | Detail of Activity / Test - Surface strung to ensure milling Depth is achieved
74f78d91-79eb-5c83-ba56-00b5be458158 | note | Action (Hold, Monitor, Witness) - M
0123031b-884b-5b78-bba0-6fdcf71d4412 | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Asphalt placement commences
dfcc7731-71b8-53e2-89db-0e71c708aa07 | note | Inspection / Test method - Confirm requirements are followed
6ec5e0f7-707f-5eb5-86ed-cd7672bb8747 | note | Acceptance Criteria - Site is suitable for paving
45ec6e44-dd9c-5202-8ec2-2cf0383d4f42 | note | Record documents (QCP - Quality Control Portal) - String Sheet
ca640911-713b-5219-a928-9558eed9a477 | note | Responsibility - Paving Contractor
42aabd7c-e6e9-502e-839d-a36f4cad42b9 | note | Eng. Rep / NZTA - I
4ecc12c8-7cbd-53c3-b3be-6ce4b759da36 | note | Contractor - R
c1901290-5afd-546e-88c8-0396896c848d | checkpoint | 3.2 - Tack Coat, OR
c9c7ce01-306e-5e9c-8ace-efcfedd72378 | note | Detail of Activity / Test - Application of Tack Coat
e80a6edc-1539-59cb-b407-127fcdb5426e | note | Action (Hold, Monitor, Witness) - M
dde623c8-667f-501f-8e04-320a13d376cd | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
323b794e-2a62-584b-98e0-77558edcffc0 | note | Inspection / Test method - Dip bitumen emulsion tank before and after
b6e9ec8c-4810-57df-86f4-121cab8f86f8 | note | Acceptance Criteria - Target Between 0.2l/m2 - 0.6l/m2 +/- 0.1l/m2 From Target Application Rate
a0cf0b75-8e07-5a7d-9c95-a69003ef6c78 | note | Record documents (QCP - Quality Control Portal) - Site Diary
15462aca-4cf2-55a6-a108-2dec644cab2f | note | Responsibility - Paving Contractor
f89f9dd0-5eae-5307-8c3c-398ef4bd983e | note | Designer - I
1eb29a48-ad52-5c84-bb10-0c6e3944aef0 | note | Eng. Rep / NZTA - I
e74d6b75-e0f8-5f10-abcd-ae2b95963b80 | note | Contractor - R
df0ed961-0b8e-50ef-9ab8-76aa993c07c2 | checkpoint | 3.3 - Membrane Seal
e2877635-5919-5e6a-8d9f-3c8b1f1e1baa | note | Detail of Activity / Test - Application of Membrane Seal
42504c03-7be9-51c2-9a7a-fc44b13fbbf1 | note | Action (Hold, Monitor, Witness) - M
ef5a2051-993b-5633-a649-250e877ec858 | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
53210a76-b687-55ae-bd33-729e339863c9 | note | Inspection / Test method - Sealing Records
29d930b7-56ca-5d55-9f72-d40c931b4965 | note | Acceptance Criteria - Application rate, chip type and binder as per membrane seal design
b0ba6261-59bf-5a1f-95da-1642ff66c166 | note | Record documents (QCP - Quality Control Portal) - Sealing Records
b9ab2520-58c8-50e2-b69a-7c845ce47456 | note | Responsibility - Paving Contractor
8b4ef8dc-18e7-5050-9c33-89ba693d3d10 | note | Designer - I
7fe5fe2b-c6c4-5985-aedd-5604f1100bf0 | note | Eng. Rep / NZTA - I
a5a695ad-cbf3-53c1-88bb-48546c271eae | note | Contractor - R
0daedfae-4bad-5421-a834-ad22dcfca3c4 | checkpoint | 3.4 - Temperature
9ce74458-c2a9-53ec-b8d7-04a8603381ae | note | Detail of Activity / Test - Pavement Surface
4e3b8987-7ce4-5d55-94fb-bf4ce9df7593 | note | Action (Hold, Monitor, Witness) - M
9d25d0da-bf0b-5c73-a9c3-3b11efb3d720 | note | Minimum Test Frequency (Lot = 1 day’s production) - Start of shift and every 1 hour until temperature rising
a26bb330-96bc-5085-86ad-16dd4924bdcb | note | Inspection / Test method - Infrared gauge
33f077db-2a74-51fd-990b-8ffb135b596f | note | Acceptance Criteria - ≥ 10 °C for Wearing Course, ≥ 5°C for Structural, or as otherwise agreed with NZTA
11fc846d-3210-5b47-b4cf-570b83299ae8 | note | Record documents (QCP - Quality Control Portal) - Site diary
3a8b9c84-9317-56de-928e-1991055f7221 | note | Responsibility - Paving Contractor
e5495ac5-c7ae-5030-aec3-b530d7cf0e2e | note | Project Specific Notes / Instructions - Must get NZTA approval if < 10°C for Wearing Course, or < 5°C for Structural
d6ff8cf9-e40a-5ed0-ae81-a18dd6d56099 | note | Designer - I
9b2ddfba-747e-590a-89e3-dabb398d30d7 | note | Eng. Rep / NZTA - I
0747e564-a136-5dad-b523-5542f52edffb | note | Contractor - R
a636365a-b32b-5a0f-be50-623afca95fe8 | checkpoint | 3.5 - Temperature
e1ea31c1-c8dd-56b2-a536-0d1c69852854 | note | Detail of Activity / Test - Asphalt Delivery temperature
589d035c-1b50-5736-bb0c-dc29bb869718 | note | Action (Hold, Monitor, Witness) - M
7bb8b5aa-bc74-55d8-89e8-6c0793e76ce9 | note | Minimum Test Frequency (Lot = 1 day’s production) - Every Load on delivery to the Paver Hopper
2657637b-0bf7-532e-ae72-f729377d9bbe | note | Inspection / Test method - Temperature Probe
9535b49c-ea10-5bbf-9ced-4dfd4b4aaf2b | note | Acceptance Criteria - Target ≥ 150 deg.C. in the Paver
82644e93-34ec-53ce-9f8f-39b78793924c | note | ○ Min. ≥ 130 deg.C in the Paver
5eb609f0-6f6a-5715-b1c7-366d83a98e6b | note | ○ <130°C to be Rejected
df3eb953-6195-5725-85ab-0faabbbf7983 | note | Record documents (QCP - Quality Control Portal) - Site Diary
22abe056-2b59-5b3f-82ce-4f558f8bd2fb | note | Responsibility - Paving Contractor
ebb56cef-93c5-5901-8cf3-316e5a2dc8ee | note | Designer - I
a2e075e1-774c-5590-81d0-814f470b4416 | note | Eng. Rep / NZTA - I
6bef778d-2833-5bd0-a2ab-69647dc0da64 | note | Contractor - R
fc27c880-a17c-5bed-a0b4-ac7a516aee69 | checkpoint | 3.6 - Temperature
94046fa4-b99b-5add-8fdf-8ca61836649b | note | Detail of Activity / Test - Compaction Temperature
31768de2-cac2-5485-a7ef-a530c4cb5a04 | note | Action (Hold, Monitor, Witness) - M
31e9b9ee-182f-53c3-b0a0-d69324bace8e | note | Minimum Test Frequency (Lot = 1 day’s production) - During compaction
b9940a43-60cd-5b49-8c34-20fcba7c8578 | note | Inspection / Test method - Temperature Probe/Infrared gauge
e6878c2e-aa94-5abc-a72d-cc36d33789e9 | note | Acceptance Criteria - ≥ 125°C at commencement of compaction. < 80°C - Stop Rolling
0445e197-5f30-55e0-83a7-c9024d2c86ff | note | Record documents (QCP - Quality Control Portal) - Site diary
0cd8a205-abb6-588f-a527-67425753a7e8 | note | Responsibility - Paving Contractor
06395ddd-3cae-565f-854e-d4ec5b999cad | note | Designer - I
e45d6c27-95a3-5f13-b419-eaa0a035def9 | note | Eng. Rep / NZTA - I
15574fe7-1bda-5d49-a4d4-dda6b1b20135 | note | Contractor - R
2958dd76-c13f-500e-b3c1-c072d547f681 | checkpoint | 3.7 - Mat
72eda37c-45f8-5360-8774-2e2e8a9574ad | note | Detail of Activity / Test - Load Locate
71b4cb42-413a-5140-b4cb-d547ec5bf032 | note | Action (Hold, Monitor, Witness) - M
ce404ef5-c30a-5fb7-9313-025319cd60d0 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each load
f740b200-e3e4-574d-be54-f51d6ce4690a | note | Inspection / Test method - M/10
678f0c7d-73ca-5169-9091-3b5710b5d95f | note | Acceptance Criteria - Each load can be indentified to a location using a diagram. Record includes:
0f0f8ecf-a6e4-50ac-abe1-3bdee94bad3f | note | – Truck ID/Rego/Driver
18049b05-9dd6-52e4-a379-fd1f7e16d085 | note | – Depart Plant Time
7a726e94-ac97-5e23-80c9-45fe5035f9d8 | note | – Arrive Site Time
58342887-d9a1-5617-be80-e05f2d508209 | note | – AC Temp on Arrival
162aabec-eee4-5f16-aaa3-a75c93aa1b9a | note | – Tonnage
8bc16c42-8050-53fa-914a-460503458673 | note | – Run Width
3f73fcb7-b805-512f-a4e1-5357cbede231 | note | – Estimated Run Length
0fa53ed0-6051-55a7-b3a4-540474fe82a9 | note | – Calculated Area
fe2a9eeb-49a1-5716-8630-d4ff869b68a5 | note | – Calculated Average Depth
40622319-f5ab-5342-bc2c-8a9d9544a9d8 | note | Record documents (QCP - Quality Control Portal) - Paving Run Sheet
8201fc58-be64-58fc-b081-1dbf8bae2d4f | note | Responsibility - Paving Contractor
05d50c83-0cdf-5b04-8d49-dc3eec43da41 | note | Designer - I
40dd0bff-4f3a-50e9-ba40-6a1330ffd62a | note | Eng. Rep / NZTA - I
7d1ffb06-3e4a-5973-870d-3387650d2605 | note | Contractor - R
2dfb52ca-11cc-51fc-874c-1a8a1bb99335 | checkpoint | 3.8 - Mat
f2862130-cbff-5bf5-988a-6102f6125a2b | note | Detail of Activity / Test - Thickness Monitoring
ef664afd-ecbe-5a3a-9545-644706c20e61 | note | Action (Hold, Monitor, Witness) - M
e44edf86-bdf5-5430-a588-2e9ac632eccb | note | Minimum Test Frequency (Lot = 1 day’s production) - Continuously
9061d7b7-a3e6-5e10-91a1-5ebd9fe80b99 | note | Inspection / Test method - Dipping
67b665e7-7a9c-56fe-930a-6d9ee9679d7c | note | Acceptance Criteria - Target Loose Thickness -0mm / +10mm
0282c8b5-ba41-5b88-9273-38da1b55dfb8 | note | Responsibility - Paving Contractor
e46a79aa-f971-5d12-b036-01761c89fbd5 | note | Designer - I
38686789-d013-566b-a4a0-79e1be4fc9a9 | note | Eng. Rep / NZTA - I
4d6ee64b-abba-5ce0-bf78-7a38ad2ae3a8 | note | Contractor - R
bc1d43ab-1cea-564d-af06-6d166c441d88 | checkpoint | 3.9 - Mat
eeaee7d8-10c8-5992-bebb-5d8169b9675c | note | Detail of Activity / Test - Compaction - NDM
12056382-edbf-5608-8399-a89930a23f6a | note | Action (Hold, Monitor, Witness) - M
c40755b3-c592-5a52-ae07-9982595f5f74 | note | Minimum Test Frequency (Lot = 1 day’s production) - Plateau to be completed on 1st run, thereafter monitor compaction/roller passes to achieve target density.
d5a84ad0-1f3e-5867-9c5d-6092d663d6cc | note | Inspection / Test method - Insitu density and air voids
9578d3e1-4975-5fa7-85f8-10617a8c00ec | note | Acceptance Criteria - NZTA M/10: 2020 - section 9.9
c77bac23-eedd-52e1-ae48-13b451fa8aa4 | note | Responsibility - Paving Contractor
171f8284-9d69-5470-bad1-a3111c4cc064 | note | Project Specific Notes / Instructions - Use a calibrated NDM with established core correlation. Locate and mark cores, record NDM Bulk density by core location (including any offset used).
cd5407db-85db-58f0-87ff-947ce3f1efec | note | Designer - I
d37bbf6a-015f-5ec2-820b-c18fa1bd3115 | note | Eng. Rep / NZTA - I
2523ef71-a133-56e2-b49a-e7a6f1074201 | note | Contractor - R
615f2750-e1a1-5ab6-b4ac-f904650a9e16 | checkpoint | 3.10 - Mat
2c70cf5d-874e-552a-9066-e89ddda32e7d | note | Detail of Activity / Test - Compaction
d2258ba6-909f-56fa-96af-54127f5808af | note | Action (Hold, Monitor, Witness) - H
6b11db14-7c83-5711-9441-bd06fc522afa | note | Minimum Test Frequency (Lot = 1 day’s production) - Mat: 1 per 300m2/min. 8 per Lot Joint: 1 per 100m/min. 3 per Lot, In the event of a day's production being > 30t but < 2400m2, then it will be permissable to reduce the number of cores to; Mat: 1 per 300m2 with a minimum of 4 per Lot, and Joint: 1/100m with a minimum of 3 per Lot
0c8926e2-4d11-5b41-9e56-29818dbdba34 | note | Inspection / Test method - Insitu density and air voids
f01fbdee-820d-59bb-b27a-f93b2984c1a1 | note | Acceptance Criteria - NZTA M/10: 2020 - section 9.9
a4311d36-5059-50eb-87b4-d76f64cbdf9c | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
50a5ac5e-3e17-5673-9518-08d68b5ad2a6 | note | Responsibility - Paving Contractor
655fa23b-b1c5-5930-b022-9afba5439155 | note | Project Specific Notes / Instructions - A pavement lot shall be an essentially homogeneous section of work completed within a shift of production.
be2de66c-9cf1-5a0d-becc-fbfceea07511 | note | ○ The lot shall be divided into an appropriate number of approximately equal sub-lots and a core shall be taken randomly within each sub-lot. The Engineer or their delegate shall use a random method for locating each core position, such as ASTM D5361 or a similar process.
96a7bb90-3758-5015-9150-cf3132a7e4a8 | note | Designer - A
1695f5d8-6197-5cc4-9de8-1948ae4338dd | note | Eng. Rep / NZTA - I
efc40f21-da29-5d13-941c-1306cbd98073 | note | Contractor - R
5acec208-2386-5bba-9d2d-6780bed52aed | signoff | AUTHORITY HOLDPOINT
6198ba65-6fd7-5465-beba-32845e3f5a5d | checkpoint | 3.11 - Mat
f9859819-d450-5ad4-9486-f2c6a37303a0 | note | Detail of Activity / Test - Thickness
493a0ac0-d645-5036-abf2-32aa7c9c2b54 | note | Action (Hold, Monitor, Witness) - H
bb8639d4-3187-56be-8be4-bb4067e195fd | note | Minimum Test Frequency (Lot = 1 day’s production) - Average of 4 measurements per core
b02d3e89-8a49-5fd1-925d-6500f156fa48 | note | Inspection / Test method - Measure Cores
16012aa3-f12d-5cb3-a087-e6bba439daea | note | Acceptance Criteria - Average Thickness > Specified Depth (Nominal)
13a4dfa4-2f1f-5681-ae6b-eaf0b1a9756f | note | ○ NZTA M/10: 2020 - section 9.7
0bbda88c-031f-5e44-a3f0-1f9db3d2b450 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
f5c648cd-8c0e-514f-9554-6a1890f1d200 | note | Responsibility - Paving Contractor
d8e62af9-046f-51c2-a236-467265fbc144 | note | Designer - A
ffbd0e0d-aaee-56e6-9969-d075c2cb2a82 | note | Eng. Rep / NZTA - I
bef90c11-0c92-5245-ad6a-51e043af8614 | note | Contractor - R
25efa1fd-9d50-52dc-8d57-44ee0879215b | signoff | AUTHORITY HOLDPOINT
dc746dc5-1a53-536d-a625-2a8c137d686d | checkpoint | 3.12 - Mat
0efc036c-387e-5326-a82b-bf3d59c0195d | note | Detail of Activity / Test - Shape
3e55d7d4-3bc1-5d11-8bec-24769cf75954 | note | Action (Hold, Monitor, Witness) - M
fe86c7c3-773f-5167-b13d-40411a2376f3 | note | Minimum Test Frequency (Lot = 1 day’s production) - Continuously
ce819ebf-0b57-5e72-88cf-7fe9898f81ae | note | Inspection / Test method - 3m Straight edge
1de63698-6123-51af-967a-d8c6d0cca533 | note | Acceptance Criteria - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Refer NZTA M/10: 2020 - section 9.8.
b6c958a6-1318-5094-b113-f4c818ccf99c | note | ○ Not more than 5mm under a 3m Straight Edge.
d693d56a-02fe-5ef8-b469-f41aeae25f8b | note | Record documents (QCP - Quality Control Portal) - Straight Edge Record
dbc50d02-6ad8-5d2e-990e-32bc82e5e82a | note | Responsibility - Paving Contractor
4ac8d7dd-f5a3-5b98-ba7a-9ef7277727bf | note | Designer - I
d6e95887-4312-5691-aea8-f9fb4c5d20c6 | note | Eng. Rep / NZTA - I
3efeb511-ac91-5c71-98a3-846c7b3b690c | note | Contractor - R
ce641ca5-a4cd-5426-aa9c-a3d11eed951b | checkpoint | 3.13 - Paving Quality
5dd21b2d-ffdf-52f5-91c9-0ba166c973d2 | note | Detail of Activity / Test - Texture
6d0d390c-3f76-5926-a0b3-a00deb507eb3 | note | Action (Hold, Monitor, Witness) - M
16167ded-c63d-5746-b37f-2940dbb65afd | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
7705b1a5-7398-5c62-b2ee-b2c3f0d24eef | note | Inspection / Test method - Sand Circle or HSD
15d96ae1-645c-591a-8331-8f2924042620 | note | Acceptance Criteria - NZTA T/10: 2013
a2ae3b35-b13a-571d-ae33-51402843a45c | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
20c2c91e-9f8f-5a2c-97e2-8714b7e1a456 | note | Responsibility - Paving Contractor
3c5bb43e-053a-5189-bf4c-45b59ae2575c | note | Designer - I
e7b3bc6f-b32e-56cc-b44f-896fcff39eee | note | Eng. Rep / NZTA - I
b3385393-7e43-525a-af9a-5657adcee51e | note | Contractor - R
eb6303d9-2fd7-5668-89d7-0b3543df30e9 | checkpoint | 3.14 - Paving Quality
ad68d3cf-605a-5057-b826-e0caa10cbab3 | note | Detail of Activity / Test - Level
de21658e-6419-5db9-b83e-414cdc658636 | note | Action (Hold, Monitor, Witness) - M
c255537f-28b2-549e-88b5-60e57660efd8 | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
978ad515-a879-5dac-8525-230269da3370 | note | Inspection / Test method - As Built Survey
d605d838-b327-5735-a5c9-79141510aa90 | note | Acceptance Criteria - -0 < +5mm from Specified Level
0cf8c53c-29db-51d8-a741-64e02d4cc67c | note | ○ Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC.
94b4d5ce-3b8c-5b43-8288-037af5761d24 | note | ○ NZTA M/10: 2020 - section 10.2
acafe90b-4841-5c99-9d76-4486871c1860 | note | Record documents (QCP - Quality Control Portal) - Survey As builts
56ab4525-91bd-53a3-8f04-c39b233bcbdb | note | Responsibility - Paving Contractor
1434ee20-f6bf-5b39-b344-e85ec87cc20d | note | Designer - I
3ab766a6-16de-5a96-a00b-57412f820d2d | note | Eng. Rep / NZTA - I
225cdfea-b426-50cb-a711-fb6c2ef9055a | note | Contractor - R
b4580cdb-399d-5c04-8475-ef9a0e00367a | checkpoint | 3.15 - Paving Quality
47ef9f18-2afb-524a-a2a0-41768005ba96 | note | Detail of Activity / Test - Alignment
07123450-d2bc-52d8-946a-3e8f49c4f1e5 | note | Action (Hold, Monitor, Witness) - M
0cc2dd62-560d-57de-ad8a-1715a0f5abf9 | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
6b9e6218-0931-5370-a023-a469a2abc85a | note | Inspection / Test method - As Built Survey
25a75973-c098-55d1-82ce-a0f41012873c | note | Acceptance Criteria - ±50 mm from drawings
a5254d62-5642-5e16-8e06-e5a8d1cfc082 | note | Record documents (QCP - Quality Control Portal) - Survey As builts
af51a166-ada1-56da-9241-2bb8fd035a59 | note | Responsibility - Paving Contractor
335b42e2-1094-5270-8483-e04fe6466b8f | note | Designer - I
c6a7bf70-5f55-531f-9b29-6855a6db322d | note | Eng. Rep / NZTA - I
1ad6ccf6-ac6f-5e40-8c50-39e3bf4a723b | note | Contractor - R
00105797-510f-56ba-ab8d-1222cda60376 | checkpoint | 3.16 - Post Paving Completion Checks
0262cedc-dc6b-5bbf-8e3c-2964cb628954 | note | Detail of Activity / Test - Site clear and cleanup
1b7b182d-7a7c-5103-b757-e34a8a030d0c | note | Action (Hold, Monitor, Witness) - W
0da07941-39a7-5b34-b15e-cc158ba4a7a4 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
ad2e3a45-aced-547e-97de-7731f4f4ddd5 | note | Inspection / Test method - Visual
78b63e5e-1155-5aac-946d-8bfe3a60c638 | note | Acceptance Criteria - Site is cleared of plant (or parked in safe location) cleanup of all waste mix, paper and detritus is complete
6a04d4a8-3040-5525-9be7-3e8e4caabcb3 | note | Record documents (QCP - Quality Control Portal) - Site Diary
2b1a0734-a1af-5b1c-8195-bf1d448e4e9b | note | Responsibility - Paving Contractor
edadde4c-cefa-5cde-b506-15ce444204d5 | note | Eng. Rep / NZTA - I
9409898f-1dcd-5c98-9fd9-d0dd01d9006e | note | Contractor - R
407fba02-08ef-5699-958d-9c47c94b35c2 | checkpoint | 3.17 - Post Paving Completion Checks
17b45995-c2de-5104-a7ed-acc0bbb17610 | note | Detail of Activity / Test - Pavement Marking
13952a04-78fc-51f0-bb1a-028ca07ed2e1 | note | Action (Hold, Monitor, Witness) - W
adc833fd-48e8-5067-ad02-ec5bd43728bf | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
c9586197-390b-5903-aa3b-f027b4dd642f | note | Inspection / Test method - Visual
c5f41d11-5b91-59ee-96f9-197e8d52a93f | note | Acceptance Criteria - Roadmarking is complete
a9ed0788-f9a1-54bc-a316-1453afb4792e | note | Record documents (QCP - Quality Control Portal) - Site Diary
9d3c852b-9b24-5585-bfb1-29f5c6cfb108 | note | Responsibility - Paving Contractor
a3482e90-d6ba-52b6-b423-110d2366ae2c | note | Eng. Rep / NZTA - I
eb6ff85f-5868-5e5b-856a-2b8e60eca81c | note | Contractor - R
36703db0-c4cc-5ead-b664-ab50c10635e5 | checkpoint | 3.18 - Post Paving Completion Checks
b6b6f90a-8fb6-549f-bd3b-3788ce9abee9 | note | Detail of Activity / Test - Cold Joint Bandaging
80254a14-b7af-554c-add8-d97649051772 | note | Action (Hold, Monitor, Witness) - W
8c64414c-8d77-54c9-bf1c-c146bf9104e2 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
c0364a91-e507-5aeb-a331-b2909c018b1d | note | Inspection / Test method - Visual
40025b55-1c43-5460-9955-eeb305fb2504 | note | Acceptance Criteria - Cold joint bandaging is complete
c7eefd0a-7e1d-5c9e-af81-d56c893d9610 | note | Record documents (QCP - Quality Control Portal) - Site Diary
36463068-7e8f-5fad-a032-a450c19735e0 | note | Responsibility - Paving Contractor
1984778d-c536-559f-a8c9-f840fc0e3c60 | note | Eng. Rep / NZTA - I
ba4934d7-3d53-5309-89f4-135fe94d4ccf | note | Contractor - R
d3e6551d-a129-513b-967e-1769d0a7ba70 | checkpoint | 3.19 - Post Paving Completion Checks
6f187f73-0792-5510-b063-45c6851832ea | note | Detail of Activity / Test - Service Covers Checked
68b5e5c6-a91b-5129-a38e-1f8d7fb23734 | note | Action (Hold, Monitor, Witness) - W
1762dc0d-97b2-5cdf-9347-a7743d8a3efb | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
4defb7ef-df4a-5558-9874-c86f61eb8f88 | note | Inspection / Test method - Visual
4e26cb36-4755-53f3-ae49-2e30c610ef9f | note | Acceptance Criteria - Check that service covers are cleared and level with the pavement
8a77868c-f830-5c5a-be32-a2ed6d41d962 | note | Record documents (QCP - Quality Control Portal) - Site Diary
f8756dac-9b15-5f64-a0e3-af021138f38c | note | Responsibility - Paving Contractor
7c965098-4d50-510c-86a0-e02664cbb8ee | note | Eng. Rep / NZTA - I
5755ac51-7773-52c5-8a21-555b1c3a9121 | note | Contractor - R
381498b5-871e-56de-bba0-c3c7bd29cb5b | checkpoint | 3.20 - Post Paving Completion Checks
a476531d-603b-5cae-9a2d-c6a785443368 | note | Detail of Activity / Test - Traffic Loops Reinstated
27820b46-eb6e-5dd6-9c59-a77fb0fa8ab0 | note | Action (Hold, Monitor, Witness) - W
1548be5b-e04c-572f-afc7-0e04b509d526 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
836274b6-cd1d-5ff9-8291-9d074adecb16 | note | Inspection / Test method - Visual
3562fc5c-deac-5815-8f9c-faca5988b1b8 | note | Acceptance Criteria - Check that affected traffic loops have been reinstated
de231616-3bb1-5990-803f-a4fdc892ed01 | note | Record documents (QCP - Quality Control Portal) - Communication
4da8a842-a596-58ab-9564-7804bd05cd7f | note | Responsibility - Paving Contractor
9d94ba7c-4545-5825-b099-971abfcb9169 | note | Eng. Rep / NZTA - I
32b103b3-17fa-5c53-a431-b6b76db1b453 | note | Contractor - R
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
6d9903df-32cb-567a-9a07-e72d1c2d2523 | textbox | Contractor's Rep Name:
c8bd6bdf-30c3-5fec-91dd-6e886aabaa60 | textbox | Engineer's Rep. Name:
c5ab3705-a142-529e-9702-ff82d1353020 | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
3c437ff5-0380-5e7c-aa4d-37a2e54723ee | checklist | ITP - M10 Dense Graded Asphalt - Post Construction Rev 0 | itp | ITP - M10 Dense Graded Asphalt - Post Construction
00c5fd4e-c721-5091-9792-e7260336b98c | section | 4.0. As Built Records
eb9326c3-b830-539c-845a-0c560e957a4a | checkpoint | 4.1 - Assessment of all test results for conformity
3ef263db-8aae-54d9-b581-900e0420545e | note | Detail of Activity / Test - Review against ITP Requirements
efc6b8f9-a550-58d4-8c02-258ab8e249a9 | note | Action (Hold, Monitor, Witness) - H
a0dcd90f-afbd-52b9-b7f9-c9622e59f3e5 | note | Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project
da1f0f4c-b633-51ce-b18b-b9b1f12138f7 | note | Inspection / Test method - Review
fbe16547-d906-55b4-84ae-31f7ffa48c34 | note | Acceptance Criteria - Reporting of any non-conforming results to Engineer via NCR
0e9d2536-4a63-52fe-b7f9-2b426b3e3910 | note | Record documents (QCP - Quality Control Portal) - NCR
1e397c8a-f9f2-5f11-84eb-41b0abea218e | note | Responsibility - Paving Contractor
7fa37107-220d-5478-bdb6-a2f1e047ae5c | note | Designer - I
8cd1cb90-541a-5934-8a43-0265a9ef74e6 | note | Eng. Rep / NZTA - A
b04348cd-9650-59bd-a1d6-d2af8d8787a3 | note | Contractor - R
bae1816b-f7ba-5aaf-ad84-7c32829252e7 | signoff | AUTHORITY HOLDPOINT
45836d55-ec84-5341-8d97-fba59ddcda40 | checkpoint | 4.2 - RAMM pavement and surface records
71ae4c94-1701-543a-9c94-86b752b71f9d | note | Detail of Activity / Test - RAMM surfacing pavement data spreadsheet updated
58fd624c-ce3e-52b2-a9ba-62624eb8437b | note | Action (Hold, Monitor, Witness) - W
73d4444b-2a90-5b65-9867-a7f5bc37018a | note | Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project
aa871860-a8c1-5295-a526-b08fd5cd26b2 | note | Inspection / Test method - Prepare Data
35edda65-d953-5a02-afa4-481f623bb951 | note | Acceptance Criteria - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA
007e0b20-629e-5e9e-8978-7b543e8ffb5b | note | ○ Spray sheets for membrane area received by Contract Engineer from Sealing Team.
67ef7932-63ab-5b67-8852-059600693099 | note | ○ Surfacing layer extents recorded and verified by Contract Engineer.
ae0811ee-8ee3-5a32-a5a9-2e384a5fafbc | note | Record documents (QCP - Quality Control Portal) - RAMM Spreadsheet
9d1ae705-366a-5e99-8acd-bc027ef749cc | note | Responsibility - Paving Contractor
8bc0d294-03b9-513a-aac4-da8b831b8a4b | note | Designer - I
52e5cce6-4193-5b8a-b595-fe774d9634aa | note | Eng. Rep / NZTA - A
112ea26a-20b2-55fc-aaa4-f91b1491a352 | note | Contractor - R
d4139e43-70b3-5d8a-ac8a-641ccf9056aa | checkpoint | 4.3 - Paving Quality
42e69495-9e48-5b0d-89fb-cb09039259af | note | Detail of Activity / Test - Ride Quality - Wearing Course only
9f0f34dc-2171-52eb-9d85-7e223baa859b | note | Action (Hold, Monitor, Witness) - W
25a1464c-50e3-5568-b8e5-bdaa36521bd5 | note | Minimum Test Frequency (Lot = 1 day’s production) - Continuous every lane
13c12974-324d-5aab-918c-dc188e16a3ee | note | Inspection / Test method - NAASRA
95ebe006-ea34-545d-b2ee-866be8e3f91c | note | Acceptance Criteria - Max 100m Rolling Average 60 Counts/km
4548144b-0425-5ba4-a905-bd6dfefd9403 | note | ○ Max 20m NASSRA 70 Counts/km
c60cf560-9fb5-5b38-9e91-afeb8f6b60b8 | note | ○ Refer TNZ TM 7003 v1 (2006)
b15bb706-b09d-5b14-bfde-4e46f67c147e | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
0b3b7d6d-ed69-58dd-a909-6f92168b34d9 | note | Responsibility - Paving Contractor
8e5aec63-6eac-5940-8f10-60741816d790 | note | Project Specific Notes / Instructions - For structural mixes, refer clause 1.7 of this ITP - Hold Point must be observed on this layer before proceeding to a final Surfacing Layer
4bdbd333-003a-5f23-9365-a2edbe562005 | note | Designer - A
3443b1c1-6770-5227-905a-e1f2851e2967 | note | Eng. Rep / NZTA - I
9d0bd1d2-9325-5709-922b-25dfc64f4185 | note | Contractor - R
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
8b3a3a41-a12a-534a-9595-d374af476770 | textbox | Contractor's Rep Name:
6fa4fc8e-b828-50a0-a02c-bf44f7f2c87c | textbox | Engineer's Rep. Name:
1863b059-b32a-5bd0-9c02-326c9418f244 | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
d0078109-7434-5e90-a771-e4e7f37022f0 | checklist | ITP - M10 Dense Graded Asphalt - Pre Construction Rev 0 | itp | ITP - M10 Dense Graded Asphalt - Pre Construction
9aab8254-dcd5-5ba8-a67a-8a0e0e7591b2 | section | 1.0. Pre-Commencement Activities
846aee1d-ef5f-5136-afce-7c66dd76e096 | checkpoint | 1.1 - Approved JMF for Asphalt Base or Wearing Course
35210cd2-ab3f-52d2-aa1e-cbae54b4e61e | note | Detail of Activity / Test - JMF reference in here
1478cedb-0e86-51f9-9bfa-f5bbde5998df | textbox | JMF reference
672f620a-d1c5-5f4b-8da1-f8fadc003269 | note | Action (Hold, Monitor, Witness) - H
4be0d44c-2376-57e7-8711-0029b52964fd | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
5ee0b913-285d-58eb-86e2-ab992f302622 | note | Inspection / Test method - Confirm requirements are followed
74169f45-9f4a-57a0-9ec5-afaf19e9e889 | note | Acceptance Criteria - JMF Validated in accordance with NZTA M/10:2020
0a3438dd-9aa1-56a9-85b3-e19020f795bb | note | Record documents (QCP - Quality Control Portal) - Mix Design Report
29366633-88e1-5bd1-9c3f-24b6d5b37a7a | note | Responsibility - Paving Contractor
d041215b-a0d9-560b-8aa9-3068d05c3c29 | note | Project Specific Notes / Instructions - JMF expiry date and validation details in here
2f2ca765-0cbd-5de6-9857-f75c8fea6896 | note | Designer - A
6b0b3b11-15db-553c-a266-7b34d1a34d98 | note | Eng. Rep / NZTA - I
94905ef8-8049-525b-8849-44df16be7eb4 | note | Contractor - R
3fce116f-079c-5d20-bd96-71b331fb1bcc | signoff | AUTHORITY HOLDPOINT
728297c4-4011-53d8-b463-319a7422f4a0 | checkpoint | 1.2 - Site Conditions
24d8a3fd-49e0-5052-8d6b-a482361927d9 | note | Detail of Activity / Test - Weather suitable, Site extents marked, surface suitable for paving (Depths/milling/cleanup complete etc), Environmental Controls in place
5137779b-e802-5037-8922-228364bf94be | note | Action (Hold, Monitor, Witness) - H
98be39aa-a34d-594c-9b2a-746bd99b8d45 | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
7283f038-d775-552d-9d54-1d41a8be4b44 | note | Inspection / Test method - Confirm requirements are followed
9780d620-2bd1-56da-b215-d7f14ad4c99e | note | Acceptance Criteria - Weather conditions and Site is suitable for paving
3f87e560-870e-5593-bb4f-0abd50c321f3 | note | Record documents (QCP - Quality Control Portal) - Site Diary
588e3715-3d22-528b-adc3-60dc5c4a9a37 | note | Responsibility - Paving Contractor
9be71d1c-70ca-58c9-810f-9b0d4e1c2d4a | note | Eng. Rep / NZTA - I
8bd74bdf-05b4-5c4c-bc6a-3fd36f58d24f | note | Contractor - R
46db81eb-b8f1-5fd6-98ce-1a36924349d7 | signoff | AUTHORITY HOLDPOINT
a9cb1710-5e45-5f0b-a7a4-9bbfc60e78f9 | checkpoint | 1.3 - Roughness
6fd2e4a1-f382-5cf5-9fc1-8584e046c09c | note | Detail of Activity / Test - Previous layer checked for suitability to achieve Specified Ride
29e8b982-6c85-595d-86ee-3523455a5074 | note | Action (Hold, Monitor, Witness) - H
93afeefd-941c-59d5-86ae-cff43568c39b | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
67bed83d-f65b-5d46-9b75-591e5f18a819 | note | Inspection / Test method - Confirm Specified Ride requirements can be met
213833c2-9b6f-58b0-8c6d-a88eeaf470d2 | note | Acceptance Criteria - Site is suitable for paving;
5e52b2a3-787b-5d6b-8cd6-5f344b21630e | note | ○ The surface to be paved on must have a smooth longitudinal profile, and where a layer of Asphalt is to be placed over a previously constructed pavement layer, the ride quality must be confirmed with the observation of a holdpoint in the previous layer ITP.
38050ea0-c232-554f-9c0a-baee7b7e9cdd | note | Record documents (QCP - Quality Control Portal) - NASSRA Report
46ffa837-ddb4-5c67-ad9e-aaf92d5f4254 | note | Responsibility - Paving Contractor
50103030-4a5c-5cc6-a484-e29a8549c494 | note | Project Specific Notes / Instructions - Where FBS & Chipseal has been previously constructed ensure NASSRA is viewed and signed off as acceptable for paving
5aef6ae3-9b52-5971-9d19-1dfc9c0b462c | note | Eng. Rep / NZTA - I
de19352b-d84e-50f9-b9d0-18f19d705242 | note | Contractor - R
af3bbdba-014c-52a0-bb1b-90c717d8bbe9 | signoff | AUTHORITY HOLDPOINT
2d8eb3de-b771-57e1-8a0e-6b8c9f91e7ba | checkpoint | 1.4 - Traffic Loops
8453a2c9-de8f-5220-ae9f-09cf9949c4c9 | note | Detail of Activity / Test - Communication with affected parties
db68a601-6dce-51e5-a1ac-16572408846d | note | Action (Hold, Monitor, Witness) - H
83bf7659-4b7a-519b-83cd-e9d184994796 | note | Minimum Test Frequency (Lot = 1 day’s production) - Minimum of 7 days Before Works commence
b0369a38-90ba-5014-9134-3831c62c076d | note | Inspection / Test method - Visual
effbc94d-6166-5c7d-b420-97b8079e2933 | note | Acceptance Criteria - Notify RC at least 7 days before surfacing is programmed
c3f1980e-f8d0-536b-af84-235a6a465cb0 | note | Record documents (QCP - Quality Control Portal) - Communication
fd489ca3-7132-54a0-a500-19a699845b50 | note | Responsibility - Paving Contractor
7a516d26-34d3-5b36-961a-c732a2a51e6e | note | Project Specific Notes / Instructions - only required where existing traffic loops are present
37c83c1c-fd07-577f-96cc-ab1518b813ab | note | Eng. Rep / NZTA - A
e36a4d32-a825-521e-a074-07dffcc3d510 | note | Contractor - R
c406dae7-4f12-5ae0-8ea3-326a2e279662 | signoff | AUTHORITY HOLDPOINT
0fdc8ef1-2e43-5382-908f-b35bfa1f644c | checkpoint | 1.5 - Paving Plan
d62133cb-b43f-551e-a0ab-a9d6534e451b | note | Detail of Activity / Test - Paving Plan to be completed
3964343f-5ecc-5a59-ac68-4e368bf42c4d | note | Action (Hold, Monitor, Witness) - H
2830e935-ccbf-5e4f-baa8-acf50af47a39 | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
7a3f8fd4-9bcf-55a3-8f90-74e564fc88ae | note | Inspection / Test method - NZTA M10: 2020 Clause 9.5.1
5d4ff509-ddc3-560a-b8fd-5f8f9b3d271c | note | Acceptance Criteria - Paving Plan to be completed for each shift with dimensions, location and type of (hot/cold) joints, areas and tonneages
b7f3b4bb-0960-506f-8e92-d03cf3aa7910 | note | Record documents (QCP - Quality Control Portal) - String Sheet
dd27ff57-8e98-5123-a4d8-3955dcff7ddf | note | Responsibility - Paving Contractor
d5cc1000-383b-5410-98a6-ee7565e8bfae | note | Eng. Rep / NZTA - I
f57183b5-f0dc-51ee-af9d-96f37f3369ff | note | Contractor - R
c8cfc14b-5230-5eba-b1b7-bdc924f2cf5f | signoff | AUTHORITY HOLDPOINT
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
62f67ec1-dbbd-5c83-90d0-72eabf3b3c35 | textbox | Contractor's Rep Name:
6808396f-ef40-5895-9c86-c0fdefa1dc19 | textbox | Engineer's Rep. Name:
54121dfc-8310-59b8-aba8-01725ed0c2a3 | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
58e6e94c-9bf6-5ce1-a62b-6d031f130190 | checklist | ITP - M27 SMA - Construction Rev 0 | itp | ITP - M27 SMA - Construction
e37f64ad-2e1d-5892-9ad5-ee339d5a3957 | section | 2.0. MANUFACTURE OF ASPHALT
9ed5d845-4845-59b1-8427-9a3acc3b9c38 | checkpoint | 2.1 - Temperatures
0cd4ac54-3bf9-5659-ae4c-dcb57e730b07 | note | Detail of Activity / Test - Mixing of aggregates and bitumen
79f5fe9c-ad5c-54bd-bd71-db1bf5ba52e8 | note | Action (Hold, Monitor, Witness) - M
09715eb0-287e-5338-ad4b-7d7ee6878d37 | note | Minimum Test Frequency (Lot = 1 day’s production) - Constant monitoring of temperature by calibrated euipment
39ea361c-b7d1-5cee-a570-a7da92986f85 | note | Inspection / Test method - Plant temperature probes
b84c15d9-8167-5be6-8434-670246c9b650 | note | Acceptance Criteria - PG64 V/E (Flexiplus Bind) binder mixing range:
7be98896-7910-5630-9c3c-424baf24fa98 | note | ○ 170 to 190 deg.C
81eb6361-6c29-59b7-bdcd-ca04a97e3c27 | note | ○ NZTA M27: 2020 states max. 185 deg.C
51e2d031-09a7-5d5f-9ff5-7825a108ee1e | note | Record documents (QCP - Quality Control Portal) - Plant site diary
3dbbd397-f399-53f0-9253-b65b923f53e1 | note | Responsibility - Asphalt Manufacturer
27d4a62d-6ee5-5f05-9e48-e791a7207ab5 | note | Designer - I
893d5bbe-afb5-5023-b06e-bb1e6daf53dd | note | Eng. Rep / NZTA - I
a9bb2145-474c-52a8-ad28-ececab6bfec3 | note | Contractor - R
371b495f-cbbd-51d8-98fd-3096d0f2d646 | checkpoint | 2.2 - Production Asphalt
08cd0093-f987-5151-8a75-046814b175f8 | note | Detail of Activity / Test - Particle Size Distribution
21376612-221e-52d4-a6d8-e6930d5b6bbd | note | Action (Hold, Monitor, Witness) - M
dd132f88-dc04-576f-9ac0-d46c0fe2f6a1 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
9f462442-a88f-5c08-a30d-99927d35aa5c | note | Inspection / Test method - NZS 4407, Test 3.8.1
4cb6b721-ee80-5378-ae2a-cbae739014f7 | note | Acceptance Criteria - NZTA M27: 2020, Refer to Table 5.3
d2d94947-7d67-5030-876c-ada34cd2535e | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
2b9fc570-6962-5d60-a67e-f8e3864335e8 | note | Responsibility - Asphalt Manufacturer
c2ed2cc0-6dfe-5413-bd84-e1130364444c | note | Designer - I
8f26f2cc-582e-59fa-b140-1bd6ec607b52 | note | Eng. Rep / NZTA - I
ae159831-35b8-5ae4-b777-5cf47a4032a5 | note | Contractor - R
da6c9329-532a-54f2-9369-db8989f73e9b | checkpoint | 2.3 - Production Asphalt
fd110533-8ae4-57a3-a9e6-3d42d00c0f34 | note | Detail of Activity / Test - Binder Content
3281b770-c85c-5ede-abfc-371c18deea3c | note | Action (Hold, Monitor, Witness) - M
b4d9e48f-e041-5eca-ba0b-9633d14306cc | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
e4f03caa-9f95-57e7-98cc-1da1e9b227bd | note | Acceptance Criteria - NZTA M27: 2020
37f47e7b-3fa3-5017-b174-f2e5e6801a7d | note | ○ Individual Test Result: ± 0.5
d5983896-8500-518a-a84c-3721b8815445 | note | ○ Mean of Three Test Results: ± 0.3
c1e4913a-dc1b-5aab-b03c-6b4ab486235d | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
b348e82b-5187-5c11-9b48-472a6460bab0 | note | Responsibility - Asphalt Manufacturer
20de7409-2098-5e81-b9f8-5d8d28f9b3db | note | Designer - I
1f26de50-446e-5b90-843e-acff5409174a | note | Eng. Rep / NZTA - I
805a0e99-1078-5faa-939b-f8dd7afdcd9c | note | Contractor - R
d005f834-a3b6-51b4-8e32-d7fbf27a8fbb | checkpoint | 2.4 - Production Asphalt
62236592-1750-5265-922e-7c9b0b7684ab | note | Detail of Activity / Test - Max. Specific Gravity (MSG) of mix
cd03e55b-4107-5051-ad3f-ab33e2ed45b0 | note | Action (Hold, Monitor, Witness) - M
86e015a4-8df0-548c-ae1f-cd1eca43dc62 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 600t at asphalt plant
a04260ed-8637-56d3-911c-f004159b3ef9 | note | Acceptance Criteria - Report
bd3d62a8-16df-542d-ae52-1c23b88af8d8 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
c72a438a-6840-546f-b06b-5676b97ad2af | note | Responsibility - Asphalt Manufacturer
10d6c228-6361-5363-8a9f-2d357d4a7e34 | note | Designer - I
63fb9588-a2ff-5de3-839f-d29fb80b8bee | note | Eng. Rep / NZTA - I
5e0a70d1-e846-5028-99f8-fc5917aa6417 | note | Contractor - R
9680cc3b-0b4b-5394-9dff-da10e33d09d1 | checkpoint | 2.5 - Production Asphalt
2683bf23-7ef2-57f1-b4a1-c1e742847e5c | note | Detail of Activity / Test - Air Voids at lab design compaction
41f34f5f-bc19-5770-8312-e2fbfd264fb6 | note | Action (Hold, Monitor, Witness) - M
7a812efb-b830-55e4-b464-b3191fa74484 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 600t at asphalt plant
6bcec35f-76e8-5e87-945c-96860c730a8c | note | Acceptance Criteria - NZTA M27: 2020:
308316ed-bbc5-57fa-9699-8ca78bcbdcdb | note | ○ Individual Test Results: +2.0, -1.0
f00ff6c4-136a-5eba-8b37-4cc9bc344a45 | note | ○ Mean of Three Test Results: +1.2, -0.6
1a4c4ef8-1339-56f3-9c60-155778e06c98 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
1ec27d60-605b-56cf-bf7f-8b92ef5cac41 | note | Responsibility - Asphalt Manufacturer
11f9366d-99e7-5d36-b42a-1bc18e82a86b | note | Designer - I
d9fda4ed-9bbe-5694-903a-f682bea4c919 | note | Eng. Rep / NZTA - I
d771bb4e-d304-5c92-b973-9c2c351a9ef2 | note | Contractor - R
4ee242ad-877a-59da-9474-f2ca98f5c556 | section | 3.0. PLACING AND FINISHING
fa3cebdc-265b-5a4a-b405-b1aa87d1625a | checkpoint | 3.1 - Milling
7958113a-9765-5bc2-8c60-12a94e6182ca | note | Detail of Activity / Test - Surface strung to ensure milling Depth is achieved
204270c7-3ab0-59c4-900c-c38d4de3b2f6 | note | Action (Hold, Monitor, Witness) - H
e477147b-27e9-5708-a6a7-8ba42eb05a17 | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
d01358c0-b9db-5411-a445-92f41c614e05 | note | Inspection / Test method - Confirm requirements are followed
fa4762e6-7243-5bd4-9aa1-e132fc477926 | note | Acceptance Criteria - Site is suitable for paving
153bb9d5-09cd-5145-9b43-64f15f89ffe1 | note | Record documents (QCP - Quality Control Portal) - String Sheet
6307d789-5767-55bc-be77-89ed9bd45bbc | note | Responsibility - Paving Contractor
7fc06494-fbd5-550e-b77e-7b964bcbd19f | note | Eng. Rep / NZTA - I
f85a90b6-720b-533b-809b-06bc87812541 | note | Contractor - R
1e199791-51e5-500a-a6a5-bbb41684326c | signoff | AUTHORITY HOLDPOINT
c1901290-5afd-546e-88c8-0396896c848d | checkpoint | 3.2 - Tack Coat, OR
295e6b04-d906-5688-8670-68b0c204af2f | note | Detail of Activity / Test - Application of Tack Coat
27d35492-bb84-5609-a0e8-a76f92ae5177 | note | Action (Hold, Monitor, Witness) - M
5b4ec1d6-ca21-5365-9964-912ee3031462 | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
4a5744ea-e00c-51fa-821a-53ca80f864af | note | Inspection / Test method - Dip bitumen emulsion tank before and after
d8bbd130-edbf-536c-bde1-083d1653c803 | note | Acceptance Criteria - Target Between 0.2l/m2 - 0.6l/m2 +/- 0.1l/m2 From Target Application Rate
77265491-839a-567e-a184-7918ab3fe630 | note | Record documents (QCP - Quality Control Portal) - Site Diary
2521c130-3f51-56c7-8f8a-4bf3ec773a47 | note | Responsibility - Paving Contractor
c5fe5e71-2280-5d6e-ac42-0f70d2e295db | note | Designer - I
95e3f5a3-a654-5b86-87d8-dde518172bcf | note | Eng. Rep / NZTA - I
2339cee7-253c-54e9-af01-5b6c04d0c8f9 | note | Contractor - R
df0ed961-0b8e-50ef-9ab8-76aa993c07c2 | checkpoint | 3.3 - Membrane Seal
ca0622f0-599c-5091-b983-74af38784a43 | note | Detail of Activity / Test - Application of Membrane Seal
79807ca4-b0ea-5d52-bbde-b4ead0643f0d | note | Action (Hold, Monitor, Witness) - M
5ba5e0e1-d113-52e3-ad46-e0ab429b550e | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
9d07c0c6-557f-5577-8a0b-c564eb9faf70 | note | Inspection / Test method - Sealing Records
a9b37050-877e-5d62-b045-201c4d4c49b3 | note | Acceptance Criteria - Application rate, chip type and binder as per membrane seal design
e47c8255-53b8-5af5-8abf-3a93a8432882 | note | Record documents (QCP - Quality Control Portal) - Sealing Records
c6b3ead4-cc4d-545f-be1f-1c4332d40c19 | note | Responsibility - Paving Contractor
677cefbd-3d65-5c69-b0ab-0aff868d6dce | note | Designer - I
c95149bf-8e1f-5193-9f30-192c5b801cb6 | note | Eng. Rep / NZTA - I
cb7615e8-e9b5-55b4-8117-ae414a3888fe | note | Contractor - R
0daedfae-4bad-5421-a834-ad22dcfca3c4 | checkpoint | 3.4 - Temperature
b801aea5-d6d3-5e55-85c2-fcbcfe2f0e7b | note | Detail of Activity / Test - Pavement Surface
cc9b929b-361b-5b21-b4c8-6473c5e83589 | note | Action (Hold, Monitor, Witness) - M
1358d814-c9b0-55e3-bb3d-ebd1ae547923 | note | Minimum Test Frequency (Lot = 1 day’s production) - Start of shift and every 1 hour until temperature rising
5ebf5868-86c8-5604-a504-4454e021e3fb | note | Inspection / Test method - Infrared gauge
fc22a6db-0d63-5ce7-b43a-79b15da8cf58 | note | Acceptance Criteria - ≥ 10 °C or as otherwise agreed with NZTA
8585945f-3beb-5c81-a0d1-5554ea2dcb1e | note | Record documents (QCP - Quality Control Portal) - Site diary
84d2d25d-86a3-5166-9897-9032f566620b | note | Responsibility - Paving Contractor
417ff4c4-ca68-58c3-905b-a2f10c73e9e8 | note | Project Specific Notes / Instructions - Must get NZTA approval if < 10°C
43173c85-509b-547d-ace1-cad4a05af6c5 | note | Designer - I
84871fe9-2fb7-5475-8b0b-caa163f405bb | note | Eng. Rep / NZTA - I
cdd2ab80-a082-58c7-8972-8bd8bbda641f | note | Contractor - R
a636365a-b32b-5a0f-be50-623afca95fe8 | checkpoint | 3.5 - Temperature
95494348-1e26-5636-8767-4c9f01ad32f9 | note | Detail of Activity / Test - Asphalt Delivery temperature
a926bf91-28df-5061-a7ba-403512c05558 | note | Action (Hold, Monitor, Witness) - M
b1d0f28c-8f1c-52b4-8bbd-288d43c92c7b | note | Minimum Test Frequency (Lot = 1 day’s production) - Every Load on delivery to the Paver Hopper
c8d64bf7-bd35-518e-9360-5bda3702f8fc | note | Inspection / Test method - Temperature Probe
af628963-8429-578a-a302-833bfd0f377e | note | Acceptance Criteria - Target ≥ 150 deg.C. in the Paver
a82fbdc0-ae5d-5fc4-a430-185ec46a6b62 | note | ○ Min. ≥ 130 deg.C in the Paver
2e68acef-dfde-52de-8901-3f5e43a63c00 | note | ○ <130°C to be Rejected
17d9a730-75f2-56db-b481-5e9141c56454 | note | Record documents (QCP - Quality Control Portal) - Site Diary
0011a71e-c912-5184-ba58-e1e8fb508226 | note | Responsibility - Paving Contractor
78dde585-226e-58f7-a25c-fab807ed1696 | note | Designer - I
430a7b21-332e-5c4c-8307-3883504e0e7a | note | Eng. Rep / NZTA - I
2e2f16b4-da89-5f3d-b199-b6945067a238 | note | Contractor - R
fc27c880-a17c-5bed-a0b4-ac7a516aee69 | checkpoint | 3.6 - Temperature
d1f816cc-99c2-5e2b-9e7e-2293073e9882 | note | Detail of Activity / Test - Compaction Temperature
e05ce69b-7835-5ed6-bef9-cd9eac8268ab | note | Action (Hold, Monitor, Witness) - M
8cfba789-42d4-5ae0-ad59-9377e2d1c144 | note | Minimum Test Frequency (Lot = 1 day’s production) - During compaction
15d45c0f-efa3-51cd-8106-0d1149488995 | note | Inspection / Test method - Temperature Probe/Infrared gauge
2db86b40-cc23-544a-be62-bbc7c16fc07b | note | Acceptance Criteria - ≥ 125°C at commencement of compaction. < 80°C - Stop Rolling
6f642ca1-d772-5b48-94f1-ec8e9a83f209 | note | Record documents (QCP - Quality Control Portal) - Site diary
706bd2c1-adc8-5253-a59a-eccd07d2b44b | note | Responsibility - Paving Contractor
7eb5426d-9c46-511a-95ab-e79a4578b832 | note | Designer - I
9c96ce96-dde5-50ff-8adc-14fa32160749 | note | Eng. Rep / NZTA - I
b00cb0ea-53c2-5065-83f4-30f3666d58ec | note | Contractor - R
2958dd76-c13f-500e-b3c1-c072d547f681 | checkpoint | 3.7 - Mat
43e04df9-2055-5797-b3ef-540a568897ea | note | Detail of Activity / Test - Load Locate
a1b69dea-73d2-5497-95cb-ae6df75d9142 | note | Action (Hold, Monitor, Witness) - M
2879cea4-3d99-5794-b2d6-7e5b1687600d | note | Minimum Test Frequency (Lot = 1 day’s production) - Each load
047800bf-ab8e-5e14-bef2-4a8adb315d25 | note | Inspection / Test method - M/27
231f224d-83ea-5497-8534-f38743985028 | note | Acceptance Criteria - Each load can be indentified to a location using a diagram. Record includes:
65d26546-a924-5a5b-88ea-97e0177ee399 | note | – Truck ID/Rego/Driver
7e80e918-2121-5b7a-9c34-eddf70631acb | note | – Depart Plant Time
1d5f80ab-1131-5a41-a96e-3f78016607d9 | note | – Arrive Site Time
c0f76eb8-e6fb-56a5-a8f4-753152222032 | note | – AC Temp on Arrival
9b3b69c5-611a-5908-bdb1-3286eb3e69fb | note | – Tonnage
1ea10510-fb0c-5d3c-bec2-6104918d51d3 | note | – Run Width
62a2e452-bb19-5e88-b2a0-fab43c5f8b74 | note | – Estimated Run Length
9a267892-4964-58fb-85d2-43387584c63c | note | – Calculated Area
3f4144c6-335f-5a89-b778-0dcf3713b17f | note | – Calculated Average Depth
10729f31-6e09-5cc0-a273-b9317a47a403 | note | Record documents (QCP - Quality Control Portal) - Paving Run Sheet
0a490bee-4c70-511b-832a-eea8b5719a90 | note | Responsibility - Paving Contractor
a0e6e892-8a14-54cc-a9bd-e397f7acdd0a | note | Designer - I
98728f0e-8dda-51e1-8b58-015385d5dc57 | note | Eng. Rep / NZTA - I
c6e354ef-6f2f-5f39-94d1-e5f14ba5bf8c | note | Contractor - R
2dfb52ca-11cc-51fc-874c-1a8a1bb99335 | checkpoint | 3.8 - Mat
ddf0002b-1575-54f7-9c1b-46193960a781 | note | Detail of Activity / Test - Thickness Monitoring
81d71a09-a20c-58c5-af75-e8ba77d7b789 | note | Action (Hold, Monitor, Witness) - M
90f58dfe-1fd7-50d4-9927-c45de0842212 | note | Minimum Test Frequency (Lot = 1 day’s production) - Continuously
debe9aa1-8b51-5274-90ea-23637c061755 | note | Inspection / Test method - Dipping
1aec5965-001a-5eec-9c07-7936ab8900c5 | note | Acceptance Criteria - Target Loose Thickness -0mm / +10mm
593ac737-1d58-5000-a8fb-d8b89402f9d4 | note | Responsibility - Paving Contractor
027a4183-5a0e-52dd-b6ba-4fcb2c479ffe | note | Designer - I
f21c3ae1-d08d-5eb2-a87b-d56cb238e8e8 | note | Eng. Rep / NZTA - I
c8c7e810-919c-5dda-aa36-155bdc93d117 | note | Contractor - R
bc1d43ab-1cea-564d-af06-6d166c441d88 | checkpoint | 3.9 - Mat
83990351-386b-5e8f-afd7-10fa0fdb1510 | note | Detail of Activity / Test - Compaction - NDM
b68e4b40-0632-5fa0-b20e-c4b907fe35bf | note | Action (Hold, Monitor, Witness) - M
0f90478d-7e96-52ee-98f8-ccc0a5635c79 | note | Minimum Test Frequency (Lot = 1 day’s production) - Plateau to be completed on 1st run, thereafter monitor compaction/roller passes to achieve target density.
aa550475-a7ae-5c8f-b4ec-55f44a45c07a | note | Inspection / Test method - Insitu density and air voids
d25419ef-3e9a-5675-b8e6-d5d5498cffd5 | note | Acceptance Criteria - NZTA M/27: 2020 - section 9.9
9313ddc4-7a37-541e-b2cb-c48754b65b20 | note | Responsibility - Paving Contractor
9153595c-9203-5d89-b630-6a8e69e896a7 | note | Project Specific Notes / Instructions - Use a calibrated NDM with established core correlation. Locate and mark cores, record NDM Bulk density by core location (including any offset used).
8fd27ec3-529b-586b-b97b-bb68b0a18f3e | note | Designer - I
bba983f6-d53b-5ae9-8619-7f6eb18087ca | note | Eng. Rep / NZTA - I
abc0fe91-6461-5c8f-afec-79b0dac9ad7f | note | Contractor - R
615f2750-e1a1-5ab6-b4ac-f904650a9e16 | checkpoint | 3.10 - Mat
08f036b7-a26d-54c3-87e0-3e0db87495f8 | note | Detail of Activity / Test - Compaction
9e817b5c-9a3f-5897-88bc-27a8c8119b1a | note | Action (Hold, Monitor, Witness) - H
a92d60a1-1244-5de2-b7ee-92389714be64 | note | Minimum Test Frequency (Lot = 1 day’s production) - Mat: 1 per 300m2/min. 8 per Lot Joint: 1 per 100m/min. 3 per Lot, In the event of a day's production being > 30t but < 2400m2, then it will be permissable to reduce the number of cores to; Mat: 1 per 300m2 with a minimum of 4 per Lot, and Joint: 1/100m with a minimum of 3 per Lot
48a64f1e-5c1a-5b44-a502-aa7ddba0f749 | note | Inspection / Test method - Insitu density and air voids
a8f881fb-e9a8-5bf4-8ee2-abe88195b773 | note | Acceptance Criteria - NZTA M/27: 2020 - section 9.9
eda42a1e-2830-593c-b4e6-8f9f4a3b24c7 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
1abb13c6-a568-51d0-b6d1-884892428127 | note | Responsibility - Paving Contractor
789ff348-867c-5c53-a332-36d5d1708eeb | note | Project Specific Notes / Instructions - A pavement lot shall be an essentially homogeneous section of work completed within a shift of production.
ecb433cd-3d67-5ad8-aba3-250b609a80b5 | note | ○ The lot shall be divided into an appropriate number of approximately equal sub-lots and a core shall be taken randomly within each sub-lot. The Engineer or their delegate shall use a random method for locating each core position, such as ASTM D5361 or a similar process.
92fbe534-14cc-563c-8683-879f627e3737 | note | Designer - A
4b14b51f-e4e8-5a71-99e2-4f594ad925d3 | note | Eng. Rep / NZTA - I
8eb90c77-80a7-5d8b-bf2e-47304058b7ba | note | Contractor - R
5acec208-2386-5bba-9d2d-6780bed52aed | signoff | AUTHORITY HOLDPOINT
6198ba65-6fd7-5465-beba-32845e3f5a5d | checkpoint | 3.11 - Mat
14f178f6-20f9-56a4-a548-08319effbb2f | note | Detail of Activity / Test - Thickness
a467aabd-400c-5294-bc24-2d98a592b9d2 | note | Action (Hold, Monitor, Witness) - H
9e5906d5-e984-5c90-9ef9-7e36153b0453 | note | Minimum Test Frequency (Lot = 1 day’s production) - Average of 4 measurements per core
b2656095-38c9-5242-9e98-1457679629ec | note | Inspection / Test method - Measure Cores
d9e65025-dea8-5891-980a-ace4381534cd | note | Acceptance Criteria - LCV ≥ Specified Depth
05f5dfea-e27e-5310-b143-b6f01f8b2602 | note | ○ NZTA M/27: 2020 - section 9.7
23a86083-f8d4-5804-95e9-67f60bc28243 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
607abb37-bcea-5c8f-bcd8-d2fa031c86a2 | note | Responsibility - Paving Contractor
43d74561-e00a-5656-8a8d-b9dff4800b14 | note | Designer - A
6956c640-c3ce-5f6e-957c-fa58deee0ee9 | note | Eng. Rep / NZTA - I
d3188e7f-2f47-5d0d-a447-03f0e6109b1c | note | Contractor - R
25efa1fd-9d50-52dc-8d57-44ee0879215b | signoff | AUTHORITY HOLDPOINT
dc746dc5-1a53-536d-a625-2a8c137d686d | checkpoint | 3.12 - Mat
51b9e6f8-1678-57ae-86e6-b96f782b9277 | note | Detail of Activity / Test - Shape
460715c0-a852-5a32-befb-39f9b706f539 | note | Action (Hold, Monitor, Witness) - M
24966c87-d23a-57e0-b7da-8c1a8b4dd957 | note | Minimum Test Frequency (Lot = 1 day’s production) - Continuously
5a0e71c4-ca9d-57d3-95f2-dec53fd4f983 | note | Inspection / Test method - 3m Straight edge
4115f144-f2ee-5df5-bbe3-e0f3c1531051 | note | Acceptance Criteria - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Refer NZTA M/27: 2020 - section 9.8.
0568b0ee-0910-5b2b-856d-27d6a89df412 | note | ○ Not more than 5mm under a 3m Straight Edge.
76d61491-96df-54fd-bf55-cb213a55b364 | note | Record documents (QCP - Quality Control Portal) - Straight Edge Record
f0b6816e-7db4-5b30-b8ef-4eeaa7fd3a87 | note | Responsibility - Paving Contractor
b704fddc-98c5-5c27-baf5-bc0e8d8764df | note | Designer - I
97059a4f-ff85-560d-b71c-048bbffd35df | note | Eng. Rep / NZTA - I
c006f7ea-414d-5cb2-9204-6bc9f108fa71 | note | Contractor - R
ce641ca5-a4cd-5426-aa9c-a3d11eed951b | checkpoint | 3.13 - Paving Quality
701a9a98-7727-5044-8091-3afa7e1038c2 | note | Detail of Activity / Test - Texture
f771032c-6398-5ca6-9446-a5537aa98d39 | note | Action (Hold, Monitor, Witness) - M
bdfc6168-272f-5103-8a2b-26f97f1d1d41 | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
f08cfa53-5367-5279-a1c2-959635bef323 | note | Inspection / Test method - Sand Circle or HSD
9b43bfc3-7328-5aa2-b4dc-a59d7ee8951d | note | Acceptance Criteria - NZTA T/10: 2013
20d5379e-98d8-5031-8c6b-4c807dd87991 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
ee1cce4f-3d4c-53af-b6a3-9b3a941b9d36 | note | Responsibility - Paving Contractor
49f0c9c4-99c0-586c-9b32-ccabece52574 | note | Designer - I
b874ce3d-95a4-52e9-bb9b-1d7166500fea | note | Eng. Rep / NZTA - I
e7144423-2995-5316-a681-46c02302ed32 | note | Contractor - R
eb6303d9-2fd7-5668-89d7-0b3543df30e9 | checkpoint | 3.14 - Paving Quality
585ac5f1-d6dd-5b3d-b19c-daf0a96f370c | note | Detail of Activity / Test - Level
264221ae-05df-5220-a40a-d052a5fd9e9f | note | Action (Hold, Monitor, Witness) - M
b7e93a2e-4f55-587b-a8dc-ed7066972b02 | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
a0265243-6033-5f22-be62-d5875de5f3a2 | note | Inspection / Test method - As Built Survey
d0c5dd86-2838-5197-9833-dee4a7b24458 | note | Acceptance Criteria - -0 < +5mm from Specified Level
13821854-3ed6-59bf-8475-7b8ef868db5d | note | ○ Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC.
fcf98dab-2758-5ce1-88fd-ca6b89d278f4 | note | ○ NZTA M/27: 2020 - section 10.2
8342bca5-55a1-595f-b719-155885f770ba | note | Record documents (QCP - Quality Control Portal) - Survey As builts
1ddab218-3519-5655-a977-a1440bab84e2 | note | Responsibility - Paving Contractor
3b1f2e09-1573-5f7d-803f-425209bbed6b | note | Designer - I
660aae3c-23e9-55f3-a47c-b879f371c8e9 | note | Eng. Rep / NZTA - I
38b99f87-4552-5b63-aee2-5d8c189e145c | note | Contractor - R
b4580cdb-399d-5c04-8475-ef9a0e00367a | checkpoint | 3.15 - Paving Quality
10cf96d4-f49e-577c-b33b-6bd247e7c8e4 | note | Detail of Activity / Test - Alignment
cf16fd56-515f-591b-9223-d3de732385d0 | note | Action (Hold, Monitor, Witness) - M
9b7cb835-45bc-5bc7-a430-190626a25de5 | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
0c99eec0-db51-5668-afae-8f34ea8a42cb | note | Inspection / Test method - As Built Survey
d7932955-397b-534a-9f98-c84349d60869 | note | Acceptance Criteria - ±50 mm from drawings
081d84b2-b0dd-5e38-bb15-28da6e71f707 | note | Record documents (QCP - Quality Control Portal) - Survey As builts
059c086c-48d2-5679-b8f3-e1e4fcb43c21 | note | Responsibility - Paving Contractor
14d5160c-86f4-5375-bd4c-64b0f2138829 | note | Designer - I
6bdd9a15-81eb-5daf-8420-b115701aa8f7 | note | Eng. Rep / NZTA - I
0cb43704-a9bb-512b-ad83-90ce6066daf9 | note | Contractor - R
00105797-510f-56ba-ab8d-1222cda60376 | checkpoint | 3.16 - Post Paving Completion Checks
2a86eb1b-771b-5c3f-9dc7-5529a12118b4 | note | Detail of Activity / Test - Site clear and cleanup
6aa22827-b62a-57cf-a439-68cd9c0a31f5 | note | Action (Hold, Monitor, Witness) - W
306275b4-8f9c-5285-abfe-1e72c225ef1e | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
fb376a1e-f2c7-50e4-a2f4-90defa7bae58 | note | Inspection / Test method - Visual
5de72337-493e-5ea3-b893-aea2df6c91ed | note | Acceptance Criteria - Site is cleared of plant (or parked in safe location) cleanup of all waste mix, paper and detritus is complete
094dad04-277f-5d15-a0d5-890d9557ba79 | note | Record documents (QCP - Quality Control Portal) - Site Diary
7bdb085c-09d4-5df6-bedc-02eb6ebfe386 | note | Responsibility - Paving Contractor
0895e8e1-11b5-5a18-9c8a-7a692ff6e145 | note | Eng. Rep / NZTA - I
164fa66d-fda9-5328-acad-59073e62ccf6 | note | Contractor - R
407fba02-08ef-5699-958d-9c47c94b35c2 | checkpoint | 3.17 - Post Paving Completion Checks
dc48e937-4fad-5713-a7f9-21deb5ef472d | note | Detail of Activity / Test - Pavement Marking
850eeaa8-d864-5500-b8bf-28aed0ebe042 | note | Action (Hold, Monitor, Witness) - W
72ad566f-bf8b-5e83-8cfe-b9ceee2e3072 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
bba088a9-33fc-554b-83bf-d4ec14e13abb | note | Inspection / Test method - Visual
f56c689e-ebd5-586d-bd02-21da8daa35b5 | note | Acceptance Criteria - Roadmarking is complete
edc55174-e962-5ed9-8dc8-1f8df0e51bca | note | Record documents (QCP - Quality Control Portal) - Site Diary
f63761bb-f940-5837-ab1e-5d836d2866e2 | note | Responsibility - Paving Contractor
e5508c69-6950-5ea2-b1c9-f24a46c276de | note | Eng. Rep / NZTA - I
fd3f74a1-07b8-5feb-abe8-70a668ccd97a | note | Contractor - R
36703db0-c4cc-5ead-b664-ab50c10635e5 | checkpoint | 3.18 - Post Paving Completion Checks
dd78112e-4eee-5d04-9c87-0bef3d239fdc | note | Detail of Activity / Test - Cold Joint Bandaging
4f41afd9-6ac6-5e53-90b2-aef3a374aab0 | note | Action (Hold, Monitor, Witness) - W
98fd7802-5da2-595c-856c-91d2a3e9b04c | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
3f49cbf9-e7f6-572d-8bc5-cc2c771082ce | note | Inspection / Test method - Visual
62ef8be8-7604-5a33-8b06-e41c4c522d44 | note | Acceptance Criteria - Cold joint bandaging is complete
d5adf5bd-b6f4-522d-84d9-843d90f91abe | note | Record documents (QCP - Quality Control Portal) - Site Diary
1d8fa841-a102-514d-974d-6726b1bee660 | note | Responsibility - Paving Contractor
44207757-71bf-507e-bc26-5ea2782ba9c1 | note | Eng. Rep / NZTA - I
a95899c3-0014-51ae-b4c8-1e75d2cb195f | note | Contractor - R
d3e6551d-a129-513b-967e-1769d0a7ba70 | checkpoint | 3.19 - Post Paving Completion Checks
39fd6b61-c54b-5c0f-839a-d53d9a641ac9 | note | Detail of Activity / Test - Service Covers Checked
b44df150-20c7-564f-9d87-051608fb0b9e | note | Action (Hold, Monitor, Witness) - W
edd20dd1-b2cf-5ffc-b9b2-d9f30bf1d682 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
4f760552-3796-5cc3-94bf-2e9677a3c62e | note | Inspection / Test method - Visual
81705233-2ce8-55c6-bd41-2c6726072bcc | note | Acceptance Criteria - Check that service covers are cleared and level with the pavement
f42299e2-b0c4-5471-a81d-498ec2527bc2 | note | Record documents (QCP - Quality Control Portal) - Site Diary
421ea3a5-68df-5bea-871c-4a16c1e465d4 | note | Responsibility - Paving Contractor
6f75a20c-839c-5973-8a7c-1bff282fe5e2 | note | Eng. Rep / NZTA - I
76a3ea7c-260c-57f7-9bc4-b569bea30172 | note | Contractor - R
381498b5-871e-56de-bba0-c3c7bd29cb5b | checkpoint | 3.20 - Post Paving Completion Checks
d0ce6099-40ba-55d0-8ab0-7e9c0cdd8c62 | note | Detail of Activity / Test - Traffic Loops Reinstated
0e26e707-9f64-58a6-be0c-fdd77162707e | note | Action (Hold, Monitor, Witness) - W
10f1f7eb-05d4-59ad-87b4-f031387a70d7 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
cd1477c1-5b5f-5901-8495-fd9bf8a73d48 | note | Inspection / Test method - Visual
ea582cde-5c7a-5dcc-98a5-b79576cfa0a0 | note | Acceptance Criteria - Check that affected traffic loops have been reinstated
d6007bc4-39bf-5a9f-a73b-4d98ac6907e0 | note | Record documents (QCP - Quality Control Portal) - Communication
da647790-4242-5a0d-a5b2-838fa262e1af | note | Responsibility - Paving Contractor
8924b63f-c6f1-5eb9-b513-c8b45aeaa1b5 | note | Eng. Rep / NZTA - I
1a13f939-cb72-5b8e-a981-53933384c052 | note | Contractor - R
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
16d6a162-dc2f-5f6f-8a0e-89cea6883b00 | textbox | Contractor's Rep Name:
44cb92ed-8f15-5776-b33e-4811f5dd5390 | textbox | Engineer's Rep. Name:
67496dc8-b3aa-5205-9883-ae15ca3c20cf | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
2c38746e-654f-52f4-897c-dbf64d197770 | checklist | ITP - M27 SMA - Post Construction Rev 0 | itp | ITP - M27 SMA - Post Construction
00c5fd4e-c721-5091-9792-e7260336b98c | section | 4.0. As Built Records
eb9326c3-b830-539c-845a-0c560e957a4a | checkpoint | 4.1 - Assessment of all test results for conformity
a7ba25ed-ffa0-5763-9e71-20211ea509ea | note | Detail of Activity / Test - Review against ITP Requirements
ea48fc14-059d-5886-be4e-5fcd73990697 | note | Action (Hold, Monitor, Witness) - H
b5a07cca-1fa7-5fbd-ad4d-cbfa66f8d8b9 | note | Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project
8a51a882-494a-5d27-8119-714a084c3d21 | note | Inspection / Test method - Review
b40c3036-6a82-536b-8754-e28666200563 | note | Acceptance Criteria - Reporting of any non-conforming results to Engineer via NCR
473c1c35-11d0-5ea6-9bbd-630e539434d4 | note | Record documents (QCP - Quality Control Portal) - NCR
46adebeb-6800-58c2-8707-1e93379583c7 | note | Responsibility - Paving Contractor
5faa5bee-ad26-581b-9796-0f722a2277a1 | note | Designer - I
5b118c71-cab9-5bc3-a4cb-f93ee0a13ab2 | note | Eng. Rep / NZTA - A
6911fe09-f0c4-5f5a-83fb-8bd03211558b | note | Contractor - R
bae1816b-f7ba-5aaf-ad84-7c32829252e7 | signoff | AUTHORITY HOLDPOINT
45836d55-ec84-5341-8d97-fba59ddcda40 | checkpoint | 4.2 - RAMM pavement and surface records
be50487b-0cfb-5834-bbbf-67136aa26782 | note | Detail of Activity / Test - RAMM surfacing pavement data spreadsheet updated
bfdd4e3a-ba39-5a81-8ab6-c3a1f629691d | note | Action (Hold, Monitor, Witness) - W
8f4b9c27-a234-5063-bb92-057cf403ec1f | note | Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project
22cff86b-56e6-57fe-9245-2bd460401d29 | note | Inspection / Test method - Prepare Data
b0ec2140-beb2-5e41-b98d-9ec1faf805f1 | note | Acceptance Criteria - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA
cc51525c-bac8-5f24-ae0a-683cbffa43c4 | note | ○ Spray sheets for membrane area received by Contract Engineer from Sealing Team.
3dee4949-59fc-555d-a5cb-0eda09f02a63 | note | ○ Surfacing layer extents recorded and verified by Contract Engineer.
989292d3-7031-57e5-96dd-aa3d76201fd1 | note | Record documents (QCP - Quality Control Portal) - RAMM Spreadsheet
46ac8207-26ca-55d8-982b-d9b1b20b1e0e | note | Responsibility - Paving Contractor
97110584-a1a9-5010-8bbb-cf50ed1c3792 | note | Designer - I
308c43b6-1ac4-5ca8-9f0c-5381c38bf23c | note | Eng. Rep / NZTA - A
ac58df6a-038d-59cc-a6fb-02c7e1e1c4f0 | note | Contractor - R
d4139e43-70b3-5d8a-ac8a-641ccf9056aa | checkpoint | 4.3 - Paving Quality
a35426e9-f039-5270-8fce-a88d38d8e44b | note | Detail of Activity / Test - Ride Quality
9e12baec-974b-5dd9-ab38-cc035f694c59 | note | Action (Hold, Monitor, Witness) - W
79cee824-1c30-57dd-acc5-78a84248b7f2 | note | Minimum Test Frequency (Lot = 1 day’s production) - Continuous every lane
81c585d0-4034-52a4-b9ce-ba7c92102b29 | note | Inspection / Test method - NAASRA
1771826e-1eff-5f70-9245-51a5cc3f0056 | note | Acceptance Criteria - Max 100m Rolling Average 60 Counts/km
90558d50-b49e-5486-bdb1-5f5fd2008902 | note | ○ Max 20m NASSRA 70 Counts/km
b5282304-6322-581a-be8e-fb6b19b2e060 | note | ○ Refer TNZ TM 7003 v1 (2006)
aedd6fe3-4e96-5e72-b443-9c1084515949 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
418f70c5-b3e5-5f87-b16a-e4b47cb43904 | note | Responsibility - Paving Contractor
b3428100-776b-5b01-b64c-5eb28a4ab30a | note | Designer - A
68802d0a-c261-5c53-b27a-3c6b993afdf5 | note | Eng. Rep / NZTA - I
5503b952-f057-5f3c-81fb-07fe6ab57485 | note | Contractor - R
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
d9ce165b-b392-5655-931b-be0e778ac4a0 | textbox | Contractor's Rep Name:
18f20f88-0f0c-5d97-bb29-e007da1a4902 | textbox | Engineer's Rep. Name:
7808c2dd-a676-54e8-a568-11c665c16fcb | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
cc84ddac-51e3-5ec0-be8e-f55a28d8d229 | checklist | ITP - M27 SMA - Pre Construction Rev 0 | itp | ITP - M27 SMA - Pre Construction
9aab8254-dcd5-5ba8-a67a-8a0e0e7591b2 | section | 1.0. Pre-Commencement Activities
aad4a963-7f20-5656-834c-d2b95167f8a8 | checkpoint | 1.1 - Approved JMF for Asphalt Surfacing
50ccb1aa-ecb4-5cee-9c70-c854c68ca7c6 | note | Detail of Activity / Test - JMF reference in here
29c5445c-4e2b-51c3-b322-65641610e4f7 | textbox | JMF reference
d1be4c5f-651d-57bd-a230-1bf6abf0376f | note | Action (Hold, Monitor, Witness) - H
5470bfc2-cbdb-5082-a19a-ca3305cee857 | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
373ec5ce-67ba-5c31-881a-4695b20b8696 | note | Inspection / Test method - Confirm requirements are followed
19cda169-2ddd-5052-81f5-c2744fb64eb3 | note | Acceptance Criteria - JMF Validated in accordance with NZTA M/27:2020
9ebee7f5-30ca-5572-b480-85decea80fa1 | note | Record documents (QCP - Quality Control Portal) - Mix Design Report
65715bf0-bde3-54ee-a2f8-90351ab7aa17 | note | Responsibility - Paving Contractor
47970d18-3802-558f-bcb1-c75dca978d1b | note | Project Specific Notes / Instructions - JMF expiry date and validation details in here
94a5d9ab-774e-5ea2-8bb6-52160b873195 | note | Designer - A
f43c6a40-349e-5f4d-a787-5ca50ca772d0 | note | Eng. Rep / NZTA - I
7bdd9c4d-af11-5a5b-90f2-e5e8759c356b | note | Contractor - R
70d0f527-86f6-5f09-a5e0-3d99d26a6b56 | signoff | AUTHORITY HOLDPOINT
728297c4-4011-53d8-b463-319a7422f4a0 | checkpoint | 1.2 - Site Conditions
c733034e-333c-5b61-9b45-02ae951631a5 | note | Detail of Activity / Test - Weather suitable, Site extents marked, surface suitable for paving (Depths/milling/cleanup complete etc), Environmental Controls in place
bebbdbdd-7c65-5eda-9b6c-f6d655e1ed7e | note | Action (Hold, Monitor, Witness) - H
9d298616-cfa7-5ec4-afeb-80f72c538186 | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
3fa8204d-3289-5099-b20b-16854537f644 | note | Inspection / Test method - Confirm requirements are followed
4422bfae-34e2-5591-80d0-29d3e01ad784 | note | Acceptance Criteria - Weather conditions and Site is suitable for paving
e41fdd93-d48b-5376-8392-e7cc90d51686 | note | Record documents (QCP - Quality Control Portal) - Site Diary
23ef008d-9af4-5293-a46a-2a956192d126 | note | Responsibility - Paving Contractor
b3613384-c931-5bc2-8008-2a9f46e05413 | note | Eng. Rep / NZTA - I
7fb7e3ec-b68b-585f-b1e6-ccbd34be788a | note | Contractor - R
46db81eb-b8f1-5fd6-98ce-1a36924349d7 | signoff | AUTHORITY HOLDPOINT
a9cb1710-5e45-5f0b-a7a4-9bbfc60e78f9 | checkpoint | 1.3 - Roughness
37ed59e8-27b6-56da-8949-32af9b92f7e6 | note | Detail of Activity / Test - Previous layer checked for suitability to achieve Specified Ride
27d90b7a-e654-54f0-9544-e5c3e71f6c62 | note | Action (Hold, Monitor, Witness) - H
a5b482fc-22c7-561e-b34f-2abc069573b8 | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
d5e16d4f-9217-5643-a56b-760920e926ec | note | Inspection / Test method - Confirm Specified Ride requirements can be met
1f76f339-e526-5675-8a51-20da654f2331 | note | Acceptance Criteria - Site is suitable for paving;
ad3575b7-a753-506f-aeef-8844c5a0cc91 | note | ○ The surface to be paved on must have a smooth longitudinal profile, and where a layer of Asphalt is to be placed over a previously constructed pavement layer, the ride quality must be confirmed with the observation of a holdpoint in the previous layer ITP.
53482f6d-67df-5ca6-a02e-db53c61f2de7 | note | Record documents (QCP - Quality Control Portal) - NASSRA Report
caf56cd8-79a4-5ec3-b9d6-94202f1b55f7 | note | Responsibility - Paving Contractor
114ccae7-f189-5a98-862b-779fbe926227 | note | Eng. Rep / NZTA - I
d25ddb6e-930f-519a-8d22-1dd094f872ab | note | Contractor - R
af3bbdba-014c-52a0-bb1b-90c717d8bbe9 | signoff | AUTHORITY HOLDPOINT
2d8eb3de-b771-57e1-8a0e-6b8c9f91e7ba | checkpoint | 1.4 - Traffic Loops
fb585cfc-84e6-5338-9b3f-5d3700d5e39a | note | Detail of Activity / Test - Communication with affected parties
1b9345ee-5b4b-5f0b-906e-66bcb17e8f56 | note | Action (Hold, Monitor, Witness) - H
e8187786-f867-5f53-b7d2-f9dbfd2d3708 | note | Minimum Test Frequency (Lot = 1 day’s production) - Minimum of 7 days Before Works commence
0bf659aa-4b6e-500c-ac2b-2f711bb6b91a | note | Inspection / Test method - Visual
37245652-9c98-5468-a193-20677d1b05e4 | note | Acceptance Criteria - Notify RC at least 7 days before surfacing is programmed
b5279447-eb77-54db-ba57-99269b7f0dd3 | note | Record documents (QCP - Quality Control Portal) - Communication
46def274-853a-5531-a244-d25fd21311ed | note | Responsibility - Paving Contractor
66292766-ca53-56a7-963b-3c85b9d6cb3e | note | Project Specific Notes / Instructions - only required where existing traffic loops are present
df435097-090f-5322-92bb-48fa3b125ef9 | note | Eng. Rep / NZTA - A
6171d075-1dd5-5ab3-b55c-ca762c72cf90 | note | Contractor - R
c406dae7-4f12-5ae0-8ea3-326a2e279662 | signoff | AUTHORITY HOLDPOINT
0fdc8ef1-2e43-5382-908f-b35bfa1f644c | checkpoint | 1.5 - Paving Plan
62a9f985-3f00-5a16-ad4e-7b63491155bb | note | Detail of Activity / Test - Paving Plan to be completed
8b87b239-0ce1-5407-927f-c6d9776f9fa9 | note | Action (Hold, Monitor, Witness) - H
c1723ad0-0be9-5531-8453-4b05ba7802f6 | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
51da450a-3fc1-5783-83cb-748af2d81ef4 | note | Inspection / Test method - NZTA M27: 2020 Clause 9.5.1
ea56cf9d-e2cc-5316-afdb-b6c67de64b65 | note | Acceptance Criteria - Paving Plan to be completed for each shift with dimensions, location and type of (hot/cold) joints, areas and tonneages
60befb09-3f80-5814-9613-79c6a3a33c7d | note | Record documents (QCP - Quality Control Portal) - String Sheet
1cbb0bb2-c79e-5a72-af3b-21f20f542fa0 | note | Responsibility - Paving Contractor
36efbe31-9000-5b8f-809b-8ec0d315e0be | note | Eng. Rep / NZTA - I
8f9fedda-528f-5928-87ed-9283110097a9 | note | Contractor - R
c8cfc14b-5230-5eba-b1b7-bdc924f2cf5f | signoff | AUTHORITY HOLDPOINT
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
16007103-ffe4-514e-82b4-5cd5ba07ca08 | textbox | Contractor's Rep Name:
2acbf8bf-9d36-59cd-866f-6e932898403f | textbox | Engineer's Rep. Name:
2d2833ff-9ba7-5cdf-a0ec-06330b0f5ca2 | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
e94ff84d-a584-43b6-af7f-eabca50347a0 | checklist | ITP - New Guardrail Installation Rev 0 | itp | ITP - New Guardrail Installation
6fb7b1d4-17f3-4de5-a7b8-c2b61acd4410 | section | 1.0. GUARDRAIL HARDWARE ACCEPTANCE
6471f2e0-206e-4ee0-b3b0-0fef4e8cd785 | checkpoint | 1.01 - Guardrail Hardware
7069a7b8-a5e9-56d3-9afb-93ed62c7272f | note | Detail of Activity / Test - Compliant with Standards
dd0e5653-6ded-52be-bcba-efe625428a88 | note | Action (Hold, Monitor, Witness) - H
5c96a097-6a75-5220-8d78-92bbb0b8fb90 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
4e011ccb-43ce-52e5-88c1-78de0aaf4efc | note | Inspection / Test method - Visual / Photo
4a85afcc-9288-5f8d-b4f4-b6df77a89f43 | note | Acceptance Criteria - AS/NZS3845
7352a327-3068-5263-a1fa-c92082c1f4fc | note | Record documents (QCP - Quality Control Portal) - Data Sheet
c6350b64-62e0-5ce9-a5cb-5630e7d5a44b | note | Responsibility - Contractor
0dcdc5de-1885-5d4e-803e-4cac61ae5db6 | note | Site Engineer - A
2bce976e-591e-56b7-927e-fe3a732ba763 | note | Eng. Rep / NZTA - I
5c9f4c62-8349-531f-89cc-73a9a911d557 | note | Contractor - R
efc7047f-e415-48ae-98bc-95932570fb50 | signoff | AUTHORITY HOLDPOINT
1117bbc4-fc8d-409f-833e-1524d76e5e0b | checkpoint | 1.02 - Guardrail Hardware
f5d4d817-6b09-5d7f-8230-0ab073e3e4a6 | note | Detail of Activity / Test - MASH Tested
cfb604e7-2998-575b-b953-900549e67f56 | note | Action (Hold, Monitor, Witness) - H
786a3971-d3d0-50ec-b645-3c34dfaabd5a | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
ca5af4c0-81f4-51ba-ba0e-f0afd77bc799 | note | Inspection / Test method - Visual / Photo
b35d5d57-fe0e-5a8b-be33-1ad35ebf676f | note | Acceptance Criteria - AS/NZS3845
83c17c45-01de-547d-8cfb-a8a838bed3b4 | note | Record documents (QCP - Quality Control Portal) - Data Sheet
c2e33503-58d9-58f2-bd2a-c364b1daaa4c | note | Responsibility - Contractor
5ba0da73-8f89-5d54-9f7a-37e92517c655 | note | Site Engineer - A
76bb51ff-e270-5cc6-ad0c-00f135e75910 | note | Eng. Rep / NZTA - I
3533e182-e654-57cc-a96b-e0f55ec09aaf | note | Contractor - R
e338b919-45f0-444b-a7fb-0ca5643ddddd | signoff | AUTHORITY HOLDPOINT
a479bf05-fe37-4aa0-b1cd-c87455ff72d7 | checkpoint | 1.03 - Labelling
dce4c1c6-1897-5972-af72-a3dd92ba2d76 | note | Detail of Activity / Test - All components labelled with AS/NZS3845
4f3041a1-1ded-5538-aecc-f0f7f26754bb | note | Action (Hold, Monitor, Witness) - H
836d4c6d-4ef5-5c43-a5af-6917096c8fd6 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
1c719180-2c28-513d-9405-8d4d2dfec484 | note | Inspection / Test method - Visual / Photo
2c8091f2-5cd8-5e3d-b39b-c1182e64ab28 | note | Acceptance Criteria - AS/NZS3845
aab5d661-6eaf-5d07-8d47-0233e5afd179 | note | Record documents (QCP - Quality Control Portal) - Data Sheet
6bebea6a-2b70-5b52-a885-a5b48a3710a8 | note | Responsibility - Contractor
cfc7702e-8a41-5561-a1e3-a4ab98e0e89a | note | Site Engineer - A
87e86f05-bafb-5cc3-8efd-d60332ace10c | note | Eng. Rep / NZTA - I
674cd7c9-eb44-5105-ae64-d68379c5446e | note | Contractor - R
fd361891-b918-4e37-8eea-5e3ba2c58366 | signoff | AUTHORITY HOLDPOINT
8620a160-6ed9-40d3-82f0-99f26515a972 | section | 2.0. CONSTRUCTION
ce3f169f-4471-4e49-8dd9-9aa113ffb9b4 | checkpoint | 2.01 - Service Location
9c8354f0-dc5d-52e0-bb11-cbd92e3dfb01 | note | Detail of Activity / Test - Ensure Service Loaction Plans are onsite. Service Provider Standover if required and potholing if services are in the construction area
e2db5020-5864-5a96-abb7-7e7176f2bb2a | note | Action (Hold, Monitor, Witness) - M
734986e5-7e17-5b46-ae57-6fb046bad728 | note | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
e56e61c1-f0eb-5473-9582-06189c3a2788 | note | Inspection / Test method - Visual on Site Potholing
025d293b-df71-579a-9db9-1311cb3a3f3b | note | Acceptance Criteria - Site Engineers Approval
ba826969-3b5e-5815-96f2-be94fd8ce037 | note | Record documents (QCP - Quality Control Portal) - Checksheet
44f228c7-0fa0-5ee5-bd7d-7de63c690250 | note | Responsibility - Contractor
73dfec51-ec24-55ce-b341-908041e553d4 | note | Site Engineer - A
477d41c3-17f0-55a0-9fc0-6e49bd5a7c63 | note | Eng. Rep / NZTA - I
7cc68c03-b6d2-575e-8b6d-52cea315348e | note | Contractor - R
f806c76e-64fc-4b97-b15a-972b2940b1fa | checkpoint | 2.02 - Drill Post Holes
9f73e28f-7fe5-5ff0-ac20-dbfbe47066b7 | note | Detail of Activity / Test - Drill post holes to a depth of 875mm for Rail Post and 1100mm-190mm for terminal ends
8cdd2aeb-dba6-5cc4-a99f-6ed722bb8a8d | note | Action (Hold, Monitor, Witness) - M
6985a70f-1d56-5607-9dc4-f08a1f4961bd | note | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
b6c20535-92a9-5577-9b51-94bbfd526241 | note | Inspection / Test method - Measure
15b26ee4-b849-5532-b976-305c5555c8c6 | note | Acceptance Criteria - Site Engineers Approval
00157ecc-a14d-5c28-b9ef-d318ba8ea081 | note | Record documents (QCP - Quality Control Portal) - Measurement Sheet
0d1feeec-542d-5848-9837-3ba8e5321336 | note | Responsibility - Contractor
ddd72230-d330-567a-8447-070c90b53d5d | note | Site Engineer - A
492af5a5-87dc-5925-9084-f0cc430a640c | note | Eng. Rep / NZTA - I
bbc84874-6c6d-55e1-b4f7-5fe12eb1930c | note | Contractor - R
48ec676d-77c5-4336-b613-eab902960549 | checkpoint | 2.03 - Install Posts
25bc994e-328b-5ecf-9265-786811ac0df1 | note | Detail of Activity / Test - Install Post 875mm deep, Top of post 786mm above finished road level
786c1541-8ac2-57d0-ab3b-4d6869b723e3 | note | Action (Hold, Monitor, Witness) - M
b0fd5346-7334-55d0-85d4-51e44e14f6b5 | note | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
945fc434-fa69-506a-90ff-1c30e6cc8a06 | note | Inspection / Test method - Measure
7eb0e725-0039-5d56-84f1-dd5b321791c6 | note | Acceptance Criteria - Site Engineers Approval
28d8fa6c-c9c7-5ead-8ca9-5bf90ec3a25f | note | Record documents (QCP - Quality Control Portal) - Measurement Sheet
47d502b5-256b-55a5-8eb8-30b9564f4333 | note | Responsibility - Contractor
9feb0038-5dca-52bb-ac8c-03dd6b181544 | note | Site Engineer - A
209099dc-b4a5-5bfe-acd5-f2e8430909b2 | note | Eng. Rep / NZTA - I
8c342ab6-e38a-500e-97b9-0115362515e5 | note | Contractor - R
d889ee0e-6b17-4284-baf9-a87bef9a32d6 | checkpoint | 2.04 - Backfill post hole
62df9b6a-473f-5a1c-9832-6433d40cec91 | note | Detail of Activity / Test - Backfill Posthole
697a8d22-c17b-54df-9072-65c88f892e71 | note | Action (Hold, Monitor, Witness) - M
35a884ee-1996-5015-af48-32ef85db7493 | note | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
5906b4d4-0f8f-5cc3-bab2-932f05d38269 | note | Inspection / Test method - Visual / Photo
27b3c5f9-eb4b-5d5a-8372-e528a6205dd2 | note | Acceptance Criteria - Site Engineers Approval
1f1c2326-d6d5-55da-b7bd-043e698139db | note | Record documents (QCP - Quality Control Portal) - Checksheet
e9591cb2-d35e-588b-9805-01821b82ccef | note | Responsibility - Contractor
2a1d8429-fafe-5c7a-b8a4-bc6e18d7ee28 | note | Site Engineer - A
da12e671-182e-57bb-a244-14c8404144af | note | Eng. Rep / NZTA - I
c0a6ca65-9902-57f4-863a-286326712d9b | note | Contractor - R
0b7256a5-9f56-497d-bd9b-0058a8c7aa3b | checkpoint | 2.06 - Install Cariages Carriages
4832b424-0fa8-535c-92b3-fa921c6b58fc | note | Detail of Activity / Test - Install New Carriages at Correct Height to Achieve 787mm above road level
3830cfd7-1f27-5cdf-bc48-21d3931aa253 | note | Action (Hold, Monitor, Witness) - H
2a21e778-f818-5752-a248-137ba0ea150f | note | Minimum Test Frequency (Lot = 1 day’s production) - At Every Post
43b5bc9d-a2dc-55f1-8a91-87ed93e8c67b | note | Inspection / Test method - Measure
2c1ff110-1186-5a7a-82a5-5625cdfb49ff | note | Acceptance Criteria - Site Engineers Approval
12460518-53f9-55df-b0ae-ad313eb2c20d | note | Record documents (QCP - Quality Control Portal) - Measurement Sheet
36bf2372-3400-5636-a944-ea3548844f7e | note | Responsibility - Contractor
20431de0-f823-5486-90d6-4e01da56edc7 | note | Site Engineer - I
42153a40-60f5-5ee8-be9a-6d7d2aabba2a | note | Eng. Rep / NZTA - A
dae8878b-60d3-5b7f-851d-ceb2baa9af9f | note | Contractor - R
8b3244ea-2380-46e5-8401-374eac0b32b8 | signoff | AUTHORITY HOLDPOINT
46366fd3-8541-4604-a45f-fa907ba83534 | checkpoint | 2.07 - Install W-Beam Rails
7e9a00fd-4bfd-5b95-a582-0e76792d0ef7 | note | Detail of Activity / Test - Reinstall W-Beam Rails to Exy Lift Carriage using M16x30mm Bolts and 75x45mm Square washers at each post
f982dd2a-9de4-590f-a12b-6de59fc702a6 | note | Action (Hold, Monitor, Witness) - M
4f45c985-7944-5e28-98fa-f2bf99eb7c2e | note | Minimum Test Frequency (Lot = 1 day’s production) - At Every Post
35453244-f0e0-54f7-88ce-339e4164d830 | note | Inspection / Test method - Visual / Photo
7afbcf31-eb25-572f-a4f9-7ce873198021 | note | Acceptance Criteria - Site Engineers Approval
2ef6577b-7d6c-5dc1-afb8-10e62e4b3e4f | note | Record documents (QCP - Quality Control Portal) - Checksheet
6200bc2f-cba8-5dea-8345-2f3deae84e95 | note | Responsibility - Contractor
36264f1d-09bf-51ff-90e7-9f4cc9aeb14c | note | Site Engineer - A
e27f6412-2f38-57c1-9793-d0d02199e48a | note | Eng. Rep / NZTA - I
bc62f895-2a4b-52e4-baea-78ba76b86e30 | note | Contractor - R
50db97ef-a258-46c1-8b2f-01d31c63aff2 | checkpoint | 2.08 - Overlap Rails
f9e5d95d-89c5-54e1-a9f3-45ee82556edb | note | Detail of Activity / Test - Overlap Rails during installation to there is no leading edge facing traffic
ef60e3fc-bf51-5eb6-8f27-f39e085fc3b5 | note | Action (Hold, Monitor, Witness) - M
87f8d9ae-3a83-5b75-b9d3-565aedb0e179 | note | Minimum Test Frequency (Lot = 1 day’s production) - Every W-Beam Rail Joint
a18cea86-18d5-5f93-bfd7-fcacb50c2339 | note | Inspection / Test method - Visual / Photo
e5b36b7c-cf89-5b18-8857-0bf084323e8f | note | Acceptance Criteria - Site Engineers Approval
6fae290c-e229-543c-bbd3-6e0b66049925 | note | Record documents (QCP - Quality Control Portal) - Checksheet
2926a81d-ea46-5fe0-981c-4da1e531f1a5 | note | Responsibility - Contractor
85f087d6-7ec4-50c0-bfd5-659a514c4d55 | note | Site Engineer - A
8b8f14c1-85df-5d07-89da-d7f52431bceb | note | Eng. Rep / NZTA - I
eb4cfce9-9c2b-535c-aaf8-c1843447edd1 | note | Contractor - R
567c1d66-585f-475e-be94-20d71397e878 | checkpoint | 2.09 - Splice Bolt Installation
e169dbf7-ef51-5dce-8ddf-aa027f44cd96 | note | Detail of Activity / Test - Install Splice bolts at every 2nd post using M16m32mm splves bolts and oversized nuts. 8 Bolts required per Splice connection
1bc4400d-fe28-547a-b6d1-13c080003e17 | note | Action (Hold, Monitor, Witness) - M
ee1e92c6-6461-5d14-988e-5547ccb7ec5d | note | Minimum Test Frequency (Lot = 1 day’s production) - Every 2nd Post
c8cfb716-9260-55ab-bdd9-5ea3603a1f5c | note | Inspection / Test method - Visual / Photo
42bf2dbe-bc4c-52aa-bd26-88c04c7d2afa | note | Acceptance Criteria - Site Engineers Approval
fdd74fbd-7ae8-5ec6-a7f5-b6da7c7f3823 | note | Record documents (QCP - Quality Control Portal) - Checksheet
18b8eea3-cfb6-5d35-b8ac-846c3bf5fcaa | note | Responsibility - Contractor
a940f1b9-06e3-519a-a104-d83a0d7091d2 | note | Site Engineer - A
03a8a939-7f0d-5939-a647-fc016f36811b | note | Eng. Rep / NZTA - I
dc337cee-2a4a-57bc-8799-eadcb152e4f9 | note | Contractor - R
b7b76532-9629-47b3-a66c-d4ccd5fc33f7 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
6dbd9143-288b-564f-8d03-5f2b67e4c82b | textbox | Contractor's Rep Name:
94089c4b-c1f3-5e0b-b57d-3b73101e99b4 | textbox | Engineer's Rep. Name:
0af88641-b580-5099-98df-fe30a694b17e | date | Date:
ee21262f-e8e4-4229-b47b-c5c2042ed0d2 | signoff | Add Signature
bba0ddc3-5849-4954-a60e-f6c831e30a72 | checklist | ITP - P11 OGPA Construction Rev 0 | itp | ITP - P11 OGPA Construction
ee3a5188-615a-4a6e-abce-0a5933586944 | section | 2.0. MANUFACTURE OF ASPHALT
cb25b8e7-f38d-4ba5-a23d-ed65db2838b5 | checkpoint | 2.1 - Temperatures
83d96191-a03b-59a0-9519-37b24a537e88 | note | Detail of Activity / Test - Mixing of aggregates and bitumen
c0399f48-8ad6-50c4-a172-c6fc29dca86b | note | Action (Hold, Monitor, Witness) - M
6b451e37-54cf-5201-bdb4-5e37469ccf14 | note | Minimum Test Frequency (Lot = 1 day’s production) - Constant monitoring of temperature by calibrated euipment
08050b38-b29e-59cd-bc18-c7611171b6bd | note | Inspection / Test method - Plant temperature probes
1b720a9b-bef6-5047-9a65-6241339978e1 | note | Acceptance Criteria - PG64 V/E (Flexiplus Bind) binder mixing range:
5a0d8357-cccf-5f06-aec4-e276df439bec | note | ○ 145 to 165 deg.C
5888f847-907e-52ad-9873-254d4a72edd2 | note | ○ NZTA M27: 2020 states max. 185 deg.C
867f019b-d80b-5bcf-92d0-e4d285a9a626 | note | Record documents (QCP - Quality Control Portal) - Plant site diary
9f063962-138c-5b82-afe1-1c66f367b42c | note | Responsibility - Asphalt Manufacturer
0da3326f-8307-539e-a75b-a97f6a10c0b5 | note | Designer - I
46a59905-2e01-5862-ab43-82dbe2c0ff03 | note | Eng. Rep / NZTA - I
7e443d78-8e4d-5fa0-b933-b875768601cd | note | Contractor - R
a8eb88b4-a13f-4483-af5d-94100b0399b6 | checkpoint | 2.2 - Production Asphalt
66291a5d-89e5-51b7-bbb8-1fe8c8c23239 | note | Detail of Activity / Test - Particle Size Distribution
801d1204-ead5-54db-bd2b-13ad07fc9600 | note | Action (Hold, Monitor, Witness) - M
769941ff-9d5d-5cf9-88be-9026d823eef5 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
8a95bb3d-0976-5314-9cab-abbec74266a3 | note | Inspection / Test method - NZS 4407, Test 3.8.1
3a166336-b6df-5009-aa81-af9e85f1fcac | note | Acceptance Criteria - NZTA P11: 2023, Refer to Table 6.3
23e72b3f-872d-5ef3-8cf5-e75e05127c13 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
8dfaf204-5167-5669-af0a-5740b1ac5b6b | note | Responsibility - Asphalt Manufacturer
571c4d10-0c36-5838-a60f-bd2f038780f9 | note | Designer - I
4b511d1d-bf29-5ffc-8154-2b47c4b9397d | note | Eng. Rep / NZTA - I
42fe40d9-996a-5cee-a5dc-2feab2468f0f | note | Contractor - R
d5c23f8b-18cf-43e6-84f8-31364524ba59 | checkpoint | 2.3 - Production Asphalt
1201dbe6-29b3-556e-a348-629837a54008 | note | Detail of Activity / Test - Binder Content
72be4121-950e-58f2-941b-7d4755313c3c | note | Action (Hold, Monitor, Witness) - M
be622bb7-4aa4-5485-ab67-404483f9420c | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
fc19c3e8-025f-5d5f-ae9d-3c4bb7eb05f4 | note | Acceptance Criteria - NZTA P11: 2023
08aecec9-dc72-536e-a41e-508be1d52694 | note | ○ Individual Test Result: ± 0.5
81cefedb-25fd-5890-a39f-0848187e6ff7 | note | ○ Mean of Three Test Results: ± 0.3
052c4916-b38d-5167-a298-592730ad59bc | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
0dd0ba8c-fcd2-54e5-bdc4-31693f7b3dd2 | note | Responsibility - Asphalt Manufacturer
c4ca8315-3081-5f86-aabd-d4ff9a57a195 | note | Designer - I
77f370fe-7cae-5edd-8f69-07ece043d52c | note | Eng. Rep / NZTA - I
8f03bb67-9820-54fb-93dd-372e1e1b1ac6 | note | Contractor - R
47a2bf87-c4fa-468f-b0b2-ef3ed1378f73 | section | 3.0. PLACING AND FINISHING
2716b6fe-6811-4435-930b-f084c56dfc3e | checkpoint | 3.1 - Milling
b974fa49-5377-5291-99c4-b782e10dd40a | note | Detail of Activity / Test - Surface strung to ensure milling Depth is achieved
7437b562-7c4c-526a-bce3-6ed2e2ed2102 | note | Action (Hold, Monitor, Witness) - H
86b8f842-a9f0-55b8-ad77-5e4f24959dd8 | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
8dc14acb-f7fc-5dfe-b46e-3554946c71d4 | note | Inspection / Test method - Confirm requirements are followed
48a72f02-e171-5bd2-91aa-89b1437c9ad2 | note | Acceptance Criteria - Site is suitable for paving
baf4ffc4-be8d-58c2-a087-3ca81b05b5b3 | note | Record documents (QCP - Quality Control Portal) - String Sheet
bf14f511-6d34-5c2d-a12d-dc8fe6b0d8eb | note | Responsibility - Paving Contractor
fb0d527c-4102-5654-97cc-40237eec93f7 | note | Designer -
e6de8d69-ec84-579d-b0f2-c02453dcf7ff | note | Eng. Rep / NZTA - I
587b5ef0-9bbe-587d-ac32-737763492ab5 | note | Contractor - R
f6347f3b-dcc4-45df-9d40-81fdfb84c9ac | signoff | AUTHORITY HOLDPOINT
15b5bdb2-0caa-49d4-abf7-268740813fb8 | checkpoint | 3.2 - Tack Coat, OR
163a39da-d84c-5b54-a99e-960d1dbdaee5 | note | Detail of Activity / Test - Application of Tack Coat
9aa33535-74db-5e51-8876-eb80fb1abf42 | note | Action (Hold, Monitor, Witness) - M
384f085d-7e2c-52f7-9d0f-0c2d9524bfea | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
3e71b146-4dc8-557a-90f1-08952704b4b3 | note | Inspection / Test method - Dip bitumen emulsion tank before and after
376c1bb6-6cde-59d6-aebc-e1fa5bb81509 | note | Acceptance Criteria - Target Between 0.2l/m2 - 0.6l/m2 +/- 0.1l/m2 From Target Application Rate
b632803d-9790-5445-9872-7b2641d0203e | note | Record documents (QCP - Quality Control Portal) - Site Diary
2174ac47-6b41-502a-af33-ef1ae0695f01 | note | Responsibility - Paving Contractor
1487dbda-345e-593f-83bc-90700faf8b66 | note | Designer - I
4b0a684f-10bd-5290-b8ba-3bc5f67a50ab | note | Eng. Rep / NZTA - I
68784bd1-0758-585d-978a-8b5432754f8b | note | Contractor - R
1b635a7d-b36c-4c35-9f43-54f904bbf8d2 | checkpoint | 3.3 - Membrane Seal
b8ce8acc-c31d-510a-b2db-df7414ff45cb | note | Detail of Activity / Test - Application of Membrane Seal
dc986063-cc64-5508-93d3-8172e680ed92 | note | Action (Hold, Monitor, Witness) - M
19aa16c7-296a-58c2-8e8d-87af79eff437 | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
98fd2ee1-3220-5d2f-a311-b505b2ed4133 | note | Inspection / Test method - Sealing Records
3c184d0b-cb3c-5a62-a053-c698b5574974 | note | Acceptance Criteria - Application rate, chip type and binder as per membrane seal design
d30d79b3-3a3a-594a-bedd-50ad0d6911bd | note | Record documents (QCP - Quality Control Portal) - Sealing Records
7c8704a4-8f67-5557-8ba9-415445dc52f7 | note | Responsibility - Paving Contractor
5a13e39c-a9f1-5ef8-a6bd-875e4dd515a0 | note | Designer - I
c0360d44-351d-5333-80c3-21a099bd2761 | note | Eng. Rep / NZTA - I
7787e804-d14e-5f70-9aa3-61fac9c5ac22 | note | Contractor - R
5eb942fd-7be7-438c-99a3-bf41328e9b39 | checkpoint | 3.4 - Temperature
bd50117e-317b-5075-a96f-1895c5a0c650 | note | Detail of Activity / Test - Pavement Surface
fb50b9c8-010c-5fbc-afdd-6a1ac205a58e | note | Action (Hold, Monitor, Witness) - M
bedd40d0-5d66-5caf-963f-3f1683a003d6 | note | Minimum Test Frequency (Lot = 1 day’s production) - Start of shift and every 1 hour until temperature rising
f8593538-9cc6-5a80-a50b-bd2192ea4325 | note | Inspection / Test method - Infrared gauge
09589c88-dfc9-5125-9caf-728ca3d1b317 | note | Acceptance Criteria - ≥ 10 °C or as otherwise agreed with NZTA
f4ce022e-4377-51be-8fa1-dec87466b4cb | note | Record documents (QCP - Quality Control Portal) - Site diary
7b09e350-57e7-5d01-8d7b-680c1259b13c | note | Responsibility - Paving Contractor
6dd900d7-0fe8-561f-ad3f-0ad54af55a84 | note | Project Specific Notes / Instructions - Must get NZTA approval if < 10°C
8bc6dbda-2663-59b9-b0c4-ce35750c3f8a | note | Designer - I
5d562746-d383-5ace-9773-b421e2753bad | note | Eng. Rep / NZTA - I
38bc1d71-3d2c-582a-88ad-fb8f5b2342f8 | note | Contractor - R
dd5f8a85-a60c-416e-ad84-ec4781c575fc | checkpoint | 3.5 - Temperature
bc155d6f-6564-5b36-834a-9140094bc4d4 | note | Detail of Activity / Test - Asphalt Delivery temperature
7ee7a99b-e74d-5ff1-aa8a-ee7fb4b9e478 | note | Action (Hold, Monitor, Witness) - M
1814aa32-e235-58d3-8e76-196a93438223 | note | Minimum Test Frequency (Lot = 1 day’s production) - Every Load on delivery to the Paver Hopper
17ad4c64-ae24-58e7-bfa1-8f9650255858 | note | Inspection / Test method - Temperature Probe
b774e4ee-5cd1-5227-9849-ae05db804447 | note | Acceptance Criteria - Target ≥ 150 deg.C. in the Paver
0037ca54-3e2f-5957-b649-95c81457e205 | note | ○ Min. ≥ 120 deg.C in the Paver
c963dfbf-1b60-5dfe-89d5-9115041ba382 | note | ○ <120°C to be Rejected
9f1965c8-5fc7-5803-bf58-76f03d893628 | note | Record documents (QCP - Quality Control Portal) - Site Diary
84ecbad5-db8f-5fd6-8992-31baa0f49f4e | note | Responsibility - Paving Contractor
84f222a5-5c59-521c-a9c8-0f7af7b8f7fd | note | Designer - I
e3f5ff2c-3045-5055-a038-a33fdcf1cd67 | note | Eng. Rep / NZTA - I
a040db96-7de7-5fae-914f-7f454dc14cd7 | note | Contractor - R
48b0d2ac-829d-4d6f-9b54-1e5f38dc83fe | checkpoint | 3.6 - Temperature
da466ce8-5d52-5de3-89ed-e47b722c864d | note | Detail of Activity / Test - Compaction Temperature
00f43dd0-59fa-592d-94f0-8618b70df34c | note | Action (Hold, Monitor, Witness) - M
ea314a14-76ba-572e-b107-4b4470e86e5c | note | Minimum Test Frequency (Lot = 1 day’s production) - During compaction
4dcb3851-4885-599c-9da9-a2d24b40973f | note | Inspection / Test method - Temperature Probe/Infrared gauge
bee4a9a5-b8b8-5228-8bba-09ea4e28a059 | note | Acceptance Criteria - ≥ 115°C at commencement of compaction. < 80°C - Stop Rolling
8dfb7786-f330-554f-9947-f87f29a37c50 | note | Record documents (QCP - Quality Control Portal) - Site diary
f7199528-f373-5ba7-97ca-485ffbfeacd0 | note | Responsibility - Paving Contractor
b5e29506-2c40-5e1e-a89b-2041dd7a811a | note | Designer - I
5c5ab3fa-369e-5c4d-9966-86996fd4b8bc | note | Eng. Rep / NZTA - I
6b65d5b6-9e38-5803-a5ad-804fccd8ad24 | note | Contractor - R
debd9fd9-cdaf-45c2-be3f-30083f8cbbb2 | checkpoint | 3.7 - Mat
075f5dae-ed82-55fd-b080-296c416432fe | note | Detail of Activity / Test - Load Locate
11ee12ba-18ca-53e8-91f0-8af741e7d5f6 | note | Action (Hold, Monitor, Witness) - M
e289e5de-932d-561c-af53-a6702f43b8b0 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each load
87ecf7bc-2c2b-5d1a-9bd5-062d2e705d4c | note | Inspection / Test method - M/27
d443f1fb-13d9-5245-866c-17e600c3b0d9 | note | Acceptance Criteria - Each load can be indentified to a location using a diagram. Record includes:
d29d0ed8-a265-5704-88cb-d89c56518dc1 | note | – Truck ID/Rego/Driver
e7fc8e52-2ac6-5648-a177-1b75d610dab7 | note | – Depart Plant Time
6e36fdb1-49f3-5e0d-87e2-bdd365d69935 | note | – Arrive Site Time
e3a58377-8214-5db4-91e2-5df74791429a | note | – AC Temp on Arrival
823985c7-4da1-5ce7-a9e4-8badb709fde2 | note | – Tonnage
8052c6d7-ad29-558a-8cd5-dcc804f723df | note | – Run Width
9f76d8fe-e9ff-51cc-81cd-bb01954dfba4 | note | – Estimated Run Length
5380454b-36f8-51e9-804b-365ddff7d813 | note | – Calculated Area
838fd194-1adc-50aa-8b23-5365d7a01fcb | note | – Calculated Average Depth
bcbfa0c2-e56a-51b8-9875-ff71a7cdaaa1 | note | Record documents (QCP - Quality Control Portal) - Paving Run Sheet
de186ac0-93a5-5cb1-a139-8518f429b27b | note | Responsibility - Paving Contractor
0a40c374-22ab-5906-a8e7-10fea2c989d9 | note | Designer - I
50d4a4d3-0d9a-57c0-bed5-859b6c35e8b3 | note | Eng. Rep / NZTA - I
b4fa22bb-606a-5dc3-9ff6-69de9c354b7d | note | Contractor - R
bb360d31-cfae-4185-ba7e-a7d3029dfbf2 | checkpoint | 3.8 - Mat
2f38f849-04e2-5b25-9986-119f971facbc | note | Detail of Activity / Test - Thickness Monitoring
e1050ac8-d1fb-5eaa-b6e6-7b8d845177c8 | note | Action (Hold, Monitor, Witness) - M
654131a2-5587-5072-a4dd-b5cecd2e6dfa | note | Minimum Test Frequency (Lot = 1 day’s production) - Continuously
2121dfe4-06e9-5ef7-bea6-fb32f3c42dd0 | note | Inspection / Test method - Dipping
0f8434f9-9b6b-5792-a4b9-b16aea2f7d94 | note | Acceptance Criteria - Target Loose Thickness -0mm / +10mm
0278de60-4158-5a04-8019-d2320c23e67e | note | Responsibility - Paving Contractor
beb4da92-937a-5043-aa19-b1a50d8988c6 | note | Designer - I
ed805516-8181-5300-8373-83e681838d11 | note | Eng. Rep / NZTA - I
eeb18a7f-fabb-5fc5-b242-f25e8f05f55a | note | Contractor - R
4a15da6e-5b45-481b-be01-173b9744fb28 | checkpoint | 3.9 - Mat
3306dfb3-8710-53b6-a633-94ebc2160de5 | note | Detail of Activity / Test - Shape
7b586c18-8d73-54a8-91e6-1004e4215b1d | note | Action (Hold, Monitor, Witness) - M
9b012e15-c6de-532a-a07a-1e54736ccf95 | note | Minimum Test Frequency (Lot = 1 day’s production) - Continuously
edc50485-84ea-5c8d-b37d-4d633a51823e | note | Inspection / Test method - 3m Straight edge
27ff99ba-62c1-5556-aecb-3e6d6b8a9402 | note | Acceptance Criteria - NZTA P11: 2023 - section 14.2.
b4e750b8-8e91-5f08-9471-7721520ef477 | note | ○ Not more than 5mm under a 3m Straight Edge parallel or perpendicular to centre line.
98780acf-e925-5752-bb45-2f1e89b73632 | note | Record documents (QCP - Quality Control Portal) - Straight Edge Record
6d827014-5365-53ff-a68a-6d453b160419 | note | Responsibility - Paving Contractor
6b8895e8-7b5f-5c51-86cb-9ecc31887a31 | note | Designer - I
0e73f002-0475-53e7-8d40-bf697f75cdef | note | Eng. Rep / NZTA - I
da3fad1c-afd0-5033-a7f5-8286fd334ec4 | note | Contractor - R
baeae327-17b6-4337-8145-51ed604387cc | checkpoint | 3.10 - Paving Quality
5b233b59-ddf4-507b-9764-60a2d6fa465f | note | Detail of Activity / Test - Texture
ae3dd9b3-3761-54c3-b1b3-b7d9c12f32a2 | note | Action (Hold, Monitor, Witness) - M
1c9ff707-75ca-5716-ab26-67ff8b2493fd | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
0b569b65-3ce2-5f08-b26a-f0ec63ea91d5 | note | Inspection / Test method - Sand Circle or HSD
3b9edcf6-1601-5ab1-849e-fe12c368f500 | note | Acceptance Criteria - NZTA T/10: 2013
9fa48d80-5052-5a4b-915e-fc9412b51475 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
1646c17d-0fdc-5b14-9a16-50ae38face0c | note | Responsibility - Paving Contractor
3749ffa7-f610-541f-b88c-cdc1f4058335 | note | Designer - I
be6db07d-2a67-5227-967d-47fedaf9a1b8 | note | Eng. Rep / NZTA - I
75e049ba-0976-5ea5-bb77-b1e0cd995d13 | note | Contractor - R
25974988-08cf-4a88-9379-5dc09fe1cbe1 | checkpoint | 3.11 - Paving Quality
7becf7e8-88bd-53dc-bbcd-74d00e9a2ecf | note | Detail of Activity / Test - Alignment
144c0816-a54b-586a-a24f-b7bcd8bdb4f5 | note | Action (Hold, Monitor, Witness) - M
d51dc3f8-a797-5c90-aabc-fbdac12b79ae | note | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
dc5b9ff3-937a-5024-8c96-3670f9220f92 | note | Inspection / Test method - As Built Survey
143a3659-1b4d-5b8a-9037-d6500a0df636 | note | Acceptance Criteria - ±50 mm from drawings
41ac8c68-c37d-5f92-9751-3be326ba3e75 | note | Record documents (QCP - Quality Control Portal) - Survey As builts
b55d68e1-649f-5ca6-9ac8-52adee54ba73 | note | Responsibility - Paving Contractor
3d55cf6f-07e7-5867-9163-9a8329c028f4 | note | Designer - I
eb6b848d-9bad-5a65-9f36-0141b8f2ea2f | note | Eng. Rep / NZTA - I
4cdacaa9-58a7-5c69-b2bb-e9745fe1f6e9 | note | Contractor - R
8172bed5-8240-4ce5-83dc-7cb413481d17 | checkpoint | 3.12 - Post Paving Completion Checks
ec721138-d60e-59e4-8ab2-c1eda4d4e668 | note | Detail of Activity / Test - Site clear and cleanup
be37f573-8690-509c-b53a-cf2fc1e26741 | note | Action (Hold, Monitor, Witness) - W
06d412a4-4854-59f0-b5ed-741c4c3f7cb6 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
2e5a5bf2-d078-5874-a584-c44ef7619e86 | note | Inspection / Test method - Visual
e92bf666-b574-5d07-b229-8b07aea40ce9 | note | Acceptance Criteria - Site is cleared of plant (or parked in safe location) cleanup of all waste mix, paper and detritus is complete
a34ef3d4-0620-5764-b82d-5759c3f53e77 | note | Record documents (QCP - Quality Control Portal) - Site Diary
bd542562-2289-500f-9d39-1fa6a6c19837 | note | Responsibility - Paving Contractor
0d01d731-b0be-5db8-a758-ce854ed398f6 | note | Designer -
2d93c2d8-62af-53e8-b1ab-f774bd3aa714 | note | Eng. Rep / NZTA - I
24e700f2-28d5-5a0a-8735-9e636521dc0c | note | Contractor - R
269c4b2d-d94a-41cc-8f44-10c57bb5ba70 | checkpoint | 3.13 - Post Paving Completion Checks
de99c956-8998-50a9-b8df-be9a46dc4e6e | note | Detail of Activity / Test - Pavement Marking
0d54a643-8104-5fc4-ae96-28101bf486ec | note | Action (Hold, Monitor, Witness) - W
60f00c07-76d2-5ca8-8030-54835b715c30 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
a91dccf0-8872-5e76-abad-bf5525602462 | note | Inspection / Test method - Visual
f220bdf7-89f7-5d5c-822b-0512e2e8e376 | note | Acceptance Criteria - Roadmarking is complete
97fb10d5-7dd9-5b0e-9ec7-be193e0c55dd | note | Record documents (QCP - Quality Control Portal) - Site Diary
4b206ce9-d7bb-56a8-978d-a2d92eaeca85 | note | Responsibility - Paving Contractor
ee6c8e3c-608b-526c-9148-af5807140768 | note | Designer -
cfaeb62f-cbb3-5b83-a803-22db5cdd6058 | note | Eng. Rep / NZTA - I
d8a350a1-bc5f-50fa-b719-b59a4188d4f2 | note | Contractor - R
86de2be9-e769-4da2-b92d-4395e207747c | checkpoint | 3.14 - Post Paving Completion Checks
6284d277-5589-5a48-a537-8a91b96db945 | note | Detail of Activity / Test - Cold Joint Bandaging
90910eb3-2814-584a-9157-122a9341aca1 | note | Action (Hold, Monitor, Witness) - W
b7ef622c-ef93-5c04-b776-718456298b01 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
83ac466d-8406-543f-9744-25ddea05dcb5 | note | Inspection / Test method - Visual
b556d9e5-aa1a-5adb-8a85-05133c6cfb1f | note | Acceptance Criteria - Cold joint bandaging is complete
ef7a9c89-fb03-5bc8-9bcf-3e51c640ce44 | note | Record documents (QCP - Quality Control Portal) - Site Diary
f92e0ab7-0646-523d-b2d0-5775078f0739 | note | Responsibility - Paving Contractor
34a85e26-de7a-5636-99fe-90dee0af5da6 | note | Designer -
c456c828-3712-533b-b00f-419452d5f54d | note | Eng. Rep / NZTA - I
51e636b2-bc5b-58a4-8262-69cb072ac9ff | note | Contractor - R
9b238d1f-10fb-4e9e-a0ec-d0fa54fa64b6 | checkpoint | 3.15 - Post Paving Completion Checks
8dfdfca3-7230-56e1-a3fe-aea9a71ef631 | note | Detail of Activity / Test - Service Covers Checked
5eb1215f-0158-58bb-bc9d-678be3c7974b | note | Action (Hold, Monitor, Witness) - W
35521167-f8e5-524a-85c5-2ee067ef7e11 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
9e9910f2-fa3a-5c80-a47f-c96cfed67f2b | note | Inspection / Test method - Visual
8ba1a259-7fae-5f2d-b7c8-447cfa4315b2 | note | Acceptance Criteria - Check that service covers are cleared and level with the pavement
e5d9cea1-d2e9-5aa3-823e-1f1a5b7a80f1 | note | Record documents (QCP - Quality Control Portal) - Site Diary
e4bbd348-c649-5ea4-98b9-4374031d5a11 | note | Responsibility - Paving Contractor
dfcdd2ec-10cd-5934-a28c-530e5d740c8d | note | Designer -
d31cb678-90d3-521f-8f2a-d47ce8fff31a | note | Eng. Rep / NZTA - I
87981bc4-65cd-5eeb-be91-278cc2493e11 | note | Contractor - R
404d8f56-ed8e-4704-b7d8-b41f413b9ac3 | checkpoint | 3.16 - Post Paving Completion Checks
177fb0a9-0662-5b0e-8c82-d2113ea208dd | note | Detail of Activity / Test - Traffic Loops Reinstated
6cbca3b4-c839-542b-a4ca-4d56e607b6d4 | note | Action (Hold, Monitor, Witness) - W
f8c8e44f-a469-5045-874b-049d723a1ba9 | note | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
ae80a0e7-99c5-5d3e-81bc-d45abdb37255 | note | Inspection / Test method - Visual
3c40a84c-9518-58f7-8c77-b29b2a9aff4f | note | Acceptance Criteria - Check that affected traffic loops have been reinstated
3bfff485-8112-5975-bce9-70c7720fbef8 | note | Record documents (QCP - Quality Control Portal) - Communication
9025e5d7-8abb-5419-8234-55fde7e64e54 | note | Responsibility - Paving Contractor
c9e98d6f-e383-56b8-8736-9790509ce281 | note | Designer -
3989379f-b33e-5d3d-b83c-af7f13544419 | note | Eng. Rep / NZTA - I
60bda9bc-f352-572d-8cdc-121e61b218be | note | Contractor - R
f7edb345-3bfe-493a-8efe-79a86af86cb9 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
174c0926-816d-5cb0-9d94-ae7905ca0014 | textbox | Contractor's Rep Name:
5e0e8b2f-8439-56b3-86b1-2b614e70e34f | textbox | Engineer's Rep. Name:
6014c57b-1249-58c1-99e3-af1e1995c085 | date | Date:
d6eef1cb-1ca6-417d-980e-06bff8d7dfb2 | signoff | Add Signature
35fbbcae-656a-490a-8fa9-339d27bee7b7 | checklist | ITP - P11 OGPA Post Construction Rev 0 | itp | ITP - P11 OGPA Post Construction
88a3419b-7e6d-45f7-abcc-41a1cb8bcf10 | section | 4.0. As Built Records
c22f7af6-510a-4a12-9e37-dda7a5af6352 | checkpoint | 4.1 - Assessment of all test results for conformity
46a5c45b-ced5-54af-87e5-041fecadea74 | note | Detail of Activity / Test - Review against ITP Requirements
6f96b52f-0f60-5c4a-898d-731a80e427ed | note | Action (Hold, Monitor, Witness) - H
4f954c05-4b06-571f-b090-da66fcc0e213 | note | Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project
3c9ba01b-aec9-5211-bdbd-5600efbf78a4 | note | Inspection / Test method - Review
f92c36ba-3fbb-5a15-b4de-50056f359d3f | note | Acceptance Criteria - Reporting of any non-conforming results to Engineer via NCR
89e660ed-b052-5be4-8fad-b21dc6871118 | note | Record documents (QCP - Quality Control Portal) - NCR
d508c3af-7d23-5c08-99eb-5166d646884e | note | Responsibility - Paving Contractor
bc00b0df-c4f2-5faf-b646-b9e9cee06c6e | note | Designer - I
44df8912-ee51-50df-95ef-69a0ec4239ca | note | Eng. Rep / NZTA - A
bd40e380-3e33-5d95-bc34-a302e2290be3 | note | Contractor - R
f00cb1bb-5880-4c8c-a2cb-af794e708c4f | signoff | AUTHORITY HOLDPOINT
f3e63df6-456f-46b7-84f4-bf49f557bc41 | checkpoint | 4.2 - RAMM pavement and surface records
9a18532f-a8e2-53be-831a-99c25e436ada | note | Detail of Activity / Test - RAMM surfacing pavement data spreadsheet updated
aff7c194-de0f-5f87-b313-6f58dabc9620 | note | Action (Hold, Monitor, Witness) - W
ecc911c3-04b7-5aa5-b263-5df78005f465 | note | Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project
c80c85c9-1a9e-581d-a5c8-92534abe8835 | note | Inspection / Test method - Prepare Data
af8becbb-395c-5a08-926f-f8813795c8bc | note | Acceptance Criteria - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA
dd17ad73-fc2d-5a17-afd1-66473c125fa5 | note | ○ Spray sheets for membrane area received by Contract Engineer from Sealing Team.
a0406b51-3a20-5e51-8d74-f25d41aa0d30 | note | ○ Surfacing layer extents recorded and verified by Contract Engineer.
b16d73fb-828b-5bb3-a11d-a4ebfc01e76d | note | Record documents (QCP - Quality Control Portal) - RAMM Spreadsheet
d6f1f155-c587-5089-af6b-ee0802c4afa5 | note | Responsibility - Paving Contractor
a9efa349-4a99-5b0d-9070-fb7b19d4c5c4 | note | Designer - I
b2cfcac7-7ec0-5772-b5f2-011c807fe26d | note | Eng. Rep / NZTA - A
700c75e9-d4a0-5a7e-9346-3941b170a22f | note | Contractor - R
d6d3415b-d6d9-4b08-86ee-44129a5e37fa | checkpoint | 4.3 - Paving Quality
cdf43b9a-e500-53a1-8864-7d1db19d26f9 | note | Detail of Activity / Test - Ride Quality
adb5402b-0f09-5bd4-8fb6-4c9c0fc13191 | note | Action (Hold, Monitor, Witness) - W
f2aac299-683d-5e09-9150-c4b75fece69d | note | Minimum Test Frequency (Lot = 1 day’s production) - Continuous every lane
038e0585-f82f-5558-97c4-0fa8c36615ba | note | Inspection / Test method - NAASRA
db6e5750-4915-5261-97a0-b18618bb3ed3 | note | Acceptance Criteria - Max 100m Rolling Average 60 Counts/km
67bf16a8-ab08-54d2-a6f4-d4ce4a601609 | note | ○ Max 20m NASSRA 70 Counts/km
7868dff0-63e8-5121-b910-dbeec4c1c579 | note | ○ Refer TNZ TM 7003 v1 (2006)
603b03a5-1461-53bd-9ba4-11b89be98237 | note | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
3d0dae37-167e-50fc-8342-11efd9e54246 | note | Responsibility - Paving Contractor
d93f4dea-c870-5e57-9437-2a57d0dbb725 | note | Designer - A
23d4522b-d7cb-53f6-aacb-ddce67433b41 | note | Eng. Rep / NZTA - I
d58f82a8-331d-596f-8d1f-03f2694f1011 | note | Contractor - R
c775ad4c-e357-4577-97c2-a195f6f4cacf | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
e8d478d4-6e3a-5a71-b960-2133d9b9ad50 | textbox | Contractor's Rep Name:
71a6c5ab-79da-57cd-92eb-babc44109f10 | textbox | Engineer's Rep. Name:
a043064e-9b3b-5f60-ad17-c44a1d09e75a | date | Date:
b7816e69-c408-40d6-9548-2bb4dbbfc820 | signoff | Add Signature
a96dfd89-fa48-40b3-8b50-ea53843a3a92 | checklist | ITP - P11 OGPA Pre Construction Rev 0 | itp | ITP - P11 OGPA Pre Construction
b26d0763-d87e-4317-b325-00236dd75232 | section | 1.0. Pre-Commencement Activities
28117a17-64d2-4fef-9c30-fb70c2153b8d | checkpoint | 1.1 - Approved JMF for Asphalt Surfacing
e8393083-8255-5e05-a8a9-8f682abb09d5 | note | Detail of Activity / Test - JMF reference in here
f1e5cbce-db99-52a0-9a97-c9b86701f91e | note | Action (Hold, Monitor, Witness) - H
986e2020-21ec-59be-ac4b-0acab203764f | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
bcceda42-8b1c-5756-9ab3-50f47befb18d | note | Inspection / Test method - Confirm requirements are followed
76ad1203-01fc-543b-9ba9-b7316543cfbd | note | Acceptance Criteria - JMF Validated in accordance with NZTA P11:2023
94a01afb-62c1-5baf-a971-1d09c64677b9 | note | Record documents (QCP - Quality Control Portal) - Mix Design Report
ae40fe16-067f-5298-82fc-65532c308f66 | note | Responsibility - Paving Contractor
4efd4223-91ee-5081-9e6d-af3c521f362e | note | Project Specific Notes / Instructions - JMF expiry date and validation details in here
a58de66e-b738-596f-ae1a-f8d97bc1cc3a | note | Designer - A
efb3f102-038d-5288-b5a6-37d7810da222 | note | Eng. Rep / NZTA - I
dfb18a69-c086-5376-a94b-9d73a3010485 | note | Contractor - R
c399db03-f246-4d6c-9975-f3f480f7160e | signoff | AUTHORITY HOLDPOINT
e1339339-f80c-4aa8-aa50-7f2e8ecdec7b | checkpoint | 1.2 - Site Conditions
fc6d95f5-d13f-5dfc-b9ad-adcc18278604 | note | Detail of Activity / Test - Weather suitable, Site extents marked, surface suitable for paving (Depths/milling/cleanup complete etc), Environmental Controls in place
245d74d7-4202-5ef7-a7be-f8675fe46520 | note | Action (Hold, Monitor, Witness) - H
2b527979-fd52-5365-adcb-084c558e9764 | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
72eae9e8-61f0-5d14-9bb8-009622092cd3 | note | Inspection / Test method - Confirm requirements are followed
21058ab4-c97a-5f17-80a7-3e2a7abadf4e | note | Acceptance Criteria - Weather conditions and Site is suitable for paving
a4553db4-b6c7-5b30-aec7-3fef1f3fc47e | note | Record documents (QCP - Quality Control Portal) - Site Diary
02657ede-ab9e-5474-b15e-fbaa0105b9c9 | note | Responsibility - Paving Contractor
ce05d702-184c-5313-bdde-ca037e2483d2 | note | Designer -
a5de9494-3b53-5941-a09f-ae229df54d79 | note | Eng. Rep / NZTA - I
54cb4d5b-c162-5342-8e6d-bbb2e02fba6c | note | Contractor - R
3a1ab5f5-1d77-4421-8ce0-d03a46f231d3 | signoff | AUTHORITY HOLDPOINT
dd0b867f-5e21-4a2a-aa2e-7c370f41fb5c | checkpoint | 1.3 - Roughness
d5dde96e-8b57-5dcd-a84c-6e7099ecc430 | note | Detail of Activity / Test - Previous layer checked for suitability to achieve Specified Ride
5e86089f-eef1-5e20-91cc-02724e00992c | note | Action (Hold, Monitor, Witness) - H
3c95dde4-c9dd-577a-a920-fd3fde373e7a | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
1a7b5b2d-02de-5e04-8400-eec8c6cfa6e2 | note | Inspection / Test method - Confirm Specified Ride requirements can be met
25c462bd-74f7-5eb4-8203-1b99cf984545 | note | Acceptance Criteria - Site is suitable for paving: The surface to be paved on must have a smooth longitudinal profile, and where a layer of Asphalt is to be placed over a previously constructed pavement layer, the ride quality must be confirmed with the observation of a holdpoint in the previous layer ITP.
7acd1dbe-2528-5e9a-b066-ed23b21315c0 | note | Record documents (QCP - Quality Control Portal) - NASSRA Report
441543fe-1dfc-5fc0-bf24-4493eb1e235e | note | Responsibility - Paving Contractor
9650c3fb-3c02-55e1-bbf9-3c925f9f6b33 | note | Designer -
be032040-1ee0-5dd8-b36e-1c3a26a51508 | note | Eng. Rep / NZTA - I
b8638844-ccd0-57e9-b054-b0ac275b8e31 | note | Contractor - R
34113733-ec51-498d-86f3-3464d6ff3ec5 | signoff | AUTHORITY HOLDPOINT
c5e1396b-ff35-4968-a444-3f184a80883c | checkpoint | 1.4 - Traffic Loops
4469ef07-a888-5cab-9c63-fa537a4061f8 | note | Detail of Activity / Test - Communication with affected parties
cb7f81fb-f0fe-5ef5-8bd8-bf5e78b25c8c | note | Action (Hold, Monitor, Witness) - H
2eaf26b2-6635-549e-9b9c-13fe28907de6 | note | Minimum Test Frequency (Lot = 1 day’s production) - Minimum of 7 days Before Works commence
c901025d-318b-5ca8-a06f-c11f7c04d94b | note | Inspection / Test method - Visual
eb8aad87-912a-58f6-8434-8019224ecf63 | note | Acceptance Criteria - Notify RC at least 7 days before surfacing is programmed
5646f9bc-060c-5c1a-b737-acb8f48419c6 | note | Record documents (QCP - Quality Control Portal) - Communication
5bdaa295-eae2-5726-8afa-fdc88cc9a949 | note | Responsibility - Paving Contractor
6cdd6a66-96c5-51e9-b325-73d7c769e9fa | note | Project Specific Notes / Instructions - only required where existing traffic loops are present
69a82072-2a97-543c-9877-1e7e6ae4e8b0 | note | Designer -
217c161b-f025-592f-99de-5f797ce2bcfe | note | Eng. Rep / NZTA - A
1f81e18d-35fd-5d9d-9595-e37af63d99be | note | Contractor - R
ae19735f-7e7f-410d-b080-190618f3265b | signoff | AUTHORITY HOLDPOINT
6e2f6b9d-8143-4039-8584-4f426b4f8caa | checkpoint | 1.5 - Paving Plan
ace690c1-a94a-5963-8c18-08f39b18def1 | note | Detail of Activity / Test - Paving Plan to be completed
e85b2ac2-1584-51f0-b5df-c63c57efa865 | note | Action (Hold, Monitor, Witness) - H
6ad2acbd-b504-5bc2-b1cd-ed0cdaaa51d3 | note | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
9ae473a1-5ca5-544a-af48-9035b814015c | note | Inspection / Test method - NZTA M27: 2020 Clause 9.5.1
65b0bf29-0ef7-58d4-ba73-fed85e6b5b3d | note | Acceptance Criteria - Paving Plan to be completed for each shift with dimensions, location and type of (hot/cold) joints, areas and tonneages
ca306eaf-359f-5439-9fec-feec43b05c9a | note | Record documents (QCP - Quality Control Portal) - String Sheet
ab599591-d577-59eb-83f7-dac8a571d96e | note | Responsibility - Paving Contractor
bb37965e-f4b4-5801-9dd3-9ddc224e5d0d | note | Designer -
b4f0f502-7f53-5c38-9feb-557b6573ed9b | note | Eng. Rep / NZTA - I
e22370d6-40d6-5628-9b1d-abbd6f604f2d | note | Contractor - R
2199675e-2d8c-4f2c-aa5d-f81e0bafe4db | signoff | AUTHORITY HOLDPOINT
419ef4e6-bf9a-4f47-84fa-804b753f26de | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
a7f89cc9-c621-5c9b-82c9-61cb34dee655 | textbox | Contractor's Rep Name:
4b1ecdae-eb87-546a-b7d7-064df7044114 | textbox | Engineer's Rep. Name:
642c36a8-0e67-5197-81a3-4f3709cea28e | date | Date:
03bc8117-b85d-450c-96e4-5b5845934092 | signoff | Add Signature
ac71ced0-9d52-486c-9194-3b3f71c255c4 | checklist | ITP - Scour Protection Rev 0 | itp | ITP - Scour Protection
67106df5-002e-4208-b4ab-4944f375366c | section | 1.0. Construction
8dcb2349-ad75-4e9d-a6e0-4942ff4ed325 | checkpoint | 1.01 - Mark out earthwork extents
38115d2e-da2c-5b9b-9d23-e4e320e599ac | note | Detail of Activity / Test - Check the start and end location of the rock riprap lining and width will be as per the design drawing
d37a3673-0dfd-5c5f-9314-dc2d18fbcfe4 | note | Action (Hold, Monitor, Witness) - M
d85db474-28c7-5eb5-8644-1db4c4e58fc4 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to earthworks
4fbeb91d-26b5-542a-8b52-343cea40a14d | note | Inspection / Test method - Visual
6e496239-337d-530e-8be8-cc82e532b007 | note | Acceptance Criteria - QA/Site Engineers Approval
7c28788d-5e47-58c0-b9a7-8a09e2e0478c | note | Record documents (QCP - Quality Control Portal) - Setout Data/Checksheet
0bf4ebc9-fdbf-54c8-b736-3623d3e33934 | note | Responsibility - Contractor
c1dd738c-af02-578e-967d-68bdf4d8dc73 | note | QA / Site Engineer - A
77c2cd02-80a4-52b9-88fb-cfb0ba615167 | note | Eng. Rep / NZTA - I
b9a3b15d-2dfd-5202-9c26-6959c797a3c0 | note | Contractor - R
7d7d0f2c-8d00-4224-99e4-5ff7e1257481 | checkpoint | 1.02 - Earthworks
a2dc51ad-00b9-50f3-829f-629c30222c28 | note | Detail of Activity / Test - Excavate to a depth specified in the design drawing
7066487e-96f7-5947-994f-6d9557e5bcff | note | Action (Hold, Monitor, Witness) - M
89de6d22-34c5-5d09-9f38-0603466d8ba4 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - As per design drawings
37400aaa-4c7e-52f2-a35f-b066b7eb31af | note | Inspection / Test method - Visual / Photo
19c920f4-2f03-5920-8ae0-29a72aacfc46 | note | Acceptance Criteria - QA/Site Engineers Approval
64c22701-320c-5f7e-949a-fd83b5c76c64 | note | Record documents (QCP - Quality Control Portal) - Photo
a3768d0d-54bd-5dcf-87b6-b9007345e9df | note | Responsibility - Contractor
b4940ca2-5703-5ce9-a653-a9855ceb2fd7 | note | QA / Site Engineer - A
6b96edec-1593-5610-bb65-0d745afcaee9 | note | Eng. Rep / NZTA - I
00539274-adf6-5dd3-b535-15068bcb591d | note | Contractor - R
a6e4de12-15af-43da-be53-e905f7242a6f | checkpoint | 1.03 - Bedding
9245b047-bedb-5221-8b2a-8e2da095e297 | note | Detail of Activity / Test - GAP40 bedding placed in 100mm layers where required due to exsisitng water table depth
562b1b98-71c4-586d-b51f-32d07018776e | note | Action (Hold, Monitor, Witness) - M
5ec7d6cf-3faa-5dd3-8491-defb9a63149f | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For site where scour protection is required
6539c143-9c2d-5120-81a2-8ed84afc5940 | note | Inspection / Test method - Visual / Photo
951c0056-f367-5304-b743-cd586bbf0507 | note | Acceptance Criteria - QA/Site Engineers Approval
e52617c6-3beb-58f7-885f-6e84061978f7 | note | Record documents (QCP - Quality Control Portal) - Photo
8851ed70-7efa-5c86-9a13-c9eea7ad2ad9 | note | Responsibility - Contractor
b25bcdb9-e705-5849-883f-648559b25ac3 | note | QA / Site Engineer - A
40ffb6e4-24e1-5674-b990-7706d8e77a7f | note | Eng. Rep / NZTA - I
fd9d902d-d360-5696-a891-9094d4e5df4a | note | Contractor - R
b2763736-4d41-438b-aa29-480c1a26821a | checkpoint | 1.04 - Geotextile
391ea13d-3e7c-5ddb-a5c7-569b50dc1951 | note | Detail of Activity / Test - Place geotextile pinned with minimum of 280mm using weed mat pins at 3m spacing along both sides
729f47c6-29ff-5f43-9e92-6f5b49cced9c | note | Action (Hold, Monitor, Witness) - M
f05ca78e-86ea-5672-9a6e-5388549ed50a | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For site where scour protection is required
a6d715f9-9c90-5a0a-a6d8-39778ba44076 | note | Inspection / Test method - Visual / Photo
2c2dbb93-d3db-5d06-aafb-a2a3d1f2acea | note | Acceptance Criteria - QA/Site Engineers Approval
3b27d981-1f28-509a-8a46-f22eacb54218 | note | Record documents (QCP - Quality Control Portal) - Photo
c36f43e7-acb1-501c-8975-526f47197d3a | note | Responsibility - Contractor
411218d3-ce17-576d-b97c-9c60ae3e2890 | note | QA / Site Engineer - A
74729384-cf40-5868-909b-00d3ef4692b4 | note | Eng. Rep / NZTA - I
cd6c2b4e-94aa-5ac5-bd9f-0cbd49dc9ef9 | note | Contractor - R
a3c269a1-14f7-4396-aa20-4d4270ea11cb | checkpoint | 1.05 - Place rocks
d175258e-0b4d-5a4b-9684-2cdee0075a6d | note | Detail of Activity / Test - Place rocks 150mm to 300mm in diameter and slope will be as per the design drawing
8c1bc0f6-bbea-50bd-a978-c62acd1799ac | note | Action (Hold, Monitor, Witness) - H
a4a97267-8a7c-5534-aa44-72e0a6d7580d | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For site where scour protection is required
1a04fec9-de7b-5878-b344-ebe87184fa3b | note | Inspection / Test method - Visual / Photo
cbd2443e-20ee-5dae-83f1-a197e440552a | note | Acceptance Criteria - QA/Site Engineers Approval
1dc934fa-53e1-5546-b44f-3747e58010ba | note | Record documents (QCP - Quality Control Portal) - Delivery Docket/Photo
b389b86b-5757-558c-8c7e-f0ee40f5a5c6 | note | Responsibility - Contractor
b5e6e12b-6ad9-5713-b7cf-d2f5ff5a1978 | note | Project Specific Notes / Instructions - Make sure the riprap is shaped to the specified slope of the channel so water flows freely
e6e9a23f-b52d-5294-9f19-ecfbb254dc09 | note | QA / Site Engineer - A
e96c121a-ef9b-5838-bb74-510b2d391cf7 | note | Eng. Rep / NZTA - I
3b628c73-336c-5d2b-a76c-7371e8ee0e12 | note | Contractor - R
959f9485-6f77-4254-8f14-7be40398b097 | signoff | AUTHORITY HOLDPOINT
2b23b86a-c9ea-44d9-b646-d74a9a0dbd5a | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
21a5b1c4-57fe-52e5-80f5-4f6a2b5a6950 | textbox | Contractor's Rep Name:
a2f52dcb-b8da-5a6d-8deb-ec311d9a3e89 | textbox | Engineer's Rep. Name:
770a91ae-10bd-5b87-98d5-f6078d765e47 | date | Date:
9155ccd4-94b7-4bad-86b7-2b1d8347fe30 | signoff | Add Signature
5219c891-15c2-597c-b5fc-b303c1f82742 | checklist | ITP - Shoulder Construction Rev 0 | itp | ITP - Shoulder Construction
c698dab8-acda-52b7-987b-2acecfeccfcf | section | 1.0. AGGREGATE ACCEPTANCE TESTING
95c95fb1-5913-5efc-bb85-ff15c1ff6647 | checkpoint | 1.01 - AP65
35e57379-9b88-5f0d-9726-151f6267832c | note | Detail of Activity / Test - Crushing Resistance
1096744a-15aa-58d7-9ab1-70159ef03235 | note | Action (Hold, Monitor, Witness) - H
3938bc9e-a39d-5cdb-af61-f6c4fce3a908 | note | Minimum Test Frequency - 1 Test per material per source
3bba8581-9c0e-59c3-b17e-e937f33b9142 | note | Inspection / Test method - NZS4407:3.10
a6b737df-58e0-5384-b75c-d4d5dbd36ef0 | note | Acceptance Criteria - > 100KN
bcc8e6aa-3581-5054-aca3-69e9e553df1f | note | Record documents (QCP - Quality Control Portal) - IANZ report
8009b0da-dce5-5c67-a2e7-9c953693f0c6 | note | Responsibility - Contractor
3cb7bf7d-2863-556a-8d96-f63466479884 | note | Designer - A
837a181b-9571-5a55-9d08-15c1d16fa5a8 | note | Eng. Rep / NZTA - I
194c03c2-1e67-5464-aad4-ccfd2f18bd34 | note | Contractor - R
7080ed31-5a25-55f5-b4e1-2dd53c72e82e | signoff | AUTHORITY HOLDPOINT
73371fb5-349c-5186-b86e-9a0df471df21 | checkpoint | 1.02 - AP65
3bb4ff76-e5df-5843-8bc5-3022912db289 | note | Detail of Activity / Test - Particle size distribution
ba2bae6a-93bb-5a10-8afb-93b8ffc8ed9b | note | Action (Hold, Monitor, Witness) - H
efe53eee-29c5-5973-abb1-a1969d5b31bb | note | Minimum Test Frequency - 1 Test per material per source
20042b9f-023f-58b6-bd2b-9f7a0bfaf07f | note | Inspection / Test method - NZS4407:3.8.1
17313f64-7cf6-51de-bec0-98fe0d434bf5 | note | Acceptance Criteria - As per NZTA M03 Specfication
5055d394-8d14-5ed8-9a56-d9c44a8b1dfb | note | Record documents (QCP - Quality Control Portal) - IANZ report
bc6c2611-62e0-5bb0-ba69-1173fdf5215e | note | Responsibility - Contractor
821cdb63-90de-50bf-ad5c-d92b82eed4fa | note | Designer - A
44f573e8-85d9-5866-9efd-10953d3c183c | note | Eng. Rep / NZTA - I
346523aa-14c1-5b38-b0c3-b2ac5b005b3a | note | Contractor - R
43624c91-c073-54f4-a277-d720aab40ea6 | signoff | AUTHORITY HOLDPOINT
4e96cf6a-d797-5ecc-9a3c-3106b6e3024c | checkpoint | 1.03 - NZTA M04
68820bbd-afd5-5cad-880e-795f725f4a2d | note | Detail of Activity / Test - Crushing Resistance
ba456ba0-f434-5faf-b396-ae6d48bb8808 | note | Minimum Test Frequency - 1 Test per material per source
537f8eb0-6d6b-52f2-8ea4-05826d635919 | note | Inspection / Test method - NZS4407:2.4.7
d77e25f7-90b5-5865-8bb8-e14bcb2b52a9 | note | Acceptance Criteria - > 130KN
311a69ef-e279-5279-a017-a2079a2ebb5d | note | Record documents (QCP - Quality Control Portal) - IANZ report
bba1042d-6ada-5cef-8f7d-8cab188e7f9a | note | Responsibility - Contractor
8068d621-c464-5a6f-95fc-9cdfe52caa2c | note | Designer - A
7a9f4a90-b0d5-58e2-ab09-fbc6f5ceca12 | note | Eng. Rep / NZTA - I
0d816ef7-8056-50e8-ad1f-7498d6a46b79 | note | Contractor - R
0d772a3c-fa2f-5bce-8a45-068038320aa5 | checkpoint | 1.04 - NZTA M04
f734e22d-647b-5fa2-831a-28dda86e6f9a | note | Detail of Activity / Test - Particle size distribution
2b48542e-5737-55b6-b565-9ed53fef28c6 | note | Action (Hold, Monitor, Witness) - H
c9d4f870-b5b8-558b-baf7-0023b3e9fca3 | note | Minimum Test Frequency - 1 Test per material per source
60097ba6-2fbb-51a3-a246-13361c159c75 | note | Inspection / Test method - NZS4407:2.4.7
788a29fc-6bc7-5fc9-93b6-6b840eea0a74 | note | Acceptance Criteria - As per NZTA M04 Specfication
9916145b-72a4-54a0-b139-9da64ec56b04 | note | Record documents (QCP - Quality Control Portal) - IANZ report
41324a53-1986-5995-aef2-826004648167 | note | Responsibility - Contractor
f2b3d62c-a149-53d8-938a-e052dfc37d9e | note | Designer - A
3e7d7ecc-78eb-5412-8add-2bf5f62ddeb9 | note | Eng. Rep / NZTA - I
c9e70f47-7ae6-5988-8057-72731abfb9fd | note | Contractor - R
8f61b55d-8a25-500a-80ba-651bf2555091 | signoff | AUTHORITY HOLDPOINT
56110d7c-4078-588c-9b46-3a22f13f0775 | section | 2.0. CONSTUCTION
5b802e8c-ba68-5859-b05d-d1617c42a80d | checkpoint | 2.01 - Earthworks
b61e58c2-cc9c-5b35-90eb-2c40aaed6e5f | note | Detail of Activity / Test - Cut to Waste Insitu Shoulder
5d5d59b9-dd36-5543-a511-93418ac916d9 | note | Action (Hold, Monitor, Witness) - M
d5391111-a4fc-5224-823c-a9ca4e2f8bb9 | note | Minimum Test Frequency - As per design drawings
c29d8b4a-87d2-54f1-977a-f6d9b195acf4 | note | Inspection / Test method - Visual / Photo
4422d707-9e84-5db7-b49a-0d4564f919dd | note | Acceptance Criteria - Site Engineers Approval
d0b39179-1c91-5845-8268-28c75a4b99d0 | note | Record documents (QCP - Quality Control Portal) - Checksheet
559b55e9-d6cd-5282-956d-99ed63e9e40c | note | Responsibility - Contractor
cffadae0-de1f-5bc7-9414-e703e6d7c9e2 | note | Designer - A
fa63a1e3-cb09-5714-8e9a-b9d2981d5829 | note | Eng. Rep / NZTA - I
b24d30da-3c00-55be-935c-d4ee735dada1 | note | Contractor - R
31360dbf-7714-5a6d-8ccd-564e3b826d4a | checkpoint | 2.02 - AP65 Placement
c4abc028-8aee-59f8-b927-9fbb7df8dd63 | note | Detail of Activity / Test - Gap 65 Placed in Accordance with Design and Survey
ee8958d7-a48c-5862-89c9-f15d5a5d7de7 | note | Action (Hold, Monitor, Witness) - M
d5075a69-4eed-5dc1-bd32-2477b41aef97 | note | Minimum Test Frequency - As per design drawings
459bdb0d-be26-52f8-ba75-d7346de03fbb | note | Inspection / Test method - Visual / Photo
67a4880a-685d-5674-86cd-e39b17507c6c | note | Acceptance Criteria - Site Engineers Approval
9c41f0d6-a996-58e8-b970-7c47aaaf8ced | note | Record documents (QCP - Quality Control Portal) - Checksheet
16db2f2c-2dcc-56a2-bc40-f7ab90d4f8ae | note | Responsibility - Contractor
d0deac72-dbd8-5a8c-9f57-140a4099f835 | note | Designer - A
45ea1efa-e37e-5b08-8847-be3c62defa0e | note | Eng. Rep / NZTA - I
3defcf44-2ff4-55db-adfc-a9034ea12277 | note | Contractor - R
82115d0e-6374-5121-a4d4-3582526729f9 | checkpoint | 2.03 - AP65 Compaction
1614fb7d-4e3d-53a5-b5ce-afde2cb34db0 | note | Detail of Activity / Test - Compact in Layers no greater than 200mm.
d05046d1-5be4-567b-81e7-44958069d048 | note | Action (Hold, Monitor, Witness) - H
fce7cf4d-b95b-5465-be02-fde96a3171bf | note | Minimum Test Frequency - 1 MDD Test per 50m
3fc660e5-07f3-5683-a165-2733938eb5ed | note | Inspection / Test method - Nuclear Densometer MDD Test
2af0169c-3963-51c0-8cb7-76a08d92199d | note | Acceptance Criteria - 95% MDD Achieved
961ea53e-17a3-5bec-a86c-27cc2c17dcfb | note | Record documents (QCP - Quality Control Portal) - IANZ report
b1b1df2a-886f-5fe1-8e2e-18f3c86145cb | note | Responsibility - Contractor
e45a41a5-817f-50bc-8983-7c3105dcb4ea | note | Designer - I
671d6270-4a90-5783-9d79-f70b5538934f | note | Eng. Rep / NZTA - A
17820d7b-c13c-577e-ae97-668df2e97395 | note | Contractor - R
c973d56d-6017-52c9-941b-58cc653eded4 | signoff | AUTHORITY HOLDPOINT
cede2b96-0930-549d-bcf2-ae66198688f5 | checkpoint | 2.04 - M4 Placement
f317e8fd-83e0-58f9-b6d1-f956fcc2d23c | note | Detail of Activity / Test - M4 Placed in Accordance with Design Drawing and Survey
2b9abca4-feea-503b-a0a3-de3ff7798540 | note | Action (Hold, Monitor, Witness) - M
0bfa817f-61ee-5fa8-a86b-e46c5e5d461c | note | Minimum Test Frequency - As per design drawings
591338a7-c1a2-5a44-b8c9-779aab333a15 | note | Inspection / Test method - Visual / Photo
fd5c0053-1cb1-50a2-9228-9478d82a3ce7 | note | Acceptance Criteria - Minimum Width 300mm.
723f53cb-ad4e-540e-8d2a-d4082357eaa3 | note | Record documents (QCP - Quality Control Portal) - Checksheet
71fb81c9-7a64-5437-a492-81ea3e6bd88f | note | Responsibility - Contractor
b128e269-c5a9-55ad-a435-98a89c5f32b2 | note | Designer - A
70804076-5b39-5600-8f06-30d8559a1beb | note | Eng. Rep / NZTA - I
b0f8acb0-6cae-5513-a27e-64a851a89397 | note | Contractor - R
16156f39-99f0-54cb-af34-316fea7147b5 | checkpoint | 2.05 - M4 Compaction
c647409c-f85c-52e9-ac6f-5ca999997459 | note | Detail of Activity / Test - Compact in Layers no greater than 150mm.
13f6bf66-2f9b-561a-8b59-8c56ae6417d7 | note | Action (Hold, Monitor, Witness) - H
8613a141-d1fe-54c0-b494-1627c2439b93 | note | Minimum Test Frequency - 1MDD Test per 50m
a0a2f320-23b8-5049-831b-d182c746c5ae | note | Inspection / Test method - Nuclear Densometer MDD Test
ffa3fdd3-2db3-521a-9786-49828baca648 | note | Acceptance Criteria - 98% MDD Achieved
267e30f7-415e-5abc-bcf7-d74096ac494c | note | Record documents (QCP - Quality Control Portal) - IANZ report
dd624d14-d62b-5e18-abc8-ed27a6dff1d4 | note | Responsibility - Contractor
9bcd581a-f1b8-5c91-aef0-f766f39a87ad | note | Designer - I
8193c8f2-ab15-50d0-8508-5c8c438b0f7c | note | Eng. Rep / NZTA - A
c9b70a26-f2f7-55c7-82dd-cbd939a89d85 | note | Contractor - R
ed601270-afaf-5ffa-8e09-0f348dc467ad | signoff | AUTHORITY HOLDPOINT
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
53af85ce-03f6-585b-82a7-92cf0e32c471 | textbox | Contractor's Rep Name:
ce81b22d-8330-5659-8c3b-d70eb55b7eef | textbox | Engineer's Rep. Name:
460765d8-ad50-5b2d-ae5d-9ec641989812 | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
72ef0b13-db04-4536-b699-ecd6532f05c7 | checklist | ITP - Shoulder Widening Rev 1 | itp | ITP - Shoulder Widening
88b7fe6f-7d86-411f-a112-b749c9083c43 | section | 1.0. AGGREGATE ACCEPTANCE TESTING
4afa8683-d1d9-4d23-adf8-3ca640d6911e | checkpoint | 1.01 - AP65
a9c8c26b-d36c-540e-810d-8a4608604e3a | note | Detail of Activity / Test - Crushing Resistance
49742604-9849-5726-a07a-aab844ef1dac | note | Action (Hold, Monitor, Witness) - H
1f56216c-e912-502b-a57c-e169e28e99c7 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
0c260a2a-d8d1-59ae-9847-57652e03d823 | note | Inspection / Test method - NZS4407:3.10
1406f717-fd4b-5884-853f-f2ad456892ce | note | Acceptance Criteria - > 100KN
c2fbf812-3950-51bf-9906-f17bed5212fe | note | Record documents (QCP - Quality Control Portal) - IANZ report
448cba55-251b-5adf-95aa-be9fcf5398db | note | Responsibility - Contractor
608c79a5-3890-5820-9042-36b0bc0d2500 | note | QA / Site Engineer - A
fe665890-f9ae-5728-b247-aedbb27b261f | note | Eng. Rep / NZTA - I
9c8ad053-7ad9-5054-acae-25300eb3222b | note | Contractor - R
c1a4e5c6-f2a1-4054-9cba-6751123a00f8 | signoff | AUTHORITY HOLDPOINT
375272ee-0ab6-43b8-b015-438cedb2454e | checkpoint | 1.02 - AP65
ad29d2b0-68fa-5ee6-b096-d70fc55063b0 | note | Detail of Activity / Test - Particle size distribution
00317d34-f2f7-510f-999a-cb715b90ebfd | note | Action (Hold, Monitor, Witness) - H
97ae2132-b3da-579f-b7aa-ae3d78e9ef05 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
5320f3d2-f59d-5cb7-8f73-42bb1fadc3c1 | note | Inspection / Test method - NZS4407:3.8.1
ff8c567a-8db2-5af1-9c59-77732e014cdb | note | Acceptance Criteria - As per NZTA M03 Specfication
41c58f76-da61-553e-aecd-4e9f2e4871a4 | note | Record documents (QCP - Quality Control Portal) - IANZ report
71713394-4ad6-510d-83c5-f37728c28728 | note | Responsibility - Contractor
14de996f-7caf-5cbb-92fe-bfca7f6492df | note | QA / Site Engineer - A
315956e9-d62d-540a-8986-eb3ecafb676f | note | Eng. Rep / NZTA - I
29279fd4-3fb5-516b-a57e-c1ff1aafb10b | note | Contractor - R
2ae11cf3-db3a-40d8-9330-2cd210ba892c | signoff | AUTHORITY HOLDPOINT
fb8ec2ca-7323-4514-88d6-b8cedb750c4c | section | 2.0. Construction
4ef21a0b-1fb6-4250-96a8-9208282a0902 | checkpoint | 2.01 - Mark out earthwork extents
3b67bb5e-3f16-5542-a7e9-c827f600bbfd | note | Detail of Activity / Test - Set out and approve extent of earthworks
725c6982-1d45-5588-ad70-1a0632377434 | note | Action (Hold, Monitor, Witness) - M
33ef10a9-1c0c-5138-a878-9857f1763111 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to earthworks
d28394e6-bb3f-57fa-9372-118a5e961c37 | note | Inspection / Test method - Visual
62a16fbf-a942-59d4-a597-fa937a240f46 | note | Acceptance Criteria - Site Engineers Approval
5dda76ed-7964-5c49-8342-eb98ed3db471 | note | Record documents (QCP - Quality Control Portal) - Checksheet
146b6fb7-2f57-59f7-9250-2d3f64d70740 | note | Responsibility - Contractor
29ed8769-7de6-5af6-8d64-11223da27834 | note | QA / Site Engineer - A
c875e7c8-1659-5ffb-8782-1bc3dc539ca0 | note | Eng. Rep / NZTA - I
d83d79d3-e48f-5a17-bebe-ccbed39a5561 | note | Contractor - R
94d1917b-cf1c-455b-9403-893517febe98 | checkpoint | 2.02 - Earthworks/Removal of organic material
eebdcad8-9cf2-5c72-9ad8-7a610d1ed498 | note | Detail of Activity / Test - Excavate/Remove organic material on granular shoulders and topsoil in grassed verge area
b46ca166-63b0-5bf1-a0a5-b9a2535a821b | note | Action (Hold, Monitor, Witness) - M
0be831dd-9067-5bef-8ebf-bfe43465a991 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - As per design drawings
1dbf5388-4b91-5643-9345-b121cd5d6c11 | note | Inspection / Test method - Visual / Photo
14dfa11d-c1e0-5c40-88aa-34775a25fc55 | note | Acceptance Criteria - Site Engineers Approval
349aa8bd-c388-5480-a1cf-a46859391e4d | note | Record documents (QCP - Quality Control Portal) - Checksheet
47e1772d-9387-50b5-b7de-d5b9bee7fa48 | note | Responsibility - Contractor
1581831b-e44e-5847-b545-d2fcee595445 | note | QA / Site Engineer - A
330cdeca-8595-5d85-ba1a-a657cc533c7c | note | Eng. Rep / NZTA - I
a3ea78ae-e0b2-5f7d-8155-fc08ed9214ad | note | Contractor - R
85183463-8770-4e29-a35b-e39e282e4123 | checkpoint | 2.03 - Determine subbase depth
51e68297-3240-55ce-8d6a-b6e178ad64a8 | note | Detail of Activity / Test - Scala penetrometer
f928f661-d312-5ecb-b4b2-6a4186bf1626 | note | Action (Hold, Monitor, Witness) - H
8eec51a6-e0eb-536f-bd09-8ae42f0906b0 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Test Every 20m
51b0d643-0c2e-5f58-a741-64df23b0f282 | note | Inspection / Test method - Scala penetrometer
5d785663-cb0f-5687-91d1-de1b4ab5839b | note | Acceptance Criteria - As per digout table "Table 1: Digout Instruction table"
b26e2835-52e7-51f2-a6a2-f19315c82275 | note | Record documents (QCP - Quality Control Portal) - Checksheet
03c578f8-fd14-5999-9a28-1cfa851f2fb7 | note | Responsibility - Contractor
330b6aca-0006-53a9-86b3-c16d806494dc | note | QA / Site Engineer - A
51eff747-fe6a-5818-9b13-9fb3e4a25f8f | note | Eng. Rep / NZTA - I
c66a4afb-5784-56a0-a0cc-7d1d4791da22 | note | Contractor - R
238fec8e-ad79-41d6-97b9-bfdc914e9de1 | signoff | AUTHORITY HOLDPOINT
f32a36f4-2d8a-4496-a8d6-d9addd7e72a9 | checkpoint | 2.04 - Placement of geogrid
986de9e3-cdc0-5ed8-9e8f-75bbf6ac7a4f | note | Detail of Activity / Test - Geogrid used a contractors discretion as per "Table 1: Digout Instruction table"
bd7a3a01-186a-5537-a4cc-715aab3c4591 | note | Action (Hold, Monitor, Witness) - M
3a807782-28ba-5743-bc1a-a7794fcfe9ab | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Once during construction
613526db-983f-5530-ae11-06ac8409b93f | note | Inspection / Test method - Visual
800186a4-ee50-5ba6-af4b-34fc623503f2 | note | Acceptance Criteria - Site Engineers Approval
fa95b499-6811-5f19-bd60-5b0cc87f5d82 | note | Record documents (QCP - Quality Control Portal) - Photos
475d3f2d-6235-52ce-b483-a4799811d905 | note | Responsibility - Contractor
20cc219d-f9e7-5e23-8a30-74919154b170 | note | QA / Site Engineer - A
e9b00df4-7911-57a6-80ed-fcd69272c37f | note | Eng. Rep / NZTA - I
ab8fecb2-9fa3-5acc-9b55-d9c7267dd1c8 | note | Contractor - R
a00e398f-730c-426d-9e9d-7536709c4896 | checkpoint | 2.05 - AP65 Placement
8a5fabf9-df03-51aa-b8f0-184a2bb2fdfb | note | Detail of Activity / Test - Compacted layers of AP65 shall be placed in layers to underside of AP40 layer
48785604-cb19-5984-8568-157a882f0690 | note | Action (Hold, Monitor, Witness) - H
3c2d9425-99a2-59b2-b220-95d61c533bde | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Test Every 20m
67b85c9f-c560-590a-a563-9ce2be0af97c | note | Inspection / Test method - Clegg test
9cf68469-f8b9-5280-b8c3-b3720017e7d9 | note | Acceptance Criteria - Clegg Result >30
86c1a8fb-dc90-53e8-9a53-8a34aa367f91 | note | Record documents (QCP - Quality Control Portal) - Checksheet
fcb76709-a469-5d8c-8ac5-2b260bb92075 | note | Responsibility - Contractor
53511447-443a-56fb-9c79-b9c0cb33657a | note | QA / Site Engineer - A
0badaf7f-2d38-5875-b079-ce034cc79213 | note | Eng. Rep / NZTA - I
350f6cc8-7da7-5b20-a942-4dabf9d34e92 | note | Contractor - R
e6057b84-317f-41ea-bd09-2dda8042a09b | signoff | AUTHORITY HOLDPOINT
e8ccdb0a-7bcc-4c38-b4ff-1bc63505e577 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
c2bcfb15-0fef-53ef-a4d8-378764a17a91 | textbox | Contractor's Rep Name:
b96d3395-4d99-5e53-bf0c-5ac67ac4b71e | textbox | Engineer's Rep. Name:
0be18f0e-5376-5fe6-ab6d-e4029480a074 | date | Date:
1fd33de4-63f4-471c-836b-cdc3a5565283 | signoff | Add Signature
43d8299c-128f-57d3-898f-78deaaa6f1fa | checklist | ITP - Subsoil Drainage Rev 1 | itp | ITP - Subsoil Drainage
93a76998-15d8-5e32-9bc5-b94428506309 | section | 1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING
a5f3e624-76ac-5efa-80b7-49de3159f4d0 | checkpoint | 1.01 - Drainage aggregate
892bd164-7761-51df-8e27-7490f12610c1 | note | Detail of Activity / Test - Crushing Resistance
f34fe5e5-f850-5a41-ad7d-4c19f3207e77 | note | Action (Hold, Monitor, Witness) - H
0f482f64-9d69-596b-9dc1-aab3b0f19226 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
0cc2c27b-fc73-5ea4-ad39-7021495c136a | note | Inspection / Test method - NZS4407:3.10
72e1e5d1-24aa-5b72-a70c-aa9ac0bf7175 | note | Acceptance Criteria - > 100KN
a3f954bb-aa6d-526e-847a-2b8394d4c523 | note | Record documents (QCP - Quality Control Portal) - IANZ report
b85e7d7c-df5e-5fe7-9e27-e8d606d98895 | note | Responsibility - Contractor
c1d2251b-6dd0-54c0-bdfc-3e5b5989687e | note | Designer / PTG - A
91887811-8daf-59e9-8d6b-f1648e47d21f | note | Eng. Rep / NZTA - I
6255aca9-f902-59b8-afec-477d240bbdfe | note | Contractor - R
cad3f223-dfae-5e66-a518-a0307edfe95a | signoff | AUTHORITY HOLDPOINT
4f88e3a8-e651-55df-b5f6-39a067d0ef36 | checkpoint | 1.02 - Drainage aggregate
a39be7b9-56b8-5f0a-9df8-f444f0f1ba4f | note | Detail of Activity / Test - Particle size distribution
95bf18d8-24eb-52de-a2c3-b590ef0b04a6 | note | Action (Hold, Monitor, Witness) - H
15c684ee-a28f-5cca-9c3d-07b6c2d8ebae | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
2f2e6f30-5519-5827-8fb7-252c3e84ef60 | note | Inspection / Test method - NZS4407:3.8.1
9aafa1ad-1738-5017-aa47-e1f31f7f0123 | note | Acceptance Criteria - as per IFC drawing
f0a83ad7-2ba9-52be-9a3a-fa3a59b0c5a5 | note | Record documents (QCP - Quality Control Portal) - IANZ report
b3e1d23f-72bf-5798-be46-12cf64e5cdc4 | note | Responsibility - Contractor
2ed164a7-a063-5cf5-8ad3-af4649b8a005 | note | Designer / PTG - A
9e7e174e-b7b0-5481-b880-ab8db2a84266 | note | Eng. Rep / NZTA - I
b9a195c4-2fad-5057-86c0-2a0211178461 | note | Contractor - R
f659b5ea-6b28-53ce-97b3-f4b3462269aa | signoff | AUTHORITY HOLDPOINT
24996430-f74a-580c-83d3-5b56d8f409bd | checkpoint | 1.03 - Pipe
043a4a1e-ad56-5d42-8fb6-1226ff2f83ad | note | Detail of Activity / Test - Subsoil Pipe Material
a5c212f6-676f-5130-a012-1859e28901bf | note | Action (Hold, Monitor, Witness) - H
81c98f48-df8f-590c-8a30-f6da899a610d | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - each delivery
c3f67e42-4975-5789-b7b3-3f892fb8d9e2 | note | Inspection / Test method - Dockets for each delivery
ad7b8bb5-35f5-5cee-87b5-59192a179345 | note | Acceptance Criteria - Compliance with TNZ F/2
72aa4e63-78e5-5f11-bc18-3a97a02dc777 | note | Record documents (QCP - Quality Control Portal) - Delivery Docket
77323653-8901-55d8-a8ce-09a1151f1bb6 | note | Responsibility - Contractor
b3ef01d4-5905-5c51-a9fd-b170d911a526 | note | Designer / PTG - A
21dbf408-3b0c-5dae-973f-d9a9427b8da1 | note | Eng. Rep / NZTA - I
dd8956b8-b4da-5615-bd99-e7d12cc8ff50 | note | Contractor - R
c05d1ced-f5c6-5f8d-97fe-3dc4fb8f5f77 | signoff | AUTHORITY HOLDPOINT
56110d7c-4078-588c-9b46-3a22f13f0775 | section | 2.0. CONSTUCTION
78562353-3a4b-5e97-8625-7909e91ad5b7 | checkpoint | 3.12 - Alignment
225b9fb8-1b4a-5cbb-a2e3-0d594a5c06b6 | note | Detail of Activity / Test - Subsoils to be placed behind the Kerb line or as instructed by Engineer
98b368a8-6c55-5105-b15a-67e58eee75a6 | note | Action (Hold, Monitor, Witness) - H
0afc5726-144e-5ee7-9769-e778a43deffa | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
3967d193-d43f-5725-b6ca-0cd961f6c630 | note | Acceptance Criteria - Engineers Approval
5e026732-6372-5e92-9a56-66e13674fd57 | note | Responsibility - Engineers Representative
41974f8b-875d-5194-bb01-fa11dcfddaf8 | note | Designer / PTG - A
1071ea6c-b3a8-5a30-9eb3-5212c6bb5811 | note | Eng. Rep / NZTA - I
321a7003-cbd6-5197-818c-1a77261ce656 | note | Contractor - R
c8c809b8-4bb6-5aae-bc34-5c485d42d3ef | signoff | AUTHORITY HOLDPOINT
7fe7dd42-2a7c-53e8-810c-42ad6557012f | checkpoint | 3.13 - Excavation
3010a6e6-b323-5d74-bc62-f8eb21293df0 | note | Detail of Activity / Test - Excavtion of Trench should be within tolerances.
df3ddbbd-71e7-5bd9-ac0e-121fc0c2acb0 | note | Action (Hold, Monitor, Witness) - M
1992c47c-36af-5815-95fc-1baa0e291559 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
bfe43eb5-d0c7-594b-ae0f-1b71d06ba224 | note | Inspection / Test method - Visual / Photo
53e12fe7-038a-53b0-a118-4c1245242f0a | note | Acceptance Criteria - Trench width should be 300mm minimum. Trench height should be 800mm Min from top of the kerb OR Top of road level where Kerb is not present or as IFC drawing if detail specified
a63e362b-7adc-5674-95de-e0a9a8205384 | note | Record documents (QCP - Quality Control Portal) - Checksheet
f73563de-d3f5-5b64-b4a8-4a0632ba7434 | note | Responsibility - Contractor
b7e2b953-19c9-5826-be95-708e61151b82 | note | Designer / PTG - A
0e7235c6-411f-53a1-b018-0f5def003cfa | note | Eng. Rep / NZTA - I
934d1e6c-df2c-50fb-bdec-05a2b3356454 | note | Contractor - R
8e5144c8-798c-58b0-94ce-a80f59ca743d | checkpoint | 3.14 - Trench Lining
4ce4f9dd-6818-59c3-b6ad-28289ebd7dc6 | note | Detail of Activity / Test - A14 or other approved Bidim to be placed and wrapped around Trench.
5a1243fe-cfdc-5b70-a5f1-a92406dfc141 | note | Action (Hold, Monitor, Witness) - M
fe07117b-979e-5db8-afd7-ba84e9f1261f | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
474083fc-76ee-5d21-9407-2a55f3e95a93 | note | Inspection / Test method - Visual / Photo
98b53697-48e3-5cc0-8c1e-675044c4e7aa | note | Acceptance Criteria - Minimum Width 300mm.
e87bdc9f-4a27-5015-8ea8-3f1ab71bd97f | note | Record documents (QCP - Quality Control Portal) - Checksheet
92d1cab1-d48f-532b-bb4a-b0f3215e9991 | note | Responsibility - Contractor
817c4db7-b05f-5f87-98b5-0ada0b95ca61 | note | Designer / PTG - A
3eb79f8f-e01a-5870-95fb-abb268e186e7 | note | Eng. Rep / NZTA - I
50ba3960-a3dc-57c7-8c34-0b942f09d818 | note | Contractor - R
0b7e61ad-8418-5fea-bf08-dc168b35c93a | checkpoint | 3.15 - Pipe laying
dd05e586-b285-56ea-994f-c14a98cbf6dd | note | Detail of Activity / Test - Pipe must have Min. 100mm of Cushion. Drainage 60:40 Material to be used.
994498ea-7c04-5e2d-803d-1da114ba5051 | note | Action (Hold, Monitor, Witness) - M
acfc6bf2-11cd-5794-ad03-d79c0637a5e8 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
4721141c-1830-5215-961c-2b3ba8c31f6f | note | Inspection / Test method - Visual / Photo
686ba410-5ef3-5823-a7d9-0761795b6caa | note | Acceptance Criteria - Minimum 100mm
acc4caa1-34d0-59cc-8fb0-b65caf60fd0f | note | Record documents (QCP - Quality Control Portal) - Checksheet
74cca688-9e98-574b-ba83-cfb86dcf0045 | note | Responsibility - Contractor
e26fdafa-62b5-5b5f-ac96-cebe5a45e7d5 | note | Designer / PTG - A
40587998-de58-5bce-bce7-342eb4a6130f | note | Eng. Rep / NZTA - I
88b97cf2-4ac2-50d2-a66c-58ab5b4ae729 | note | Contractor - R
b6f0ef5b-7f7b-5854-be83-6bdc529397dc | checkpoint | 3.16 - Pipe laying
34a97d49-6834-56d8-8abb-1479047c71f3 | note | Detail of Activity / Test - 110mm Perforated Pipe to be laid to a gradient not less than 1:200 to discharge
798e7c27-9a3e-5182-9d4b-aa774cb413a1 | note | Action (Hold, Monitor, Witness) - M
dac1bfc2-a633-5c02-8ca6-826c0857e0da | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
669ff28b-7aa5-59ec-9d19-19456949b44d | note | Inspection / Test method - Visual / Photo
4f0ef388-6f90-5ed4-b62d-91923b3436b4 | note | Acceptance Criteria - As Per IFC Drawings
af3508cc-387c-5394-b5be-e8a9ece99ec6 | note | Record documents (QCP - Quality Control Portal) - Checksheet
518de268-3038-503e-8907-f5318d5e0d4f | note | Responsibility - Contractor
900ba9b0-d336-5861-9fba-2784f3c90f40 | note | Designer / PTG - A
36b74398-9edc-56dd-a3bd-34e6f2662c15 | note | Eng. Rep / NZTA - I
6fce5f99-e748-54be-b7a2-0f9e9f304a78 | note | Contractor - R
c20966fc-fb19-549b-a1ec-40afc1bc34c3 | checkpoint | 3.17 - Backfill
0f0349b7-83d2-55d5-90bc-09859ecdf12f | note | Detail of Activity / Test - Drainage 60:40 Material to be used.
d1c9ee56-f318-5585-9173-fd2246960aa2 | note | Action (Hold, Monitor, Witness) - M
097c5c97-59d8-5edd-b816-db96a8f21189 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
d4026709-5a4b-57fc-b383-ce1ddc4b98bc | note | Inspection / Test method - Visual / Photo
af59712c-7bbf-50d8-9b71-55afbec36e81 | note | Acceptance Criteria - As Per IFC Drawings
6d1fb1a1-d590-53a7-9d87-5a2c33892e58 | note | Record documents (QCP - Quality Control Portal) - Checksheet
26cbdde5-6cef-5aae-a5f5-725870b27ed0 | note | Responsibility - Contractor
2da8a0ec-6810-5313-900d-9659becd20ac | note | Designer / PTG - A
2d587657-a17a-51cf-9a24-0a1c3f3d6e1f | note | Eng. Rep / NZTA - I
603ef748-a5fa-56bc-ba37-1c4e3691e06b | note | Contractor - R
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
039e84e0-dc07-5a3f-92dd-579192f38cab | textbox | Contractor's Rep Name:
15d42ad8-6804-55da-afef-962a10ebd38b | textbox | Engineer's Rep. Name:
cf3ae769-fb0e-549a-81b6-251edb874eee | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
b7eba96e-8c5f-4030-b981-73aa1b35d45b | checklist | ITP - Terminal End Rev 0 | itp | ITP - Terminal End
9674bb65-4ca8-4170-9206-bc8e15a94a2e | section | 1.0. GUARDRAIL HARDWARE ACCEPTANCE
799dded4-13fd-4cae-8462-7a3fdb21fa3c | checkpoint | 1.01 - Terminal Hardware
6a9fc801-1a0f-5e0e-b2b2-c07e6c797955 | note | Detail of Activity / Test - Compliant with Standards
22601d69-c9ec-5f06-856b-aba1ed038ed0 | note | Action (Hold, Monitor, Witness) - H
8d3790d8-318c-5ad5-a3d4-7417197d97e6 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
949a996f-675c-5d33-8c81-06ce10404fd4 | note | Inspection / Test method - Visual / Photo
c774dc6a-9a00-5227-b43d-4ef2e697386f | note | Acceptance Criteria - AS/NZS3845
4008f6e9-ca25-504b-b835-08e92dacf35c | note | Record documents (QCP - Quality Control Portal) - Data Sheet
f83f2177-d554-5d5d-a3f7-8f6e64a69a8d | note | Responsibility - Contractor
74444be0-593b-59f0-8e60-4cbdb9727e05 | note | Site Engineer - A
fc919192-c47c-5673-bd88-34d625b3d46e | note | Eng. Rep / NZTA - I
dacc00bd-f9e5-5552-aab3-05a9a3c7e47a | note | Contractor - R
e7cd19a4-72a2-41c7-89d9-bf114d89b2b6 | signoff | AUTHORITY HOLDPOINT
c2bf799a-3ce0-462d-827b-db0bcd0ae8c3 | checkpoint | 1.02 - Terminal Hardware
32b2fbd5-a4a3-5b4a-b949-25c5d20e0af1 | note | Detail of Activity / Test - MASH Tested
12e140b5-53ce-5654-ba65-3e0fb9d7ba78 | note | Action (Hold, Monitor, Witness) - H
5d6c3309-0806-5739-9ab1-13433a9c36d5 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
318481df-a2d5-5057-a0d5-d8bba34b45a1 | note | Inspection / Test method - Visual / Photo
a1ccaf22-e32f-5311-87c7-9c4fbe02404a | note | Acceptance Criteria - AS/NZS3845
d76694aa-8a45-58ba-8a76-152ed9808fa8 | note | Record documents (QCP - Quality Control Portal) - Data Sheet
5db7295f-f471-5623-b111-3e3134ec3982 | note | Responsibility - Contractor
51e7becd-d58d-577f-8231-085e0d291f41 | note | Site Engineer - A
9274c559-0a89-5631-882b-616c4dffe34c | note | Eng. Rep / NZTA - I
8c3bdeab-1987-5e19-ad33-54a7f751ce92 | note | Contractor - R
a6d01587-4f3f-4f48-a4b9-af9e81cf13cd | signoff | AUTHORITY HOLDPOINT
cb147815-7560-4b03-86ba-b4b309ff068a | checkpoint | 1.03 - Labelling
75daf042-fb35-5c68-b7eb-d4650ef3780e | note | Detail of Activity / Test - All components labelled with AS/NZS3845
6e64e96f-ebc6-560d-8d76-68be7ebc124a | note | Action (Hold, Monitor, Witness) - H
32f8425a-6c51-5e7d-aac9-aec86b7f9a21 | note | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
eb85f7dd-159f-5977-8a9e-391758210808 | note | Inspection / Test method - Visual / Photo
9f5901dc-10b4-5bb5-8977-5b500ac8234c | note | Acceptance Criteria - AS/NZS3845
122e1a27-6058-5bed-99f1-59b7a2cd99cc | note | Record documents (QCP - Quality Control Portal) - Data Sheet
c20b6114-e556-5c04-b81b-8cd3141c9050 | note | Responsibility - Contractor
eb08d756-e97e-5738-880d-1e4d888473c8 | note | Site Engineer - A
cc2a91bd-9dbb-5134-9c05-34198022a375 | note | Eng. Rep / NZTA - I
a789a54b-62c8-5797-a711-2f45786e6d76 | note | Contractor - R
adac6d3d-1f19-41b6-821d-c8901f122872 | signoff | AUTHORITY HOLDPOINT
74fd55c5-26bf-42ed-baee-38ae73282de7 | section | 2.0. CONSTRUCTION
3a7ba676-b85d-4dba-96c1-3179047d1428 | checkpoint | 2.01 - Service Location
0ba0a83c-c2f6-5353-9e15-6fbdba4b02cd | note | Detail of Activity / Test - Ensure Service Loaction Plans are onsite. Service Provider Standover if required and potholing if services are in the construction area
d04f9320-a361-5dc5-9f29-a0ff194effe8 | note | Action (Hold, Monitor, Witness) - M
9bbb67eb-e2fd-5770-8621-e5407e82630b | note | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
33a94bb1-8df1-57cb-a734-e03d060d09ee | note | Inspection / Test method - Visual on Site Potholing
9f80b2a7-5fff-5e0a-ba48-2d7829a4458e | note | Acceptance Criteria - Site Engineers Approval
4f41c82d-4517-5725-b002-206703cee698 | note | Record documents (QCP - Quality Control Portal) - Checksheet
d023388e-6d55-52fe-9a92-88ceac729f00 | note | Responsibility - Contractor
59a615e9-bc44-5b6d-ac63-4c359fc55aa2 | note | Site Engineer - A
61b64c72-8de8-5198-87fa-45f51d884e3e | note | Eng. Rep / NZTA - I
5d4b627a-2699-5810-8b23-5958571ca2d2 | note | Contractor - R
30fd832a-cbf9-43b3-b08b-58484d2048ea | checkpoint | 2.02 - Drill Post Holes
b4a9edc7-8655-55dd-8afa-4e66b3256fe9 | note | Detail of Activity / Test - Drill post holes to a depth of 875mm for Rail Post and 1100mm-190mm for terminal ends
ab18e814-9666-57fc-9302-a6065b4904a7 | note | Action (Hold, Monitor, Witness) - M
9477089f-22a4-5146-8c09-0aa71408dfc2 | note | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
541bcffd-ca62-5dd5-beb7-7db862eec50e | note | Inspection / Test method - Measure
e3af394c-68c9-5d9f-902f-2a1c5dc16721 | note | Acceptance Criteria - Site Engineers Approval
09197194-c846-5b8c-bf50-7c4ca92f2e65 | note | Record documents (QCP - Quality Control Portal) - Measurement Sheet
562ba4e0-2847-55f6-811d-4bf7da9c9a8f | note | Responsibility - Contractor
f6ad98c7-5f4e-54e2-ada1-868d1440bc55 | note | Site Engineer - A
39780e14-39d9-5fdf-842c-c93c23e77da9 | note | Eng. Rep / NZTA - I
038fe4d4-4339-5041-80da-254cd6723b9b | note | Contractor - R
29341d2a-740c-4f25-99e9-dfc0b5062a00 | checkpoint | 2.03 - Install Posts
3cf5dfb6-6920-5e5c-890e-472079495357 | note | Detail of Activity / Test - Install Post 1100mm-1900mm deep, Top of post 786mm above finished road level
6705710c-de69-544f-9229-c7ddfed45b78 | note | Action (Hold, Monitor, Witness) - M
fced6f5e-47aa-5d41-8320-31c899bf694b | note | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
b7567577-8ea9-561e-8c4f-a38bf54ee542 | note | Inspection / Test method - Measure
e25336a7-69e9-50f1-bbaa-c39693fead67 | note | Acceptance Criteria - Site Engineers Approval
d2151c94-c34a-5308-9941-584029d7a657 | note | Record documents (QCP - Quality Control Portal) - Measurement Sheet
4e97bd59-bb0a-5ca1-a593-6c13795ba3fa | note | Responsibility - Contractor
d630a918-577b-544b-a58b-60fa2b39a8af | note | Site Engineer - A
136d2938-dffc-51c7-836d-1708853b36b0 | note | Eng. Rep / NZTA - I
ebd5a32d-f299-55bb-a75f-99901fcddc37 | note | Contractor - R
c5f7e863-a5fb-4f01-9000-9c53bec8ac51 | checkpoint | 2.04 - Backfill post hole
733f95b1-d6ef-53df-8039-5d99401f3d04 | note | Detail of Activity / Test - Backfill Posthole
bbdfbef2-d6dc-5357-a292-4b49001f50aa | note | Action (Hold, Monitor, Witness) - M
cfc26ccd-c594-557a-afb1-06e815855dff | note | Minimum Test Frequency (Lot = 1 day’s production) - Where every post will be installed
31f57f13-b703-581e-89f2-e95ae47029f3 | note | Inspection / Test method - Visual / Photo
66275585-ca90-5f72-bfa4-aa9af0f7f414 | note | Acceptance Criteria - Site Engineers Approval
e2ce695e-4017-5abe-a5f6-258b11714bab | note | Record documents (QCP - Quality Control Portal) - Checksheet
d5951da6-6005-5e71-8724-5ab97b2ce3e1 | note | Responsibility - Contractor
275b729e-4225-52f9-9c19-2448e79771a1 | note | Site Engineer - A
775eb86f-404d-5c0f-a0a3-86572c5eb188 | note | Eng. Rep / NZTA - I
e5f808b9-bb27-5375-8891-1038f0bbef7a | note | Contractor - R
e5765110-a516-4200-bccc-4ae7acd7f669 | checkpoint | 2.06 - Terminal Ends
ff7d4162-4073-5b2c-8fde-0ec44feca319 | note | Detail of Activity / Test - Install Terminal Ends to NZTA M23 Psec and Supplier Installtion Guidelines
a9eeb605-550d-50c4-9595-400d7bbd2310 | note | Action (Hold, Monitor, Witness) - H
07befee3-eec7-57b7-a141-5ddd474d67ab | note | Minimum Test Frequency (Lot = 1 day’s production) - At Every Post
fa1ec9f2-1874-54f0-8988-a68b48164f35 | note | Inspection / Test method - Measure
84957a55-b833-580e-b084-87354489968d | note | Acceptance Criteria - Site Engineers Approval
94296c5e-0835-57d6-b855-fc8c50e33213 | note | Record documents (QCP - Quality Control Portal) - Measurement Sheet
9fb0f245-d18b-5e16-b62e-87d423a5b90a | note | Responsibility - Contractor
9240c41f-5eae-54d7-820f-354074363832 | note | Site Engineer - I
79cdb319-c166-5d86-8b3c-5e55593136cf | note | Eng. Rep / NZTA - A
7e91e4cf-9baf-5462-a065-aae1110fad46 | note | Contractor - R
fb4df3b5-fdec-436f-adb1-cb5f363a0b4d | signoff | AUTHORITY HOLDPOINT
1375cd82-9323-4aad-ac9d-7b225667eb79 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
3f42a203-f34c-5ff0-bf9a-daf21df9b06e | textbox | Contractor's Rep Name:
aac96b08-2d71-534f-8828-3ac8269a8dc7 | textbox | Engineer's Rep. Name:
bfb7c538-c12f-5de1-9ad8-8761135cce23 | date | Date:
6f8e4f54-c838-4203-831d-93e0eb3fe048 | signoff | Add Signature
6a4b6364-6685-48f6-a7b0-7ae6dcbd3ceb | checklist | ITP - WRSB Installation Rev 0 | itp | ITP - WRSB Installation
eb7f38e2-771b-4ed5-8878-153675b95307 | section | 1.0. GUARDRAIL HARDWARE ACCEPTANCE
8ac23550-9f93-4fe9-a3f8-6e264c2ecdc4 | checkpoint | 1.01 - Guardrail Hardware
aa159067-335b-59ff-83c3-337f630b6bac | note | Detail of Activity / Test - MASH Tested
869879d1-213a-52cf-b7e3-c746cf31a73e | note | Action (Hold, Monitor, Witness) - H
42f80ef4-8b70-5d33-8e14-acf787070f52 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
5c925873-15c6-5e31-8d3d-e23612b8bbeb | note | Inspection / Test method - Visual / Photo
5ad689c7-189d-5ada-a854-360a3b9dba3f | note | Acceptance Criteria - AS/NZS3845
ff5e8e06-142c-57a0-8349-1dd9e57b454a | note | Record documents (QCP - Quality Control Portal) - Data Sheet / Delivery docket
95b4e3f3-3b42-5ce2-998e-b1c32fe82125 | note | Responsibility - Contractor
511bb469-a135-5544-9fbd-dabc16ad8aea | note | Site Engineer - A
aba55a96-9aea-5963-9ea8-9201189f4203 | note | Eng. Rep / NZTA - I
0681b80b-d43c-5bd2-8bd6-7eb30daae578 | note | Contractor - R
6e7ee11a-7028-452f-9bfb-0db37fd739f4 | signoff | AUTHORITY HOLDPOINT
723bac96-339f-4647-8ce8-4df8326fcedc | checkpoint | 1.02 - Labelling
b6a642b7-9adc-5d6f-bb0f-2eea7257526e | note | Detail of Activity / Test - All components labelled with AS/NZS3845
9840c2aa-dfe9-54cf-b5e9-bba09c629531 | note | Action (Hold, Monitor, Witness) - H
cf724ab9-7fce-5e55-b03b-d01941ac7bcc | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
9a1ad508-ed3f-5457-b9a5-b4ccd52a82f0 | note | Inspection / Test method - Visual / Photo
05002369-9197-5051-bb3c-854630c4ac04 | note | Acceptance Criteria - AS/NZS3845
2d516541-412a-564a-916a-ea0a623612f8 | note | Record documents (QCP - Quality Control Portal) - Product/ supplier certification
96e880a4-2e63-5abd-b9b3-59c41fea9b65 | note | Responsibility - Contractor
dd8101c9-538a-5773-8eb6-ce9903b5d501 | note | Site Engineer - A
5a377c23-0494-526c-b0e4-e1be916e49b7 | note | Eng. Rep / NZTA - I
cb449328-72ef-5486-93d4-064f1329237a | note | Contractor - R
7f3a91ee-1fb2-478f-a511-67542d210907 | signoff | AUTHORITY HOLDPOINT
9e337bde-4705-4f6c-8c69-8092e16322e5 | section | 2.0. CONSTRUCTION
a1a19b23-09af-425b-8ef4-694e35081e40 | checkpoint | 2.01 - Leading and trailing treatments
c0e018df-c8e9-5dc8-a6cc-2a904834d8e1 | note | Detail of Activity / Test - Start and End locations marked out
121a6aa4-648a-56d1-8f82-34d436699a54 | note | Action (Hold, Monitor, Witness) - W
38c63f68-3f6a-538a-86cc-8847e2369d5b | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - All barrier lengths
2277e2ce-156c-5821-a02a-d41b278b06db | note | Inspection / Test method - Visual
2c03c51b-a1ad-5e93-9db4-5684cbfd8289 | note | Acceptance Criteria - Positions in agreed marked out location
b6b1de6c-75d1-59d2-81a7-f021efd91120 | note | Record documents (QCP - Quality Control Portal) - Check sheet
59b5a40e-7f57-5eab-ad43-bba0486ddee1 | note | Responsibility - Contractor
cfeb27e6-3a94-5be6-8e56-abec41c88c8e | note | Project Specific Notes / Instructions - Note: Terminal excavation measured for acceptance against supplier diagram, Anchor bracket installed as per supplier specification and Concrete poured and screened flush or slightly proud of seal.
14b90013-6239-57f1-9877-1044ec0ef8be | note | Site Engineer - A
96082aa6-33d6-5f97-8a66-bd8a28610719 | note | Eng. Rep / NZTA - I
16c21966-0cf5-5ac3-812e-99d7875acb98 | note | Contractor - R
c774f5b4-5e00-4fdc-ac83-db93e6bfe2bb | checkpoint | 2.02 - Leading and trailing treatments
0991ce1b-0d88-5ac5-88a2-a924698a45ad | note | Detail of Activity / Test - Correct type
d287c20a-2c90-5814-a158-e95516701ad3 | note | Action (Hold, Monitor, Witness) - W
58060393-0394-5bf2-91f1-16f5ffdfe905 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - All barrier lengths
873863b8-6d87-5648-9f43-d60506bda5f6 | note | Inspection / Test method - Visual
547def3b-2ad4-5321-b286-dca990d2b6cb | note | Acceptance Criteria - Types as specified on drawings
d3d6f1c8-bf5c-54e5-9d9e-eadc6e44a8ef | note | Record documents (QCP - Quality Control Portal) - Check sheet
ebfa5c31-f4ae-5cee-bd22-326d9e4e8b19 | note | Responsibility - Contractor
056e5f41-32d9-5a08-8ed2-534cd85a01a7 | note | Site Engineer - A
88ba732c-1e79-5138-95f5-1855a12ce0dc | note | Eng. Rep / NZTA - I
7ed2b765-550f-54e2-ad48-95b3b14f1c50 | note | Contractor - R
87b12b5d-a36d-431d-8045-abec1d52e171 | checkpoint | 2.03 - Excavate WRSB Post Holes
9a3c147a-7960-5775-baca-bf050984da30 | note | Detail of Activity / Test - Excavate post holes to a depth as specified in the design drawing
a4d300f1-63e6-56aa-afd5-80e5b8eaea32 | note | Action (Hold, Monitor, Witness) - M
524e37dc-6318-5f42-bb96-c2500f2e9340 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Where every post will be installed
94129cb6-a644-5f18-b98d-e617d0a14742 | note | Inspection / Test method - Measure
bbeabcd6-1597-549d-a6c3-3e2845b98b68 | note | Acceptance Criteria - Site Engineers Approval
674150bb-0d78-566b-ae03-448873a89b5e | note | Record documents (QCP - Quality Control Portal) - Photo / Measurement Sheet
07333d1f-17f5-588e-ba43-79a1e8509a6f | note | Responsibility - Contractor
19ad8fe9-dae0-5c14-ad2e-add164e99d70 | note | Project Specific Notes / Instructions - Sides of excavation shall be parallel and not collapsing
cc4f743d-14bb-5ec6-820c-482224b5cd63 | note | Site Engineer - A
6dfc25bb-cb29-5c05-9f38-e36e5b447638 | note | Eng. Rep / NZTA - I
6686e32e-69c7-532a-b10c-595e4eaffa13 | note | Contractor - R
6ac38c84-89a4-4d7f-b005-ad2f2dbf619e | checkpoint | 2.04 - Cast concrete into WRSB pile
185059ba-ec99-5cbd-a661-51181a489493 | note | Detail of Activity / Test - Check condition of finished pile
5740004a-5dc6-5f72-9066-b5c6c1de48f2 | note | Action (Hold, Monitor, Witness) - M
e4643df7-f675-52ff-8b14-3ce6569c0f1e | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - All piles
c67d63c0-04d0-5673-8b71-1f4581444a4a | note | Inspection / Test method - Visual / Photo
171577e6-1efd-5804-8e8e-60f24c928ae5 | note | Acceptance Criteria - Top of pile is level and Flush with ground at front face of pile
c7a093d4-8530-5543-9e9f-5b698b00c760 | note | Record documents (QCP - Quality Control Portal) - As per manufacturer's checklist
4126518a-fdf0-52db-89e9-ae234bf25b31 | note | Responsibility - Contractor
0db8bf13-e633-5152-bbe4-9faaef82231e | note | Site Engineer - A
93fe81a2-9fd6-525b-9680-9ca3496c810c | note | Eng. Rep / NZTA - I
b0b0531b-b5a1-5053-87e5-740350ca908a | note | Contractor - R
e10c0caa-2380-4161-84ba-ca7e1926099c | checkpoint | 2.05 - Install WRSB
7a6f584e-5bd5-5f04-be5b-b6701e81fdde | note | Detail of Activity / Test - Install MashFlex post at a depth specified in the design drawing and above finished road level
15f3d14e-2075-57ba-88da-85b372945431 | note | Action (Hold, Monitor, Witness) - H
458f5415-1107-5fd4-915e-e8364833649a | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Where every post will be installed
e3629599-8f64-5c9d-b257-ba0f2e948d28 | note | Inspection / Test method - Visual / Photo
8e9cdd70-982b-56f5-8dbc-94166b148ff0 | note | Acceptance Criteria - Site Engineers Approval
57ec0cbf-c469-5e3e-99de-9b3b997f5da1 | note | Record documents (QCP - Quality Control Portal) - As per manufacturer's checklist
7af77299-d3e9-58a7-aeec-0a1b39b5bf51 | note | Responsibility - Contractor
301d332c-bb90-5a0d-aecf-771d18a151ce | note | Site Engineer - I
7e5fa667-6cb8-5de7-9f42-506eec66692c | note | Eng. Rep / NZTA - A
6e2813bd-23db-5fe1-8a24-ac92d1fe8bb4 | note | Contractor - R
e112a58d-0bca-4920-ae8f-fab45e6ba180 | signoff | AUTHORITY HOLDPOINT
25963bd7-be22-4840-b6c4-156aebaeaea0 | checkpoint | 2.06 - Install WRSB
5c102cc6-307c-564c-b51e-ebb515801eaa | note | Detail of Activity / Test - Cables at correct position as per manufacturer's installation manual
e17f2abf-31c5-594f-9f9b-ca26a0ac9a4d | note | Action (Hold, Monitor, Witness) - M
0d9daabf-5377-5e4b-bed4-9df6fcb7303a | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - All post
aceb7071-7e4b-569d-897a-0b705612a1fa | note | Inspection / Test method - Visual / Photo
cfc5c004-0eed-512d-a5e9-501151796b35 | note | Acceptance Criteria - Cables are in or on the seating position
d45b9642-3fb7-5ecc-a31f-4ce48046b44e | note | Record documents (QCP - Quality Control Portal) - As per manufacturer's checklist
d06bda41-81da-5f56-a798-eaa45e2fb821 | note | Responsibility - Contractor
155bf8aa-1bce-516e-b820-203d9b265a43 | note | Site Engineer - A
cbfca5bd-6ba2-5ab6-8912-8f686e232195 | note | Eng. Rep / NZTA - I
53eb59bf-9fce-56d6-b55e-e02d0e88528c | note | Contractor - R
17feee09-a890-4a03-8c9d-4cac04bab22d | checkpoint | 2.07 - Install WRSB
ed232fb4-7334-5705-90ce-b043130c3fe1 | note | Detail of Activity / Test - Ensure posts have plastic cap inserted into the post and insert MashFlex Plug into hole on side of cap.
ea55439e-f159-56b0-b51d-481a9e3e07fb | note | Action (Hold, Monitor, Witness) - M
98407d10-2518-5bdd-b32c-ff5a35d9ef3c | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - All post
dd4f786b-8027-529d-ac07-152ed7ee9495 | note | Inspection / Test method - Visual / Photo
ea2ad359-b2fd-52f7-87eb-bc688b3a194a | note | Acceptance Criteria - 100%
ffac00fe-6e4f-5075-9d9b-6ab18046671a | note | Record documents (QCP - Quality Control Portal) - As per manufacturer's checklist
5e982672-1a57-55bb-a1fd-ad98747dd7ec | note | Responsibility - Contractor
b254adf3-2bb0-549e-83de-f5c8f2102172 | note | Site Engineer - A
96e28bd4-445f-5d12-8fef-892a5e01c4b1 | note | Eng. Rep / NZTA - I
2901c488-bed2-5c63-b12a-fae7bbd572cd | note | Contractor - R
b797ec3a-463f-4282-b052-8cb2e2d15d50 | checkpoint | 2.08 - Install WRSB
74fb5cd6-e363-55c4-ae0b-5dfde5bba7fe | note | Detail of Activity / Test - All cables are tensioned correctly
d816f421-c0a8-5e23-9996-4b735e1a7472 | note | Action (Hold, Monitor, Witness) - M
d6667655-6e22-5196-b97f-55a2b1d5add4 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - All barrier lengths
2509cefa-6dd8-583f-9546-713e3004da09 | note | Inspection / Test method - Visual / Photo
6b86e92d-cbf2-5870-98c0-a93174528ddf | note | Acceptance Criteria - As per manufacturer's installation manual
1f4b992a-bac5-56f4-98df-ac83976a9cab | note | Record documents (QCP - Quality Control Portal) - Photo
b336abb5-70f7-5ca1-b41f-18b3b2d655e1 | note | Responsibility - Contractor
5faa44ba-69b7-5785-8173-f08601528f4b | note | Site Engineer - A
04b3f64e-ef4f-5e03-86b1-a96df90c179a | note | Eng. Rep / NZTA - I
be77862f-bdcc-5701-8d00-ec4dbda3e05a | note | Contractor - R
7601d310-19ca-4be4-b979-e99e1ee7c0d2 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
4e6a6a48-b9d1-5be2-a618-55e4491e4919 | textbox | Contractor's Rep Name:
cb83690f-0fe8-5d01-b28f-be88bd4700a3 | textbox | Engineer's Rep. Name:
a857e97f-9a7f-5765-8d31-e88090d0307f | date | Date:
4cccbd23-b429-489b-883c-5b45bd667648 | signoff | Add Signature
c0970c14-aae2-53ed-8e5c-64e9984b5341 | checklist | Shoulder Clearing Checklist | itp | Shoulder Clearing Checklist
2d3217d1-0311-5796-bbb2-85a233b2c3a9 | section | Pre-site checks for the following
54d56f08-9e7e-517a-bbeb-3bac1959be22 | checkpoint | Photos taken @ Pre start of works
31f33bbd-b990-58c9-8b9d-cc285d03fdb9 | note | Responsibility - FP/Su
f8a85bed-dcec-5d78-a485-fa951ca62bd8 | note | Comment - Field evidence for ITP
7e1aa7dc-8b91-595e-992b-543542958d74 | checkpoint | Check culverts in vicinty of work inlet/outlets
33ca181a-550a-5984-b965-e85fb5d2de8b | note | Responsibility - FP/Su
89e19212-9364-5f6b-8da2-1cf5d168e948 | note | Comment - Field evidence for ITP
36c71a00-55a0-5ed7-a591-e406d7a55914 | checkpoint | Edge Delineators - offset position to re-instate if required
fcf70c19-6229-509d-8d08-222fc744504c | note | Responsibility - FP/Su
ac60b28b-00d3-58d0-8842-51662efa6209 | note | Comment - Field evidence for ITP
f3b6cafb-c052-5bd0-b213-b28a6da66d2a | checkpoint | Permanent Roadside Signage - Offset position to re-instate if required
ff28d3da-8737-5e5d-9079-8732e62388da | note | Responsibility - FP/Su
24b5329e-5718-56e3-9ea6-2ee18fcb9644 | note | Comment - Field evidence for ITP
3498be21-27ac-5327-af21-6944e6ff9c67 | checkpoint | Photos - Post completion of works
9404eeba-5ce8-5a5c-a782-4b0e1a108e33 | note | Responsibility - FP/Su
08d6ecf5-a0b7-56fb-b83a-285aa90dbcd4 | note | Comment - Field evidence for ITP
c681973c-6acc-42a8-8813-a2b387f1a153 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
00e0032e-845d-5f68-9178-b1b4f80d1c01 | textbox | Contractor's Rep Name:
164f802a-b55d-5e89-bd5e-1208ebb6c612 | textbox | Engineer's Rep. Name:
aa7f008a-4862-5955-b803-8e1a99a0e147 | date | Date:
4190a210-9b21-4334-b779-00bdf8ce8574 | signoff | Add Signature
8c6b90b8-2864-5bf2-8550-9d07cc76840f | checklist | Ω (DEPRECATED) ITP - Foam Bitumen Stabilisation - FBS operation Rev 2 | itp | ITP - Foam Bitumen Stabilisation - FBS operation
7d8a5c07-ef63-556c-91c1-09845e30bb0e | section | 3.0. BITUMEN STABILISATION OPERATION
af608214-ad76-51ac-821e-53c72ea11907 | checkpoint | 3.01 - Weather conditions
bf1c6484-4b5e-599c-aff6-4722bd752707 | note | Detail of Activity / Test - Material behind stabiliser
cdf1b233-2a1d-5c1a-b9c7-dd1bcb655c44 | note | Action (Hold, Monitor, Witness) - M
d838f44e-9a10-5cb5-b979-fd669fb2bab8 | note | Minimum Test Frequency - Prior to spreading
98a45d6b-e562-5ecd-8240-2dbf96931769 | note | Inspection / Test method - Measurement
4d534a52-1dc6-57b6-950e-bad9018476bc | note | Acceptance Criteria - Material after stabilisation: BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C
8786e057-2936-5946-b99d-128744a666e4 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
c1c867d9-57ac-5da8-8439-1f5e91066b83 | note | Responsibility - Stabilsing Contractor
04bdeb91-8204-5121-a78c-9fd9e57f7678 | note | Eng. Rep - I
c8c8c6d2-2d9a-5978-87e0-392a05228f96 | note | Contractor - R
a57503f8-34ae-5b48-83b2-56d2988c043e | checkpoint | 3.02 - Weather conditions
9255db96-2df0-5fc4-919a-6424bfc78c63 | note | Detail of Activity / Test - Wind
f22f8524-43dd-5f8f-b417-136e8ffa5aab | note | Action (Hold, Monitor, Witness) - M
f6234824-4928-5d75-aedf-7c99101bfe98 | note | Minimum Test Frequency - Prior to spreading cement or lime
e262af5f-9d8d-5b2d-ada6-ebcb322dca50 | note | Inspection / Test method - Local weather stations
5e3fbcac-d352-59fe-b537-6d9b4966cef5 | note | Acceptance Criteria - Wind speed < 25 km/hr
1d78ceb9-6e31-5c53-89ff-cdbb31a7db45 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
5aef50e8-cbb7-5a16-a362-1d1db4d9b89d | note | Responsibility - Stabilsing Contractor
5c6b9215-5943-5ccd-acb7-57ba5020552b | note | Eng. Rep - I
28355262-de83-5a0d-b325-40df4aacdeeb | note | Contractor - R
370a565e-09ba-5066-89b2-d312ed8fe6fe | checkpoint | 3.03 - Weather conditions
3b794877-a84b-54cf-86fd-87a89688ddbd | note | Detail of Activity / Test - Rain
26b4d3f9-9704-5640-809b-7c837883e26a | note | Action (Hold, Monitor, Witness) - M
e4dd5ad0-7a3f-58a2-9707-2d02a96332e5 | note | Minimum Test Frequency - Prior to spreading cement or lime
7bf939e6-39e4-53a9-8246-e21f9ccc898f | note | Inspection / Test method - Local weather stations
c62bca29-645b-569f-96ba-3bd3961f6e0e | note | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
26a6ec8d-2d6c-5ffa-96a7-65dd831857a3 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
c3084073-454a-5df3-b6c1-ed5878fb6d32 | note | Responsibility - Stabilsing Contractor
21c67299-4991-5c32-b249-dc198fba966f | note | Eng. Rep - I
2399a71f-aec1-5630-b5c3-98c8fe71bbb5 | note | Contractor - R
95561bda-63b7-59ad-be16-92671b5fa5b7 | checkpoint | 3.04 - Spreading of powdered stabilising agent (Cement / Lime)
ebdb1c69-d01e-542a-af29-cd00411caf01 | note | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
665587d1-b012-5647-8432-1169cb2afaf7 | note | Action (Hold, Monitor, Witness) - M
8533d432-e1b2-5c15-b878-ef3a8320e208 | note | Minimum Test Frequency - every 400 m2, every 150m for a 2.4m width
9cef32df-05e5-5425-9134-7f9fd809a187 | note | Inspection / Test method - Weigh mat or tray
aee8a673-c0dc-59b5-b3f8-bb8c5cbb09b1 | note | Acceptance Criteria - ± 0.5kg/m2 of specified rate
83e4c2fc-c068-5a10-b192-d0ac196c3388 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
89ceb06f-fee8-5bb4-86c0-307e7d9a6b2e | note | Responsibility - Stabilising Contractor
29cd1974-c2da-5922-baa2-88a4cbc5bac9 | note | Eng. Rep - I
c7f4d48b-4d9a-5019-b34b-d5df5e927170 | note | Contractor - R
b10437ad-780d-5cf5-a32b-86b5c2169f58 | checkpoint | 3.05 - Spreading of powdered stabilising agent (Cement / Lime)
721b9694-e710-5062-a80a-2c1a80b7e893 | note | Detail of Activity / Test - Compare area spread with weight used for each spreader load
39bdd341-c01e-55b9-afeb-4829d9188ed0 | note | Action (Hold, Monitor, Witness) - M
898403a8-f1ab-5ede-b6b3-be8830b07c14 | note | Minimum Test Frequency - On-going measurement by computer/load cells
cd0ea3a3-dc21-5660-94b5-e5700441918e | note | Inspection / Test method - Measurement each run
eb69fde7-e6dd-5ded-9fa7-6a546d982673 | note | Acceptance Criteria - ± 2.5% of specified rate
ce11192f-f779-5859-8e34-89eb156ba096 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
f007fd1b-4641-5084-ae1a-e95076be6a89 | note | Responsibility - Stabilising Contractor
9dae86dc-7376-5177-8d7f-5f509797a55f | note | Eng. Rep - I
58ed924f-d949-5ef1-8aa7-c5bbfe1fdaff | note | Contractor - R
24af8700-e3ad-53e2-9872-5b973e8627df | checkpoint | 3.06 - Injection of bituminous stabilising agent (FBS or BE)
940f8bac-e707-5c09-921d-bfc2384abc8c | note | Detail of Activity / Test - Flow meter and operator's display readings
cbc6c9a2-98ec-5d4a-9fcc-c8405a95e72c | note | Action (Hold, Monitor, Witness) - M
ba0a952b-8b1e-5900-b5d8-c96c58f6f379 | note | Minimum Test Frequency - Continous monitoring by the operator and the grounds person
612965e8-1945-55f3-bbbe-1bd8f3e3f032 | note | Inspection / Test method - Visual display reading
f1bae931-f2bb-5e7a-8290-8f5e3f8b6929 | note | Acceptance Criteria - ± 5% of specified rate
3dae57ad-629a-57de-8d75-41d373c95675 | note | Record documents (QCP - Quality Control Portal) - N/A
330630e0-7f68-5251-b816-28e36f0f854e | note | Responsibility - Stabilising Contractor
b54dc74d-7779-5a9c-9438-9cc5cc5bf1b8 | note | Eng. Rep - I
b6370a95-48c9-50fd-bbcb-9b46560931af | note | Contractor - R
fd632e27-bdba-59c0-a38e-517af357b185 | checkpoint | 3.07 - Injection of bituminous stabilising agent (FBS or BE)
9320143c-0558-5fc9-b7ce-999549f52ac5 | note | Detail of Activity / Test - Compare tonnes used (from the stabiiser's PCU) with the measured area
cdaa59eb-ff58-5585-9e21-f93edc3474f3 | note | Action (Hold, Monitor, Witness) - M
160259bd-88e0-5a5d-8e1b-0cd57f49e9ad | note | Minimum Test Frequency - Record usage from PCU at the end of each run
dcc6f9b6-b9aa-5d01-80cf-c58c86534daf | note | Inspection / Test method - Record readings at the end of each run
4ab0a6de-ddff-53b9-9f23-8157df54b886 | note | Acceptance Criteria - ± 3% of specified rate
1dfd94d0-9320-5f6a-80c8-ff72b3a184e8 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
ec833f0c-252d-5576-bb29-ceee63c7e41d | note | Responsibility - Stabilising Contractor
4cf0a763-56b8-51d8-ad8c-2948b0ef7a15 | note | Eng. Rep - I
8347c761-20a3-5dbe-8303-aee196d54d13 | note | Contractor - R
f20e4018-cb02-5018-9a42-2135814126cd | checkpoint | 3.08 - Injection of bituminous stabilising agent (FBS or BE)
2dd6d971-5a56-5978-950f-dca62e4477fa | note | Detail of Activity / Test - Compare tonnes used (from delivery docket) with measured area
16513ca9-3a36-5c1c-ad9f-fc4e6ea26e51 | note | Action (Hold, Monitor, Witness) - M
72ff0555-6dcd-5757-938b-2bba4c86928e | note | Minimum Test Frequency - For each bitumen tanker load
907e172b-62c4-5a34-90f8-8f3027a798d7 | note | Inspection / Test method - Dip bitumen tanker before and after
02bd6f9e-f851-5293-bb90-ff3fdddcdb03 | note | Acceptance Criteria - ± 2.5% of specified rate
3918916f-6cd1-5ae7-bcea-bb3743346dac | note | Record documents (QCP - Quality Control Portal) - Daily work Log
a4612f46-baf9-5726-9e84-32d33c073036 | note | Responsibility - Stabilising Contractor
69da0d7f-161a-5500-aa0d-84e1220a9e45 | note | Eng. Rep - I
53afbbac-fe02-58e7-aee1-0862280ba0aa | note | Contractor - R
8e3bb8b0-9071-5b5f-b803-b9492dc4af38 | checkpoint | 3.09 - Injection & Mixing of Water
9164c521-fc99-5ef6-918b-143af100a014 | note | Detail of Activity / Test - In-situ Stabilisation process
eeb9939d-2e3e-5bd3-80b4-ce465bcff4b6 | note | Action (Hold, Monitor, Witness) - M
9077b394-9922-5c18-8188-434f7faee5bc | note | Minimum Test Frequency - On-going visual assessment
85f12cce-8a44-5d29-9303-933b7c6baad0 | note | Inspection / Test method - Visual and hand squeeze test
1d7be9ec-bc16-57fc-b2ae-e020b7a190d2 | note | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
a2d59421-dee9-58d9-b74d-466dcc535607 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
081cdd09-0532-5be3-ad5f-145b1451c3e7 | note | Responsibility - Stabilising Contractor
b4fc1109-2dd0-51ae-8355-6b154724a956 | note | Eng. Rep - I
40df0563-2e8c-5cf5-a35c-280d40772c0a | note | Contractor - R
6f689875-b573-5a5d-a031-c872cab76c63 | checkpoint | 3.10 - Depth of stabilisation
430efee4-866e-5c94-95ff-c2b89438033a | note | Detail of Activity / Test - Depth of stabilisation
e73d659d-a765-5b9f-8431-4c3482cd6067 | note | Action (Hold, Monitor, Witness) - M
318b605b-00c5-533d-bfa9-9abfdfc91ac2 | note | Minimum Test Frequency - Every 200m
dd1e137a-4bad-5474-8907-e3e2c2988ead | note | Inspection / Test method - Measurement
b0642379-449f-5949-89b9-b42debbc1ba7 | note | Acceptance Criteria - +15mm / -5mm from specified depth
43a3ff64-86db-5034-a083-78cb508d0002 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
7f4b1954-163c-51fd-91da-4363d2284609 | note | Responsibility - Stabilising Contractor
4a236261-8177-5f5a-b552-b774d90ab1ae | note | Eng. Rep - I
50774958-11af-5df4-b8cf-f823fb6197aa | note | Contractor - R
996c047b-b383-5398-b2e5-174cc51d9571 | checkpoint | 3.11 - FBS material
46ddfceb-e2dc-5285-bef1-5d42bbff8e5f | note | Detail of Activity / Test - Stabilised material strength - ITS
aba067f2-10d9-5920-9874-263c29977d4a | note | Action (Hold, Monitor, Witness) - M
9eddfadb-2bf8-55e1-b56d-864742308805 | note | Minimum Test Frequency - 3 soaked ITS + 3 dry ITS per Lot or when the material changes
9302794f-4594-5093-a1dc-020f08e22296 | note | Inspection / Test method - NZTA T/19N: 2020
243da002-7e36-5e35-88d7-d6a5361beda8 | note | Acceptance Criteria - Testing at 1mm/min:
a12c0c0a-c8ef-5ae4-8c5d-234cd28ade6b | note | – BSM Dry ITS: 150 kPa to 400 kPa
ad0ef415-126e-5b68-9b35-f156f5ecbda3 | note | – BSM Soaked ITS: 120 kPa to 350 kPa
3e92d676-8338-58c8-afeb-d3b2f94af728 | note | ○ Testing at 50.8mm/min:
0c75f157-1187-5bda-a8fe-e2dc77d687e3 | note | – BSM Dry ITS: 180 kPa to 450 kPa
dcd870d0-d701-54aa-8c7e-f95f2be36e84 | note | – BSM Soaked ITS: 150 kPa to 420 kPa
fd85fda4-7d45-5544-8430-b728d11602c2 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
bbb9674e-69f1-5c83-9126-4d55f4da1ef0 | note | Responsibility - Stabilising Contractor
6bfcaeac-1fab-5138-b203-6cffa1ba0cfe | note | Project Specific Notes / Instructions - ITS briquettes to be produced on site if travel time to lab > 30 minutes.
3194d33e-6103-5de6-b860-6d56d9eb56bb | note | Designer - I
44d1196c-c8e6-5363-9096-2a74ac38df9a | note | Eng. Rep - A
85966a30-6d1b-5449-a6ef-c17c4500b91f | note | Contractor - R
282cd773-5475-5295-be4e-fe72c63daca4 | checkpoint | 3.12 - Compaction
94df43cc-3457-5f64-9a9c-9b7c901de1dc | note | Detail of Activity / Test - Plateau Density Test
97c1bfc2-fe8d-5f3e-b0f0-5efdc97cc65d | note | Action (Hold, Monitor, Witness) - H
ce2ba0b4-32ec-5c6f-a084-6e613a485634 | note | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
619a2e82-8961-53ac-b044-885cf1ea6e39 | note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
8cfac5bb-cd9f-54ca-94db-717ae8f9debe | note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
fda27670-4486-58fe-9106-9305fa135f94 | note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed.
46fabe8f-2536-512b-b496-67468c67d8df | note | Responsibility - Stabilising Contractor
b38976f3-013d-5de3-a279-68d125e3211c | note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
aff8f298-738e-59f2-8515-b4da5176d8d3 | note | Designer - I
337ccb98-0115-561f-8b36-affafc83a401 | note | Eng. Rep - A
bfa39a51-afb0-59a1-9454-0fa170473a11 | note | Contractor - R
44f1ac26-1aa0-52de-b445-284dd2c096eb | signoff | AUTHORITY HOLDPOINT
b240a4e1-ae7d-55fb-8fc7-2291889e060f | checkpoint | 3.13 - Compaction
895ffb88-e626-5b90-ae93-29cb6d7b2e5f | note | Detail of Activity / Test - Maximum Dry Density
dd87a4f8-5552-563b-b16b-c77ebc9dbefa | note | Action (Hold, Monitor, Witness) - M
135ee69a-60d5-5818-b118-62e6b8e39b42 | note | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
8f33c499-ffe7-508b-a7c4-d1db3d998c16 | note | Inspection / Test method - NZS 4402.4.1.3
6a862b84-251b-5649-8fa7-97c714e2aa62 | note | Acceptance Criteria - For analysis of DoC
2c1efbd0-5101-5e99-8226-3234f2dd5ee1 | note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squeeze test on site
1c711be7-0074-50c3-96dd-6cc129d50e92 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
04f668bf-4e54-5c14-9dce-09bba300c67a | note | Responsibility - Stabilising Contractor
1f04e8eb-0cf1-5d60-be40-ad0335c75f2a | note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
2def514a-7ca6-5f8d-a5f4-e3a14069e43a | note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
4b5f73eb-1e11-5297-b682-04741336cb04 | note | Designer - I
8eff42b5-fbe8-58db-bb8b-9fad6c1d48ab | note | Eng. Rep - A
602aa6ca-e822-5916-b1fe-be624525db29 | note | Contractor - R
0a559649-a0d2-52f7-b074-270ca0fd084d | checkpoint | 3.14 - Compaction
ea7c2f8b-85da-5cae-9a2b-bed429949bcb | note | Detail of Activity / Test - Degree of Compaction (DoC)
a06659eb-2a21-5e7d-a1ea-5224ac7e6dc6 | note | Action (Hold, Monitor, Witness) - H
d2be0f71-255f-5330-a37e-665929025a42 | note | Minimum Test Frequency - 5 per 1,000m2
24996e1d-2b67-5194-baa0-e8735f9c7167 | note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
51d15499-b0f0-5b14-bcce-1578834a3321 | note | Acceptance Criteria - Average DoC ≥ 98%, Minimum DoC ≥ 95%
3c856d1e-d8a6-58b2-b2e3-48939a227795 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
cb326d81-f1c7-5b33-a680-19e6a606be28 | note | Responsibility - Stabilising Contractor
a31fbe3f-f80c-5432-8e27-9459b5a67caa | note | Designer - I
204779c9-1ab2-509b-8cdd-8f485e24b9e4 | note | Eng. Rep - A
845e8c38-421b-52ea-b999-778ed3d695b5 | note | Contractor - R
09907a7e-b8ac-55af-86d7-54a4eb6dd2d4 | signoff | AUTHORITY HOLDPOINT
ee894289-8d62-5908-a46f-1f8cb914db27 | checkpoint | 3.15 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
279a365b-eb80-5950-8b33-18400b76f6bb | note | Detail of Activity / Test - Clegg Impact Value
9ccbea11-2515-51b6-b136-0310bc9c1773 | note | Action (Hold, Monitor, Witness) - H
0d398692-c5db-5cb8-89e8-8dad889b3e49 | note | Minimum Test Frequency - 5 per 1000m2
2f454144-5322-5840-8b1a-9e6308c59667 | note | Acceptance Criteria - CIV ≥ 50
bd73bf20-b534-5666-9df9-a13d92368c17 | note | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
3a1d5b3b-5040-5666-a36e-5dc27cdd0564 | note | Responsibility - Stabilising Contractor
9322bdb9-2f67-5cac-9cfd-5df2e99c2af9 | note | Designer - I
87b0d417-32cb-5566-9a04-cb4b936b8bd9 | note | Eng. Rep - A
8907282d-39fe-5149-8657-f7b421b9e6a5 | note | Contractor - R
ff9696ad-6315-5efc-8a40-f00e8b18ec4b | signoff | AUTHORITY HOLDPOINT
2ff06908-b759-5c93-b9dd-ef2534702099 | checkpoint | 3.16 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
076f6efb-1864-5aaa-b943-39404e4dc85c | note | Detail of Activity / Test - Degree of Saturation, DOS
7513f3ed-f9ac-5c1e-a55c-b08777cdd7a9 | note | Action (Hold, Monitor, Witness) - M
b12a852c-f85c-564a-8140-54251915d391 | note | Minimum Test Frequency - 5 per 1000m2
4bc976ad-567d-58db-9d01-ce89e5c7c727 | note | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
770a66a2-4b4e-5ade-a53a-49fa580e620c | note | Acceptance Criteria - aim for DOS ≤ 80%
c038888e-0ba7-524f-90e7-10f82f6f0348 | note | Record documents (QCP - Quality Control Portal) - IANZ report
1e36d244-7c1f-5908-b258-d0c17461c8e4 | note | Responsibility - Contractor
025eca51-65aa-5d1e-b0a3-249a203ec500 | note | Project Specific Notes / Instructions - Report only
83003806-b015-58b5-92f8-9896692fb120 | note | Designer - I
5dd4b705-ce13-554f-9a3c-dec1e8853a3e | note | Eng. Rep - A
b71769bc-6331-566c-bb51-a56302930a33 | note | Contractor - R
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
9f467806-3159-5af2-b225-c579ce379a68 | textbox | Contractor's Rep Name:
9175d3c1-8949-512c-87ba-fbc4f3ac627a | textbox | Engineer's Rep. Name:
6d81d04d-d8d1-5ae3-8178-e344ab519238 | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
53b728fd-35dd-5895-b9d5-efb641fae0d1 | checklist | Ω (DEPRECATED) ITP - Foam Bitumen Stabilisation - Material testing Rev 2 | itp | ITP - Foam Bitumen Stabilisation - Material testing
2c878e23-6776-56d1-b32d-96c1f8886c38 | section | 1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING / DESIGN and DRAWINGS
2189a59b-ab5c-5aaf-a16d-20e4889b64a5 | checkpoint | 1.01 - AP40 Basecourse Aggregates used for overlay (if applicable)
2be96bb7-6c0c-5926-ac1b-ca0c880debba | note | Notes:
6b60cde3-a076-52c2-82cb-df72348a8c74 | note | ○ H = Hold point up to approval of Optimisation Testing
b8d9dc26-c68a-59c8-b140-84cb741e195a | note | ○ M = Monitor during production
44cb94e2-5deb-581d-9fdf-7decd2b94643 | note | Detail of Activity / Test - Crushing Resistance
a67ddada-b7d7-59f0-a839-8eb6538b623a | note | Action (Hold, Monitor, Witness) - H
abe27d99-e116-52e8-8500-ca71c2c91d9a | note | Minimum Test Frequency - 1 per 10,000 m3
1004da4d-d78a-5f86-a8b7-167c3ea963db | note | Inspection / Test method - NZS4407:3.10
835c398d-d1f2-5be2-972e-393135dfe6d8 | note | Acceptance Criteria - < 10% passing 2.36mm sieve at 130kN
bdd2553f-368c-5c42-90cb-7da4b2340459 | note | Record documents (QCP - Quality Control Portal) - IANZ report
358f516b-6ef8-56fc-a67e-819b6ce0c527 | note | Responsibility - Contractor
af8d10bb-b98c-5920-bf44-ba976690ee0b | note | Designer - A
8f75bd8f-5beb-5835-8727-0dcad67ca5d7 | note | Eng. Rep - I
dff76d2c-7bc4-5932-87ac-3a15feddf510 | note | Contractor - R
f8ac0270-c831-5210-a25b-4023a5c9921e | signoff | AUTHORITY HOLDPOINT
7190500f-a01e-5474-b73b-446c15351b48 | checkpoint | 1.02 - AP40 Basecourse Aggregates used for overlay (if applicable)
4ffc1667-558d-5388-9a19-c25608ca297a | note | Notes:
5208cf25-d715-5648-b791-86dbcaf71eac | note | ○ H = Hold point up to approval of Optimisation Testing
3a938b9d-195f-5759-9869-f515bac7f3ea | note | ○ M = Monitor during production
9ac6ef2d-185e-5a2a-9c4e-4e0bfe5f9a86 | note | Detail of Activity / Test - Weathering Quality Index
831d9244-bb0d-5074-97b5-5b8ba2437ef0 | note | Action (Hold, Monitor, Witness) - H
36bacb34-47e9-506d-ba36-ea0b6a0c7e1f | note | Minimum Test Frequency - 1 per 10,000 m3
1ea0bfbc-c0bd-51d3-927a-712a8ff6869e | note | Inspection / Test method - NZS4407:3.11
8ff42178-5bad-5583-8443-e087b12c236c | note | Acceptance Criteria - AA, AB, AC, BA, BB, CA
e6ce47ce-3640-5558-b8f8-c90f901c4b1c | note | Record documents (QCP - Quality Control Portal) - IANZ Report
9f301995-af5d-599b-af26-6391a3c266d1 | note | Responsibility - Contractor
221c93a4-bdf9-5933-a11f-1992e3cc3311 | note | Designer - A
b7b87438-fb95-5e7c-aef0-894e66d5b883 | note | Eng. Rep - I
7630fb3e-7c51-5c6f-9373-4d8af63dd6e9 | note | Contractor - R
a79ec079-6ee7-5270-af93-8acdb5f2f916 | signoff | AUTHORITY HOLDPOINT
1e2e44c9-c466-505c-ac8a-b66f589ae86e | checkpoint | 1.03 - AP40 Basecourse Aggregates used for overlay (if applicable)
7cef6196-93cb-5f10-85df-2deb45cb78cd | note | Notes:
41fa4727-9d24-56c1-b832-be570278357d | note | ○ H = Hold point up to approval of Optimisation Testing
3c555323-b2d0-5dbe-99c3-1390e979a593 | note | ○ M = Monitor during production
0c225179-17fe-572b-bd00-5aa340f45ce6 | note | Detail of Activity / Test - Calfornia Bearing Ratio (CBR)
3f7d1555-d69b-5bce-a03c-3ad6330875fd | note | Action (Hold, Monitor, Witness) - H
e5432fe0-047f-5ee2-9369-f3331185303c | note | Minimum Test Frequency - 1 per 10,000 m3
f95a00e1-b939-5c44-8fc2-43512b8cb33f | note | Inspection / Test method - NZS4402:4.1.3, NZS4407:3.15
aaf1f638-37d5-52f9-9d05-6c3727fca140 | note | Acceptance Criteria - Compaceted using NZ Vibe Hammer, 4-day soaked CBR ≥ 80%
839a0cbd-512c-5aad-8a6c-a24d2001a0ea | note | Record documents (QCP - Quality Control Portal) - IANZ Report
1fedaadb-0da6-54c7-9f88-564f09fcad4c | note | Responsibility - Contractor
d0919354-e816-596d-9c14-30a0531d1316 | note | Designer - A
f1c7cfb3-4f9b-518f-93e0-df4835143364 | note | Eng. Rep - I
06b309dc-9592-56ff-bacf-833d4cc24188 | note | Contractor - R
f19ba02e-cb02-5f5a-8fc9-1bf64b0c820d | signoff | AUTHORITY HOLDPOINT
1f70fbad-bf68-541e-9e4c-8004a811fcb4 | checkpoint | 1.04 - AP40 Basecourse Aggregates used for overlay (if applicable)
29fcdce0-c389-5938-b623-1485fbcbba1e | note | Notes:
c4a5d39d-1721-5084-8ae0-791b9f28fe02 | note | ○ H = Hold point up to approval of Optimisation Testing
dc8f0e98-f62f-5ce8-ab9b-860ef99ece95 | note | ○ M = Monitor during production
61a25e50-cf99-5f27-be64-bb170fd19e4f | note | Detail of Activity / Test - Quality of Fines, either PI or SE or CI
a79f631f-322f-5335-b815-87d8d8e8918b | note | Action (Hold, Monitor, Witness) - H
82269d80-64b8-576f-8a68-b08f83f06e69 | note | Minimum Test Frequency - 1 per 1,000 m3
6dfe5250-37a9-5a4c-8629-42d16901527f | note | Inspection / Test method - NZS4407:3.4 - PI, NZS4407:3.5 - CI
c8042915-cf0c-5795-8a82-e189f07b399f | note | Acceptance Criteria - PI ≤ 5, CI ≤ 3
f5d8e078-c06b-5ec4-8238-7e433a310a72 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
fdfae6bf-3aeb-5d04-a63d-727e80ee607f | note | Responsibility - Contractor
7479c61b-713f-517c-abf5-761e0c5db5a1 | note | Project Specific Notes / Instructions - NZTA M04: 2024
ebe7da54-3c7a-5966-936d-b20cc790048e | note | ○ AP40 - Class 2
48518c5f-8864-5ac2-a828-d00caab28b47 | note | ○ PI and CI applies
36dd4c22-363b-59bf-a5cc-63d880ce3898 | note | Designer - A
50322dbc-73d3-5fb5-848d-1d329bf73e05 | note | Eng. Rep - I
32d3bbe7-7e78-523e-8559-ec0722529793 | note | Contractor - R
9ff5300f-182a-5806-afa6-2b910a068af9 | signoff | AUTHORITY HOLDPOINT
d13ee096-7e11-5355-8393-18024c9d1e70 | checkpoint | 1.05 - AP40 Basecourse Aggregates used for overlay (if applicable)
0c8e92c7-7ed4-5e55-a6b1-c094cbfd809f | note | Notes:
5670b73e-8239-5ed4-975d-67de0012093e | note | ○ H = Hold point up to approval of Optimisation Testing
55f8240c-d2f9-5723-87b6-cc644a7b53f6 | note | ○ M = Monitor during production
ba53d257-936c-5200-9d7f-47ba0c1ae8cd | note | Detail of Activity / Test - Broken Faces Content
ff907705-dc70-5ab8-9370-466ce9e07338 | note | Action (Hold, Monitor, Witness) - H
61e0549e-a006-5b26-8501-fda74e9e538c | note | Minimum Test Frequency - 1 per 1,000 m3
68257f0d-71d4-5a88-b80e-3aabe1d9cce6 | note | Inspection / Test method - NZS4407:3.14
7d2908e5-c9cb-5b64-b3e9-333ee71491ef | note | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
1b96b731-05a8-5032-97b2-201415efc3b0 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
b691630f-ad4a-5d35-8a1b-39fa1398989a | note | Responsibility - Contractor
36088737-964a-5328-a9fb-81c5ee27000e | note | Project Specific Notes / Instructions - Waived if aggregate is from crushed hard rock quarry
e39af9a5-5302-5b14-85e4-3c63e757e768 | note | Designer - A
7608746f-7cfc-51fe-b885-4f448dccf5dc | note | Eng. Rep - I
2f4ff281-89e9-53bf-9ffc-bfb352ad1ffe | note | Contractor - R
59facf33-8b24-5aea-a70e-27302b09c103 | signoff | AUTHORITY HOLDPOINT
da58415a-8ab9-59e6-a272-90011bf9daff | checkpoint | 1.06 - AP40 Basecourse Aggregates used for overlay (if applicable)
330c3d66-c883-57af-98a4-2d261d85644a | note | Notes:
1cac7bad-f3a4-55fc-89c0-668808964e8b | note | ○ H = Hold point up to approval of Optimisation Testing
6d32ce48-c6f8-5c7c-82ca-0b3cb2dbc346 | note | ○ M = Monitor during production
3360b542-c969-5a28-9f98-80bd0c1e68a0 | note | Detail of Activity / Test - Particle Size Distribution
b8815777-d2c8-5db3-abb5-57a9320d1306 | note | Action (Hold, Monitor, Witness) - H
968e708b-f84e-569a-9a61-3d609440e0e1 | note | Minimum Test Frequency - 1 per 1,000 m3
e15ec36a-d3cd-5293-b4a8-8564744661dd | note | Inspection / Test method - NZS4407:3.8.1
aaa5a23e-c000-5d21-acc0-f98f5a181e30 | note | Acceptance Criteria - NZTA M04:2024-Class 2
1c59c933-0ade-5e3b-878d-10e94d0c2c4f | note | ○ Class 2 in Table 12 for PSD
9bf9f95d-3d07-57f6-914f-767b0adb961a | note | ○ Table 13 for shape control
df88dd2a-a737-5ca3-a67b-171d6c5abb55 | note | Record documents (QCP - Quality Control Portal) - IANZ report
d4c03406-3f39-5ed4-bbdc-b09b08d7f07c | note | Responsibility - Contractor
98119672-b744-502f-b9c1-c400e8fd798f | note | Designer - A
0bdab5ea-76d5-50de-8520-17b36a370269 | note | Eng. Rep - I
101f5f10-b192-5239-b8eb-8e8a82e01502 | note | Contractor - R
07af15a4-f073-507a-b3a2-d1390d2fea53 | signoff | AUTHORITY HOLDPOINT
08896f81-0242-586b-b2c9-7af7fcc93201 | checkpoint | 1.07 - Optimisation of Stabilising Agent(s)
c59cb70f-a542-5d0f-ac29-4bde8dc67a53 | note | Detail of Activity / Test - Blend Particle Size Distribution
e40a9819-80f4-5c76-bc58-8fc8f4f07a40 | note | Action (Hold, Monitor, Witness) - H
a76fc138-9412-5945-8caf-01a3e81813b9 | note | Minimum Test Frequency - 1 per 1,000 m3
3c7cfd20-f8e8-52fc-bc2f-f7388661b91b | note | Inspection / Test method - NZS4407:3.8.1
5d9d3997-c568-5166-8d5d-115b1ea8df4c | note | Acceptance Criteria - Check if average of existing (from TPs) and any overlay will meet the ideal FBS / BE grading.
6ed90226-d0d2-51c2-9269-886ed53b0c95 | note | Record documents (QCP - Quality Control Portal) - Report using IANZ Reports for AP40 and TP PSDs
ce2e495a-de60-5618-9cb8-b09f40f19297 | note | Responsibility - Designer
a6bea5a2-5454-56ec-ada1-96031f36b355 | note | Project Specific Notes / Instructions - Designer to advise if "average" blend is acceptable.
af2c082e-4053-5eab-9356-9c3c75d88c3c | note | Designer - R
cd0edee6-a0be-521a-a4d7-1a19b180149c | note | Eng. Rep - A
c81e4e7b-2b17-5be5-8e37-94bbfe9136a5 | note | Contractor - I
f36f75d4-7750-5515-81f8-aa50ccb50b7b | signoff | AUTHORITY HOLDPOINT
35ce236a-4a10-5624-9faa-7f5d956b1e82 | checkpoint | 1.08 - Optimisation of Stabilising Agent(s)
b8e9cf8c-b981-546b-bf0a-e0e00d0d04e4 | note | Detail of Activity / Test - Indirect Tensile Strength, ITS
d3a8fcd3-444d-5d5d-bd54-bb0e37dc4f51 | note | Action (Hold, Monitor, Witness) - H
3c804a95-cc5c-540a-8881-6de58d0482aa | note | Minimum Test Frequency - 1 Optimisation test per aggregate type
74cbca82-d97a-5a9e-9ed3-3a454bd13b3d | note | Inspection / Test method - NZTA T/19: 2020
d0ab84cd-8747-5223-8a47-6edef0ef086e | note | Acceptance Criteria - Testing at 1mm/min:
6b36fd4d-306e-5241-9486-0be75b963fa1 | note | – BSM Dry ITS: 175 kPa to 400 kPa
d80eeca7-92f0-58bb-b447-2cfd4bff2890 | note | – BSM Soaked ITS: 150 kPa to 350 kPa
4be42e74-757e-51cb-ad97-62f97ba94f74 | note | ○ Testing at 50.8mm/min:
1aa46efc-7ec9-5e20-930e-dcaf9776fe55 | note | – BSM Dry ITS: 210 kPa to 480 kPa
9f9249ad-db95-5dcf-bfb1-65d999187cae | note | – BSM Soaked ITS: 180 kPa to 450 kPa
8a27c126-f71d-554c-b0ba-e7aa44571343 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
37996d42-76c0-5a62-b6b9-4aa8f47d0d61 | note | Responsibility - Designer
61007cb8-3a85-57c9-8445-0c9fac31e3dc | note | Project Specific Notes / Instructions - Designer to advise on binder content(s)
8a7d9996-331d-560b-931f-1ff888c72da0 | note | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
da00eef4-6cd9-5740-8650-6434740c164c | note | Designer - R
b6b33a87-f49c-55cf-b58d-d8dee93fdf8c | note | Eng. Rep - A
ccdbf693-802a-52fa-aa75-dad9369ec8b3 | note | Contractor - I
de74396f-e7d9-545b-942a-ccbba3cf64f8 | signoff | AUTHORITY HOLDPOINT
566a2cac-17fc-5bee-abbc-76f7e15f851c | checkpoint | 1.09 - Optimisation of Stabilising Agent(s)
a43eccaf-f3b5-5d54-b3aa-1ccc10dab72a | note | Detail of Activity / Test - Unconfined Compressive Strength, UCS
5163e712-a786-51e3-8069-17a32cc042ea | note | Action (Hold, Monitor, Witness) - H
d5033425-d998-5db1-b0a2-91fcc6156d5d | note | Minimum Test Frequency - 1 Optimisation test per aggregate type
1a3d7d3f-eba9-526a-8968-99f14d19ccae | note | Inspection / Test method - CCNZ / NPTG / CETANZ Industry Guide
dd908091-e0ec-5756-8afa-58542f7f37a8 | note | Acceptance Criteria - UCS limits set by the design engineeer
d10f92e6-d951-5ffd-89f1-c2eca2332b5d | note | Record documents (QCP - Quality Control Portal) - IANZ Report
32f5c099-7e9f-5928-beaf-b35549621023 | note | Responsibility - Designer
ef8b71cf-6267-503d-86cf-eaa6b44ac946 | note | Project Specific Notes / Instructions - Designer to advise on binder content(s)
d44724e7-6631-5725-b128-f939d46f2d8e | note | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
00c77a89-1741-5e69-a3dd-73078bdc2a38 | note | Designer - R
710e85aa-f817-508b-88f6-bccf0ac0a3bc | note | Eng. Rep - A
d32b622a-c529-583a-9105-bc0b874eab64 | note | Contractor - I
9e943081-4317-5d39-9b7f-ba8cece60612 | signoff | AUTHORITY HOLDPOINT
195a2faf-7a45-5eb2-8042-63df8f67bc36 | checkpoint | 1.10 - Optimisation of Stabilising Agent(s)
5102cd68-90d2-5f9c-a82c-5880b9f96ac9 | note | Detail of Activity / Test - Modified Maximum Dry Density
2696df96-953a-5fd3-8a6b-698ca7ec44ff | note | Action (Hold, Monitor, Witness) - H
3cabd14b-f360-537d-b6f2-2ce15f9bc54e | note | Minimum Test Frequency - At Optimised Binder selection
9a915276-6433-5acc-ac28-a72f5029b9db | note | Inspection / Test method - NZS 4402.4.1.3
aaa84404-cd28-52ec-b0af-cb3219e22549 | note | Acceptance Criteria - To determine target density
beb493d0-25c7-5ada-ae3f-0d2a808d7a2d | note | Record documents (QCP - Quality Control Portal) - IANZ Report
ca37069a-6583-5821-a55e-4a2005c6c0bb | note | Responsibility - Designer
c2bd7448-1fc6-5d5e-aae3-f798e9e64b2f | note | Project Specific Notes / Instructions - Required before Stabilisation comences
2ee64c4e-f5ed-5bb8-87b1-d7b60069103c | note | Designer - R
7e0c8a3b-73f2-58af-9bc4-ba5b86cb8f11 | note | Eng. Rep - A
d32f49b2-7cf0-5a4f-8cad-2563797a760e | note | Contractor - I
2c4925be-5308-5d55-8f78-d036bac09a05 | signoff | AUTHORITY HOLDPOINT
c8f4a115-4a04-511e-850d-81372308e158 | checkpoint | 1.11 - Stabilising Agents
c4ce7296-c36c-4013-8ca6-002309b6fa93 | note | Detail of Activity / Test - Lime (if applicable - check PI delete otherwise)
bad54209-3657-4c90-9f62-6c873e6964ec | note | Action (Hold, Monitor, Witness) - M
7b85f721-201d-4b25-a3ab-08d2516b25e2 | note | Minimum Test Frequency - Per Batch
36aa5dab-10d1-524c-b47f-ead486899240 | note | Inspection / Test method - TNZ M/15
935bf754-ffa7-50de-a0aa-f74c9b262f4b | note | Acceptance Criteria - Conform to Specification
8f195ba8-32b1-56e2-be03-c2c27ff002a2 | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
82922af0-569f-5f43-a6fe-cef54b8a1b91 | note | Responsibility - Stabilising Contractor
a76a6524-eac5-5436-b47c-b9a7e3b7f33a | note | Eng. Rep - I
32662f39-395e-54a3-8ca6-79d0083de5cd | note | Contractor - R
172bde55-4d7e-5f39-9978-237b26419b12 | checkpoint | 1.12 - Stabilising Agents
2a71928f-f6e8-5aa8-9b44-ad2173ea3bb0 | note | Detail of Activity / Test - Cement, GP
d14576ee-0953-574d-ad25-e8bbd702dd95 | note | Action (Hold, Monitor, Witness) - M
017160d4-1215-5c55-966c-27cacdbc9704 | note | Minimum Test Frequency - Per Batch
72f5dd1d-8efd-5df2-a878-55524fbd1ff3 | note | Inspection / Test method - NZS 3122
2e1bff71-7117-50de-add8-0d432f2ffcef | note | Acceptance Criteria - Conform to Specification
41134f69-b911-59aa-a51b-9b4534e3d04f | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
6d8e47c0-160b-509e-b789-a817012ce8c9 | note | Responsibility - Stabilising Contractor
c32b6bcd-6d75-5b8b-ab42-6354f04a80cb | note | Eng. Rep - I
923dd80c-15f1-548a-b020-9c1ad26295ac | note | Contractor - R
de45a645-a240-595c-966a-58a1636ee3af | checkpoint | 1.13 - Stabilising Agents
7c9e023a-aa4f-5b49-97c6-887c60fac9d3 | note | Detail of Activity / Test - Bitumen (130/150)
9f0f6b93-0b33-5bd8-8265-74934fb4fbaa | note | Action (Hold, Monitor, Witness) - M
cf385a56-b6a1-5519-9811-3a852321ae28 | note | Minimum Test Frequency - Per Batch
aeb405e1-9120-5281-bc9a-f8f4ca477fba | note | Inspection / Test method - M/1
d7293de5-c7ae-5eee-9a27-5942037a7774 | note | Acceptance Criteria - Conform to Specification
1e7f7990-1964-5e67-86f0-0d8d47ec9061 | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
f13a01f1-800b-56d3-b6de-353e4d3de7c9 | note | Responsibility - Stabilising Contractor
0fca182b-80f7-5cf5-94d3-7577addc0b85 | note | Eng. Rep - I
b772df7e-da45-5f7a-8d2f-8d4b397402e3 | note | Contractor - R
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
eafcf5ad-e777-5b4a-b855-eb62fa796eb8 | textbox | Contractor's Rep Name:
28925e9f-edf1-5c44-b410-ed24b68961b4 | textbox | Engineer's Rep. Name:
9d58d381-e766-5776-9b99-cbc21798a670 | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
c0afefc0-0d3a-59fa-ba49-690741245615 | checklist | Ω (DEPRECATED) ITP - Foam Bitumen Stabilisation - Post FBS testing Rev 2 | itp | ITP - Foam Bitumen Stabilisation - Post FBS testing
ef9933ec-a5b2-5221-99d3-63e2931331b8 | section | 4.0. Testing and Sgnoff
0ae622e6-7eb0-50ce-9c0b-b2705d1eae59 | checkpoint | 4.01 - Finished Pavement
96c1be4c-60c1-5af3-b10e-3ab1676e1599 | note | Detail of Activity / Test - Crossfall
303ee57f-7e45-5ed3-b9af-e69ff1d41927 | note | Action (Hold, Monitor, Witness) - H
e427087e-3806-5b1c-9a5d-696fdc1a6d8a | note | Minimum Test Frequency - every 20m
cd26945e-6c83-5332-9c4c-a4838a29ddac | note | Inspection / Test method - Measurement
d783f69d-f1d9-5fa4-bb5c-07d2402ba2b3 | note | Acceptance Criteria - ± 0.5% of specified crossfall measure 2m apart
6f3b24d5-e97c-5132-a9c9-b049e9d8f82f | note | Record documents (QCP - Quality Control Portal) - Survey
f99fdda2-79d3-5b01-94b9-579976d2a95a | note | Responsibility - Stabilising Contractor
1af74a00-ece8-5248-92d0-32e6ac4951fe | note | Eng. Rep - A
c288a246-2924-55f4-95db-dfabd4a429b5 | note | Contractor - R
ada2a90e-b6d9-5ad3-b6c6-6963fb6cdc85 | signoff | AUTHORITY HOLDPOINT
a4334684-77b4-54c9-81df-5f4c11875473 | checkpoint | 4.02 - Finished Pavement
fb854560-f217-52d6-98bc-32e4bcaaf74f | note | Detail of Activity / Test - Stabilised width
6656ef11-04a7-5799-a0e0-84f9bd6e32fd | note | Action (Hold, Monitor, Witness) - H
be250ba6-823a-5bfd-9178-52044238cf01 | note | Minimum Test Frequency - 1 every 20m
0e59090d-6e7f-530d-bdae-0dd73ade6a95 | note | Inspection / Test method - Measurement
0a254045-5eaf-5241-a10c-375498b3e064 | note | Acceptance Criteria - -20mm, +100mm
7090634a-fd50-50b8-bab0-1381ebc1db90 | note | Record documents (QCP - Quality Control Portal) - Survey
df2a1356-65af-5d6f-8693-2fc9168375fd | note | Responsibility - Stabilising Contractor
5d696d34-0140-5877-87a0-5115d0fd463e | note | Eng. Rep - A
b2e1d640-6df6-5fda-a61e-72cc41705be7 | note | Contractor - R
934b6ffe-a825-5a81-aee2-91d8b63fe426 | signoff | AUTHORITY HOLDPOINT
b6bc4d38-17d7-5e78-b522-122c00f03e47 | checkpoint | 4.03 - Finished Pavement
689d31fa-bccd-5568-825a-0ae6c72bc43c | note | Detail of Activity / Test - Surface Shape
737b2d76-73da-5158-86dd-102d50866d30 | note | Action (Hold, Monitor, Witness) - H
42e8bdea-ec00-56a0-a1ad-2f5be8abdc86 | note | Minimum Test Frequency - every 20m
1fe05709-b8e2-5a0d-80aa-4f5d5ba95b5e | note | Inspection / Test method - Measurement
6f9d14b2-46f4-50a8-af67-f8ccbb08df5d | note | Acceptance Criteria - < 10mm using 3m straight edge
3a0cd3d7-d49b-51c7-993b-605c78daad95 | note | Record documents (QCP - Quality Control Portal) - Survey
ae285b78-4acb-5d7f-8a07-512b1b10c016 | note | Responsibility - Stabilising Contractor
5a1bcd6d-e926-575b-9cc2-3691eab78352 | note | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
de955122-cb8e-510e-b716-0a18c6c9d246 | note | Eng. Rep - A
5dba1616-d55b-59d7-ab96-8cc6f7917e80 | note | Contractor - R
248d83b7-7123-50af-a279-986aae3af4b7 | signoff | AUTHORITY HOLDPOINT
255fb776-d469-5fdb-ba2e-7f8919edd342 | checkpoint | 4.04 - Finished Pavement
0305029f-b78f-5ca7-9764-0e97885dc83c | note | Detail of Activity / Test - Surface Levels
8aa1d9c0-9856-5df4-8538-bdfbe4f21ed6 | note | Action (Hold, Monitor, Witness) - H
759311f6-505c-5d77-96a6-1a6fe0697e9e | note | Minimum Test Frequency - every 20m
6878214a-d5fb-5076-9855-6e8cf72854e7 | note | Inspection / Test method - Measurement
7fce1301-1f40-51fe-a9e1-fbd8e8bcb9e2 | note | Acceptance Criteria - -5mm, +15mm
b64790f4-39d8-58bd-9edb-0e75a248f2aa | note | Record documents (QCP - Quality Control Portal) - Survey
6a648ff2-1886-5207-84a3-9241ef3d88ac | note | Responsibility - Stabilising Contractor
7b0581f2-8f3e-561d-846c-5ddcbd87db02 | note | Eng. Rep - A
65b376ea-59cc-5737-82e8-a2b775df8de2 | note | Contractor - R
e9339e84-75fe-5708-9519-17147eeac825 | signoff | AUTHORITY HOLDPOINT
ae75c6db-f39b-562e-99b2-31135d9b2bda | checkpoint | 4.05 - Finished Pavement
689509f4-e511-5e09-ac74-9d2f562b6e7e | note | Detail of Activity / Test - Surface Finish
d6b1ee2c-44be-51c8-b99f-f3c7f784dc91 | note | Action (Hold, Monitor, Witness) - H
b9b7073b-f7a1-5587-ad70-46d0bde008ca | note | Minimum Test Frequency - Per Lot
7a1944e0-55bc-5927-98d3-2a902006222a | note | Inspection / Test method - Visual
0dd6c5ef-9088-5d24-a462-201fc044e19d | note | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate
7be3d1f7-24f2-521e-b391-f315b69acacd | note | 2. Smaller aggregate held in place by fine material
eb34b168-bb56-57b7-a5df-618af16be619 | note | 3. matrix does not displace under normal trafficking and/or sweeping
7e34500f-4af4-5b88-b4d7-f0feaff4ef18 | note | Record documents (QCP - Quality Control Portal) - Survey
813c4773-95ab-5454-9ab4-2187fb2fc493 | note | Responsibility - Stabilising Contractor
0127748e-d36e-5a17-b62e-65ae51c4dabd | note | Project Specific Notes / Instructions - ER to be present at pre-seal inspection
c93da31d-8d3a-50d8-80ca-7a6e81a8df9b | note | Eng. Rep - A
a96b2e46-0455-5146-9e8b-5e388fe6e83b | note | Contractor - R
ed24b156-18b7-5514-8f17-2a36224f3386 | signoff | AUTHORITY HOLDPOINT
7897e817-f7ba-5b64-895f-252e4f9a31ba | checkpoint | 4.06 - Finished Pavement
9e3201ae-a942-5a4a-bcdc-cc5db18ab0e5 | note | Detail of Activity / Test - Roughness
a4dac419-ac24-55c2-91bb-a00aa183ee37 | note | Action (Hold, Monitor, Witness) - H
969d6d55-4d71-57a3-8fab-fa4a935e7bd6 | note | Minimum Test Frequency - Before Sealing
5f431c6e-7e0a-516a-88c4-d43fd57e4bf2 | note | Inspection / Test method - TNZ TM 7003 v1
64247a25-5e34-5e9d-b060-1b068b66c40c | note | Acceptance Criteria - 100m rolling average ≤ 75 counts/km
9ead2cea-2a9d-5541-85b9-d9a319465190 | note | Record documents (QCP - Quality Control Portal) - Test Certificate
90feccc1-bc12-58b2-a483-3c45bdb5c05a | note | Responsibility - Contractor
404d4612-81e0-5ada-a4f4-804699b11957 | note | Eng. Rep - A
8d42ca14-67de-5863-81ff-3359bc06b541 | note | Contractor - R
4d36e68d-0791-5825-9003-c3ddacd76129 | signoff | AUTHORITY HOLDPOINT
4dc83566-2b54-5917-a0b2-af7e46c1f654 | checkpoint | 4.07 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
f609e5f4-9f21-55c8-b5e6-639809885834 | note | Detail of Activity / Test - Clegg Impact Value
92e7565d-1fd8-5053-847c-d54c76d98e2e | note | Action (Hold, Monitor, Witness) - H
bf7182e8-0fc7-5ff4-98d1-8c309ffec07e | note | Minimum Test Frequency - 5 per 1000m2
73f414f4-2e9b-577c-aa4b-ac38e12dfc88 | note | Acceptance Criteria - CIV ≥ 50
55d07aa6-d51e-5913-b811-c769595ff291 | note | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
253faca2-8fa0-5aa4-9231-f9c540774c71 | note | Responsibility - Stabilising Contractor
67f393de-03f0-5dc9-8598-ed1458f07db0 | note | Designer - I
5879cfc6-f54d-52c5-b49d-f3d183065cde | note | Eng. Rep - A
0f952d34-1784-50da-aa2b-075ba33b4205 | note | Contractor - R
92bfeb8e-d658-51db-88af-371dbdc2b6db | signoff | AUTHORITY HOLDPOINT
e0d12d11-3fe6-5066-8f07-dfd0eab986d4 | checkpoint | 4.08 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
769bf83c-afac-5518-b734-3e1645cca1b6 | note | Detail of Activity / Test - Degree of Saturation, DOS
78924db4-f33a-55d2-a996-12e95566b576 | note | Action (Hold, Monitor, Witness) - M
d9a4e6a0-2ae7-52ef-a2e4-cc560cb00456 | note | Minimum Test Frequency - 5 per 1000m2
34e02569-7033-530d-8cce-7fabf520a176 | note | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
694b0f07-07f5-5775-9203-3a9a312c270f | note | Acceptance Criteria - aim for DOS ≤ 80%
2e4568b6-fd36-5651-b47b-a2f6f3de5434 | note | Record documents (QCP - Quality Control Portal) - IANZ report
ca99d6c1-6f9e-5151-82f9-a787a0209250 | note | Responsibility - Contractor
b21f3d7c-8b55-53ae-95a3-dfe29ae193c8 | note | Project Specific Notes / Instructions - Report only
15b4fda8-ff06-574c-8fcf-0c65172d6d85 | note | Designer - I
98d6f31a-0228-5574-863f-64f0dba48ad7 | note | Eng. Rep - A
87c8315e-cfe7-5c49-8f09-e73acd65a55b | note | Contractor - R
bf9aa5a4-4f84-5833-9c3f-5f06cdbdc554 | checkpoint | 4.09 - Pavement Layer Signoff
59db984f-18fc-5bbb-8c93-c40efc20b576 | note | Detail of Activity / Test - Assessment of all test results for conformity
3ff8f330-7dd1-5612-97cd-f61cb88f8986 | note | Action (Hold, Monitor, Witness) - H
24c5f4fa-69a4-5b90-9f12-ec06abc3a504 | note | Minimum Test Frequency - Each Lot
b08eb498-07a5-559b-b196-aece4f631eb7 | note | Inspection / Test method - Site Inspection
95857bec-9882-52ee-ae71-eecd084b9079 | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
40ea1a6d-5e3b-5a16-bf7c-5fb88d319f6c | note | Record documents (QCP - Quality Control Portal) - NCR
ec6aacfb-7a40-5e84-945f-4617db91e072 | note | Responsibility - Engineers Representative
13d0bd72-ef15-5dfc-9ebb-f7c308a770df | signoff | AUTHORITY HOLDPOINT
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
c70b3a1f-4316-5bc1-b043-c02bb00899ab | textbox | Contractor's Rep Name:
d0b10919-6ee0-51a3-9ab1-5ce99b85cec7 | textbox | Engineer's Rep. Name:
89b0e04a-acb2-5690-9d09-1ed07e8437e9 | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
62c98eff-12a5-5815-a0e9-ce29c3ae03af | checklist | Ω (DEPRECATED) ITP - Foam Bitumen Stabilisation - Pre Treatments Rev 2 | itp | ITP - Foam Bitumen Stabilisation - Pre Treatments
f5b26802-56e5-5ba0-a846-0b42f4a8f00b | section | 2.0. BEFORE BITUMEN STABILISATION STARTS
73925125-4bb6-5b15-9df0-f1097d746b20 | checkpoint | 2.01 - Setout section
9986ba90-c19e-53d7-b6d6-543561667f35 | note | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
d42cc76d-8c2c-5f25-9fdb-b5a43a1d8d6a | note | Action (Hold, Monitor, Witness) - H
50fd8f32-62cf-51f6-ac17-c53fbd7cbc91 | note | Minimum Test Frequency - Prior to each section
04e2fb85-c450-58d6-b7f8-ba471b0d3495 | note | Inspection / Test method - Survey
d59bd00e-cbe4-5658-8e55-bc7191d452b2 | note | Acceptance Criteria - Document existing furniture
aebf6bc9-949e-510f-b1b0-f77b7dcd0b8e | note | Record documents (QCP - Quality Control Portal) - Electronic survey files
c2209223-fd6f-5f44-bf2b-643faf798da6 | note | Responsibility - Contractor
b35cdc80-4ade-57cf-be0b-80128ce338e5 | note | Eng. Rep - I
62925157-f9bd-5bd5-a326-d480d3964f1b | note | Contractor - R
b37353bf-82bc-59ab-8210-8aa26b900eb1 | signoff | AUTHORITY HOLDPOINT
6577eaaf-f9d6-5757-8631-64b6f9d2763a | checkpoint | 2.02 - Setout section
8ed385f4-ae21-42ec-b914-db8263db9da4 | note | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
124a5b3d-2bb7-413a-9e19-9eddce469ee1 | note | Action (Hold, Monitor, Witness) - H
0fe913ff-aeb9-4aeb-a34e-391d4e90e1e3 | note | Minimum Test Frequency - Prior to each section
1e102184-047d-4da0-8ebb-9e964d570f8f | note | Inspection / Test method - Survey
07c3e80d-699d-4154-88b6-8834a2b8a61f | note | Acceptance Criteria - Document existing furniture
eb446f25-9e54-4735-b670-02c49d0b4475 | note | Record documents (QCP - Quality Control Portal) - Electronic survey files
1b0805a0-dd1c-42a8-ae24-ff25eafcfc19 | note | Responsibility - Contractor
c4235e74-5413-4162-be32-ec4e9d4c47c4 | note | Eng. Rep - I
6a1402e5-fea8-41e2-aa2b-8153b08bba91 | note | Contractor - R
abae6ffa-7398-580b-88e2-a37900dda993 | signoff | AUTHORITY HOLDPOINT
efa35cbc-c67b-5fe5-a7b5-bc7651308ac5 | checkpoint | 2.03 - Pre-hoe, shape and proof roll
e86205a7-3a5e-544d-af31-274cae7c83d3 | note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
f225cb08-9cb7-55b8-bb68-3f285d265540 | note | Action (Hold, Monitor, Witness) - H
67e775ab-3697-554b-b93b-f667e659c874 | note | Minimum Test Frequency - Prior to stabilisation per section
2a715791-f618-5cf4-8e44-9adb1da04d7d | note | Inspection / Test method - Use grader's machine control and inspect shape
75aa2875-41ba-5425-a3bb-96b3f8541b25 | note | Record documents (QCP - Quality Control Portal) - N/A
336b9167-5e70-5cfb-8da8-3cd9ebbed80a | note | Responsibility - Stabilising Contractor
baf45511-898a-5660-b3d4-b5bde1ce1ab1 | note | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
79cf8e45-e680-530a-acf3-fc6b8913857d | note | Eng. Rep - A
8bdaa2e4-5a90-5288-9f3c-f2b88eb85969 | note | Contractor - R
5280ec0c-1aba-5058-a333-43986c60eb43 | signoff | AUTHORITY HOLDPOINT
6eb8f315-ef2e-5e9b-a474-a945d238ce0c | checkpoint | 2.04 - Pre-hoe, shape and proof roll
67c09e5e-9f7c-52f5-98c5-36988159ee07 | note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
a17a2f57-8250-5e9a-b9ee-ac5b932b2df6 | note | Action (Hold, Monitor, Witness) - H
e7e1b973-5f2a-5cd1-acac-b3548f626313 | note | Minimum Test Frequency - Prior to stabilisation per section
a95a23a8-7cac-51b7-b6f9-b216b30c979a | note | Inspection / Test method - Visual check or Vibratory Roller's response meter
ffa7385d-50db-511e-8b9f-ac59b0ab7d5b | note | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
eeddcd5e-3b16-5d6d-930f-e74bec2e70b2 | note | Responsibility - Stabiliisng Contractor
5df9f9d4-d87f-5c6e-8aaa-0be95a4e724c | note | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
54bd17e1-1b4d-5bfa-8423-e5bac4204f8b | note | Eng. Rep - A
a81a7ab6-3421-5636-a0a6-8e93a855df89 | note | Contractor - R
371e9bf6-3059-5c34-943a-3cfa902e3837 | signoff | AUTHORITY HOLDPOINT
da17c8d0-621d-511d-92c7-ede1066b5aaf | checkpoint | 2.05 - Overlay and check levels
c3a51bfa-7a87-5b34-aa78-c70890ac5204 | note | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
0dedecaa-21cd-544e-99ed-5d5975f77bd0 | note | Action (Hold, Monitor, Witness) - H
b8165694-2c15-5b3d-8eaf-48aa667ab772 | note | Minimum Test Frequency - Prior to stabilisation per section
b9f35ebb-3655-5dde-98f0-4125773fa528 | note | Inspection / Test method - Survey
ec63e4c3-2d36-5cd6-b5ea-fbc5b713aee2 | note | Acceptance Criteria - As per NZTA Z/16
12bfcd31-7c74-5183-8aff-28f67e4b0602 | note | Record documents (QCP - Quality Control Portal) - Check with Grader and visual inspection
dcb2dd0e-2ac6-5a20-b5e6-ede5308ee183 | note | Responsibility - Stabilising Contractor with Main Contractor
bb4cca72-5c2c-5035-8201-71bc1f7e659c | note | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to):
ce01f28a-f4a2-5de6-ad2d-32e02eb1f21e | note | ○ overlay aggregate quality / consistency
b936cdfe-c3f4-5cff-9f95-0ee6d44746c3 | note | ○ moisture content
e871f201-2d14-5b09-9f6e-82eea378ac1d | note | ○ any concerns with shape and tie in
5dcc2e8a-2d26-576d-842a-48702c0e13cc | note | ○ etc.
070cd3b7-1635-521c-846e-ff3a7653b6ac | note | Eng. Rep - I
96baf954-914a-57c5-9e8b-313ff02458f3 | note | Contractor - R
25355f90-a4be-5db4-b425-91795a4ba379 | signoff | AUTHORITY HOLDPOINT
32ada8e3-16fa-5532-ab52-ca23c1d10dfe | checkpoint | 2.06 - Production Plan
76f59c41-311e-581a-8b1b-dd5c9ed7ea45 | note | Detail of Activity / Test - Plan showing cut lines and sequencing of works
e7906efa-ddc0-52da-878e-f63410b4190c | note | Action (Hold, Monitor, Witness) - M
62ea7800-71a8-55f1-bdc0-08b361da46d4 | note | Minimum Test Frequency - Prior to each section
0b8692db-a34a-58c0-87eb-7217b37eb3d3 | note | Inspection / Test method - Daily Report
4a287c83-bd50-5cb0-a027-002df82957b9 | note | Acceptance Criteria - Points covered in NZTA B/5
55727680-c289-50b5-b90e-07c662c7358e | note | Record documents (QCP - Quality Control Portal) - Daily Production Plan
427b4c64-6026-5795-81a5-166b003a0572 | note | Responsibility - Stabilising Contractor
6de6d099-8cf1-55e7-a226-d8c7d249080f | note | Eng. Rep - I
ad938dbf-33c6-5ee1-bc7c-3f2580b9f3aa | note | Contractor - R
ed38ca4f-e94d-558a-b9f2-b91aa0a17f56 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
dec22408-23ba-52f0-ac47-94c4efe99291 | textbox | Contractor's Rep Name:
5297358a-d7fd-53d9-a3f4-60f28620cbc5 | textbox | Engineer's Rep. Name:
f587f3d4-b7fa-5105-bf17-8e59fbf7dd05 | date | Date:
a0cd76f9-9cf2-55d2-a4ea-cf3c54090a5e | signoff | Add Signature
d92c0699-415c-4d2f-bfad-1bf6051f6310 | checklist | Ω (DEPRECATED) ITP - Shoulder Widening Rev 0 | itp | ITP - Shoulder Widening
99ef2ceb-90ef-4e01-881c-dfc14dbcf1ff | section | 1.0. AGGREGATE ACCEPTANCE TESTING
ddd3971b-a3ad-4e7d-825c-da920ab2d160 | checkpoint | 1.00 - AP40 Basecourse Aggregates used for overlay
da5ae25a-6603-5a99-a7ee-e5980f4aeb0a | note | Detail of Activity / Test - Crushing Resistance
6488e2a3-46aa-5341-a88f-5576d48dd13e | note | Action (Hold, Monitor, Witness) - H
a1140d64-462a-5e83-ad2f-59d050e6b0a4 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 10,000 m3
47e9b89e-3f56-5086-89ea-3df8fbf5e8bf | note | Inspection / Test method - NZS4407:3.10
a652ab95-9bd9-5671-8d34-00d3544fae20 | note | Acceptance Criteria - < 10% passing 2.36mm sieve at 130kN
c65dcb0f-fd04-5605-bb9d-8ed960ee480f | note | Record documents (QCP - Quality Control Portal) - IANZ report
488e5290-794c-56d0-af6f-d6e904d56ff8 | note | Responsibility - Contractor
40972114-6e58-5465-baa1-3079d3c28570 | note | QA / Site Engineer - A
97fbeba2-70a5-56f7-a59b-f2d99fbdc0d6 | note | Eng. Rep / NZTA - I
2bf90524-efd9-57c4-8315-3324ded7169f | note | Contractor - R
10b811ba-9c54-43f7-a4a9-7ffb7c5bf856 | signoff | AUTHORITY HOLDPOINT
5b85f7db-9d77-4504-871e-3203ab6dec50 | checkpoint | 1.01 - AP40 Basecourse Aggregates used for overlay
f3b44d85-109c-5bcc-9017-740cb3e25eb6 | note | Detail of Activity / Test - Particle Size Distribution
a391fb6c-43b5-5f62-9e68-b4cfb5c4af95 | note | Action (Hold, Monitor, Witness) - H
b0c7c94f-f95c-50de-9db0-ecb1dc074638 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m3
2a083ab9-1206-59bb-b437-f0de2252e9d3 | note | Inspection / Test method - NZS4407:3.8.1
e82d3c6e-b770-506a-a974-37cb407f64c7 | note | Acceptance Criteria - NZTA M04:2024-Class 2
54e4d0f2-7313-5238-a363-2f44c7903573 | note | ○ Class 2 in Table 12 for PSD
4eef44df-fdd7-5f34-a169-6ee2757d9dcf | note | ○ Table 13 for shape control
c685b84b-8522-5113-8746-e88349886cc1 | note | Record documents (QCP - Quality Control Portal) - IANZ report
67ece4c6-3346-5e45-82f8-2eb6b8219b59 | note | Responsibility - Contractor
2c86bf00-a111-5e99-85fd-3a1a42544d20 | note | QA / Site Engineer - A
ced0fab7-d272-5caf-bdcb-7c20dcce4295 | note | Eng. Rep / NZTA - I
02d30db9-69fb-53b8-93cc-189a52abac7e | note | Contractor - R
591dd880-0508-4139-845f-acb32dd47c07 | signoff | AUTHORITY HOLDPOINT
a4186828-0343-493c-821f-e52d9b892f44 | section | 2.0. Construction
bdb6c7f9-170e-4f6a-a7bb-baf942fae2b5 | checkpoint | 2.01 - Mark out earthwork extents
fe39d67a-6fad-5fd7-b6a6-7d607b41351d | note | Detail of Activity / Test - Set out and approve extent of earthworks
f7a0d800-c986-53ce-ab8a-fa000ebf8b13 | note | Action (Hold, Monitor, Witness) - M
6bf4f86a-99d0-59f7-9bd1-ea6d363546d7 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to earthworks
a2ccb0f1-8f04-5a1d-9bec-7c0169119e37 | note | Inspection / Test method - Visual
24796412-2364-5588-b82c-2d9879c3924b | note | Acceptance Criteria - Site Engineers Approval
840a24cb-662c-520b-922e-dfa2bb48f7e7 | note | Record documents (QCP - Quality Control Portal) - Checksheet
618fe906-5ca5-5a02-92ea-b8762b161480 | note | Responsibility - Contractor
46bb6989-002a-5fc6-88b2-479859882095 | note | QA / Site Engineer - A
136d4829-a5a0-591e-9168-8aa815b4f43b | note | Eng. Rep / NZTA - I
ec2230a7-a656-5198-b7e6-a45aac0ca905 | note | Contractor - R
d1f58af3-47b4-488e-9930-9e4b08678468 | checkpoint | 2.02 - Earthworks
17bd84b9-cdce-5d8c-8d69-06cd735b1768 | note | Detail of Activity / Test - Cut 150mm rebate at Edge of seal (EOS) and strip organic material from shoulder
383621fb-6aed-59c8-ac27-2429c84890a1 | note | Action (Hold, Monitor, Witness) - M
13a9db74-ead6-5bc1-83a3-d3ffc52602b8 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - As per design drawings
288c05cf-7263-5a28-b03c-8189a5eb58f5 | note | Inspection / Test method - Visual / Photo
f8a95975-e504-504c-9ed8-9306d4298e8c | note | Acceptance Criteria - Site Engineers Approval
39acd28e-2a28-5b02-800e-2b7d27f5ec7f | note | Record documents (QCP - Quality Control Portal) - Checksheet
74ede8ce-9938-5055-8968-a7a3d702d7e2 | note | Responsibility - Contractor
c7d15e69-b02c-511c-98cb-fa1ca6810941 | note | QA / Site Engineer - A
cb24f574-f5d9-5271-b535-1d4e953bb3fa | note | Eng. Rep / NZTA - I
9dba9899-c4f4-518a-8a4f-ed4ac1b1831e | note | Contractor - R
38ef12b0-0235-4d4c-b339-2f7673468dd8 | checkpoint | 2.03 - M04 AP40 Placement
9a0895f2-bb35-58f0-bb41-428558f5ab12 | note | Detail of Activity / Test - M04 AP40 Placed in Accordance with Design Drawing and Survey
1c1905ed-1d6a-5ad3-a20c-891f5421334c | note | Action (Hold, Monitor, Witness) - M
b13850dd-d533-564e-9ff2-94f526b10cf0 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - As per design drawings
3d71c3c9-7e40-59be-9237-8600c38ed517 | note | Inspection / Test method - Visual / Photo
1d3d1ffd-b644-5d6d-a568-b03326945905 | note | Acceptance Criteria - In Accordance with Design Drawing
2ea46593-4bc9-5e51-89bc-023b39bc47f2 | note | Record documents (QCP - Quality Control Portal) - Checksheet
d5b0ba57-362c-5ed2-afda-7ceda196aff0 | note | Responsibility - Contractor
fae1aaba-462d-5a9d-858e-d8d46b1008d2 | note | QA / Site Engineer - A
d0ce75e6-a1c5-5d98-9548-ef93742b9cd0 | note | Eng. Rep / NZTA - I
94a9f70e-5d24-5ae2-a74d-05acf5b39660 | note | Contractor - R
91461e43-69dc-49a0-b396-db7d1e1766de | checkpoint | 2.04 - M04 AP40 Compaction
e18a8369-011f-5100-949b-aa7f1095033e | note | Detail of Activity / Test - Compact in Layers no greater than 150mm.
7abef8e7-a9eb-515b-bb47-aa375b6f421c | note | Action (Hold, Monitor, Witness) - H
0107d0d4-86c9-5046-affc-210f0c9e7a29 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1MDD Test per 50m
584ef280-c3d7-55b3-975b-a9fd7e78e19d | note | Inspection / Test method - Nuclear Densometer MDD Test
9e9178b6-f7ed-535c-b8d1-94eaa84647f3 | note | Acceptance Criteria - Average of 95% MDD with individual result >/= 92%
946a2c25-363c-5ddb-8e1c-ce5abbaadee6 | note | Record documents (QCP - Quality Control Portal) - IANZ report
3fc46306-9418-585f-a5a7-d0baef82cf8a | note | Responsibility - Contractor
4045603f-b3dd-5cbd-8f3a-03d27b9a3a79 | note | QA / Site Engineer - A
913d9fa0-41a2-53da-8adc-367c1af5a9a4 | note | Eng. Rep / NZTA - I
f54b9213-47ac-5278-b2c1-18b3faeeef4f | note | Contractor - R
bc12e4ed-078b-4b6c-9cd3-b7d68d76e0f4 | signoff | AUTHORITY HOLDPOINT
31df2de8-fa12-4285-8850-9df1a5f8fee5 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
e29cb0b8-3488-5c66-89c0-8a3a5b739e5a | textbox | Contractor's Rep Name:
c18d995f-b540-50f8-a046-0ac0480e9f3c | textbox | Engineer's Rep. Name:
60f39eef-2349-56f2-b8ba-3aeeccc96222 | date | Date:
d351953a-1c24-463d-b835-8df72cad2370 | signoff | Add Signature