## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Pre Construction Works | itp |  |  |  |  | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Pre Construction Works Rev C
section | 2.0 Pre Construction Works
checkpoint | 2.01 - Setout section
label | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
label | ○ Refer to Project Specific Notes
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to each section
label | Inspection / Test method - Survey
label | Acceptance Criteria - Document existing furniture
label | Record documents (QCP - Quality Control Portal) - Electronic survey files
label | Responsibility - Contractor & Stabilising Contractor
label | Project Specific Notes / Instructions - Note that the two transition ends of the site will require a digout as per the digout table on DWG#T2W-802-007.
label | ○ Extent of these as follows:
label | — RP 4235 to RP 4270
label | — RP 7580 to RP 7640
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Pre-hoe entire area, then shape and proof roll
label | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site specific methodology statement and/or IFC drawings and proof roll while compacting
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to stabilisation per section
label | Inspection / Test method - Use grader's machine control and inspect shape
label | Record documents (QCP - Quality Control Portal) - N/A
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Pre-hoe entire area, then shape and proof roll
label | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site specific methodology statement and/or IFC drawings and proof roll while compacting
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to stabilisation per section
label | Inspection / Test method - Visual check or Vibratory Roller's response meter
label | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
label | Responsibility - Stabiliisng Contractor
label | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Spreading of Cement (for modified subbase). (2.24t/m3 x 0.19m x 1.5% = 6.4 kg/m2)
label | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - every 400 m2
label | ○ every 150m for a 2.4m width
label | Inspection / Test method - Weigh mat or tray
label | Acceptance Criteria - ± 0.5kg/m2 of specified rate
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | Contractor - R
checkpoint | 2.05 - Spreading of Cement (for modified subbase). (2.24t/m3 x 0.19m x 1.5% = 6.4 kg/m2)
label | Detail of Activity / Test - Compare area spread with weight used for each spreader load
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - On-going measurement by computer/load cells
label | Inspection / Test method - Measurement each run
label | Acceptance Criteria - ± 2.5% of specified rate
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | Contractor - R
checkpoint | 2.06 - Compaction of Modified Subbase
label | Detail of Activity / Test - Plateau Density Test
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
label | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
label | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve MDD
label | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - If MDD can't be achieved then the PDT- MDD must be approved by the ER
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Compaction of Modified Subbase
label | Detail of Activity / Test - Maximum Dry Density
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
label | Inspection / Test method - NZS 4402.4.1.3
label | Acceptance Criteria - For analysis of DoC
label | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
label | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
checkpoint | 2.08 - Compaction of Modified Subbase
label | Detail of Activity / Test - Degree of Compaction (DoC)
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 5 per 1,000m2
label | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
label | Acceptance Criteria - Average DoC ≥ 95%
label | ○ Minimum DoC ≥ 92%
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.09 - Compaction of Modified Subbase
label | Detail of Activity / Test - Benkelman Beam
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - 20m staggered per lane
label | Inspection / Test method - NZTA T/1
label | Acceptance Criteria - For review and design verification
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - Used to identify soft areas
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
checkpoint | 2.10 - Overlay and check levels
label | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to stabilisation per section
label | Inspection / Test method - Survey
label | Acceptance Criteria - Subbase + 15 / - 5
label | Record documents (QCP - Quality Control Portal) - Surveyor
label | Responsibility - Stabilising Contractor with Main Contractor
label | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to):
label | ○ overlay aggregate quality / consistency
label | ○ moisture content
label | ○ any concerns with shape and tie in
label | ○ etc.
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Production Plan
label | Detail of Activity / Test - Plan showing cut lines and sequencing of works
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Prior to each section
label | Inspection / Test method - Daily Report
label | Acceptance Criteria - Points covered in NZTA B/5
label | Record documents (QCP - Quality Control Portal) - Daily Production Plan
label | Responsibility - Stabilising Contractor
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Pre Construction Works | itp |  |  |  |  | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Pre Construction Works Rev C
section | 2.0 Pre Construction Works
checkpoint | 2.01 - Setout section
label | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
label | ○ Refer to Project Specific Notes
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to each section
label | Inspection / Test method - Survey
label | Acceptance Criteria - Document existing furniture
label | Record documents (QCP - Quality Control Portal) - Electronic survey files
label | Responsibility - Contractor & Stabilising Contractor
label | Project Specific Notes / Instructions - Note that the two transition ends of the site will require a digout as per the digout table on DWG#T2W-802-007.
label | ○ Extent of these as follows:
label | — RP 4235 to RP 4270
label | — RP 7580 to RP 7640
label | Contractor - R