## Master List Templates
Id | Type | Name | Values | Prompting Name
a89ea8ab-d63c-4227-b0c8-fb0ce5e545f8 | checklist | Drawings attached |  | Document:
700d5cd3-d75b-4707-b6f5-7eb22e64b1b2 | checkpoint | Document Attached
f89a6c20-12f0-55be-b5af-b42fad43a03e | checklist | Roofing QA - Torch-On Concrete Checklist |  | Torch-On Concrete Checklist
14bc4ab5-1705-513e-9e54-f9ddea119b0d | section | Substrate Check
950d6b1e-fff2-54a9-b599-dac507b6de23 | checkpoint | Concrete substrate has been allowed to fully cure - at least 28 days from pour
088ab65a-6600-5313-8818-46c419593a4d | textbox | Concrete Pour date:
07c3a514-267e-5c2b-8733-4e65712316b4 | checkpoint | Fill hallows or holes with a cement plaster, or FLC
93eef60b-3efa-57d9-83fe-2f34073324ff | checkpoint | Surface smooth, clean, dry and free of debris or release agents
2195aecb-7bba-50ed-979f-fb2f2fb5d90e | checkpoint | Substrate venting installed as required
7854515d-6ba9-5981-9070-e63f1b107158 | checkpoint | Minimum 20mm triangular fillets at the base of upstands
924acc3e-edb2-59f8-a4e3-cf2bed2a4f8d | checkpoint | All drains and outlets are membrane compatible. Refer to your Allco Representative prior to installation if unsure.
70d3bd8f-5e07-55ee-b1dc-278071b4f442 | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
6e2052c2-d046-5dd6-8b44-1d3b6bca1954 | section | Torch-On Horizontal & Vertical Application
24fc83fb-06de-5dfa-a911-f428539ab339 | checkpoint | Check sheets are correctly aligned, unrolled completely and positioning them
28fa8e9c-9b8a-5600-b494-824f66eb9758 | checkpoint | Ensure side laps are at least 100mm and at head laps should be 150mm
1bbde419-6da1-51c5-92da-a522f9b8f62d | checkpoint | Ensure dermaprimer is used appropriately on the substrate
bad89745-282d-5e28-98cc-94abf268df65 | checkpoint | The second layer fully bonded on to the first layer, staggering the side overlaps by 500mm and the head overlaps by half a roll
abb13c5d-efdb-5e90-9fdb-21af316c76bb | checkpoint | Ensure 150mm upstand height of membrane
ec5e027e-53c0-5143-a4af-1b1589263cce | checkpoint | Attach application photos (1 photo per 20m2)
b6fe72ec-62aa-5dd4-be6c-dc7d452e8517 | section | Torch-On Detailing (Drains, Gutters, Joints, Overflows, Penetrations)
26ac7a47-9a78-50fe-8f02-7024380fb3f2 | checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
fdff54fa-699d-520d-b435-94dcba844f17 | tickbox | Attach Photos (1 photo per drain/outlet )
a72f285d-ca15-5e9f-870a-1d8a3d26bf09 | checkpoint | Penetrations - appropriate detailing techniques used
dc985bd2-046a-53e6-b064-a75a177689ab | button | Ensure 100mm extension from edge of penetration in all sides | Yes, No, N/A
31698445-c9ef-5b61-a68f-5fa7f1ab39b7 | button | Ensure 100mm upstand extension over pipe | Yes, No, N/A
9a33342c-9182-55ee-8088-924783123b47 | tickbox | Attach Photo (1 photo per penetration)
6631aced-d989-5bdd-aee0-4987eafde8b5 | checkpoint | Transitions - appropriate detailing techniques used
6173f3dd-60b8-591f-bc4a-bd12fe0705a4 | button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
43a089ae-379a-550d-b169-ced634c24482 | tickbox | Application photos of transitions
6e36b282-c24a-531d-b6c0-c6a6a8a6feb6 | checkpoint | Joints - appropriate detailing techniques used
79680e6c-2e75-5cae-8205-9c829d285858 | button | For expansion joints, ensure there is 150mm extension cover over the joint | Yes, No, N/A
164e8cff-49ad-5175-b5ee-e795dc1391b1 | tickbox | Application photos (1 photo per joint)
1edbe179-2e68-5044-8872-386bd3e1cd5a | section | Torch-On Terminations
1d6fff18-17ad-5ecf-b145-e357008627bc | checkpoint | Ensure appropriate 100mm laps at transitions
c9461874-1fa0-58ae-8231-25814851677d | checkpoint | Ensure appropriate detailing is used on terminations
0e2609a5-e5bc-5ff4-8711-1cf8aa979c83 | checkpoint | Application photos (1 photo per termination)
48a15495-2208-5059-83aa-aff0a03fe50d | checklist | Roofing QA - Torch-On Plywood Checklist |  | Torch-On Plywood Checklist
14bc4ab5-1705-513e-9e54-f9ddea119b0d | section | Substrate Check
62d3e75f-3d02-5089-924f-294fbcd45abf | checkpoint | Framing supports at 400mm centres for 17.5m ply (in one direction). All plywood edges must also be supported.
d3c5ccc7-6e28-56a7-8a1c-4def4274c0e2 | checkpoint | Framing supports at 600mm centres for 19.5m ply (in one direction). All edges must also be supported.
2c5c7f38-cc54-53e0-849e-4ca7b99f9b53 | checkpoint | Minimum 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
e1b41d70-4ff7-5402-8175-f90858f0b515 | checkpoint | Plywood screw-fixed with 10g x 50mm SS counter sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
8f3e20e8-0400-59eb-b95e-da904ed996d0 | checkpoint | Plywood laid with face grain at right angles to supports.
eb168657-c560-50b9-a774-3387e6141ce2 | checkpoint | Plywood is to be laid with staggered joints in a brick-bond pattern with a continuous bead of suitable construction adhesive on top of timber supports. Sheet edges to be carefully glued with a continuous bead of suitable construction adhesive (no spot gluing) and tight butt-jointed. Once sheets have been placed together remove any excess adhesive by scraping the joint with a chisel. Ensure joints and sheets are not walked on within 2 hours of application. When fully cured remove excess and sand off joints.
e80afbc0-ecc1-534d-bb2b-bedf2a833ff0 | checkpoint | Provide min. 20mm timber fillets at the base of all upstands.
048c7033-b0e1-53c6-8f1a-c527e0716782 | checkpoint | Chamfer all external edges with a minimum radius of 5mm.
2867074f-5527-59b1-8682-c1808ea886e0 | checkpoint | Plywood is to be laid with staggered joints in a brick-bond pattern with a continuous bead of suitable construction adhesive on top of timber supports. Sheet edges to be carefully glued with a continuous bead of suitable construction adhesive (no spot gluing) and tight butt-jointed. Once sheets have been placed together remove any excess adhesive by scraping the joint with a chisel.
1f4e6808-eef4-5842-bac4-7dcee8d4d241 | checkpoint | Ensure joints and sheets are not walked on within 2 hours of application. When fully cured remove excess and sand off joints
de67533f-1e8d-5f4e-abf1-7089e9d6edfe | checkpoint | Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18% moisture content.
17e4da6e-bb7a-5474-a2f2-64e8116ee4a9 | checkpoint | Leave a 5mm minimum expansion gap around the perimeter of the plane. The fixing specification allows for a maximum 50m2 without expansion joints (dependant on design). 5mm expansion joints should be used on areas over 50m2 . For further information regarding placement of expansion joints for your design, please contact your Allco Representative .
70d3bd8f-5e07-55ee-b1dc-278071b4f442 | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
924acc3e-edb2-59f8-a4e3-cf2bed2a4f8d | checkpoint | All drains and outlets are membrane compatible. Refer to your Allco Representative prior to installation if unsure.
6e2052c2-d046-5dd6-8b44-1d3b6bca1954 | section | Torch-On Horizontal & Vertical Application
24fc83fb-06de-5dfa-a911-f428539ab339 | checkpoint | Check sheets are correctly aligned, unrolled completely and positioning them
28fa8e9c-9b8a-5600-b494-824f66eb9758 | checkpoint | Ensure side laps are at least 100mm and at head laps should be 150mm
1bbde419-6da1-51c5-92da-a522f9b8f62d | checkpoint | Ensure dermaprimer is used appropriately on the substrate
bad89745-282d-5e28-98cc-94abf268df65 | checkpoint | The second layer fully bonded on to the first layer, staggering the side overlaps by 500mm and the head overlaps by half a roll
abb13c5d-efdb-5e90-9fdb-21af316c76bb | checkpoint | Ensure 150mm upstand height of membrane
ec5e027e-53c0-5143-a4af-1b1589263cce | checkpoint | Attach application photos (1 photo per 20m2)
b6fe72ec-62aa-5dd4-be6c-dc7d452e8517 | section | Torch-On Detailing (Drains, Gutters, Joints, Overflows, Penetrations)
26ac7a47-9a78-50fe-8f02-7024380fb3f2 | checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
0ef38849-5a2d-53a1-baa8-474efc14221c | tickbox | Attach Photos (1 photo per drain/outlet )
a72f285d-ca15-5e9f-870a-1d8a3d26bf09 | checkpoint | Penetrations - appropriate detailing techniques used
08bba0d9-28d6-5733-b033-ab73ed008bed | button | Ensure 100mm extension from edge of penetration in all sides | Yes, No, N/A
83c09441-9dba-52af-a337-198f088a8b01 | button | Ensure 100mm upstand extension over pipe | Yes, No, N/A
56bb04f1-0aa3-54dd-8dd5-7df6a8dac461 | tickbox | Attach Photo (1 photo per penetration)
6631aced-d989-5bdd-aee0-4987eafde8b5 | checkpoint | Transitions - appropriate detailing techniques used
0f306cf2-5adf-59f7-bbf7-00d9f912bb79 | button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
833dbfe2-a339-5a1f-abb9-930ca76a38da | tickbox | Application photos of transitions
6e36b282-c24a-531d-b6c0-c6a6a8a6feb6 | checkpoint | Joints - appropriate detailing techniques used
7e4b4a6c-6356-572b-9123-7b8eab44d0c2 | button | For expansion joints, ensure there is 150mm extension cover over the joint | Yes, No, N/A
9040c8d1-b139-5369-9a48-c55ecc71c462 | tickbox | Application photos (1 photo per joint)
1edbe179-2e68-5044-8872-386bd3e1cd5a | section | Torch-On Terminations
bfd9b010-84e0-5813-9f62-31c2a7701cf7 | checkpoint | Areas of installation input
f890f283-7e04-552c-85f7-3add7bf9107c | textbox | Description, grid sections, etc
1d6fff18-17ad-5ecf-b145-e357008627bc | checkpoint | Ensure appropriate 100mm laps at transitions
c9461874-1fa0-58ae-8231-25814851677d | checkpoint | Ensure appropriate detailing is used on terminations
0e2609a5-e5bc-5ff4-8711-1cf8aa979c83 | checkpoint | Application photos (1 photo per termination)
cf3f1b4a-b7ed-5eaf-8ec2-8c1e20e56b66 | checklist | Roofing QA - TPO Concrete Checklist |  | TPO Concrete Checklist
14bc4ab5-1705-513e-9e54-f9ddea119b0d | section | Substrate Check
950d6b1e-fff2-54a9-b599-dac507b6de23 | checkpoint | Concrete substrate has been allowed to fully cure - at least 28 days from pour
fbbbfc7f-c53f-5125-88cb-dd2af7835305 | textbox | Concrete Pour date:
07c3a514-267e-5c2b-8733-4e65712316b4 | checkpoint | Fill hallows or holes with a cement plaster, or FLC
93eef60b-3efa-57d9-83fe-2f34073324ff | checkpoint | Surface smooth, clean, dry and free of debris or release agents
2195aecb-7bba-50ed-979f-fb2f2fb5d90e | checkpoint | Substrate venting installed as required
924acc3e-edb2-59f8-a4e3-cf2bed2a4f8d | checkpoint | All drains and outlets are membrane compatible. Refer to your Allco Representative prior to installation if unsure.
70d3bd8f-5e07-55ee-b1dc-278071b4f442 | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
49285aa6-c5ec-5010-93c9-e3d2e499c431 | section | TPO Horizontal & Vertical Application
fb9965a0-805b-5481-87ba-002d4c8a45bc | checkpoint | Conducted test weld on an off cut of membrane prior to installation?
906e3702-841c-53d8-9516-7db09357730d | checkpoint | Ensure even coating of approved adhesive used on JM sheet as well as substrate
7c8ef285-48a9-534a-b234-e32035a37a65 | checkpoint | Ensure 40mm minimum sheet laps
1a4ffc4d-423d-5f67-bd1d-0f160369b255 | checkpoint | Ensure all weld areas thoroughly cleaned with JMCLEAN membrane cleaner
e1e020cb-7165-53e0-b50d-9887ebe7381e | checkpoint | Test all welds with a seam probe
ec5e027e-53c0-5143-a4af-1b1589263cce | checkpoint | Attach application photos (1 photo per 20m2)
08405d50-16b9-59cc-b3b0-3e6da272780c | section | TPO Detailing (Gutters, Corners, Overflows)
26ac7a47-9a78-50fe-8f02-7024380fb3f2 | checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
4a4f813f-3ecd-5700-bc0e-1b8c0a366074 | button | Ensure the correct JM accessories are used? | Yes, No, N/A
b72b4533-2ce0-5412-8edc-63261e92130f | tickbox | Attach Photos (1 photo per drain/outlet )
a72f285d-ca15-5e9f-870a-1d8a3d26bf09 | checkpoint | Penetrations - appropriate detailing techniques used
7a73e521-d6cb-577b-a97a-03b30c622fdf | button | Ensure JM Single ply caulking is applied on appropriate areas? | Yes, No, N/A
2e0b04af-ed4c-51ca-a6a0-450dd77caa03 | button | Ensure 200mm upstand extension over pipe penetrations, and 150 mm for vent and square post (deck) penetrations | Yes, No, N/A
10471b7e-31d9-59a7-85cb-c7bca7bbb42e | tickbox | Attach Photo (1 photo per penetration)
6631aced-d989-5bdd-aee0-4987eafde8b5 | checkpoint | Transitions - appropriate detailing techniques used
c871e184-d555-5bf0-bd78-157f637d136b | button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
20b2c95a-3e79-5810-bd04-72a92ca366fa | tickbox | Application photos of transitions
6b65f3c3-1276-5808-ac15-95ff095d049a | checkpoint | External & Internal Corners - appropriate detailing techniques used
12bc8171-3b18-52d3-bf49-461925734c14 | button | Ensure appropriate JM corners accessories are used? | Yes, No, N/A
91ef4d14-f67b-5940-8244-3c5fe2115bb9 | button | Ensure appropriate detailing techniques used? | Yes, No, N/A
dda72123-b942-51b0-815f-6a086bbd0916 | button | Ensure 40mm wield length on all sides and corner fully welded | Yes, No, N/A
7247cb19-b79b-5162-937d-51251151c056 | tickbox | Application photos of corners ( 1 per corner)
e01d6eae-deee-5c9b-8b1f-f85882c3c6d5 | section | TPO Concrete Termination
5b9debf3-fffd-5313-a72f-d1389ec7a17b | checkpoint | Ensure appropriate detailing used for termination?
31bc4952-9929-5dd4-a627-28b36c8627af | checkpoint | Ensure 40mm hot weld between TPO and steel folded flashing (if appropriate)
6017b5c0-d48b-5f39-9134-22a4e015ddfb | checkpoint | Application photos of terminations (1 photo per termination)
97a226c5-a392-5a9b-aa13-abad275769ef | checklist | Roofing QA - TPO Plywood Checklist |  | TPO Plywood Checklist
14bc4ab5-1705-513e-9e54-f9ddea119b0d | section | Substrate Check
62d3e75f-3d02-5089-924f-294fbcd45abf | checkpoint | Framing supports at 400mm centres for 17.5m ply (in one direction). All plywood edges must also be supported.
6aaa7cd9-3fac-585c-b6f3-18e4b875ca8a | checkpoint | Tongue and groove plywood NOT used
86459540-0767-5ea1-ba50-bf18a6382f5c | checkpoint | Framing supports at 600mm centres for 19.5m ply (in one direction). All plywood edges must also be supported.
daa8e8a5-0ae2-5259-b081-091977df63d1 | checkpoint | Minimum thickness 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
4585285d-c93c-5da1-b3e2-03567e4202b1 | checkpoint | Minimum CD grade with the sanded C face upwards
f43050ae-9873-5482-8a63-2a6208116596 | checkpoint | Plywood to be laid at right angles (90 degrees) to supporting timber.
d1e0a570-0a5f-5cee-8fcf-0d2be56a5d30 | checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges.
4a41c5d3-eeaf-5868-bc9d-1594634e6a99 | checkpoint | Plywood is screw-fixed with 10g x 50mm SS counter-sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
048c7033-b0e1-53c6-8f1a-c527e0716782 | checkpoint | Chamfer all external edges with a minimum radius of 5mm.
c275b1eb-f5ae-5bc3-8cb3-9957946e6c08 | checkpoint | Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood to be at no more than 18%moisture content.
4cd8609a-f69f-58e6-9e73-a6f2226fbbdc | checkpoint | For Roofs and Roof Decks over living spaces, all cavities must be ventilated and insulated in compliance with clause H1 NZBC. - 1 vent for the first 40m2 and one for every 50m2 thereafter. Cavity ventilation is not required for a Warm Roof system which meets or exceeds the minimum R value requirements.
1bb3944f-d4e1-5618-9e42-91c521ef6ae4 | checkpoint | All drains and outlets are membrane compatible. Note that TPO membranes cannot be welded to Stainless Steel scuppers or sumps. Accessories must have Clamped Grates or be TPO weldable.
70d3bd8f-5e07-55ee-b1dc-278071b4f442 | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
49285aa6-c5ec-5010-93c9-e3d2e499c431 | section | TPO Horizontal & Vertical Application
fb9965a0-805b-5481-87ba-002d4c8a45bc | checkpoint | Conducted test weld on an off cut of membrane prior to installation?
906e3702-841c-53d8-9516-7db09357730d | checkpoint | Ensure even coating of approved adhesive used on JM sheet as well as substrate
7c8ef285-48a9-534a-b234-e32035a37a65 | checkpoint | Ensure 40mm minimum sheet laps
1a4ffc4d-423d-5f67-bd1d-0f160369b255 | checkpoint | Ensure all weld areas thoroughly cleaned with JMCLEAN membrane cleaner
e1e020cb-7165-53e0-b50d-9887ebe7381e | checkpoint | Test all welds with a seam probe
ec5e027e-53c0-5143-a4af-1b1589263cce | checkpoint | Attach application photos (1 photo per 20m2)
08405d50-16b9-59cc-b3b0-3e6da272780c | section | TPO Detailing (Gutters, Corners, Overflows)
26ac7a47-9a78-50fe-8f02-7024380fb3f2 | checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
cdfe299f-70ad-5846-8bf8-7fc29a0cfa7c | button | Ensure the correct JM accessories are used? | Yes, No, N/A
1d2ded02-90a2-5cb6-901d-3769dd231eca | tickbox | Attach Photos (1 photo per drain/outlet )
a72f285d-ca15-5e9f-870a-1d8a3d26bf09 | checkpoint | Penetrations - appropriate detailing techniques used
3bc3079a-f19b-5805-a14b-edbf23fb6d6f | button | Ensure JM Single ply caulking is applied on appropriate areas? | Yes, No, N/A
26d3b2c8-c1eb-5d9c-94d1-f78449f24645 | button | Ensure 200mm upstand extension over pipe penetrations, and 150 mm for vent and square post (deck) penetrations | Yes, No, N/A
3df8f016-ee74-525f-81c2-458707a5e63c | tickbox | Attach Photo (1 photo per penetration)
6631aced-d989-5bdd-aee0-4987eafde8b5 | checkpoint | Transitions - appropriate detailing techniques used
faaca1e3-d4d1-5539-9b73-08d4f63fb32f | button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
93ed54c2-e24a-5fdc-a2fa-89a16776e499 | tickbox | Application photos of transitions
6b65f3c3-1276-5808-ac15-95ff095d049a | checkpoint | External & Internal Corners - appropriate detailing techniques used
49e019f4-9fb3-5752-bda9-1d9e1cf54ba7 | button | Ensure appropriate JM corners accessories are used? | Yes, No, N/A
db1382fe-222c-5317-ae8a-ed515da48ec0 | button | Ensure appropriate detailing techniques used? | Yes, No, N/A
4e50c5c5-99bd-533d-aee7-9d52e9316985 | button | Ensure 40mm wield length on all sides and corner fully welded | Yes, No, N/A
3cf01868-36aa-554e-a52b-51944a277d18 | tickbox | Application photos of corners ( 1 per corner)
f095d640-3e52-519e-be44-d2c09b4da368 | section | TPO Plywood Termination
5b9debf3-fffd-5313-a72f-d1389ec7a17b | checkpoint | Ensure appropriate detailing used for termination?
31bc4952-9929-5dd4-a627-28b36c8627af | checkpoint | Ensure 40mm hot weld between TPO and steel folded flashing (if appropriate)
6017b5c0-d48b-5f39-9134-22a4e015ddfb | checkpoint | Application photos of terminations (1 photo per termination)
c512492b-805c-53f1-bed3-3019f9bd8790 | checklist | TA - Site Visit |  | Site Visit date:
cd6a7ee9-c00d-594d-96fb-b5f5ad13ba34 | checkpoint | Site Details
803bb503-7c92-5178-8ba8-e3af2ac36a86 | textbox | Project Name/Address:
b8d6211d-06a5-5504-876a-68d3b631269c | textbox | Contractor Name:
5262d06a-6c4d-5b8e-a3f1-3210f475a8ee | textbox | Applicator Name:
77f12cf7-45d2-5a02-9f49-f37461b18235 | button | System Warranty | Yes, No
77d43eb4-5aee-54a5-b990-143051e6103f | checkpoint | Product(s) Used
85513cb1-4e1b-5ecc-8b98-ef5279099770 | tickbox | Voltex
4382e2c3-f2c9-5312-a45e-facd8a7bf596 | tickbox | Voltex DS
642cfad9-acd9-55f0-8b15-88fe61c9fe0f | tickbox | Voltex SWR
f9442cd5-8f4d-55c8-b2d7-ea55923d200c | tickbox | Sweltite
48469363-e5a3-5d88-91c6-a36100dbd656 | tickbox | Rx Waterstop 101
869204ee-0435-5126-98b6-c07bf97354b6 | tickbox | Rx Waterstop 102
121242c2-c10a-5010-9598-8bb1272301bb | tickbox | Aquadrain
f91b3367-fbf8-5728-a3c2-d16021a15471 | tickbox | Corflute
227ef504-9958-5fd4-8a5c-b82b88a68248 | tickbox | Accessories
5e4d95a4-b980-546f-8468-1a02894cf8a8 | textbox | Other
4496e9f5-e793-5d51-9704-4f0a97088e17 | checkpoint | Site Visit complete and NO REPAIRS REQUESTED
7098332b-39ec-509e-bb25-022126b4d199 | button | Substrate acceptable | Yes, No
6c6f4af9-d746-5651-82b6-7bd21005b9ba | textbox | Location or Grid Lines:
0571855f-cf00-58ea-a398-f217ae64d88f | textbox | Inspection Notes
e2f113f3-987a-4f61-a9de-7b04e1d3cd2e | checklist | Waterproofing QA - Hydrotech Checklist |  | Hydrotech for Area:
35c53941-d657-4a44-9b93-e1edf4c9a83b | section | Hydrotech Area of Installation
a661ea9f-783b-4f9f-bac1-f60badad3169 | checkpoint | Checklist named with location or text box below or marked up drawing attached
2d3d4c20-fb70-5d83-96fd-207f0dd3a956 | textbox | Description, grid sections, etc:
391da067-7ea3-4789-8e34-4322653678b3 | section | Hydrotech Site & Substrate Prep
09169e0a-d133-48df-a47e-65a5d9bf3fbd | checkpoint | Wind uplift has been considered prior to installation
314bb4e2-451e-4185-83aa-96dfccd359d9 | checkpoint | Ensure all drains and outlets are membrane compatible. Confirm with Allco rep if required
7dc9d595-909a-4c15-91e1-b3a17d12b799 | checkpoint | Concrete substrate has been allowed to fully cure with a minimum wood float finish
90d1e221-7135-4b37-a6fd-cde35a666c23 | checkpoint | Substrate clean, dry and free of debris or release agents
2f6d0d43-12ec-4faa-bba6-69fcf43bc44f | checkpoint | Substrate photos taken
b1a2820c-5a7a-46a0-aec6-bdf5b14de46d | section | Hydrotech Horizontal & Vertical Application
56d81087-0b94-45db-bebd-be07ab151a0e | checkpoint | Test conducted to ensure membrane creates a mechanical bond to the substrate
40874f5c-c1ce-5481-adc2-2f53299527a8 | note | Attach application photo (1 photo per 20m2 or separate area)
1a43fb99-5b16-4381-996d-2b76e6407838 | checkpoint | First membrane layer applied at 3mm thickness
b04ecb4d-0965-5d27-b902-50ddb82afc51 | note | Attach application photos (1 photo per 20m2)
7ca13507-7d66-4b35-9a9e-b43508c14114 | checkpoint | Top coat of Hydrotech applied at 3mm thickness
9546d650-1820-523e-be13-805dfef4cfcf | note | Attach application photos (1 photo per 20m2)
5a278e2a-28f3-4da4-aafc-319e23d3ff58 | checkpoint | Photo proving total thickness of membrane system is 9mm (including protection layer)
cb6b05e4-90f8-45d3-a909-78f84fcfc207 | checkpoint | Photo of complete installation
0e5357a5-506d-4075-851a-04bed5294dfc | section | Hydrotech Detailing
1893e298-eae1-4b07-8230-84afd568789b | checkpoint | All penetrations have detailed as per Allco specifications
77232a47-8bfb-446a-8491-0264fea3934b | section | Hydrotech Terminations
025f92bb-7df1-4b0c-9793-ab13fcbe1290 | checkpoint | Ensure the approved sealant or tape is used for termination
fa5aa2fc-47d3-4f3f-9a49-a96950ef72d1 | checklist | Waterproofing QA - Protection & Backfill Checklist |  | Protection & Backfill for Area:
e6dd6f2d-2e0e-4958-b892-4279ed35cc47 | checkpoint | Checklist named with location or text box below or marked up drawing attached
59231477-162a-5580-aea2-dccab183f5b4 | textbox | Description, grid sections, etc:
1d53630b-907d-4958-ad3c-78788c999ec5 | checkpoint | Allguard has been installed as per Allco specifications?
e59f2df4-dec1-4163-a2c5-2f1240425fae | checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm?
bba2a201-8152-58ce-8d6c-9ab9490030cb | textbox | Backfill date
8dc7ad74-e3df-4a49-b0ae-c8f5b4bc716d | checklist | Waterproofing QA - Sweltite Checklist |  | Sweltite for Area:
2ffd6adb-8ef4-419c-bf4c-967c85d07718 | section | Sweltite Area of Installation
7d4ab972-ea09-44ef-ab3d-eee5dee03d40 | checkpoint | Checklist named with location or text box below or marked up drawing attached
1e8ed08f-80a0-5b0d-a678-e215d747965b | textbox | Description, grid sections, etc:
e408906c-3d4c-4598-93a1-82e61a39a787 | section | Sweltite Site & Substrate Prep
8fd6f465-ce38-4dc2-a5cd-427485ecc90a | checkpoint | Appropriate site conditions for installation
b96bfdb6-50dd-489f-becf-b9dca310e5e9 | checkpoint | Appropriate water control in place
1fcf066e-2177-4421-87eb-dafacda65bca | checkpoint | Substrate photos taken
cd9461a9-cb7a-42de-b29e-e7b40421cf63 | section | Sweltite - Foundation walls
25db66bb-1a1f-469a-a343-aa35514d6c7c | checkpoint | Appropriate detailing done as per Allco specifications
7c70e2d2-f281-4380-8849-aac29bafa33b | checkpoint | Ensure 100mm laps between membrane
eba2a6f4-8447-453c-ae51-f0bb499f593d | checkpoint | All laps seam taped horizontally & vertically using Allco seam tape
d992e46d-5786-4522-b3ef-01a181c70551 | checkpoint | Sweltite exceeds 150mm past F.F.L
6308c59d-d19e-4b5f-8a59-d2426b267afd | checkpoint | Drainage coil has been placed 100mm from the floor/wall joint
2921a5f9-60be-4e30-95ca-5b970bfd0a6f | section | Sweltite Penetrations
6a7bb5a8-de7b-4103-b4a6-0de9ee06ee13 | checkpoint | Penetrations detailed appropriately using appropriate accessory Volclay products
826705bc-9a3f-437c-83ef-68d10d706449 | section | Sweltite Termination
c2851ea5-47bd-461c-ae74-64a429162a21 | checkpoint | Termination bar used on vertical & horizonal edges
d2b6276e-371c-4cfe-a4fa-d0964bbb051f | checkpoint | Cetcoat applied at appropriate areas
90c8f9c6-04c7-4736-a864-014d6789bc3d | checkpoint | Termination sealed off correctly (i.e. M2000, Cetseal)
906c0466-4cb5-49c4-b1e8-dd51c687cc02 | section | Sweltite Backfill & Protection
ec973e07-51a0-42ba-9290-8b28412e4f9e | checkpoint | Allguard has been installed as per Allco specifications
be2613a0-32a3-4d40-8bf5-5dc0e6b7378d | checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm
12ea88f5-0476-56b6-96bd-fd5150dcce4d | textbox | Backfill date
72a5a29f-7435-40bd-a783-7c8d1958051e | checklist | Waterproofing QA - Voltex Checklist |  | Voltex for Area:
95731d0d-ab45-40df-a615-f3f8ab306c34 | section | Voltex Area of Installation
45a535b4-5803-40b9-937a-89573eec6869 | checkpoint | Checklist named with location or text box below or marked up drawing attached
345fe001-05ba-5e52-bc8e-d281f8fd964c | textbox | Description, grid sections, etc:
a9e1466b-2f62-4ade-bd37-fa5136f368f0 | section | Voltex Site & Substrate Prep
78c0ad10-529d-4910-86aa-fb26623269e2 | checkpoint | Appropriate site conditions for installation
1fe5420f-9532-459c-bb61-3991bbe267c4 | checkpoint | Appropriate water control in place
5af86c0a-73e9-59b9-b097-42759eeb694f | textbox | Concrete pour date
b989aa8b-7251-4155-8621-ed86ab69e0e8 | checkpoint | Substrate photos taken
c7918b2b-34a5-4350-bbb2-7b35ca9b2caa | section | Voltex Walls, Underslab and Footings
6ff6e03f-825c-4a69-b37d-005928d116a4 | checkpoint | Membrane appropriately laid on substrate with dark grey (woven) side up
15eb7cf9-4048-47dc-86a9-855ac792bfc9 | checkpoint | 100 mm overlap between each sheet, and stagger sheets end at a minimum of 300mm
e24108f5-6928-4c41-8a58-5f383fffb51a | checkpoint | Appropriate detailing done to external/internal corners
a491e44d-9ae6-409d-9dc8-bdceca839d02 | section | Voltex Penetrations
2294b019-7211-4e95-b098-8b65909dc675 | checkpoint | Penetrations detailed as per Allcos recommendations
735fcec4-54b5-48c3-9f66-cac98daf7f35 | section | Voltex Backfill & Protection
7f897f54-ca82-4130-8171-eb8f9f1dd35e | checkpoint | Allguard has been installed as per Allco specifications
5cedd7b4-2b48-4468-826e-51d0df82e70c | checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm
d0e82439-9d99-5db4-821d-a9d69c6c4400 | textbox | Backfill date
8165a34f-ee54-410a-b4a0-f6f61618cb69 | checklist | Waterproofing QA - Waterstop-RX Checklist |  | Waterstop-RX for Area:
b38a051a-ec9d-4bb8-a234-3cf5076cce2a | section | Waterstop-RX Area of Installation
bb50bd23-e3f3-41ab-98db-c387e757e4ec | checkpoint | Checklist named with location or text box below or marked up drawing attached
75d6dba4-47e4-50ec-bee6-387daf2d6af3 | textbox | Description, grid sections, etc:
3d33fdd4-c4eb-49f8-9ad6-863af68dc7ba | section | Waterstop-RX Site & Substrate Prep
7ed3e8a4-874d-4787-8971-b00ad2da52dd | checkpoint | Substrate is acceptable
41ca0397-3221-4958-bf83-ea0277dd4a22 | checkpoint | Confirm appropriate Waterstop-RX is going to be used in relation to concrete thickness
bdde70d4-e30b-5c50-ac40-bf1df3880cae | textbox | Concrete pour date
ebf72f68-f779-4a0b-9669-6f2a82ba54ad | checkpoint | Substrate photos taken
38ea3901-edbc-4b8f-a092-a55520af2f79 | section | Waterstop-RX Installation
0bbbd67c-cfcc-497d-b44e-328ec4698830 | checkpoint | Waterstop-RX has been installed as per Allco specifications
cbbd194c-3769-46a4-ad09-ea901cd42cef | checkpoint | All parties aware of Waterstop-RX requirements with exposure to climatic conditions