## Black Seal
QUALITY ASSURANCE PROGRAMME Application of Sika BlackSeal Elastic Waterproofing membrane
Prior to application commencing:
(a) The Applicator shall provide evidence to the Client that the applicator is currently approved by Sika (NZ) Ltd (the Manufacturer) for the application of Sika BlackSeal Elastic.
(b) The Applicator shall provide a Quality Assurance Plan to the Client prior to commencing work.
(c) The Client or representative shall determine that all surface preparation work has been completed to the agreed standards, before the product shall be applied.
(d) The Client or representative should ensure that all joints and penetrations to be sealed have been prepared to the required standard. Alternatively, in lieu of inspecting all joints and penetrations, the Client or representative shall agree with the Applicator the standard to be achieved by way of a sample area prepared by the Applicator.
During application, the Applicator shall keep the following records:
1. One Sika BlackSeal Elastic Application Record shall be completed for every day of application, including confirmation of:
 The specific area of the project applied that day.  The amount and batch numbers of all Sika BlackSeal Elastic used.  The calculated average film thickness of Sika BlackSeal Elastic used.  Whether or not a primer coat of Sika BlackSeal Elastic was applied to the substrate.  The weather conditions. (These shall be measured and recorded at least three times during the day and at any time that there is a significant change in the weather.)
2. The construction joints in the substrate shall be clearly designated on a copy of the plans. This designation is to be used when referring to these joints.
This information shall be recorded on the form provided, and verified by the Client or representative.
The Applicator shall maintain a register of the completed Application Records, which shall be available for inspection on request by the Client and shall supply a copy of these records to the Client and Sika (NZ) Ltd on completion of the works.
SIKA BLACKSEAL ELASTIC APPLICATION PLAN
Project: 0107 | [8 empty] | Date:
Client: | [5 empty] | Site Address:
Applicator:
Operators:
Surface preparation required:
Method of preparing joints:
Method of preparing pipe penetrations:
Primer Coat of Sika BlackSeal Elastic applied:
Proposed protection board:
Applicator: Name: |  |  |  | Signature:
Copies to: Sika (NZ) Ltd · Client · Applicator
SIKA BLACKSEAL ELASTIC APPLICATION RECORD
Project: | [8 empty] | Date:
Client: | [5 empty] | Site Address:
Approved Applicator:
Operators:
Surface prepared in accordance with specification:
Joints and penetrations prepared in accordance with specification:
Primer coat of Sika BlackSeal Elastic applied:
Sika BlackSeal Protection Sheet applied to all surfaces:
Area applied: |  |  | Identification:
Square metres: m²
Sika BlackSeal Elastic: |  |  | Number used:
Batch Numbers:
Calculated average film thickness: mm
Measured dry film thickness:
Location
Thickness (mm)
Weather Conditions:
|  | Start of day |  |  | Midday |  | End of day |  |  | (Other) | (Other)
Time
Ambient Temperature (oC)
Surface Temperature (oC)
Sunny/Overcast/Rain
Wind (light/ moderate/ strong)
Wind Direction
Approved Applicator: |  |  |  |  | Client:
Name: | Signature: |  |  |  | Name: |  |  | Signature:
Copies to: Sika (NZ) Ltd · Client · applicator