## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-206-CIV-Calder-Street Lighting (Supply and Install) | itp |  |  |  |  | ITP-206-CIV-Calder-Street Lighting (Supply and Install) Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-206-CIV-Calder-Street Lighting (Supply and Install)
label | ITP Description: Street Lighting (Supply and Install)
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 8/10/2024
label | ITP created by: Jason Quan/Derek Collins
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - IFC Drawings
label | 1.2 - Non Dependent
label | Reference - Jemena Electricity Networks
label | 1.3 - Non Dependent
label | Reference - VR Section 733
label | 1.4 - Non Dependent
label | Reference - AS/NZS 3000
label | 1.5 - Non Dependent
label | Reference - AS/NZS 1158.3.1
section | 2. Preliminaries Preliminaries - Materials
checkpoint | 2.1 - Material Compliance - Obtain and review manufacturer documentations for the supply of materials.
label | Reference - IFC Drawings Section 733
label | Acceptance Criteria - Materials comply with IFC Drawings,VESI Standards.
label | ○ All materials shall comply with the standards and specifications shown on the drawings. All structural steel, associated components and welding consumables shall be manufactured by companies that hold quality systems certification to AS/NZS ISO 9001.
label | * Enter: Teambinder Hold Point Release Number
label | Method - Document Review
label | Frequency - Per Source
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Inspection of supplied items upon delivery.
label | Reference - IFC Drawings VR Std Dwg TC1064, TC1065
label | Acceptance Criteria - Supplied items are to correct spec, class, size, undamaged and brand new.
label | ○ Luminaires: At the time of delivery, the supplier shall provide hard copies of the following:
label | — Installation Instruction Manual
label | — Operation Instruction Manual
label | — Storage, handling, loading and off–loading instructions
label | — Test Certificates
label | — Warranty Information
label | ○ Attach Delivery Dockets & Records Required
label | Method - Visual /Site Inspection & Document Review
label | Frequency - Per Delivery
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - ACCC Form (Australian Competition and Consumer Commission)
label | Reference - MRPA Quality Management Plan, Jemena Electricity Networks
label | Acceptance Criteria - Before any works commence, the accredited contractor shall obtain an "ACCC Form" from AusNet Services representative for permission to commence works.
textbox | * Enter: Teambinder Hold Point Release Number
label | Method - Document Review
label | Frequency - Once prior to works commencing
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Subcontractor Prequalificaiton
label | Reference - MRPA Quality Management Plan, Jemena Electricity Networks
label | Acceptance Criteria - Subcontractor to be a VEDN (Victorian Electrical Distribution Networks) accredited contractor.
textbox | * Enter: Teambinder Hold Point Release Number
label | Method - Document Review
label | Frequency - Once prior to works commencing
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - VESI (Victorian Electricity Supply Industry) Auditor
label | Reference - MRPA Quality Management Plan, Jemena Electricity Networks
label | Acceptance Criteria - VEDN approved civil auditor. (VESI Auditor Register)
textbox | * Enter: Teambinder Hold Point Release Number
label | Method - Document Review
label | Frequency - Once prior to works commencing
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-installation Activities
checkpoint | 4.1 - IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | Method - Document Review
label | Frequency - Prior to starting Works and at regular intervals
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 4.2 - Survey set out
label | Reference - IFC Drawings, Jemena Electricity Networks, Technical Specifications
label | Acceptance Criteria - Set-out survey carried out by a surveyor and within the tolerances as per IFC Drawings and AusNet drawings/specs.
label | Method - Visual, Survey
label | Frequency - Each Element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
section | 5. Installation Activities
checkpoint | 5.1 - Pit and Conduit Installation
label | Reference - IFC Drawings
label | Acceptance Criteria - Conduits and pits to be installed as per IFC Drawings
label | ○ Attach: Subcontractor Installation Checklist
label | Method - Document Review, Visual
label | Frequency - Prior to commencement
label | Category - WP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.2 - Conduit and Cable Detailing
label | Reference - Jemena Electricity Networks Technical Specification
label | Acceptance Criteria - Trench inspection detailing all conduits and cables being installed by a AusNet services approved detailer.
label | ○ Attach: Verification Document (As-Builts)
label | Method - Site Inspection
label | Frequency - Upon completion of each section
label | Category - IP
label | Responsibility - SE/PE/SPE, Services Engineer
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.3 - Prepare the plinth foundation (Excavation & levels)
label | Reference - IFC Drawings
label | Acceptance Criteria - Check levels conform to relevant drawing depending on type of pole to be installed.
label | Method - Visual, Survey
label | Frequency - Per Lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.4 - Installation of Light poles
label | Reference - IFC Drawings
label | Acceptance Criteria - Light Poles to be installed as per IFC drawings in accordance with VESI requirements.
label | Method - Visual /Site Inspection & Document Review
label | Frequency - Per Lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.5 - Asset Labelling
label | Reference - IFC Drawings
label | Acceptance Criteria - Pole Labelling to be as per IFC Drawings.
label | Method - Visual Inspection
label | Frequency - Per Lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.6 - Commissioning & Testing (Civil Audit)
label | Reference - Jemena Electricity Networks Technical Specification
label | Acceptance Criteria - Upon completion of all trenching and conduit install, a Civil audit by a VEDN approved Civil auditor will be completed and approved before procceding.
label | Method - Commissioning & testing
label | Frequency - Upon completion of each section
label | Category - IP
label | Responsibility - SE/PE/SPE, Services Engineer
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.7 - Commissioning & Testing (Trench Inspection)
label | Reference - Jemena Electricity Networks Technical Specification
label | Acceptance Criteria - Trench inspection detailing all conduits and cables being installed by a AusNet services approved detailer
label | ○ Verification document: As-Builts
label | Method - Commissioning & testing
label | Frequency - Upon completion of each section
label | Category - IP
label | Responsibility - SE/PE/SPE, Services Engineer
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.8 - Commissioning & Testing (Pre-commissioning)
label | Reference - Jemena Electricity Networks Technical Specification
label | Acceptance Criteria - Passing of the pre-commissioning audit with all non-conformances rectified.
label | Method - Commissioning & testing
label | Frequency - Upon completion of each section
label | Category - IP
label | Responsibility - SE/PE/SPE, Services Engineer
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.9 - Commissioning & Testing (Final Audit)
label | Reference - Jemena Electricity Networks Technical Specification
label | Acceptance Criteria - Passing of the final audit will be completed by Jemena Electricity Networks to inspect the completed works with all non-conformances rectified.
label | Method - Commissioning & testing
label | Frequency - Upon completion of each section
label | Category - IP
label | Responsibility - SE/PE/SPE, Services Engineer
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.10 - Testing and Certificate of Electrical Safety
label | Reference - Jemena Electricity Networks Technical Specification, IFC Drawings
label | Acceptance Criteria - Prior to final acceptance, the contractor shall test all distribution cabinets, circuits, switches, PE Cells, luminaires, and all other electrical and electronic components for correct installation and operation
label | ○ Attach Documentation: Certificate of Electrical Safety for electrical installation
label | Method - Document Review
label | Frequency - Upon completion/ Work area
label | Category - IP
label | Responsibility - SE/PE/SPE, Services Engineer
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.11 - PC Cert of Jemena Electricity Networks Agreement
label | Reference - Jemena Electricity Networks Technical Specification, IFC Drawings
label | Acceptance Criteria - To be accepted and signed-off by MRPA and Jemena Electricity Neworks
label | Method - Document Review
label | Frequency - Upon completion/ Work area
label | Category - IP
label | Responsibility - SE/PE/SPE, Services Engineer
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
section | 6. Post-installation Activities
checkpoint | 6.1 - Verification of Subcontractor conformance records / signed ITPs including any relevant verification sheets.
label | Reference - IFC Drawings Notes
label | Acceptance Criteria - Check conformance report against project conformance criteria.
label | ○ Attach Verification Docs: QA Records, Signed ITP including any verification documents, Commissioning & Testing Certificates.
label | Method - Visual /Site Inspection & Document Review
label | Frequency - Per Lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 6.2 - As-Built Drawings
label | Reference - IFC Drawings Notes
label | Acceptance Criteria - As built drawings for the metered lighting installations to be provided to the satisfaction of MRPA & Cardinia Shire Council.
label | ○ Attach: As Constructured Plans / As-Builts
label | Method - Document Review
label | Frequency - Upon completion/ Work area
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in TeamBinder.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - WP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP