## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - 138 - Texas Rail Installation ITP | itp |  |  |  |  | ITP - 138 - Texas Rail Installation ITP Rev D
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
label | Standard / Specification - Downer
label | Verifying Document - Approved ITP on CONQA
label | Frequency - Submit 10 days prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.01.03 - Service Location
label | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard / Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.04 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.05 - External Permits
label | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard / Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.06 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Precast Traffic Barrier
label | Acceptance / Conformance Criteria - All precast barrier QA to be in separate ITP for precast element. – This item to be acceptance of precast QA ITP
label | Standard / Specification - PS-1
label | Verifying Document - BBO
label | Frequency - Before Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.01.02 - Ellipse Handrail
label | Acceptance / Conformance Criteria - Eclipse handrail QA to demonstrate compliance with Structural steel notes on IFC DWG 4001 (refer to fabrication ITP)
label | Standard / Specification - Structural steel notes on IFC DWG 4001
label | Verifying Document - Shop Drawing/Material Certificate/PDS
label | Frequency - Before Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.01.03 - Non-Conductive Barrier Coating
label | Acceptance / Conformance Criteria - Non-Conductive Barrier Coating to be Carboguard 636 XT (approved in RFI-0263), min. 150 microns to be applied to underside and side of baseplate (refer to fabrication ITP)
label | Standard / Specification - AS/NZS 2312/HERA Report
label | Verifying Document - Shop Drawing/Coating Certificate/delivery dockets
label | Frequency - Before Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.01.04 - Fall Protection Wire Rope
label | Acceptance / Conformance Criteria - Wire rope shall be 6mm stainless steel wire rope or otherwise approved; Material certs to demonstrate compliance of SS wire rope to be SS316 as per NZTA M23 Appendix B Rev.2
label | Standard / Specification - NZTA M23 Appendix B Rev.2 & NTT003
label | Verifying Document - Material Certification
label | Frequency - Before Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.01.05 - M16 & M24 bolts, washers and nuts
label | Acceptance / Conformance Criteria - Property Class 8.8 Hold Down Bolts, HDG
label | Standard / Specification - AS/NZS 3845.1: 2015, AS 3569, AS2759
label | Verifying Document - Material Certification
label | Frequency - Before Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.01.06 - Sleeve Member and Pin on bottom of Sleeve, Base Plate and Rail Vertical Posts, Rail Termination Cap
label | Acceptance / Conformance Criteria - Material certs to demonstrate compliance with Structural steel notes on IFC DWG 4001 (refer to fabrication ITP)
label | Standard / Specification - Structural steel notes on IFC DWG 4001
label | Verifying Document - Material Certification
label | Frequency - Before Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.01.07 - Wire Rope Termination
label | Acceptance / Conformance Criteria - Material cert on U bolt or similar approved for safety wire rope termination detail
label | Standard / Specification - Structural steel notes on IFC DWG 4001
label | Verifying Document - Material Certification
label | Frequency - Before Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint | 5.01.01 - Temporary Works (Stitch Pour Formwork)
label | Acceptance / Conformance Criteria - Temporary works to be installed as per design drawings. Permit to load to be issued by temporary works inspector prior to loading element
label | Standard / Specification - Downer
label | Verifying Document - Permit to load/Inspection
label | Frequency - As defined in the temporary works design
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.02 - Cast-In M24 Bolt
label | Acceptance / Conformance Criteria - Re-check all bolt assemblies are Class 8.8 high strength unless otherwise specified on the drawings
label | Standard / Specification - NZS 3404.1
label | Verifying Document - IFC/Material Certification
label | Frequency - Before Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 5.01.03 - Check cast-in bolt set-out
label | Acceptance / Conformance Criteria - As-built bolt locations, and overall alignment of precast barriers, for rail baseplate hole positioning. Set-out shims/packers
label | Standard / Specification - Downer
label | Verifying Document - Survey Data
label | Frequency - Before Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.04 - Baseplate and Ellipse Handrail tolerance
label | Acceptance / Conformance Criteria - Install vertical post with handrail and partly tension bolts onto the baseplate. Ensure tensioning tolerances for steelwork/bolts are checked.
label | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | TABLE G1
label | MINIMUM BOLT TENSION
label | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | Nominal diameter of bolt ¦¦ Minimum bolt tension kN
label | M16 ¦¦ 95
label | M20 ¦¦ 145
label | M24 ¦¦ 210
label | M30 ¦¦ 335
label | M30 ¦¦ 335
label | M36 ¦¦ 490
label | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | Standard / Specification - Downer/AS/NZS 5131: 2016
label | Verifying Document - Hold Point Release
label | Frequency - Before Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 5.01.05 - Tension bolts
label | Acceptance / Conformance Criteria - Check each bolt has a washer, nut and locknut and tension all bolts using part turn methodology
label | Standard / Specification - AS/NZS 5131: 2016 A1 Section 8.5
label | Verifying Document - Photo/Site-Approval
label | Frequency - Each Baseplate
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.06 - Grouting under baseplate
label | Acceptance / Conformance Criteria - While Hi-ab is holding the handrail components, adjust/tighten, and apply Sika212 or similar (approved by Engineer) to the underside of the baseplate (nom. 15mm)
label | Standard / Specification - AS/NZS 5131: 2017
label | Verifying Document - PDS
label | Frequency - Each Baseplate
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.07 - Fall Protection Wire Rope
label | Acceptance / Conformance Criteria - Prior to installation make sure wire ropes are free from: wear or scraping, kinking, crushing, bird caging damages. Wire Rope to be installed within the following tolerance.
label | AS/NZS 3845.1:2015
label | Unless specified otherwise in the system documentation of by the Road Authority, the following shall apply:
label | (a) Fittings such as swages, rigging screws and the like, shall be placed so that the end of the fitting is a minimum distance of 50 mm away from a post. In order to comply with Item (a), the requirements to avoid clashes with fittings, it is permissible to move the location of a post.
label | (b) Variation from the true plan position of posts ±30 mm.
label | (c) Variation in rope height ±20 mm.
label | (d) Variation from true plan position of barrier ±20 mm.
label | (e) Fottings (length, width and depth) -10, +50 mm.
label | (f) Anchor blocks (length, width and depth) -20, +100 mm.
label | (g) Height of footing relative to finished surface levels +20, -0mm.
label | (h) The system shall be tensioned to a tolerance of ±1.0 kN.
label | (i) All anchors, footings and posts shall be capable of resisting the load nominated by the System Supplier (see Clause 2.5.4).
label | (j) Upon completion of the installation, the wire rope shall be free of creases or fracture strands and the galvanizing undamaged.
label | Standard / Specification - AS/NZS 3845.1: 2015
label | Verifying Document - Inspection/Site-Approval
label | Frequency - Before Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.01 - Construction Record Compilation
label | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.01.02 - Survey Records
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 6.01.03 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any changes to footpath location or basecourse depth.
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 6.01.04 - Defect, Snag and Punch List
label | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | Standard / Specification - Downer
label | Verifying Document - Register
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE