## ITP Cover Page
Northern access & carpark Pavements - Pavement Type 6 - Inspection and Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2 - 006-003 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project - SP2 |  |  |  |  | ITP Number: |  |  | 006-003
Project Number: |  |  | DN1210 - SP2 |  |  |  |  | ITP Status: |  |  | Issued for construction
ITP Description: |  |  | Northern access & carpark Pavement Type 6 |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-PVS
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Contract Specifications TCC-IDC-IT-4
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft |  |  | Cordelia Girdler-Brown & Nick Adams | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Draft | 2024-12-10 |  | WSP |  | 1. Section 4.1.3 stringline tolerance level changed from -15+0 to -25+5mm - As per NTC 0349 |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams |  |  | #VALUE! |  | 2024-12-10 | Downer PM
Downer QM |  | Cordelia Girdler-Brown |  |  |  |  | 2024-12-09 | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Northern access & carpark Pavements - Pavement Type 6 - Inspection and Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2 - 006-003 - Rev 1
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 1 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
1.1 | Subbase Layer TCC-AP65-1 - SOURCE PROPERTY TESTING - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
1.1.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | < 10% fines passing 2.36mm under a load of 130kN | TCC-IDC IT-4.7.1 table 4.4 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.1.2 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | ≥ 60% | TCC-IDC IT-4.7.1 table 4.4 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.1.3 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA, AB, AC, BA, BB or CA | TCC-IDC IT-4.7.1 table 4.4 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.2 | Subbase Layer TCC-AP65-1 - PRODUCTION PROPERTY TESTING - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
1.2.1 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Sieve Size % Passing 63.0mm 100% passing 37.5mm 55-85% passing 19.0mm 33-65% passing 9.5mm 20-50% passing 4.75mm 10-36% passing 2.36mm 5-27% passing 1.18mm 2-20% passing 0.425mm 1-13% passing 0.075mm 6% max passing | TCC-IDC IT-4.7.2 table 4.5 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.2.2 | Shape Control | Tolerance allowed from approved grading curve (%) | Sieve Size % Tolerance 37.5 – 9.5 34-50% 19.0 – 4.75 18-40% 9.5 – 2.36 12-32% 4.75 – 1.18 6-24% 2.36 – 0.6 2-20% 1.18 – 0.3 0-15% 0.6 – 0.15 0-12% | TCC-IDC IT-4.7.2 table 4.5 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.2.3 | Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent | ≥ 30 | TCC-IDC IT-4.7.2 table 4.5 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.2.4 | Cone Penetrometer Limit | NZS4407:2015, Test 3.2 Cone Penetration | Cone Penetrometer ≤ 25 | TCC-IDC IT-4.7.2 table 4.5 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.2.5 | Plasticity Index | NZS4407:2015, Test 3.4 Plasticity Index | Plasticity Index ≤ 8 | TCC-IDC IT-4.7.2 table 4.5 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.2.6 | Accelerated Weathering | NZTA T/20 Ethylene Glycol Accelerated Weathering Test | ≤ 30% increase in fines | TCC-IDC IT-4.7.2 table 4.5 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.2.7 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | TCC-IDC IT-4.7.1 | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.3 | Geogrid and Geotextile
1.3.1 | Geogrid | The Contractor shall submit the full details of the geogrid they propose to use to the Engineer for approval prior to installation. | Engineers Approval | PS 20.5.2 PS 16.5.13 | Data Sheets and Approval | Results to Engineer for Approval | HP | ENG
1.3.2 | Geotextile Fabric | The Contractor shall submit the full details of the geotextile fabric they propose to use to the Engineer for approval prior to installation. | Engineers Approval | PS 20.5.2 PS 16.5.14 | Data Sheets and Approval | Results to Engineer for Approval | HP | ENG
1.4 | Basecourse Layer TCC-AP40-1 - PRODUCTION PROPERTY TESTING - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
1.4.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | < 10% fines passing 2.36mm under a load of 130kN | PS 20.9 TCC-IDC IT-4.8 table 4.6 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.4.2 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | ≥ 80% | PS 20.9 TCC-IDC IT-4.8 table 4.6 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.4.3 | Accelerated Weathering | NZTA T/20 Ethylene Glycol Accelerated Weathering Test | ≤ 30% increase in fines | PS 20.9 TCC-IDC IT-4.8 table 4.6 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.4.4 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA, AB, AC, BA, BB or CA | PS 20.9 TCC-IDC IT-4.8 table 4.6 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.5 | Basecourse Layer TCC-AP40-1 - PRODUCTION PROPERTY TESTING - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
1.5.1 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Sieve Size % Passing 37.5mm 100% passing 19.0mm 60-75% passing 9.5mm 37-50% passing 4.75mm 20-35% passing 2.36mm 12-28% passing 1.18mm 9-20% passing 0.600mm 7-12% passing 0.300mm 3-10% passing 0.150mm 0-5% passing 0.075mm 0-5% passing | PS 20.9 TCC-IDC IT-4.8 table 4.7 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.5.2 | Shape Control | Tolerance allowed from approved grading curve (%) | Sieve Size % Tolerance 37.5 – 9.5 28-48% 19.0 – 4.75 14-34% 9.5 – 2.36 7-27% 4.75 – 1.18 6-22% 2.36 – 0.6 2-20% 1.18 – 0.3 5-19% 0.6 – 0.15 2-14% | PS 20.9 TCC-IDC IT-4..8 table 4.7 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.5.3 | Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent | ≥ 40 | PS 20.9 TCC-IDC IT-4.8 table 4.7 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.5.4 | Cone Penetrometer Limit | NZS4407:2015, Test 3.2 Cone Penetration | Cone Penetrometer ≤ 30 | PS 20.9 TCC-IDC IT-4.8 table 4.7 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.5.5 | Plasticity Index | NZS4407:2015, Test 3.4 Plasticity Index | Plasticity Index ≤ 8 | PS 20.9 TCC-IDC IT-4.8 table 4.7 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.5.6 | Clay Index NZS 4407 Test 3.5 | Clay Index NZS 4407 Test 3.5 | ≤ 5 | PS 20.9 TCC-IDC IT-4.8 table 4.7 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
SECTION 2 – Subgrade Handover from Earthworks
2.1 | QA Submission | Submit all Subgrade QA before proceeding with next pavement layer | Engineers Approval | Appendix V | Conqa Siggnoff | Once | HP | ENG
SECTION 3 – PLACEMENT OF GEOGRID AND GEOTEXTILE FABRIC
3.1 | Placement of Geogrid and Geotextile
3.1.1 | Placement of Geotextile Fabric | Place Geotextile Fabric Strength Class B across pavement area, with 500mm overlaps | Visual inspection | NTC0097 232735.02-WSP-DR-PVS-0401-REV4 | Visual Inspection and photos | During construction | WP | ENG
3.1.2 | Onsite Check by Engineer on Geogrid | Installation of Geogrid shall not commence until the Engineer has inspected the proposed geogrid on site and confirmed that the correct types of geogrid have been supplied. | Visual inspection | NTC0100 232735.02-WSP-DR-PVS-0401-REV4 | Visual Inspection and photos | During construction | HP | ENG
3.1.3 | Placement of Geogrid | The Duragrid X 30/30 Geogrid shall be placed on top of the Geotextile Fabric, and overlap areas of structural fill by a minimum of 2m, or as directed by the Engineer on site where the layer depth of structural fill is insufficient to limit deflections from the subgrade. | Visual inspection | NTC0100 232735.02-WSP-DR-PVS-0401-REV4 | Visual Inspection and photos | During construction | WP | ENG
SECTION 4 – PAVEMENT TYPE 6
4.1 | Subbase Layer Construction (AP65-1)
4.1.1 | Plateau Density Test | Using a 14T Roller carry out plateau density test to determine optimum rolling pattern using static and vibratory passes | Plateau Density Report | NZTA B/02 7.5 (a) | IANZ Accredited Report | 1 Test | I | SE
4.1.2 | 3m Straight Edge | Formation check to ensure surface is smooth | +/- 10mm | TNZ B/2 7.7 | Check Sheet | Every 20m Centres 1 each lane | I | SE
4.1.3 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface | -25mm +5mm | NZTA B/02 5.1 NTC 349 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
4.1.4 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD | NZTA B/02 7.6 | IANZ Accredited Report | 1 set (5 tests) 1000m2 | I | SE
4.1.5 | Benkelmen Beam | As directed by Engineer 15m staggered by wheel path for each lane. | 90th Percentile: 2.47mm Maximum: 2.92mm | PS 20.14.5 NTC0160 | Test Report | As directed by Engineer | HP | ENG
4.2 | HOLD POINT - Submission of QA from Subbase
4.2.1 | QA Submission | Submit all Subbase QA before proceeding with next pavement layer | Engineers Approval | Appendix V | All test reports Material Test Results Laboratory MDD NDM results Proof Roll | Once | HP | ENG
4.3 | Basecourse Layer Construction- (AP65-1)
4.3.1 | Plateau Density Test | Using a 14T Roller carry out plateau density test to determine optimum rolling pattern using static and vibratory passes | Plateau Density Report | NZTA B/02 7.5 (a) | IANZ Accredited Report | 1 Test | I | SE
4.3.2 | 3m Straight Edge | Formation check to ensure surface is smooth | +/- 10mm | TNZ B/2 7.7 | Check Sheet | Every 20m Centres 1 each lane | I | SE
4.3.3 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface | -15mm + 0mm | NZTA B/02 5.1 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
4.3.4 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >98% of MDD Min >95% of MDD | NZTA B/02 7.6 | IANZ Accredited Report | 1 set (5 tests) 1000m2 | I | SE
4.3.5 | Benkelmen Beam | As directed by Engineer 15m staggered by wheel path for each lane. | 90th Percentile: 1.85mm Maximum: 2.24mm | PS 20.14.5 NTC0160 | Test Report | As directed by Engineer | HP | ENG
SECTION 5 – AS-BUILTS / REDPEN MARKUPS
5.1 | As-Builts/ Red pen markup | As-Built records and drawings shall accurately record the layout and extents of all the work | All works meet project specifications and standards. | PS 16.7.6 | Red pen markups | During construction | D | SV/SE