## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-006 ITP Northern Access Carpark Pavement 4 | itp |  |  |  |  | DN1210-006 ITP Northern Access Carpark Pavement 4 Rev 1
section | SECTION 1 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 1.1.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 130kN
label | Standard / Specification - TCC-IDC IT-4.7.1 table 4.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - ≥ 60%
label | Standard / Specification - TCC-IDC IT-4.7.1 table 4.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
label | Standard / Specification - TCC-IDC IT-4.7.1 table 4.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 63.0mm ¦¦ 100% passing
label | 37.5mm ¦¦ 55-85% passing
label | 19.0mm ¦¦ 33-65% passing
label | 9.5mm ¦¦ 20-50% passing
label | 4.75mm ¦¦ 10-36% passing
label | 2.36mm ¦¦ 5-27% passing
label | 1.18mm ¦¦ 2-20% passing
label | 0.425mm ¦¦ 1-13% passing
label | 0.075mm ¦¦ 6% max passing
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.2 - Shape Control
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 34-50%
label | 19.0 – 4.75 ¦¦ 18-40%
label | 9.5 – 2.36 ¦¦ 12-32%
label | 4.75 – 1.18 ¦¦ 6-24%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 0-15%
label | 0.6 – 0.15 ¦¦ 0-12%
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.3 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - ≥ 30
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.4 - Cone Penetrometer Limit
label | Detail - NZS4407:2015, Test 3.2 Cone Penetration
label | Acceptance / Conformance Criteria - Cone Penetrometer ≤ 25
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.5 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - Plasticity Index ≤ 8
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.6 - Accelerated Weathering
label | Detail - NZTA T/20 Ethylene Glycol Accelerated Weathering Test
label | Acceptance / Conformance Criteria - ≤ 30% increase in fines
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.7 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - TCC-IDC IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.1 - Geogrid
label | Detail - The Contractor shall submit the full details of the geogrid they propose to use to the Engineer for approval prior to installation.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 20.5.2, PS 16.5.13
label | Verifying Document - Data Sheets and Approval
label | Testing Quantity Required (based from schedule qtys) - Once prior to works commencting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.2 - Geotextile Fabric
label | Detail - The Contractor shall submit the full details of the geotextile fabric they propose to use to the Engineer for approval prior to installation.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 20.5.2, PS 16.5.14
label | Verifying Document - Data Sheets and Approval
label | Testing Quantity Required (based from schedule qtys) - Once prior to works commencting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 100kN
label | Standard / Specification - NZS4407:2015, Test 3.10, TCC-IDC-IT-4.3.1-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - ≥60%
label | Standard / Specification - NZS4402, Test 6.1.1, TCC-IDC-IT-4.3.1-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB, CA or CB
label | Standard / Specification - NZS4407, Test 3.11, TCC-IDC-IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 63.0mm ¦¦ 100% passing
label | 37.5mm ¦¦ 68-90% passing
label | 19.0mm ¦¦ 42-76% passing
label | 9.5mm ¦¦ 26-58% passing
label | 4.75mm ¦¦ 16-44% passing
label | 2.36mm ¦¦ 10-33% passing
label | 1.18mm ¦¦ 6-24% passing
label | 0.425mm ¦¦ 3-14% passing
label | 0.075mm ¦¦ 1-6% passing
label | Standard / Specification - NZS4407, Test 3.8.1, TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.2 - Shape Control
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 34-50%
label | 19.0 – 4.75 ¦¦ 18-40%
label | 9.5 – 2.36 ¦¦ 12-32%
label | 4.75 – 1.18 ¦¦ 6-24%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 0-15%
label | 0.6 – 0.15 ¦¦ 0-12%
label | Standard / Specification - TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.3 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4407, Clause 4.3, TCC-IDC-IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.4 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - ≤ 8
label | Standard / Specification - NZS4407:2015, Test 3.4, TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.4 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent Washing method
label | Acceptance / Conformance Criteria - ≥25
label | Standard / Specification - NZS4407, Test 3.6, TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.5 - Accelerated Weathering
label | Detail - NZTA T/20 Ethylene Glycol Accelerated Weathering Test
label | Acceptance / Conformance Criteria - ≤ 30% increase in fines
label | Standard / Specification - TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 – Subgrade Handover from Earthworks
checkpoint | 2.1 - QA Submission
label | Detail - Submit all Subgrade QA before proceeding with next pavement layer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Conqa Siggnoff
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 3 – PLACEMENT OF GEOGRID AND GEOTEXTILE FABRIC
checkpoint | 3.1.1 - Placement of Geotextile Fabric
label | Detail - Place Geotextile Fabric Strength Class B across pavement area, with 500mm overlaps
label | Acceptance / Conformance Criteria - Place Geotextile Fabric Strength Class B across pavement area, with 500mm overlaps
label | Standard / Specification - NTC0097, 232735.02-WSP-DR-PVS-0401-REV4
label | Verifying Document - Visual Inspection and photos
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 3.1.2 - Onsite Check by Engineer on Geogrid
label | Detail - Installation of Geogrid shall not commence until the Engineer has inspected the proposed geogrid on site and confirmed that the correct types of geogrid have been supplied.
label | Acceptance / Conformance Criteria - Installation of Geogrid shall not commence until the Engineer has inspected the proposed geogrid on site and confirmed that the correct types of geogrid have been supplied.
label | Standard / Specification - NTC0100, 232735.02-WSP-DR-PVS-0401-REV4
label | Verifying Document - Visual Inspection and photos
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Placement of Geogrid
label | Detail - The Duragrid X 30/30 Geogrid shall be placed on top of the Geotextile Fabric, and overlap areas of structural fill by a minimum of 2m, or as directed by the Engineer on site where the layer depth of structural fill is insufficient to limit deflections from the subgrade.
label | Acceptance / Conformance Criteria - The Duragrid X 30/30 Geogrid shall be placed on top of the Geotextile Fabric, and overlap areas of structural fill by a minimum of 2m, or as directed by the Engineer on site where the layer depth of structural fill is insufficient to limit deflections from the subgrade.
label | Standard / Specification - NTC0100, 232735.02-WSP-DR-PVS-0401-REV4
label | Verifying Document - Visual Inspection and photos
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
section | SECTION 4 - PAVEMENT TYPE 4
checkpoint | 4.1.1 - Plateau Density Test
label | Detail - Using a 14T Roller carry out plateau density test to determine optimum rolling pattern using static and vibratory passes
label | Acceptance / Conformance Criteria - Plateau Density Report
label | Standard / Specification - TNZM/03, TCC IDC IT-4.7, AS per NTC 349
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.2 - 3m Straight Edge
label | Detail - Formation check to ensure surface is smooth
label | Acceptance / Conformance Criteria - +/- 10mm
label | Standard / Specification - TNZM/03, TCC IDC IT-4.7, AS per NTC 350
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - Every 20m Centres, 1 each lane
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.3 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -15mm + 0mm
label | Standard / Specification - TNZM/03, TCC IDC IT-4.7, AS per NTC 351
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.4 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - TNZM/03, TCC IDC IT-4.7, AS per NTC 352
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.5 - Benkelmen Beam
label | Detail - As directed by Engineer 15m staggered by wheel path for each lane.
label | Acceptance / Conformance Criteria - 90th Percentile: 2.1mm
label | ○ Maximum: 2.62mm
label | Standard / Specification - PS 20.14.5, NTC0160
label | Verifying Document - Test Report
label | Testing Quantity Required (based from schedule qtys) - As directed by Engineer
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.1 - QA Submission
label | Detail - Submit all Subbase QA before proceeding with next pavement layer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - All test reports
label | ○ Material Test Results
label | ○ Laboratory MDD
label | ○ NDM results
label | ○ Proof Roll
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3.1 - Plateau Density Test
label | Detail - Using a 14T Roller carry out plateau density test to determine optimum rolling pattern using static and vibratory passes
label | Acceptance / Conformance Criteria - Plateau Density Report
label | Standard / Specification - NZTA B/02 7.5 (a)
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3.2 - 3m Straight Edge
label | Detail - Formation check to ensure surface is smooth
label | Acceptance / Conformance Criteria - +/- 10mm
label | Standard / Specification - TNZ B/2 7.7
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - Every 20m Centres, 1 each lane
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3.3 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -15mm + 0mm
label | Standard / Specification - NZTA B/02 5.1
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3.4 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >98% of MDD
label | ○ Min >95% of MDD
label | Standard / Specification - NZTA B/02 7.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3.5 - Benkelmen Beam
label | Detail - As directed by Engineer 15m staggered by wheel path for each lane.
label | Acceptance / Conformance Criteria - 90th Percentile: 1.44mm
label | ○ Maximum: 1.78mm
label | Standard / Specification - PS 20.14.5, NTC0160
label | Verifying Document - Test Report
label | Testing Quantity Required (based from schedule qtys) - As directed by Engineer
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 – AS-BUILTS / REDPEN MARKUPS
checkpoint | 5.1 - As-Builts/ Red pen markup
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Red pen markups
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - D
label | Verification Activity: By - SV/SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1210-006 ITP Northern Access Road Carpark Pavement 5 | itp |  |  |  |  | DN1210-006 ITP Northern Access Road Carpark Pavement 5 Rev 0
section | SECTION 1 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 1.1.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 130kN
label | Standard / Specification - TCC-IDC IT-4.7.1 table 4.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - ≥ 60%
label | Standard / Specification - TCC-IDC IT-4.7.1 table 4.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
label | Standard / Specification - TCC-IDC IT-4.7.1 table 4.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 63.0mm ¦¦ 100% passing
label | 37.5mm ¦¦ 55-85% passing
label | 19.0mm ¦¦ 33-65% passing
label | 9.5mm ¦¦ 20-50% passing
label | 4.75mm ¦¦ 10-36% passing
label | 2.36mm ¦¦ 5-27% passing
label | 1.18mm ¦¦ 2-20% passing
label | 0.425mm ¦¦ 1-13% passing
label | 0.075mm ¦¦ 6% max passing
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.2 - Shape Control
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 34-50%
label | 19.0 – 4.75 ¦¦ 18-40%
label | 9.5 – 2.36 ¦¦ 12-32%
label | 4.75 – 1.18 ¦¦ 6-24%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 0-15%
label | 0.6 – 0.15 ¦¦ 0-12%
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.3 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - ≥ 30
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.4 - Cone Penetrometer Limit
label | Detail - NZS4407:2015, Test 3.2 Cone Penetration
label | Acceptance / Conformance Criteria - Cone Penetrometer ≤ 25
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.5 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - Plasticity Index ≤ 8
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.6 - Accelerated Weathering
label | Detail - NZTA T/20 Ethylene Glycol Accelerated Weathering Test
label | Acceptance / Conformance Criteria - ≤ 30% increase in fines
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.7 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - TCC-IDC IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.1 - Geogrid
label | Detail - The Contractor shall submit the full details of the geogrid they propose to use to the Engineer for approval prior to installation.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 20.5.2, PS 16.5.13
label | Verifying Document - Data Sheets and Approval
label | Testing Quantity Required (based from schedule qtys) - Once prior to works commencing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.2 - Geotextile Fabric
label | Detail - The Contractor shall submit the full details of the geotextile fabric they propose to use to the Engineer for approval prior to installation.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 20.5.2, PS 16.5.14
label | Verifying Document - Data Sheets and Approval
label | Testing Quantity Required (based from schedule qtys) - Once prior to works commencing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 100kN
label | Standard / Specification - NZS4407:2015, Test 3.10, TCC-IDC-IT-4.3.1-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - ≥60%
label | Standard / Specification - NZS4402, Test 6.1.1, TCC-IDC-IT-4.3.1-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB, CA or CB
label | Standard / Specification - NZS4407, Test 3.11, TCC-IDC-IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 63.0mm ¦¦ 100% passing
label | 37.5mm ¦¦ 68-90% passing
label | 19.0mm ¦¦ 42-76% passing
label | 9.5mm ¦¦ 26-58% passing
label | 4.75mm ¦¦ 16-44% passing
label | 2.36mm ¦¦ 10-33% passing
label | 1.18mm ¦¦ 6-24% passing
label | 0.425mm ¦¦ 3-14% passing
label | 0.075mm ¦¦ 1-6% passing
label | Standard / Specification - NZS4407, Test 3.8.1, TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.2 - Shape Control
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 34-50%
label | 19.0 – 4.75 ¦¦ 18-40%
label | 9.5 – 2.36 ¦¦ 12-32%
label | 4.75 – 1.18 ¦¦ 6-24%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 0-15%
label | 0.6 – 0.15 ¦¦ 0-12%
label | Standard / Specification - TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.3 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4407, Clause 4.3, TCC-IDC-IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.4 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - ≤ 8
label | Standard / Specification - NZS4407:2015, Test 3.4, TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.4 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent Washing method
label | Acceptance / Conformance Criteria - ≥25
label | Standard / Specification - NZS4407, Test 3.6, TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.5 - Accelerated Weathering
label | Detail - NZTA T/20 Ethylene Glycol Accelerated Weathering Test
label | Acceptance / Conformance Criteria - ≤ 30% increase in fines
label | Standard / Specification - TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 130kN
label | Standard / Specification - PS 20.9, TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - ≥ 80%
label | Standard / Specification - PS 20.9, TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6.3 - Accelerated Weathering
label | Detail - NZTA T/20 Ethylene Glycol Accelerated Weathering Test
label | Acceptance / Conformance Criteria - ≤ 30% increase in fines
label | Standard / Specification - PS 20.9, TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6.4 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
label | Standard / Specification - PS 20.9, TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 37.5mm ¦¦ 100% passing
label | 19.0mm ¦¦ 60-75% passing
label | 9.5mm ¦¦ 37-50% passing
label | 4.75mm ¦¦ 20-35% passing
label | 2.36mm ¦¦ 12-28% passing
label | 1.18mm ¦¦ 9-20% passing
label | 0.600mm ¦¦ 7-12% passing
label | 0.300mm ¦¦ 3-10% passing
label | 0.150mm ¦¦ 0-5% passing
label | 0.075mm ¦¦ 0-5% passing
label | Standard / Specification - PS 20.9, TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7.2 - Shape Control
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 28-48%
label | 19.0 – 4.75 ¦¦ 14-34%
label | 9.5 – 2.36 ¦¦ 7-27%
label | 4.75 – 1.18 ¦¦ 6-22%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 5-19%
label | 0.6 – 0.15 ¦¦ 2-14%
label | Standard / Specification - PS 20.9, TCC-IDC IT-4..8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7.3 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - ≥ 40
label | Standard / Specification - PS 20.9, TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7.4 - Cone Penetrometer Limit
label | Detail - NZS4407:2015, Test 3.2 Cone Penetration
label | Acceptance / Conformance Criteria - Cone Penetrometer ≤ 30
label | Standard / Specification - PS 20.9, TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7.5 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - Plasticity Index ≤ 8
label | Standard / Specification - PS 20.9, TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7.6 - Clay Index NZS 4407 Test 3.5
label | Detail - Clay Index NZS 4407 Test 3.5
label | Acceptance / Conformance Criteria - ≤ 5
label | Standard / Specification - PS 20.9, TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 – Subgrade Handover from Earthworks
checkpoint | 2.1 - QA Submission
label | Detail - Submit all Subgrade QA before proceeding with next pavement layer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Conqa Siggnoff
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 3 – PLACEMENT OF GEOGRID AND GEOTEXTILE FABRIC
checkpoint | 3.1.1 - Placement of Geotextile Fabric
label | Detail - Place Geotextile Fabric Strength Class B across pavement area, with 500mm overlaps
label | Acceptance / Conformance Criteria - Place Geotextile Fabric Strength Class B across pavement area, with 500mm overlaps
label | Standard / Specification - NTC0097, 232735.02-WSP-DR-PVS-0401-REV4
label | Verifying Document - Visual Inspection and photos
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 3.1.2 - Onsite Check by Engineer on Geogrid
label | Detail - Installation of Geogrid shall not commence until the Engineer has inspected the proposed geogrid on site and confirmed that the correct types of geogrid have been supplied.
label | Acceptance / Conformance Criteria - Installation of Geogrid shall not commence until the Engineer has inspected the proposed geogrid on site and confirmed that the correct types of geogrid have been supplied.
label | Standard / Specification - NTC0100, 232735.02-WSP-DR-PVS-0401-REV4
label | Verifying Document - Visual Inspection and photos
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Placement of Geogrid
label | Detail - The Duragrid X 30/30 Geogrid shall be placed on top of the Geotextile Fabric, and overlap areas of structural fill by a minimum of 2m, or as directed by the Engineer on site where the layer depth of structural fill is insufficient to limit deflections from the subgrade.
label | Acceptance / Conformance Criteria - The Duragrid X 30/30 Geogrid shall be placed on top of the Geotextile Fabric, and overlap areas of structural fill by a minimum of 2m, or as directed by the Engineer on site where the layer depth of structural fill is insufficient to limit deflections from the subgrade.
label | Standard / Specification - NTC0100, 232735.02-WSP-DR-PVS-0401-REV4
label | Verifying Document - Visual Inspection and photos
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
section | SECTION 4 –PAVEMENT TYPE 5
checkpoint | 4.1.1 - Plateau Density Test
label | Detail - Using a 14T Roller carry out plateau density test to determine optimum rolling pattern using static and vibratory passes
label | Acceptance / Conformance Criteria - Plateau Density Report
label | Standard / Specification - NZTA B/02 7.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.2 - 3m Straight Edge
label | Detail - Formation check to ensure surface is smooth
label | Acceptance / Conformance Criteria - +/- 10mm
label | Standard / Specification - TNZ B/2 7.7
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - Every 20m Centres, 1 each lane
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.3 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -25mm + 5mm
label | Standard / Specification - NZTA B/02 5.1
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.4 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - NZTA B/02 7.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.5 - Benkelmen Beam
label | Detail - As directed by Engineer 15m staggered by wheel path for each lane. Unbound layer.
label | Acceptance / Conformance Criteria - 90th Percetile: 1.90mm
label | ○ Maximum: 2.34mm
label | Standard / Specification - PS 20.14.5, NTC0160
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - As directed by Engineer
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.1 - Plateau Density Test
label | Detail - Using a 14T Roller carry out plateau density test to determine optimum rolling pattern using static and vibratory passes
label | Acceptance / Conformance Criteria - Plateau Density Report
label | Standard / Specification - NZTA B/02 7.5 (a)
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.2 - 3m Straight Edge
label | Detail - Formation check to ensure surface is smooth
label | Acceptance / Conformance Criteria - +/- 10mm
label | Standard / Specification - TNZ B/2 7.7
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - Every 20m Centres, 1 each lane
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.3 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -15mm + 0mm
label | Standard / Specification - NZTA B/02 5.1
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.4 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - NZTA B/02 7.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.5 - Benkelmen Beam
label | Detail - As directed by Engineer 15m staggered by wheel path for each lane.
label | Acceptance / Conformance Criteria - 90th Percentile: 1.39mm
label | ○ Maximum: 1.70mm
label | Standard / Specification - PS 20.14.5, NTC0160
label | Verifying Document - Test Report
label | Testing Quantity Required (based from schedule qtys) - As directed by Engineer
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3.1 - QA Submission
label | Detail - Submit all Subbase QA before proceeding with next pavement layer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - All test reports
label | ○ Material Test Results
label | ○ Laboratory MDD
label | ○ NDM results
label | ○ Proof Roll
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4.1 - Plateau Density Test
label | Detail - Using a 14T Roller carry out plateau density test to determine optimum rolling pattern using static and vibratory passes
label | Acceptance / Conformance Criteria - Plateau Density Report
label | Standard / Specification - NZTA B/02 7.5 (a)
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.4.2 - 3m Straight Edge
label | Detail - Formation check to ensure surface is smooth
label | Acceptance / Conformance Criteria - +/- 10mm
label | Standard / Specification - TNZ B/2 7.7
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - Every 20m Centres, 1 each lane
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.4.3 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -15mm + 0mm
label | Standard / Specification - NZTA B/02 5.1
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres, 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.4.4 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >98% of MDD
label | ○ Min >95% of MDD
label | Standard / Specification - NZTA B/02 7.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 – AS-BUILTS / REDPEN MARKUPS
checkpoint | 5.1 - As-Builts/ Red pen markup
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Red pen markups
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - D
label | Verification Activity: By - SV/SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature