## Breakdown
Breakdown | Tier 1 | Tier 2 | Tier 3 (CHECKLISTS) | Checklist
QA
DUL & KEOWN
Health And Saftey
SSSP
Workshop QA DOCUMENTS
Fabrication Quality Plan
Contract and Technical Review
Steel Mill Certs
Workshop QA ITP
Structural Coatings
Welders Ticket
Third Party NDT
Site QA DOCUMENTS
Erection Operating Procedures
Methodology
Bolt Batch Numbers
GA Drawings
Bolting Diagram
Welders Tickets
Site Weld NDT
|  |  | Installation QA | Site Install Checklist
Overview QA Checklist

## Checklist
Site Install Checklist | Section | Prestart
| checkpoint | Work area clear, tidy and accessible
| checkpoint | Substrate acceptable
| Section | Steel Delivery
| checkpoint | Corrosion protection accepatble
| checkpoint | Numbers stamped / id tags attached
| Section | Steel Erection
| checkpoint | Grid Lines marked for Set out
| checkpoint | Wall heights marked and checked
| checkpoint | PC Panels Plumb
| checkpoint | Cast in plates in place
Overview QA Checklist | Section | Overview QA
| checkpoint | Steel Erects to Level
| checkpoint | Steel Erects to Plumb
| checkpoint | Bracing Systems Installed to Specification
| checkpoint | Temporary bracing secured, if required
| checkpoint | Purlins and Bracing Installed to Specification
| checkpoint | Bolts installed to Correct Requirements
| checkpoint | Chemsets installed to Specification
| checkpoint | HD bolts installed correctly
| Section | Welding
| checkpoint | All welding completed to spec and weld procedure
| Section | Coating
| checkpoint | Coating touch up completed
| checkpoint | Steel surface left clean
| Section | Handover
| checkpoint | All site debris removed
| checkpoint | Ready For Handover To Next Trade
Photo and written evidence for this line