## Sheet1
1.1 | Mix Design approval | Prior to commencing paving | Mix design to be used has been approved by project superintendent, prior to use | 407.09 Mix Design Registration | Approval Correspondance | Completed ITP | HP | Project Engineer/ Supervisor | 1.1 - Mix Design approval | FREQUENCY: Prior to commencing paving | ACCEPTANCE CRITERIA: Mix design to be used has been approved by project superintendent, prior to use | REFERENCE DOCUMENTS: 407.09 Mix Design Registration | INSPECTION/TEST METHOD: Approval Correspondance | RECORD OF CONFORMITY: Completed ITP | HP | RESPONSIBILITY: Project Engineer/ Supervisor | Date Completed: | 1.1 - Mix Design approval
1.2 | Site Inspection and Base Condition | Prior to commencing paving | Surface on which asphalt is to be placed is essentially dry and free from puddles, defects (holes, cracks, unstable material and edge irregularities) and loose materials. | 407.17 AS2150 10.1 AS2150 10.3 | Visual Inspection | Completed ITP | WP | Asphalt Supervisor | 1.2 - Site Inspection and Base Condition | FREQUENCY: Prior to commencing paving | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles, defects (holes, cracks, unstable material and edge irregularities) and loose materials. | REFERENCE DOCUMENTS: 407.17 AS2150 10.1 AS2150 10.3 | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: Completed ITP | WP | RESPONSIBILITY: Asphalt Supervisor | Date Completed: | FREQUENCY: Prior to commencing paving
1.3 | Ambient Conditions for Placing | Prior to commencing paving | The majority of the surface area to be paved has a temperature greater than or equal to the following: Base CHAR(AMP) Intermediate Courses: 5°C for conventional binders or 10°C for PMBs CHAR(AMP) Class 600 Wearing Courses: 10°C for conventional binders or 15°C for PMBs Where the above temperatures cannot be achieved, asphalt must be laid under the "Fulton Hogan Cold Weather Paving Plan" | 407.17 | Infrared Thermometer | Completed ITP | IP | Asphalt Supervisor | 1.3 - Ambient Conditions for Placing | FREQUENCY: Prior to commencing paving | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following: Base CHAR(AMP) Intermediate Courses: 5°C for conventional binders or 10°C for PMBs CHAR(AMP) Class 600 Wearing Courses: 10°C for conventional binders or 15°C for PMBs Where the above temperatures cannot be achieved, asphalt must be laid under the "Fulton Hogan Cold Weather Paving Plan" | REFERENCE DOCUMENTS: 407.17 | INSPECTION/TEST METHOD: Infrared Thermometer | RECORD OF CONFORMITY: Completed ITP | IP | RESPONSIBILITY: Asphalt Supervisor | Date Completed: | ACCEPTANCE CRITERIA: Mix design to be used has been approved by project superintendent, prior to use
1.4 | Planning of Joints | Prior to commencing paving | Runs to be marked to ensure placement of all Longitudinal Joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints for the final Wearing Course are located on lane lines Longitudinal Joints for Intermediate and Base Layers offset from layer to layer by 150mm, and no more than 300mm from lane lines | 407.21 | Measure and mark out runs by tape measure or survey | Completed ITP | WP | Project engineer FHC | 1.4 - Planning of Joints | FREQUENCY: Prior to commencing paving | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of all Longitudinal Joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints for the final Wearing Course are located on lane lines Longitudinal Joints for Intermediate and Base Layers offset from layer to layer by 150mm, and no more than 300mm from lane lines | REFERENCE DOCUMENTS: 407.21 | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey | RECORD OF CONFORMITY: Completed ITP | WP | RESPONSIBILITY: Project engineer FHC | Date Completed: | REFERENCE DOCUMENTS: 407.09 Mix Design Registration
1.5 | Tack Coat | Prior to Commencing paving | Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.25-0.50 L/m2 of CRS60. This rate is to be doubled on joints and chases. Tack coat must be allowed to fully cure . NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces Photographical evidence must be obtained (with an identifiable landmark) *from 1st July 2023, "trackless Tack Coat" must be used | 407.19 AS2150 11 | Spray area and inspect | Completed ITP Photograph | IP | Asphalt Foreman | 1.5 - Tack Coat | FREQUENCY: Prior to Commencing paving | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.25-0.50 L/m2 of CRS60. This rate is to be doubled on joints and chases. Tack coat must be allowed to fully cure . NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces Photographical evidence must be obtained (with an identifiable landmark) *from 1st July 2023, "trackless Tack Coat" must be used | REFERENCE DOCUMENTS: 407.19 AS2150 11 | INSPECTION/TEST METHOD: Spray area and inspect | RECORD OF CONFORMITY: Completed ITP Photograph | IP | RESPONSIBILITY: Asphalt Foreman | Date Completed: | INSPECTION/TEST METHOD: Approval Correspondance
3.1 | Commencement of Placing | Prior to Commencing paving | The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client's nominated authority. | 407.23 | Visual Inspection | Completed ITP | HP | Asphalt Supervisor / Superintendent | 3.1 - Commencement of Placing | FREQUENCY: Prior to Commencing paving | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client's nominated authority. | REFERENCE DOCUMENTS: 407.23 | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: Completed ITP | HP | RESPONSIBILITY: Asphalt Supervisor / Superintendent | Date Completed: | RECORD OF CONFORMITY: Completed ITP
3.2 | Delivery of Mix | Each lot | Check correct mix design has been supplied, as per pavement design. | Pavement Design Details 407.20 | Check asphalt delivery docket | Completed ITP | IP | Asphalt Foreman | 3.2 - Delivery of Mix | FREQUENCY: Each lot | ACCEPTANCE CRITERIA: Check correct mix design has been supplied, as per pavement design. | REFERENCE DOCUMENTS: Pavement Design Details 407.20 | INSPECTION/TEST METHOD: Check asphalt delivery docket | RECORD OF CONFORMITY: Completed ITP | IP | RESPONSIBILITY: Asphalt Foreman | Date Completed: | HP
3.3 | Delivery of Mix | Each load | Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C. | 407.11 Table 407.111 | Visual Inspection CHAR(AMP) Delivery Docket | Completed ITP | WP | Asphalt Foreman | 3.3 - Delivery of Mix | FREQUENCY: Each load | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C. | REFERENCE DOCUMENTS: 407.11 Table 407.111 | INSPECTION/TEST METHOD: Visual Inspection CHAR(AMP) Delivery Docket | RECORD OF CONFORMITY: Completed ITP | WP | RESPONSIBILITY: Asphalt Foreman | Date Completed: | RESPONSIBILITY: Project Engineer/ Supervisor
3.4 | Traceability | Each lot | Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer | Fulton Hogan Quality Plan | Measure and Record on Daily Lot Record | Completed ITP | IP | Fulton Hogan Foreman/ Engineer | 3.4 - Traceability | FREQUENCY: Each lot | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan | INSPECTION/TEST METHOD: Measure and Record on Daily Lot Record | RECORD OF CONFORMITY: Completed ITP | IP | RESPONSIBILITY: Fulton Hogan Foreman/ Engineer | Date Completed: | Date Completed:
3.5 | Layer Thickness and Level Control | Regularly during paving | Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications | Pavement Design Details 407.25(a),(b) | Dips using ruler or dip stick | Completed ITP | WP | Asphalt Foreman | 3.5 - Layer Thickness and Level Control | FREQUENCY: Regularly during paving | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications | REFERENCE DOCUMENTS: Pavement Design Details 407.25(a),(b) | INSPECTION/TEST METHOD: Dips using ruler or dip stick | RECORD OF CONFORMITY: Completed ITP | WP | RESPONSIBILITY: Asphalt Foreman | Date Completed: | 1.2 - Site Inspection and Base Condition
3.6 | Paver Stoppages | If paver stops | A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C | 407.25 (c) | Thermometer | Completed ITP | WP | Asphalt Foreman | 3.6 - Paver Stoppages | FREQUENCY: If paver stops | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C | REFERENCE DOCUMENTS: 407.25 (c) | INSPECTION/TEST METHOD: Thermometer | RECORD OF CONFORMITY: Completed ITP | WP | RESPONSIBILITY: Asphalt Foreman | Date Completed: | FREQUENCY: Prior to commencing paving
3.7 | Surface Finish of Wearing Course | During paving and after final roll | The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks | 407.25 (c) | Visual Inspection | Completed ITP | WP | Asphalt Foreman | 3.7 - Surface Finish of Wearing Course | FREQUENCY: During paving and after final roll | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks | REFERENCE DOCUMENTS: 407.25 (c) | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: Completed ITP | WP | RESPONSIBILITY: Asphalt Foreman | Date Completed: | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles, defects (holes, cracks, unstable material and edge irregularities) and loose materials.
3.8 | Kerb and Channel | During paving and after final roll | The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified | 407.29 (a)(ii) | Visual Inspection CHAR(AMP) Measurement | Completed ITP | WP | Asphalt Foreman | 3.8 - Kerb and Channel | FREQUENCY: During paving and after final roll | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified | REFERENCE DOCUMENTS: 407.29 (a)(ii) | INSPECTION/TEST METHOD: Visual Inspection CHAR(AMP) Measurement | RECORD OF CONFORMITY: Completed ITP | WP | RESPONSIBILITY: Asphalt Foreman | Date Completed: | REFERENCE DOCUMENTS: 407.17 AS2150 10.1 AS2150 10.3
3.9 | Trafficking pavement after placment | After final roll | Trafficking or placement of asphalt over type SF asphalt is not permitted unless the majority of the SF asphalt has a surface temperature of 50°C or less and Falling. Where trafficking of SF aspahlt results in deformation, further trafficking shall cease until such time that the type SF asphalt has adequately cooled to allow works to continue without further damage. For Stone Mastic Asphalt, this must be 40°C | 407.28, 404.14 | Visual Inspection CHAR(AMP) Thermometert | Completed ITP | HP | Asphalt Foreman | 3.9 - Trafficking pavement after placment | FREQUENCY: After final roll | ACCEPTANCE CRITERIA: Trafficking or placement of asphalt over type SF asphalt is not permitted unless the majority of the SF asphalt has a surface temperature of 50°C or less and Falling. Where trafficking of SF aspahlt results in deformation, further trafficking shall cease until such time that the type SF asphalt has adequately cooled to allow works to continue without further damage. For Stone Mastic Asphalt, this must be 40°C | REFERENCE DOCUMENTS: 407.28, 404.14 | INSPECTION/TEST METHOD: Visual Inspection CHAR(AMP) Thermometert | RECORD OF CONFORMITY: Completed ITP | HP | RESPONSIBILITY: Asphalt Foreman | Date Completed: | INSPECTION/TEST METHOD: Visual Inspection
4.1 | Compaction Testing (Dense Graded Apshalt) | Per Lot | Test Lots >500m2, Per lot, the Characteristic Density Ratio must meet the following Minimum Limits: >50mm layer depth = 96.0% CHAR(LESS)50mm layer depth = 95.0% Additional Test must be undertaken on the longitudinal joints for wearing courses Test Lots 50m2-500m2, may be treated as a small area,in which the mean of 3x test sites must exceed the appropriate compaction requirement by 2.0% Test Lots CHAR(LESS)50m2, compaction for all lots shall be accepted on a procedural basis Mix Types where total contract supply CHAR(LESS)300t, compaction for all lots shall be accepted on a procedural basis | Section 407.27(a),(c.) 407, Section 173, Dense Graded Compaction Procedure | Nuclear Density Test, DGA Compaction Procedure | Completed ITP, Compaction rerports | TP | Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer | 4.1 - Compaction Testing (Dense Graded Apshalt) | FREQUENCY: Per Lot | ACCEPTANCE CRITERIA: Test Lots >500m2, Per lot, the Characteristic Density Ratio must meet the following Minimum Limits: >50mm layer depth = 96.0% CHAR(LESS)50mm layer depth = 95.0% Additional Test must be undertaken on the longitudinal joints for wearing courses Test Lots 50m2-500m2, may be treated as a small area,in which the mean of 3x test sites must exceed the appropriate compaction requirement by 2.0% Test Lots CHAR(LESS)50m2, compaction for all lots shall be accepted on a procedural basis Mix Types where total contract supply CHAR(LESS)300t, compaction for all lots shall be accepted on a procedural basis | REFERENCE DOCUMENTS: Section 407.27(a),(c.) 407, Section 173, Dense Graded Compaction Procedure | INSPECTION/TEST METHOD: Nuclear Density Test, DGA Compaction Procedure | RECORD OF CONFORMITY: Completed ITP, Compaction rerports | TP | RESPONSIBILITY: Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer | Date Completed: | RECORD OF CONFORMITY: Completed ITP
4.2 | Level Conformance | Each Lot | The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements as specified in 407.30 (b) Scale A: +/- 5mm Range, +/- 8mm standard deviation | 407.30, 407.29 | Survey Results | Completed ITP, Survey Conformance Results | WP | Surveyor | 4.2 - Level Conformance | FREQUENCY: Each Lot | ACCEPTANCE CRITERIA: The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements as specified in 407.30 (b) Scale A: +/- 5mm Range, +/- 8mm standard deviation | REFERENCE DOCUMENTS: 407.30, 407.29 | INSPECTION/TEST METHOD: Survey Results | RECORD OF CONFORMITY: Completed ITP, Survey Conformance Results | WP | RESPONSIBILITY: Surveyor | Date Completed: | WP
RESPONSIBILITY: Asphalt Supervisor
Date Completed:
1.3 - Ambient Conditions for Placing
FREQUENCY: Prior to commencing paving
ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following: Base CHAR(AMP) Intermediate Courses: 5°C for conventional binders or 10°C for PMBs CHAR(AMP) Class 600 Wearing Courses: 10°C for conventional binders or 15°C for PMBs Where the above temperatures cannot be achieved, asphalt must be laid under the "Fulton Hogan Cold Weather Paving Plan"
REFERENCE DOCUMENTS: 407.17
INSPECTION/TEST METHOD: Infrared Thermometer
RECORD OF CONFORMITY: Completed ITP
IP
RESPONSIBILITY: Asphalt Supervisor
Date Completed:
1.4 - Planning of Joints
FREQUENCY: Prior to commencing paving
ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of all Longitudinal Joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints for the final Wearing Course are located on lane lines Longitudinal Joints for Intermediate and Base Layers offset from layer to layer by 150mm, and no more than 300mm from lane lines
REFERENCE DOCUMENTS: 407.21
INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
RECORD OF CONFORMITY: Completed ITP
WP
RESPONSIBILITY: Project engineer FHC
Date Completed:
1.5 - Tack Coat
FREQUENCY: Prior to Commencing paving
ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.25-0.50 L/m2 of CRS60. This rate is to be doubled on joints and chases. Tack coat must be allowed to fully cure . NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces Photographical evidence must be obtained (with an identifiable landmark) *from 1st July 2023, "trackless Tack Coat" must be used
REFERENCE DOCUMENTS: 407.19 AS2150 11
INSPECTION/TEST METHOD: Spray area and inspect
RECORD OF CONFORMITY: Completed ITP Photograph
IP
RESPONSIBILITY: Asphalt Foreman
Date Completed:
3.1 - Commencement of Placing
FREQUENCY: Prior to Commencing paving
ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client's nominated authority.
REFERENCE DOCUMENTS: 407.23
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: Completed ITP
HP
RESPONSIBILITY: Asphalt Supervisor / Superintendent
Date Completed:
3.2 - Delivery of Mix
FREQUENCY: Each lot
ACCEPTANCE CRITERIA: Check correct mix design has been supplied, as per pavement design.
REFERENCE DOCUMENTS: Pavement Design Details 407.20
INSPECTION/TEST METHOD: Check asphalt delivery docket
RECORD OF CONFORMITY: Completed ITP
IP
RESPONSIBILITY: Asphalt Foreman
Date Completed:
3.3 - Delivery of Mix
FREQUENCY: Each load
ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
REFERENCE DOCUMENTS: 407.11 Table 407.111
INSPECTION/TEST METHOD: Visual Inspection CHAR(AMP) Delivery Docket
RECORD OF CONFORMITY: Completed ITP
WP
RESPONSIBILITY: Asphalt Foreman
Date Completed:
3.4 - Traceability
FREQUENCY: Each lot
ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
INSPECTION/TEST METHOD: Measure and Record on Daily Lot Record
RECORD OF CONFORMITY: Completed ITP
IP
RESPONSIBILITY: Fulton Hogan Foreman/ Engineer
Date Completed:
3.5 - Layer Thickness and Level Control
FREQUENCY: Regularly during paving
ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
REFERENCE DOCUMENTS: Pavement Design Details 407.25(a),(b)
INSPECTION/TEST METHOD: Dips using ruler or dip stick
RECORD OF CONFORMITY: Completed ITP
WP
RESPONSIBILITY: Asphalt Foreman
Date Completed:
3.6 - Paver Stoppages
FREQUENCY: If paver stops
ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
REFERENCE DOCUMENTS: 407.25 (c)
INSPECTION/TEST METHOD: Thermometer
RECORD OF CONFORMITY: Completed ITP
WP
RESPONSIBILITY: Asphalt Foreman
Date Completed:
3.7 - Surface Finish of Wearing Course
FREQUENCY: During paving and after final roll
ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
REFERENCE DOCUMENTS: 407.25 (c)
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: Completed ITP
WP
RESPONSIBILITY: Asphalt Foreman
Date Completed:
3.8 - Kerb and Channel
FREQUENCY: During paving and after final roll
ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
REFERENCE DOCUMENTS: 407.29 (a)(ii)
INSPECTION/TEST METHOD: Visual Inspection CHAR(AMP) Measurement
RECORD OF CONFORMITY: Completed ITP
WP
RESPONSIBILITY: Asphalt Foreman
Date Completed:
3.9 - Trafficking pavement after placment
FREQUENCY: After final roll
ACCEPTANCE CRITERIA: Trafficking or placement of asphalt over type SF asphalt is not permitted unless the majority of the SF asphalt has a surface temperature of 50°C or less and Falling. Where trafficking of SF aspahlt results in deformation, further trafficking shall cease until such time that the type SF asphalt has adequately cooled to allow works to continue without further damage. For Stone Mastic Asphalt, this must be 40°C
REFERENCE DOCUMENTS: 407.28, 404.14
INSPECTION/TEST METHOD: Visual Inspection CHAR(AMP) Thermometert
RECORD OF CONFORMITY: Completed ITP
HP
RESPONSIBILITY: Asphalt Foreman
Date Completed:
4.1 - Compaction Testing (Dense Graded Apshalt)
FREQUENCY: Per Lot
ACCEPTANCE CRITERIA: Test Lots >500m2, Per lot, the Characteristic Density Ratio must meet the following Minimum Limits: >50mm layer depth = 96.0% CHAR(LESS)50mm layer depth = 95.0% Additional Test must be undertaken on the longitudinal joints for wearing courses Test Lots 50m2-500m2, may be treated as a small area,in which the mean of 3x test sites must exceed the appropriate compaction requirement by 2.0% Test Lots CHAR(LESS)50m2, compaction for all lots shall be accepted on a procedural basis Mix Types where total contract supply CHAR(LESS)300t, compaction for all lots shall be accepted on a procedural basis
REFERENCE DOCUMENTS: Section 407.27(a),(c.) 407, Section 173, Dense Graded Compaction Procedure
INSPECTION/TEST METHOD: Nuclear Density Test, DGA Compaction Procedure
RECORD OF CONFORMITY: Completed ITP, Compaction rerports
TP
RESPONSIBILITY: Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer
Date Completed:
4.2 - Level Conformance
FREQUENCY: Each Lot
ACCEPTANCE CRITERIA: The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements as specified in 407.30 (b) Scale A: +/- 5mm Range, +/- 8mm standard deviation
REFERENCE DOCUMENTS: 407.30, 407.29
INSPECTION/TEST METHOD: Survey Results
RECORD OF CONFORMITY: Completed ITP, Survey Conformance Results
WP
RESPONSIBILITY: Surveyor
Date Completed: