## Earthworks for CVSC
[7 empty] | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer
Item No. | Document | ITP Tab | Section | General Queries | Date | Status | Contractor's Response | Date | Status comments / Response | Date | Contractor's Response No. 2 | Date | Status comments / Response No. 2 | Date | Contractor's Response No. 3 | Date | Status comments / Response No. 3 | Date | Contractor's Response No. 4 | Date | Status comments / Response No. 4 | Date | Contractor's Response No. 5 | Date | Status comments / Response No. 5 | Date
1 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | GENERAL | Approval | Has ITP been review internally by Downer? ITP has not been approved by Downer PM. | 2024-01-12 | Close | Yes, the ITP's are reviewed internally. The approval from the project manager is pending until the initial round of review and necessary corrections are completed. | 24/01/2024 RJ | Accepted | 2024-02-05 | Accepted
2 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | GENERAL | Specification | "Waka Kotahi NZ Transport Agency Contract 7456 " Please revise this section to list the applicable specifications for this ITP. | 2024-01-12 | Close | TNZ M/3, TNZ M/4, TNZ B/2, NZS 4402:1986, NZS 4407:2015 | 29/01/2024 SJD | Accepted | 2024-02-05 | Accepted
3 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | Receiving Inspections | 3.1.5- ESCP | How will Downer track to make sure Resource Consent Conditions are met? Is there another ITP? | 2024-01-12 | Open | In accordance with the approved ESCP, DNZ has finished the Sediment Pond and has submitted the as-built form and as-built drawing, along with the methodology outlining how DNZ is handling site controls. Following discussions with the council, it has been determined that there will not be a physical review and acceptance process for the submitted as-builts. IF any concerns will be raised upon the methodology then it will be considered and resubmit the changes. The internal review of the as-built documentation and methodology was completed by the senior Environmental & Sustainability Advisor before submission. Aprroved ESCP plan will be submitted as the verifying documnet for this line item. | 24/01/2024 RJ | Per the granted consent conditions, there are numerous other documents and monitoring reporting that is required, other than just an approved ESCP. Can DNZ confirm if there is another ITP that will be used to track the requirements outlined in the granted consent conditions? | 2024-02-05 | The construction of ESCP has been finished according to the approved plan. The only monitoring tasks include the pre-rain event checklist, maintenance, and addressing conditional complaints as necessary. The checklist will be retained as an environmental checklist and will not be incorporated as a requirement in the ITP. | 07/02/2024 RJ
4 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | Receiving Inspections |  | Items do not match the work breakdown structure as per NZTA Z8. | 2024-01-12 | Open | Do we have a WBS for this project??? | 29/01/2024 SJD | The WBS is included in the copy of the NZTA Z8 Specifications. DNZ to separate individual tests required. Section doesn't account for "Cut to Fill" material. DNZ to review the WBS included in the NZTA Z8 Specifications. How is "Incoming Materials" defined? Import material (AP65)? Why is base course included in Earthworks ITP? | 2024-02-05 | Added "Imported Fill and Structural Fill Sources" and " Cut to Fill" to Incoming Materials under sections 3.2.1 and 3.2.2 of the ITP | 15/02/2024 SJD
5 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | Receiving Inspections | Activity | Many Items have the description of the task detailed under "Acceptance Criteria" rather than the "Activity/Task Description" column. | 2024-01-12 | Open | We might have to adda column titled "Inspection Point: Quality Control Activity", which is from the Downer ITP template, just to tidy that up. | 29/01/2024 SJD | Why? Separate sections for "Cut to Fill" and "Import Fill" to be added to ITP and specific tests need to have individual rows and test result requirements for both added to the "Acceptance Criteria" column. DNZ to revise. | 2024-02-05 | Same as above | 15/02/2024 SJD
6 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | Receiving Inspections | Standard/ Specification | Standard/Specifications column makes several references to "Downer Standard". Can Downer confirm what is included in the "Downer Standard"? Has Downer submitted these for review? | 2024-01-12 | Open | Certain activities involve the internal production of document verification. These processes will be finalized using the Downer format, accompanied by the signature of the individual responsible for the review and approval of the specific document. In some cases, documents may take the form of an acknowledgment letter, confirming the completion of tasks outlined in the specific line item, such as survey set-out or service location. | 24/01/2024 RJ | Are these processes included in the DNZ management plans? | 2024-02-05 | Service location and permits are the requirements as per DG-ZH-ST043 in management plans. Survey set-out will be issues on the Downer as-built drawing formats. | 7/02/2024 RJ
7 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | Receiving Inspections | 3.2.1 - Geotextile | Geogrid Triax TX160 has been speicied for the Pavement design. Pelase revise "Project Specification" to reference the actual specification (e.g. TNZ F/7) | 2024-01-12 | Open | Changes made in the 'standards/specification' on item 3.2.1 | 24/01/2024 RJ | No changes have been made. DNZ to review and revise. Have not received copies of the materail technical data sheets. DNZ to supply for review. | 2024-02-05 | Updated | 7/02/2024 RJ
8 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | Receiving Inspections | 3.2.1 - Geotextile | Revise Acceptance Criteria to reflect the actual criteria for accceptance referenced in the applicable specification (e.g. Clause 7. - Manufacturer's Certificate of Compliance, together with IANZ endorsed or equivalent test documents) | 2024-01-12 | Open | Changes made in the 'Acceptance crieteria' on item 3.2.1 | 24/01/2024 RJ | No changes have been made. DNZ to review and revise. Have not received copies of the materail technical data sheets. DNZ to supply for review. | 2024-02-05 | Updated | 7/02/2024 RJ
9 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | Receiving Inspections | 3.2.2 | Geogrid Triax TX160 has been speicied for the Pavement design. Please remvoe and add to the Pavement ITP (DG-OWR-CVSC-ITP003). | 2024-01-12 | Open | This line item is removed and updated. | 24/01/2024 RJ | No changes have been made. DNZ to review and revise. | 2024-02-05 | Updated | 7/02/2024 RJ
10 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | Receiving Inspections | 3.2.3 | Revise Frequency to match specification requirements: • 2 tests per source, submitted 4 weeks before use in the works – not older than 2 years old. • 1 test per 10,000m3 thereafter. ) | 2024-01-12 | Open | Changes made in the 'Frequency' on item 3.2.3 (3.2.2 as per latest update) | 24/01/2024 RJ | No changes have been made. DNZ to review and revise. | 2024-02-05 | Updated. Reference section been updated to 3.2.2 | 7/02/2024 RJ
11 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | Receiving Inspections | 3.2.3 | Revise to include all Tests and the acceptance requirements: NZS 4407 : 1991, Test 3.10, The Crushing Resistance Test, under a load of 130 kN less than 10% fines passing 2.36 mm sieve size shall be produced. NZS 4407 : 1991, Test 3.11 Weathering Quality Index Test. Aggregate shall have a quality index of AA, AB, AC, BA, BB or CA NZS 4402 : 1986, Test 4.1.3 New Zealand - Vibrating Hammer Compaction Test at Optimum Water Content and, NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%. | 2024-01-12 | Open | Changes made in the 'Acceptance Crieteria' on item 3.2.3 (3.2.2 as per latest update) This is all testing and acceptance criteria for AP40 basecourse. This seems like an overkill. Am I missing something? | 24/01/2024 RJ | What is basecourse and subbase included into Earthworks ITP? No changes have been made. DNZ to review and revise, as per previous comments | 2024-02-05 | Those acceptance criterias are now under section 3.2.4 of the ITP | 15/02/2024 SJD
12 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | Receiving Inspections | 3.2.4 | Revise to include all Tests and the acceptance requirements: NZS 4407 : 1991, Test 3.6 Sand Equivalent Test., The sand equivalent shall not be less than 40. NZS 4407 : 1991, Test 3.5 Clay Index Test. The clay index of the fraction of basecourse passing the 75μm sieve shall not be greater than 3 NZS 4407 : 1991, Test 3.4 Plasticity Index Test. The plasticity index of the fraction of basecourse passing the 425μm sieve shall not be greater than 5 NZS 4407 : 1991, Test 3.14 Broken Face Test. aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces. NZS 4407 : 1991, Test 3.8.1 Wet Sieving Test. aggregate shall conform with the envelope limits defined in both Tables 2 and 3 in Clause 4.2.3. | 2024-01-12 | Open | Changes made in the 'Acceptance Crieteria' on item 3.2.4 (3.2.3 as per latest update) This is all testing and acceptance criteria for AP40 basecourse. This seems like an overkill. Am I missing something? | 24/01/2024 RJ | What is basecourse and subbase included into Earthworks ITP? No changes have been made. DNZ to review and revise, as per previous comments | 2024-02-05 | Those acceptance criterias are now under section 3.2.5 of the ITP | 15/02/2024 SJD
13 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | Receiving Inspections | 3.2.5 | What about NZS 4407:1991, Test 3.7 | 2024-01-12 | Open | Firstly, NZS 4407:1991 was superseded by NZS 4407:2015. All the labs should be operating to this standard. Secondly, test 3.7 is for the solid density of aggregate which can be done in conjunction with the MDD/OWC. I assume this is what the Engineer is talking about. | 29/01/2024 SJD | Accepted | 2024-02-05 | Accepted
14 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | Receiving Inspections | 3.2.3-3.2.4 | DNZ have noted AP65 in the Activity/Task Description column, but say, "basecourse aggregate" in the Acceptance Criteria column. Filling and compacting operations will use both onsite cut material and import material (AP65). Please revise to reflect the individual material test that are required per project specifications for both (onsite material and AP65). | 2024-01-12 | Open | Please refer to "Contractors Response No.2" column. | 15/02/2024 SJD | No response received. DNZ to review and response. | 2024-02-05 | Please refer to 3.2.1 and 3.2.2 of the ITP individual material tests. | 15/02/2024 SJD
15 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | In Process Inspection | 3.1.2 4.1.1 | Why have DNZ add 10m x 10m topographical survey of the CVSC building foot print to Earthwork ITP? Wouldn't this be as part of the Final Inspection and Handover? | 2024-01-12 | Open | There is a survey component in Item No. 5.2 | 29/01/2024 SJD | Reference section should have been 4.1.1. Does Line Item 4.1.1 need to be removed and added to the "Final Inspection and Handover" tab? | 2024-02-05 | Line Item 4.1.1 is removed and the survey as-built information will be added in the final inspection and handover | 07/02/2024 RJ
16 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | In Process Inspection | 3.2.4 4.1.4- Subgrade Suitability Testing | Please add the specific Acceptance Criteria as speicified in the Project Specifications (Blows/100mm>6). Please add Scala Penetrometer to the "Activity/Task Description". | 2024-01-12 | Open | I've made the changes to the ITP | 29/01/2024 SJD | Accepted. Reference section should have been 4.1.4. | 2024-02-05 | Accepted. Reference section been updated to 4.1.3. | 07/02/2024 RJ
17 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | In Process Inspection | 3.2.5 4.1.5- Subgrad Proof Rolling and Suitability Inspection | Spelling error "Subgrad", change "Subgrade". Per Section 2.10 of the Specifications, "If Scala testing cannot be complete, then a proof roll must be completed to a standard that is acceptable by the Engineer. Please add "(As needed)" to the Activity/Task Description title. | 2024-01-12 | Open | I've made the changes to the ITP | 29/01/2024 SJD | Accepted. Reference section should have been 4.1.5. | 2024-02-05 | Accepted. Reference section been updated to 4.1.4. | 07/02/2024 RJ
18 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | In Process Inspection | 3.2.5 4.1.5- Subgrad Proof Rolling and Suitability Inspection | Will Downer keep a record of the different areas that are proof rolled? Will with record consist of a survey or sketch of the area using civil plans? It is anticipated that not all the subgrade will be proof rolled. | 2024-01-12 | Open | The RL and area of proof rolling will be surveyed. | 29/01/2024 SJD | DNZ to add "survey" to the verifying document. Please revise and re-submit. Reference section should have been 4.1.5. | 2024-02-05 | Updated the verifying document section. Referance been updated to 4.1.4 | 07/02/2024 RJ
19 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | In Process Inspection | 3.2.6 4.1.6- Imported Fill (GAp65/AP65) Compaction Testing(NDM) | This Activity/Task is also applicable to the onsite material that will be used for fill material. Please add onsite fill material to the Activity/Task Description title. | 2024-01-12 | Open | I've made the changes to the ITP | 29/01/2024 SJD | Accepted. Reference section should have been 4.1.6. | 2024-02-05 | Accepted. Reference section should have been 4.1.5. | 07/02/2024 RJ
20 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | In Process Inspection | 3.2.6 4.1.6- Imported Fill (GAp65/AP65) Compaction Testing(NDM) | Acceptance Criteria is missing moisture content requirements and MDD is of NZ Heavy Compaction (NZ 4402 Test 4.1.2) effort. Please add the acceptance criteria. | 2024-01-12 | Open | Added, and made changes to ITP | 30/01/2024 SJD | Accepted. Reference section should have been 4.1.6. | 2024-02-05 | Accepted. Reference section should have been 4.1.5. | 07/02/2024 RJ
21 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | In Process Inspection | 3.2.6 4.1.6- Imported Fill (GAp65/AP65) Compaction Testing(NDM) | Verifying document for the compaction testing is by Test Results. Can Downer confirm when Test Results will be supplied to the Engineer for review? Daily, weekly timeframe? | 2024-01-12 | Open | I think weekly should be sufficient, but, we are at the mercy of the lab so as long as they send the results through promptly then we should be able to meet that obligation. | 29/01/2024 SJD | Accepted. Reference section should have been 4.1.6. | 2024-02-05 | Accepted. Reference section should have been 4.1.5. | 07/02/2024 RJ
22 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | In Process Inspection | 3.2.8 4.1.8- Geogrid Prep Inspection | Should this Activity/Task Description form part of the "Receiving Inspection" tasks? | 2024-01-12 | Open | Please refer to "Contractors Response No.2" column. | 15/02/2024 SJD | DNZ to provide a response. Reference section should have been 4.1.8. | 2024-02-05 | Have deleted geogrid prep from 'In Process Inspection' and re-applied to 'Receiving Inspection' under section 3.2.4 | 15/02/2024 SJD
23 | DG-OWR-CVSC-ITP001 (Earthworks for CVSC) | In Process Inspection | Standard/ Specification | General observation, DNZ have stated, "As per project specification". Please add the particular section of the project specification. | 2024-01-12 | Open | Added | 30/01/2024 SJD | Accepted | 2024-02-05 | Accepted
24
25
26

## Pavement for CVSC
[7 empty] | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer
Item No. | Document | ITP Tab | Section | General Queries | Date | Status | Contractor's Response | Date | Status comments / Response | Date | Contractor's Response No. 2 | Date | Status comments / Response No. 2 | Date | Contractor's Response No. 3 | Date | Status comments / Response No. 3 | Date | Contractor's Response No. 4 | Date | Status comments / Response No. 4 | Date | Contractor's Response No. 5 | Date | Status comments / Response No. 5 | Date
1 | DG-OWR-CVSC-ITP003_v1 (Pavement for CVSC) | GENERAL | Approval | Has ITP been review internally by Downer? ITP has not been approved by Downer PM. | 2024-01-17 | Open |  |  | No DNZ response. Assume same as Earthworks ITP. DNZ to confirm? | 2024-02-05 | Yes, the ITP's are reviewed internally. The approval from the project manager is pending until the initial round of review and necessary corrections are completed. Same comments for all the ITPs at this stage. | 7/02/2024 RJ
2 | DG-OWR-CVSC-ITP003_v1 (Pavement for CVSC) | GENERAL | Specification | "Waka Kotahi NZ Transport Agency Contract 7456 " Please revise this section to list the applicable specifications for this ITP. | 2024-01-17 | Close | Updated & added | 30/01/2024 SJD | Accepted. | 2024-02-05 | Accepted.
3 | DG-OWR-CVSC-ITP003_v1 (Pavement for CVSC) | Receiving Inspections | Standard/ Specification | Standard/Specifications column makes several references to "Downer Standard". Can Downer confirm what is included in the "Downer Standard"? Has Downer submitted these for review? | 2024-01-17 | Open |  |  | No DNZ response. Assume same as Earthworks ITP. DNZ to confirm? | 2024-02-05
4 | DG-OWR-CVSC-ITP003_v1 (Pavement for CVSC) | Receiving Inspections | 3.2 | Civil Technical Specification 3.5.4 states: "The subbase shall consist of GAP65 aggregate which has a proven track record in pavement applications and is compliant with a local subbase aggregate specification selected by the contractor. The GAP65 material testing reports and selected specification shall be provided to the engineer for review prior to construction." Please advise if DNZ is sourcing the material produced to a certain specification, if so which specification? | 2024-01-17 | Close | TNZ M/3 & TNZ M/4?? | 30/01/2024 SJD | Accepted. | 2024-02-05 | Accepted.
5 | DG-OWR-CVSC-ITP003_v1 (Pavement for CVSC) | In Process Inspection |  | Please ensure the Compliance Hold Points between all layers of the pavement structure are included as per Appendix F - Pavement Ohakea [8.9], [9.11] & [10.19]: "The Engineer must receive proof of compliance with all of the above testing requirements prior to proceeding with construction of the overlying pavement layers." | 2024-01-17 | Close | Have added testing frequency as stated in Apendix F | 30/01/2024 SJD | Accepted. | 2024-02-05 | Accepted.
6 | DG-OWR-CVSC-ITP003_v1 (Pavement for CVSC) | In Process Inspection | 4.1.3 & 4.1.6 | At other weigh right locations the frequency of testing has been revised to 1/50m2 for the CVSC area as there aren’t clear lanes. Is Downer ammenable to this revised testing frequency? If so, please revise these sections of the ITP. | 2024-01-17 | Close | Have ammended the statement in the frequency column stating the frequency of testing if no clear lanes | 30/01/2024 SJD | Accepted. | 2024-02-05 | Accepted.
7 | DG-OWR-CVSC-ITP003_v1 (Pavement for CVSC) | In Process Inspection | 4.2 | How does Downer intend to guard against segregation, the pumping cement and aggregate fines to the top of the later during the construction process? - Civil Tech Spec [3.6.7] | 2024-01-17 | Open | I wouldn't have thought that the cement would get pumped to the top if it's spread on the ground before the hoe goes through???? | 30/01/2024 SJD | Correct. Can DNZ confirm methodology how placed base course will be stabilised cement? Also, can DNZ confirm if optimum cement study being completed? | 2024-02-05 | We will follow the requirements of NZTA B/5, sections 6 and 7. No, cement study has not been completed. | 15/02/2024 SJD
8 | DG-OWR-CVSC-ITP003_v1 (Pavement for CVSC) | In Process Inspection | 4.3.1 | Agreed that TNZ B/02: 2005 states 80%, however, Civil Technical Specification 3.6.7 states: "The degree of saturation… …shall have a result no higher than 70% prior to sealing...." Please revise this section to include reference to the Civil Tech Spec & update the DOS. | 2024-01-17 | Close | Updated and added DOS and reference to contract spec | 30/01/2024 SJD | Accepted. | 2024-02-05 | Accepted.
9 | DG-OWR-CVSC-ITP003_v1 (Pavement for CVSC) | In Process Inspection | Missing Benkelmen Beam Testing | Please add Benkelmen Beam Testing of Subbase (GAP65) to the deflection requirements in Appendix F - Pavement Ohakea [8.5] which states: "Subbase: CVSC - No deflection > 2.2 mm." A Frequency of 1/10m in each lane, but 1/50m2 is preferrable due to CVSC geometry. | 2024-01-17 | Open | Updated and addded deflection and frequency of testing | 30/01/2024 SJD | Benkelman Beam is required to completed on the subbase course, as per Appendix F- Pavement Ohakea (8.5). DNZ to revise and add to ITP. | 2024-02-05 | Added Benkelman Beam requirements for CTB to CTB section under 4.2.11 | 15/02/2024 SJD
10 | DG-OWR-CVSC-ITP003_v1 (Pavement for CVSC) | In Process Inspection | 4.3.2.4 | Please revise to the deflection requirements in Appendix F - Pavement Ohakea [9.7] which states: "Basecourse: No deflection > 1.4 mm." A Frequency of 1/10m in each lane, but 1/50m2 is preferrable due to CVSC geometry. | 2024-01-17 | Open | Updated and addded deflection and frequency of testing | 30/01/2024 SJD | Wouldn't this be more applicable to Section 4.3- Sealing? Benkelman Beam is required to completed on the subbase course, as per Appendix F- Pavement Ohakea (8.5) and prior to sealing. DNZ to revise and re-submit ITP. | 2024-02-05 | Have adjusted Benkelman Beam requirements to section 4.3.2 (Sealing) | 15/02/2024 SJD
| DG-OWR-CVSC-ITP003_v1 (Pavement for CVSC) | In Process Inspection | 4.3.2.4 | Verifying document for the compaction testing is by Test Results. Can Downer confirm when Test Results will be supplied to the Engineer for review? Daily, weekly timeframe? | 2024-01-17 | Open | Added comment about results been delivered weekly. | 30/01/2024 SJD | Accepted. | 2024-02-05 | Accepted.
11 | DG-OWR-CVSC-ITP003_v1 (Pavement for CVSC) | In Process Inspection | 4.3.2.8 | AC14 has a design lift thickness of 55 mm. Please revise the lift thickness tolerance to be +/- 5 mm as per Civil Spec [3.7.15] which states: "Asphalt layers less than or equal to 55 mm shall be +/- 5 mm from the specified design thickness." | 2024-01-17 | Open | Added reference to contract specification and updated AC thickness tolerances | 30/01/2024 SJD | Accepted. | 2024-02-05 | Accepted.
12 | DG-OWR-CVSC-ITP003_v1 (Pavement for CVSC) | In Process Inspection | 4.3.2.8 | Appendix F - Pavement Ohakea [10.15] states: "In addition to the thickness requirements within M/10 and M/27. The combined thickness of all asphalt layers shall not be less than the specified total asphalt depth." | 2024-01-17 | Open | Added reference to Appendix F and added statement about total AC thickness | 30/01/2024 SJD | Accepted for the AC14. However, SMA10, or SMA012.5, is only 40mm. Please revise to reflect what is Specified in the Appendix F- Ohakea Pavement Design Section 10.15 Layer Thickness. | 2024-02-05 | Have added extra clause (4.4.6) with regard to SMA10 | 15/02/2024 SJD
13 | DG-OWR-CVSC-ITP003_v1 (Pavement for CVSC) | In Process Inspection | Missing Indirect Tensile Strength (ITS) Testing | Revise to include ITS Testing as per Civil Technical Spec [3.6.5] & Appendix F - Ohakea Pavement [9.5] - The specification requires 1 dry and 1 wet ITS test per dosage of additive prior to construction, dosages to be in the range of 1.3% to 2%. The target ITS is 150 – 350 kPa dry and 100 – 300 kPa wet. Then 2 dry and 2 wet behind the hoe samples each day of stabilisation. Should Downer experience any issues achieving the required ITS results with the permitted dosages they are to notify the Engineer ASAP. | 2024-01-17 | Open | At what stage are we expected to carry out the pre-construction ITS testing??? ITS testing been added to ITP | 31/01/2024 SJD | Per Appendix F - Ohakea Pavement Design Section 9.6 Mix Design Confirmation, "Mix design testing for the modified basecourse shall be carried out according to the requirements and methodology presented in Waka Kotahi T/19. The testing must be carried out in advance of the basecourse layer construction and shall use representative samples from each aggregate source. Target ITS values for this testing are provided in Section 9.5. The results of the mix design testing shall be submitted to the engineer for review in advance of the pavement basecourse construction.". DNZ to confirm anticiapted date for submitting test results? | 2024-02-05
14 | DG-OWR-CVSC-ITP003_v1 (Pavement for CVSC) | In Process Inspection | Missing Scala Testing | Missing Scala Testing for CVSC Subgrade Minimum CBR 3.5% as per CVSC Pvmt Type C Detail on Bartley Dwg TD002 | 2024-01-17 | Open | This should be covered in the earthworks phase. | 31/01/2024 SJD | How will DNZ confirm the CBR value of proposed subgrade to determine which pavement design is required? | 2024-02-05 | Some lab soaked CBR's will have to be sampled to determine CBR value | 15/02/2024 SJD

## WIM
[7 empty] | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer
Item No. | Document | ITP Tab | Section | General Queries | Date | Status | Contractor's Response | Date | Status comments / Response | Date | Contractor's Response No. 2 | Date | Status comments / Response No. 2 | Date | Contractor's Response No. 3 | Date | Status comments / Response No. 3 | Date | Contractor's Response No. 4 | Date | Status comments / Response No. 4 | Date | Contractor's Response No. 5 | Date | Status comments / Response No. 5 | Date
1 | DG-OWR-WIM-ITP001_v1 | GENERAL | Approval | Has ITP been review internally by Downer? ITP has not been approved by Downer PM. | 2024-01-17 | Open
2 | DG-OWR-WIM-ITP001_v1 | GENERAL | Specification | "Waka Kotahi NZ Transport Agency Contract 7456 " Please revise this section to list the applicable specifications for this ITP. | 2024-01-17 | Open | Updated | 21/02/2024 SJD
3 | DG-OWR-WIM-ITP001_v1 | Receiving Inspections | Activity | Many Items have the description of the task detailed under "Acceptance Criteria" rather than the "Activity/Task Description" column. | 2024-01-17 | Open
4 | DG-OWR-WIM-ITP001_v1 | Receiving Inspections | Standard/ Specification | Standard/Specifications column makes several references to "Downer Standard". Can Downer confirm what is included in the "Downer Standard"? Has Downer submitted these for review? | 2024-01-17 | Open | Certain activities involve the internal production of document verification. These processes will be finalized using the Downer format, accompanied by the signature of the individual responsible for the review and approval of the specific document. In some cases, documents may take the form of an acknowledgment letter, confirming the completion of tasks outlined in the specific line item, such as survey set-out or service location. | 21/02/2024 SJD
7 | DG-OWR-WIM-ITP001_v1 | In Process Inspection | 4.3.2.8 | Appendix F - Pavement Ohakea [10.15] states: "Asphalt layers shall be +/-10% to a maxiumum of 10 mm." +/- 9mm, 8mm, 8mm based as per 90/80/80mm pavement structure. | 2024-01-17 | Open | Added (in Section 4.3.2.8) | 21/02/2024 SJD
8 | DG-OWR-WIM-ITP001_v1 | In Process Inspection | 3.6 | Appendix E - ITS [2.1.2] states: "The Contractor will in advance nominate type of compliant system and manufacturer they propose to use and agree this with the Engineer." | 2024-01-17 | Open | Added (in Section 3.6.3) | 21/02/2024 SJD
9 | DG-OWR-WIM-ITP001_v1 | In Process Inspection | 4.3.2.8 4.3.2.11 | Appendix F - Pavement Ohakea [10.15] states: "In addition to the thickness requirements within M/10 and M/27. The combined thickness of all asphalt layers shall not be less than the specified total asphalt depth." | 2024-01-17 | Open | Added (in Section 4.3.2.11) | 21/02/2024 SJD
10 | DG-OWR-WIM-ITP001_v1 | In Process Inspection | 4.5 | Appendix E - ITS [2.1.3] states: "The Contractor will set out the guardrail location with the Engineer on site." | 2024-01-17 | Open | Added (in Section 4.5.1) | 21/02/2024 SJD
11 | DG-OWR-WIM-ITP001_v1 | In Process Inspection | 4.5 | NZTA Z8 (M23) "Consultant’s Hold Point All road safety barrier systems (including end treatments and crash cushions): • System checklists to be completed and co-signed by qualified contractor (who has completed the Waka Kotahi IMI workshop) and Waka Kotahi representative. Note: All faults to be rectified before acceptance into network operations (maintenance manual) and network assets register (and RAMM)." | 2024-01-17 | Open | Added (in Section 4.5.3) | 21/02/2024 SJD

## Kerb Channel Footpath
[7 empty] | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer
Item No. | Document | ITP Tab | Section | General Queries | Date | Status | Contractor's Response | Date | Status comments / Response | Date | Contractor's Response No. 2 | Date | Status comments / Response No. 2 | Date | Contractor's Response No. 3 | Date | Status comments / Response No. 3 | Date | Contractor's Response No. 4 | Date | Status comments / Response No. 4 | Date | Contractor's Response No. 5 | Date | Status comments / Response No. 5 | Date
1 | DG-OWR-CVSC-ITP002_v1 (Kerb and Channel & Footpath for CVSC) | GENERAL | Approval | Has ITP been review internally by Downer? ITP has not been approved by Downer PM. | 2024-01-12 | Open
2 | DG-OWR-CVSC-ITP002_v1 (Kerb and Channel & Footpath for CVSC) | GENERAL | Specification | "Waka Kotahi NZ Transport Agency Contract 7456 " Please revise this section to list the applicable specifications for this ITP. | 2024-01-12 | Open | Updated | 01/02/2024 SJD
3 | DG-OWR-CVSC-ITP002_v1 (Kerb and Channel & Footpath for CVSC) | Receiving Inspections | Standard/ Specification | Standard/Specifications column makes several references to "Downer Standard". Can Downer confirm what is included in the "Downer Standard"? Has Downer submitted these for review? | 2024-01-12 | Open | Certain activities involve the internal production of document verification. These processes will be finalized using the Downer format, accompanied by the signature of the individual responsible for the review and approval of the specific document. In some cases, documents may take the form of an acknowledgment letter, confirming the completion of tasks outlined in the specific line item, such as survey set-out or service location. | 01/02/2024 SJD
4 | DG-OWR-CVSC-ITP002_v1 (Kerb and Channel & Footpath for CVSC) | Receiving Inspections | Activity | Many Items have the description of the task detailed under "Acceptance Criteria" rather than the "Activity/Task Description" column. | 2024-01-12 | Open
5 | DG-OWR-CVSC-ITP002_v1 (Kerb and Channel & Footpath for CVSC) | In Process Inspections | 4.1.4 | Agreed the specification states 300 mm of AP65, but as per the Kerb details on sheet C-5110 the pavement layers described on Sheet TD003 (AP 40 Modified with Cement) is also acceptable. | 2024-01-12 | Open | Added comment about cement modified basecourse | 01/02/2024 SJD
6 | DG-OWR-CVSC-ITP002_v1 (Kerb and Channel & Footpath for CVSC) | In Process Inspection | 4.2.6, 4.2.7 | Missing Benkelmen Beam Testing as per Appendix A - Civil [5.5.2] | 2024-01-12 | Open | Added details regarding Benkelman beaming | 01/02/2024 SJD
7 | DG-OWR-CVSC-ITP002_v1 (Kerb and Channel & Footpath for CVSC) | In Process Inspections | 4.2.6, 4.2.7 | Please revise to include the site plan showing the location of every test point. | 2024-01-12 | Open | Added comment in frequency of testing column stating that all test points wil be surveyed | 01/02/2024 SJD
8
9

## 3 Waters for CVSC
[7 empty] | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer
Item No. | Document | ITP Tab | Section | General Queries | Date | Status | Contractor's Response | Date | Status comments / Response | Date | Contractor's Response No. 2 | Date | Status comments / Response No. 2 | Date | Contractor's Response No. 3 | Date | Status comments / Response No. 3 | Date | Contractor's Response No. 4 | Date | Status comments / Response No. 4 | Date | Contractor's Response No. 5 | Date | Status comments / Response No. 5 | Date
1 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | GENERAL | Approval | Has ITP been review internally by Downer? ITP has not been approved by Downer PM. | 2024-01-22 | Open
2 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | GENERAL | Specification | "Waka Kotahi NZ Transport Agency Contract 7456 " Please revise this section to list the applicable specifications for this ITP. | 2024-01-22 | Open | Updated | 02/02/2024 SJD
3 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | GENERAL | ITP Description | The description is detailed in the "Discipline" section | 2024-01-22
4 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | Receiving & In-Process | Standard/ Specification | Standard/Specifications column makes several references to "Downer Standard". Can Downer confirm what is included in the "Downer Standard"? Has Downer submitted these for review? | 2024-01-22 | Open | Certain activities involve the internal production of document verification. These processes will be finalized using the Downer format, accompanied by the signature of the individual responsible for the review and approval of the specific document. In some cases, documents may take the form of an acknowledgment letter, confirming the completion of tasks outlined in the specific line item, such as survey set-out or service location. | 02/02/2024 SJD
5 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | Receiving & In-Process | Standard/ Specification | Standard/Specifications columns make several references to "Project Specification". Please revise to include the applicable clause/section of the applicable specification. | 2024-01-22 | Open | Updated | 02/02/2024 SJD
6 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | Receiving | 3.2.6 | TWES 00013, 2.4.5.3 PE Pipe & Resin QA information "Prior to pipe procurement, advise the Engineer of the name of the pipe manufacturer and the locations of the extrusion plants for all PE pipes. Includ the name of the proposed PE resin and the manufacturer, along with product information on the properties of the resin... ...". This is a hold point as per TWES 00013, 4.3 | 2024-01-22 | Open | Updated | 02/02/2024 SJD
7 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | Receiving | Specification/ Acceptance | Please add the applicable specification for Sand (Three Waters Spec - Clause 3.1.2) & the acceptance Criteria (Gradation as per Table in 3.1.2) | 2024-01-22 | Open | Grading criteria added | 02/02/2024 SJD
8 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | Receiving | Specification/ Acceptance | Please add the applicable specification for Drainage Media (Three Waters Spec - Clause 3.1.3) & the acceptance Criteria (Gradation as per Table in 3.1.3) | 2024-01-22 | Open | Grading criteria added | 02/02/2024 SJD
9 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | Receiving | Specification/ Acceptance | Please revise to include the applicable specification for Soil Media (Three Waters Spec - Clause 3.1.4 & the acceptance Criteria (requirements in 3.1.4): e.g. 5% clean organic compost from a consistent source; Locally sourced topsoil (free of weeds or contamination); No obvious seeds, weeds, any contamination and material >25 mm in nominal diameter; ≤50% coarse sand from a consistent source to improve permeability and structure; <3% clay (particles <0.002 mm); A pH range of 7.5 – 5.5; etc... | 2024-01-22 | Open | Acceptance criteria for soil media added | 02/02/2024 SJD
10 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | Receiving | Materials | TWES 00012, 2.1 "Do not change the source of supply of materials without written approval from the Engineer". This is a hold point as per TWES 00012, 4.8 | 2024-01-22 | Open | Added to ITP under section 3.2.12 | 02/02/2024 SJD
11 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | In Process Inspection | Hold Point | TWES 00013, 3.1.1 "Submit the proposed methodology for pipe laying, concrete work, jointing and backfilling to the Engineer and obtain acceptance before starting pipe installation". This is a hold point as per TWES 00013, 4.3 & as per TWES 00012, 4.8 | 2024-01-22 | Open | Added to ITP under section 4.6.5 | 02/02/2024 SJD
12 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | In Process Inspection | Dewatering Hold Point | TWES 00011, 4.4 Hold Points references Section 3.5 which states: "Provide a Method statement for controlling water in trenches or dewatering for the Engineer's acceptance five days before construction, including: …." | 2024-01-22 | Open | Added to ITP under section 4.4.9 | 02/02/2024 SJD
13 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | In Process Inspection | 4.5.1 | Please revise to include all the accceptance testing criteria as per TWES 00012, 4.6. & include reference to 4.6.4 (a) -> (k) for Testing Record Requirements. (Note: NZS 2566.2 Section 6.4 also includes Vacuum Testing) | 2024-01-22 | Open | Added to ITP under section 4.5.2 (T-WES 00012) | 13/02/2024 SJD
14 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | In Process Inspection | 4.5.3 | Please add accceptance criteria for CCTV as per TWES 00012, 4.6.7 (a) -> (f) "- colour picture, minimum pixel resolution 500Hx 400V, flushed/cleaned prior (no debris), small flow (25% pipe diameter), & Deliverables to the Engineer i)->iii)" | 2024-01-22 | Open | Added to ITP under section 4.6.7 (T-WES 00012) | 13/02/2024 SJD
15 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | In Process Inspection | 4.6.8 | T-WES 00013, 3.1.14.1 is a hold point "Have the Engineer witness the first flanged joint completed on the PE 100 pipeline. This is a Hold point." | 2024-01-22 | Open | Added to ITP | 13/02/2024 SJD
16 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | In Process Inspection | Subsurface Drain & Pipes | Construction of Sub-Surface drains and pipes do not include the work breakdown structure as per NZTA Z8. (F/2, F/5, F/6) | 2024-01-22 | Open | I can't seem to find anything about a WBS in Z/8 | 14/02/2024 SJD
17 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | In Process Inspection | 4.7.1 | Revise to include Three Waters Specification Clause 2.4 - Amendment to T-WES 00013 Pressure Pipelines Supply, Install and Testing Specification. Change to Clause 4.5.7.2 "The system test Pressure (STP) is 1,000 kPa." | 2024-01-22 | Open | Added to ITP and updated to clause 4.5.7.2 | 14/02/2024 SJD
18 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | In Process Inspection | 4.7.1 | Revise to include the Advanced Notification outlined in T-WES 00013 [4.5.3] "Before commencing any pressure acceptance test: • Give the Engineer at least two Working Days’ notice. • Provide the Engineer with a detailed work method statement (WMS) with details of how the pressure testing will be carried out at least 10 Working Days prior to the test, including but not limited to: - Proposed equipment...; Proposed fill rate...; Calibration Certificates...; Qualified Personnel...; Water Source...; Provision for Backflow prevention etc..." | 2024-01-22 | Open | Added to ITP | 14/02/2024 SJD
19 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | In Process Inspection | 4.7.2 | T-WES 00013, 5 states: "Prepare and submit a Work Method Statement (WMS) for disinfection of potable water pipelines to the Engineer for acceptance before commencing disinfection work. The WMS must include (at least) details of: - Swabbing all potable water pipes, valves, and other fittings...; How the disinfection solution will be introduced...; How the disinfection solution will be prepared and delivered reliably into the pipeline...; Calculations of dosing and flow rates...; How to ensure all watermains, service pipes and fittings will receive the solution...; How measurements of the FAC during and at end will be acheived...; How the disinfection solution is to be safely disposed...; Identify Health & Safety Risks and proposed mitigations..." | 2024-01-22 | Open | Added to ITP | 14/02/2024 SJD
20 | DG-OWR-CVSC-ITP004_v1 (3 Waters for CVSC) | In Process Inspection | 4.7.3 | T-WES 00013, 6 states: "...connect the pipelines to the existing mains as shown on the Drawings and flush at an approved rate until the chlorine residual is 1mg/L or lower..." Where will this water be discharged? "The disinfection solution must not be discharged to the stormwater system unless it is de-chlorinated using a continuous system or a batch tank, either require the Engineer's written approval." "The maximum duration for any shutdown is typically 48 hours" | 2024-01-22 | Open | Is this coverd in the ITP section 4.7.3 as we have to submit a WMS on how to dispose of the disinfection solution. | 14/02/2024 SJD

## VMS
[7 empty] | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer
Item No. | Document | ITP Tab | Section | General Queries | Date | Status | Contractor's Response | Date | Status comments / Response | Date | Contractor's Response No. 2 | Date | Status comments / Response No. 2 | Date | Contractor's Response No. 3 | Date | Status comments / Response No. 3 | Date | Contractor's Response No. 4 | Date | Status comments / Response No. 4 | Date | Contractor's Response No. 5 | Date | Status comments / Response No. 5 | Date
1 | DG-OWR-VMS-ITP-001_v1 | GENERAL | Approval | Has ITP been review internally by Downer? ITP has not been approved by Downer PM. | 2024-01-23 | Open
2 | DG-OWR-VMS-ITP-001_v1 | GENERAL | Specification | "Waka Kotahi NZ Transport Agency Contract 7456 " Please revise this section to list the applicable specifications for this ITP. | 2024-01-23 | Open | Updated | 14/02/2024 SJD
3 | DG-OWR-VMS-ITP-001_v1 | In Process Inspection | 4.1.5 - 4.1.7 | What about concrete plastic testing as per 3309 (Slump, Air, Temp) | 2024-01-23 |  | Trying to get access to NZS 3309 through Downer Library | 14/02/2024 SJD
4 | DG-OWR-VMS-ITP-001_v1 | In Process Inspection | 4.2 | Appendix E - ITS [2.1.4] states: "Pavement shoulder widening treatment will be confirmed with Engineer on site." | 2024-01-23 | Open | Added to ITP under section 4.2.2 | 14/02/2024 SJD
5 | DG-OWR-VMS-ITP-001_v1 | In Process Inspection | 4.3 | Appendix E - ITS [2.1.3] states: "The Contractor will set out the guardrail location with the Engineer on site." | 2024-01-23 | Open | Added to ITP under section 4.3.1 | 14/02/2024 SJD
6 | DG-OWR-VMS-ITP-001_v1 | In Process Inspection | 4.2.9 | Inspection Type listed as Hold point, but Inspection Key shown as "I" inspection | 2024-01-23 | Open | Updated | 14/02/2024 SJD
7
8
9
10
11
12
13
14
15

## General
[7 empty] | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer |  | Contractor |  | Engineer
Item No. | Document | ITP Tab | Section | General Queries | Date | Status | Contractor's Response | Date | Status comments / Response | Date | Contractor's Response No. 2 | Date | Status comments / Response No. 2 | Date | Contractor's Response No. 3 | Date | Status comments / Response No. 3 | Date | Contractor's Response No. 4 | Date | Status comments / Response No. 4 | Date | Contractor's Response No. 5 | Date | Status comments / Response No. 5 | Date
1 |  |  | Appendix A - Civil [6] | Landscaping doesn't appear to be captured within the submitted Inspection & Test Plans, should this included in the Earthworks ITP? Ref: Tech Spec Appendix A - Civil, [6. Landscaping], Appendix E - ITS [2.3] | 2024-01-23 | Open
2 |  |  |  | Where is Roadway Signage & Furniture captured in ITPs? | 2024-01-23 | Open
3 |  |  |  | Where is Electrical captured in ITPs? | 2024-01-23
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
29
30
31
32
33