## General
SECTION 1 – GENERAL DETAILS
Project Name: | SP1 NZTA Ohakea Weigh Right | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | 558020 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi | [5 empty] | B | Report by Breach | CM | Construction Manager | Christopher Colman | CC
Contract Number: | 7456 | [5 empty] | C | Check | CR | Cust. Representative (WSP Engineers) | Mark Frampton & Alex Brown | MF / AB
Area/ Sub-System: | CVSC - Earthworks |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel | N/A
[7 empty] | E | Examine | MC | Material Controller | N/A
ITP Number: | DG-OWR-CVSC-ITP001 |  |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager | Glen Flint | GF
ITP Description: | This ITP comprehensively encompasses the critical aspects related to incoming materials and processes associated with earthwork. | [5 empty] | I | Inspection | PM | Project Manager | Krishna Marangat | KM
Discipline: | Earthwork | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Stephen Coyle | SC
Specification: | TNZ M/3, TNZ M/4, NZS 4402:1986, NZS 4407:2015 | [5 empty] | O | Operation | QM | QA Manager | Steve Darby | SD
[7 empty] | R | Review | SE | Site Engineer | Ribin Jose | RJ
Drawings: | Waka Kotahi NZ Transport Agency SH3 & Pukenui Rd Intersection, Ohakea Weigh Right Programme. Civil - For Construction | [5 empty] | S | Subcontractor | SP | Supervisor | Stephen Coyle (Civil) & Gareth Mclellan (Drainage) | SC / GM
[7 empty] | V | Visual Verification | ST | Superintendent | N/A
Prepared By: | Ribin Jose |  |  | Date: | 2023-11-16 |  | W | Witness Point | SV | Surveyor | Stefan Killian | SK
Quality Specified: | [8 empty] | WS | Welding Supervisor | N/A
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Ribin Jose |  |  | Signature: |  |  |  |  | Date: | 2023-11-16
Downer Approval |  | Name: | Krishna Marangat |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS
Item No. | Activity/ Task Description | Standards/Specification | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Signature | Date
[7 empty] | Key | By (Role Key)
3.1 | General Preliminary
3.1.1 | Survey Setout | Downer Standard | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Survey Records | Prior to Works | Document review | H | SV
3.1.2 | Service Location | Downer Standard | Complete the on site check to identify, locate and protect all services. | Service location documents | Prior to Works | Document review | R | SE
3.1.3 | Internal Permits | Downer Standard | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Internal Permits | Prior to Excavation | Document review | R | SE
3.1.4 | External Permits | Downer Standard | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | External Permits | Prior to Excavation | Document review | R | SE
3.1.5 | ESCP | As per contracts | Prior to starting works, Ensure that ESCP plan an approved ESCP by council is in place and valid | Approved ESCP plan | Prior to Works | Document review | R | SE
3.1.6 | Approved Construction Drawings | Issued by Client | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | IFC Drawings | Prior to works start | Document review | R | SE
3.2 | Earthwork - Incoming Materials
3.2.1 | Imported Fill and Structural Fill Sources | NZS 4402:1986 | - Max Dry Density (standard) and Optimum Water Content - Natural moisture content - Plasticity index - Particle size distribution | 1 set for each fill material and source (each 5000m3 thereafter) | Porior to works | Document review | R | CR/SE
3.2.2 | Cut to Fill Material | NZS 4402:1986 | - Max Dry Density (standard) and Optimum Water Content - Natural moisture content - Plasticity index - Particle size distribution | 1 set for each fill material and source (each 5000m3 thereafter) | Porior to works | Document review | R | CR/SE
3.2.3 | Geotextile | NZTA F/7 | Non-woven filtration class 1 and Geotextile strenght class C. Confirm the above grade from the Manufacturer's Certificate of Compliance with IANZ endorsed or equivalent test documents. | Product data sheet, Docket | Each lot | Document review | Inspection | SE
3.2.4 | Geogrid Prep Inspection | As per project specification, Section 2.15 | Prior to placement of the geogrid, verification of the grade, length, orientation and layout is required against the drawings. | Product data sheet, Photos, As-built | each application | Action | W | SE
3.2.5 | Source Property Tests and Sampling (AP65) | TNZ M/3 Notes : 1986 TNZ M/4: 2006 NZS 4407 : 1991 NZS 4402 : 1986 | NZS 4407 : 1991, Test 3.10, The Crushing Resistance Test, under a load of 130 kN less than 10% fines passing 2.36 mm sieve size shall be produced. NZS 4407 : 1991, Test 3.11 Weathering Quality Index Test. Aggregate shall have a quality index of AA, AB, AC, BA, BB or CA NZS 4402 : 1986, Test 4.1.3 New Zealand - Vibrating Hammer Compaction Test at Optimum Water Content and, NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%. | IANZ Lab Reports | 2 tests per source, submitted 4 weeks before use in the works – not older than 2 years old. 1 test per 10,000m3 thereafter. | Document review | H | CR
3.2.6 | Production Property Test Sampling (AP65) | TNZ M/3 Notes : 1986 TNZ M/4: 2006 NZS 4407 : 1991 | NZS 4407 : 1991, Test 3.6 Sand Equivalent Test., The sand equivalent shall not be less than 40. NZS 4407 : 1991, Test 3.5 Clay Index Test. The clay index of the fraction of basecourse passing the 75μm sieve shall not be greater than 3 NZS 4407 : 1991, Test 3.4 Plasticity Index Test. The plasticity index of the fraction of basecourse passing the 425μm sieve shall not be greater than 5 NZS 4407 : 1991, Test 3.14 Broken Face Test. aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces. NZS 4407 : 1991, Test 3.8.1 Wet Sieving Test. aggregate shall conform with the envelope limits defined in both Tables 2 and 3 in Clause 4.2.3. | IANZ Lab Reports | 3 per source initially, then 1/1000m³ | Document review | H | CR
3.2.7 | Testing for Layer Compaction - MDD (AP65) | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at Optimum Water Content (OWC). | IANZ Lab Reports | 5,000m2 | Document review | H | CR

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS
Item No. | Activity/ Task Description | Spectification | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Signature | Date
[7 empty] | Key | By (Role Key)
4.1 | Earthwork - Construction
4.1.1 | Site clearance | As per project specification, Section 2.3 | Clearing shall include the complete removal of stumps, trees, logs, scrub and coarse vegetation and disposal by burning, or dumping and burying in accordance with any particular requirements of the contract documents | Photos, Checklist as per requirements | Prior to topsoil removal | Visual | V | SE
4.1.2 | Top soil strip | As per project specification (200mm), Section 2.9 | Topsoil shall be removed within the limits of the earthworks. Care shall be taken during the removal to avoid contamination of the topsoil. | Photos, As-built | All | Dimension Inspection Visual | D,V | SV, SE
4.1.3 | Subgrade Suitability Testing - Scala Penetrometer Testing | As per project specification, Section 2.18.2 | The Subgrade must be tested by Scala penetrometer or Shear Vane to confrim suitiablity. 3 blows per 100mm | Shear vane/scala checksheet | Whole area by 20x20m Intervals | Inspection | H | SE
4.1.4 | Subgrade Proof Rolling and Suitability Inspection | As per project specification, Section 2.10 and NZTA F/1, 10.5.1 | The subgrade shall be proof rolled to verify the subgrade stiffness and consistency. "Indents" left in the compacte layer shoiuld be no more than 7mm for bulk fill and 5mm for subgrade fill. The RL and area of proof rolling will be surveyed. | Proof Rolling Sheet, Photos, Survey area | Prior to the placement of any filling, Whole area | Visual Inspection | H | CR, SE
4.1.5 | Imported & Onsite Fill (Gap65/AP65) Compaction Testing (NDM) | As per project specification, Sections 2.13 & 2.18 | Bulk fill shall be tested by NDM with a minimum Dry Density of 95% MDD Cohesive soils shall be compacted at OWC (moisture limits are 4% below OWC to 2% below OWC) Minimum acceptable dry density for AP65 is 2100 kg/m3 , a minimum dry density of 95% must be achieved (moisture limits are 4% below OWC to 2% below OWC) | Test Results | 10m x 10m grid | Inspection | H | SE
4.1.6 | Geotextile Installation and Lap Length | As per project specification, Section 2.15 | All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. | Photos, As-built | each application | Action | W | SE

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type | Inspection |  | Inspection Point/Signature & Date
[7 empty] | Key | By | Downer Signature | Date | Customer Requirements Verification Records/Location
5.1 | Construction Record Compilation | Upon completion of works | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Closed-out NCR/Defects | Post construction | Review | R | SE
5.2 | As-built Survey | Upon completion of works | Ensure all items have been surveyed and records are assembled for asbuilting | As built survey record completed | Post construction | Review | R | SV
5.3 | Red-line As-built Drawings | Upon completion of works | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar | Signed As-built Drawings | Post construction | Review | R | SE,SV
5.4 | Defect, Snag and Punch List | Upon completion of works | Update the project Defect, Snag and Punch List Register | Register | Post construction | Review | R | PE
5.5 | All QA documentation collated & signed-off | Upon completion of works | All signed and closed out | Signed off Documents | Post construction | Review | R | QM