## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DG-OWR-CVSC-ITP001_v1 - Earthworks for CVSC | itp |  |  |  |  | DG-OWR-CVSC-ITP001_v1 - Earthworks for CVSC
section | 3.1 General Preliminary
checkpoint | 3.1.1 - Survey Setout
label | Specification - Downer Standard
label | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - SV
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Service Location
label | Specification - Downer Standard
label | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
label | Verifying Document - Service location documents
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.3 - Internal Permits
label | Specification - Downer Standard
label | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.4 - External Permits
label | Specification - Downer Standard
label | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.5 - ESCP
label | Specification - As per contracts
label | Acceptance Criteria - Prior to starting works, Ensure that ESCP plan an approved ESCP by council is in place and valid
label | Verifying Document - Approved ESCP plan
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.6 - Approved Construction Drawings
label | Specification - Issued by Client
label | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 3.2 Earthwork - Incoming Materials
checkpoint | 3.2.1 - Imported Fill and Structural Fill Sources
label | Specification - NZS 4402:1986
label | Acceptance Criteria - Max Dry Density (standard) and Optimum Water Content
label | – Natural moisture content
label | – Plasticity index
label | – Particle size distribution
label | Verifying Document - 1 set for each fill material and source (each 5000m3 thereafter)
label | Frequency - Porior to works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - CR/SE
checkpoint | 3.2.2 - Cut to Fill Material
label | Specification - NZS 4402:1986
label | Acceptance Criteria - Max Dry Density (standard) and Optimum Water Content
label | – Natural moisture content
label | – Plasticity index
label | – Particle size distribution
label | Verifying Document - 1 set for each fill material and source (each 5000m3 thereafter)
label | Frequency - Porior to works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - CR/SE
checkpoint | 3.2.3 - Geotextile
label | Specification - NZTA F/7
label | Acceptance Criteria - Non-woven filtration class 1 and Geotextile strenght class C.
label | ○ Confirm the above grade from the Manufacturer's Certificate of Compliance with IANZ endorsed or equivalent test documents.
label | Verifying Document - Product data sheet, Docket
label | Frequency - Each lot
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - Inspection
label | Inspection: By - SE
checkpoint | 3.2.4 - Geogrid Prep Inspection
label | Specification - As per project specification, Section 2.15
label | Acceptance Criteria - Prior to placement of the geogrid, verification of the grade, length, orientation and layout is required against the drawings.
label | Verifying Document - Product data sheet, Photos, As-built
label | Frequency - each application
label | Inspection Type (Visual, other) - Action
label | Inspection: Key - W
label | Inspection: By - SE
checkpoint | 3.2.5 - Source Property Tests and Sampling (AP65)
label | Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991, NZS 4402 : 1986
label | Acceptance Criteria - NZS 4407 : 1991, Test 3.10, The Crushing Resistance Test, under a load of 130 kN less than 10% fines passing 2.36 mm sieve size shall be produced.
label | ○ NZS 4407 : 1991, Test 3.11 Weathering Quality Index Test. Aggregate shall have a quality index of AA, AB, AC, BA, BB or CA
label | ○ NZS 4402 : 1986, Test 4.1.3 New Zealand - Vibrating Hammer Compaction Test at Optimum Water Content and,
label | ○ NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per source, submitted 4 weeks before use in the works – not older than 2 years old.
label | ○ 1 test per 10,000m3 thereafter.
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.6 - Production Property Test Sampling (AP65)
label | Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991
label | Acceptance Criteria - NZS 4407 : 1991, Test 3.6 Sand Equivalent Test., The sand equivalent shall not be less than 40.
label | ○ NZS 4407 : 1991, Test 3.5 Clay Index Test. The clay index of the fraction of basecourse passing the 75μm sieve shall not be greater than 3
label | ○ NZS 4407 : 1991, Test 3.4 Plasticity Index Test. The plasticity index of the fraction of basecourse passing the 425μm sieve shall not be greater than 5
label | ○ NZS 4407 : 1991, Test 3.14 Broken Face Test. aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces.
label | ○ NZS 4407 : 1991, Test 3.8.1 Wet Sieving Test. aggregate shall conform with the envelope limits defined in both Tables 2 and 3 in Clause 4.2.3.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 3 per source initially, then 1/1000m³
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.7 - Testing for Layer Compaction - MDD (AP65)
label | Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Acceptance Criteria - Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at Optimum Water Content (OWC).
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
section | 4.1 Earthwork - Construction
checkpoint | 4.1.1 - Site clearance
label | Specification - As per project specification, Section 2.3
label | Acceptance Criteria - Clearing shall include the complete removal of stumps, trees, logs, scrub and coarse vegetation and disposal by burning, or dumping and burying in accordance with any particular requirements of the contract documents
label | Verifying Document - Photos, Checklist as per requirements
label | Frequency - Prior to topsoil removal
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.1.2 - Top soil strip
label | Specification - As per project specification (200mm), Section 2.9
label | Acceptance Criteria - Topsoil shall be removed within the limits of the earthworks. Care shall be taken during the removal to avoid contamination of the topsoil.
label | Verifying Document - Photos, As-built
label | Frequency - All
label | Inspection Type (Visual, other) - Dimension Inspection, Visual
label | Inspection: Key - D,V
label | Inspection: By - SV, SE
checkpoint | 4.1.3 - Subgrade Suitability Testing - Scala Penetrometer Testing
label | Specification - As per project specification, Section 2.18.2
label | Acceptance Criteria - The Subgrade must be tested by Scala penetrometer or Shear Vane to confrim suitability.
label | ○ 3 blows per 100mm
label | Verifying Document - Shear vane/scala checksheet
label | Frequency - Whole area by 20x20m Intervals
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.4 - Subgrade Proof Rolling and Suitability Inspection
label | Specification - As per project specification, Section 2.10 and NZTA F/1, 10.5.1
label | Acceptance Criteria - The subgrade shall be proof rolled to verify the subgrade stiffness and consistency. "Indents" left in the compacte layer shoiuld be no more than 7mm for bulk fill and 5mm for subgrade fill.
label | ○ The RL and area of proof rolling will be surveyed.
label | Verifying Document - Proof Rolling Sheet, Photos, Survey area
label | Frequency - Prior to the placement of any filling, Whole area
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - H
label | Inspection: By - CR, SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.5 - Imported & Onsite Fill (Gap65/AP65) Compaction Testing (NDM)
label | Specification - As per project specification, Sections 2.13 & 2.18
label | Acceptance Criteria - Bulk fill shall be tested by NDM with a minimum Dry Density of 95% MDD
label | ○ Cohesive soils shall be compacted at OWC (moisture limits are 4% below OWC to 2% below OWC)
label | ○ Minimum acceptable dry density for AP65 is 2100 kg/m3 , a minimum dry density of 95% must be achieved (moisture limits are 4% below OWC to 2% below OWC)
label | Verifying Document - Test Results
label | Frequency - 10m x 10m grid
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.6 - Geotextile Installation and Lap Length
label | Specification - As per project specification, Section 2.15
label | Acceptance Criteria - All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
label | Verifying Document - Photos, As-built
label | Frequency - each application
label | Inspection Type (Visual, other) - Action
label | Inspection: Key - W
label | Inspection: By - SE
section | Final Inspection and Handover
checkpoint | 5.1 - Construction Record Compilation
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Verifying Document - Closed-out NCR/Defects
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 5.2 - As-built Survey
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Verifying Document - As built survey record completed
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SV
checkpoint | 5.3 - Red-line As-built Drawings
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
label | Verifying Document - Signed As-built Drawings
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE,SV
checkpoint | 5.4 - Defect, Snag and Punch List
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
label | Verifying Document - Register
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PE
checkpoint | 5.5 - All QA documentation collated & signed-off
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - All signed and closed out
label | Verifying Document - Signed off Documents
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - QM