## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DG-OWR-CVSC-ITP002_v1 - Kerb and Channel Footpath for CVSC | itp |  |  |  |  | DG-OWR-CVSC-ITP002_v1 - Kerb and Channel Footpath for CVSC
section | 3.1 General Preliminary
checkpoint | 3.1.1 - Survey Setout
label | Specification - Downer
label | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - SV
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Service Location
label | Specification - Downer
label | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
label | Verifying Document - Service location documents
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.3 - Internal Permits
label | Specification - Downer
label | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.4 - External Permits
label | Specification - Downer
label | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.5 - Approved Construction Drawings
label | Specification - Downer
label | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 3.2 Receiving Materials/Parts - Kerb & Channel/Nib
checkpoint | 3.2.1 - Concrete mix design
label | Specification - Pre-construction
label | Acceptance Criteria - 20Mpa concrete as per design notes
label | ○ Drawing/Notes Sheet No :C 5110
label | Verifying Document - Mix design
label | Frequency - Per type of mix
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - SE,CR
holdpoint | AUTHORITY HOLDPOINT
section | 3.3 Receiving Materials/Parts - Footpath
checkpoint | 3.3.1 - Concrete mix design
label | Specification - Pre-construction
label | Acceptance Criteria - 20Mpa concrete as per Civil Technical Spec Section 5.3
label | Verifying Document - Mix design
label | Frequency - Per type of mix
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - SE,CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.2 - Steel reinforcement
label | Specification - Pre-construction
label | Acceptance Criteria - As per Civil Technical Spec Section 5.3
label | Verifying Document - Material Certificate/Docket, Photos
label | Frequency - Per Delivery/Batch
label | Inspection Type (Visual, other) - Visual, Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 4.1 Kerb & Channel/Nib
checkpoint | 4.1.1 - Service Location
label | Specification - As per TDS
label | Acceptance Criteria - As per project specification locate on site 4 weeks prior to construction
label | Verifying Document - ITP Sign Off/Photos
label | Frequency - Prior to the works starting
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SP
checkpoint | 4.1.2 - Kerb/Nib Location
label | Specification - As per design
label | Acceptance Criteria - Surveyor to set-out location of kerb & channel for foundation preparation
label | Verifying Document - ITP Sign off
label | Frequency - Prior to constructing foundation
label | Inspection Type (Visual, other) - Survey Setout
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.1.3 - Subgrade Testing
label | Specification - Construction Drawings Sheet No: C-5110
label | Acceptance Criteria - Clegg testing at 10m intervals
label | ○ Subgrade CBR ≥ 7%
label | Verifying Document - Clegg Hammer Result Sheet
label | Frequency - 10m Intervals
label | Inspection Type (Visual, other) - Subgrade Compaction Testing
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.4 - Foundation Preparation and Asbuilt Survey
label | Specification - Civil Technical Specification Section 4.3
label | Acceptance Criteria - 300mm of AP65 or cement modified basecourse
label | Verifying Document - Photos & Asbuilt Survey
label | Frequency - 10m Cross Sections
label | Inspection Type (Visual, other) - Dimension Inspection
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.1.5 - Foundation Testing
label | Specification - Civil Technical Specification Section 4.3
label | Acceptance Criteria - Compacted to a minimum dry density of 2100kg/m3
label | ○ In accordance with NZS 4407: NZ Heavy Compaction
label | ○ Results provided to Engineer to proceed
label | Verifying Document - IANZ Accredited Laboratory Report
label | Frequency - 10m Intervals
label | Inspection Type (Visual, other) - NDM Compaction Testing
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.6 - Kerb/Nib Setout
label | Specification - As per design & Construction Drawings Sheet No: C-5110
label | Acceptance Criteria - Surveyor to set-out stringline of kerb and channel.
label | ○ Dimensions as per standard detail in Construction Drawings Sheet No: C-5110
label | Verifying Document - ITP Sign Off
label | Frequency - Straight: 10m Intervals
label | ○ Curve: 2m Intervals
label | ○ Survey every tangent
label | Inspection Type (Visual, other) - Survey Setout
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.1.7 - Heavy Duty Vehicle Crossing
label | Specification - Construction Drawings Sheet No: C-5110
label | Acceptance Criteria - Construct heavy duty vehicle crossing including reinforcing steel as per standard detail in Construction Drawings Sheet No: C-5110
label | Verifying Document - ITP Sign Off/Photos
label | Frequency - Prior to pouring the concrete
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.1.8 - Pre-Pour Inspection
label | Specification - As per TDS
label | Acceptance Criteria - Stringline Check, Concrete Pour Inspection Checksheet completed, and Written approval from Engineer to proceed
label | Verifying Document - Checksheet: DN-QC-04 & Written Approval from Engineer
label | Frequency - Prior to pouring the concrete
label | Inspection Type (Visual, other) - Pre-pour Inspection
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.9 - Supply and Installation of Concrete
label | Specification - Civil Technical Specification Section 4.3
label | Acceptance Criteria - 20MPa at 28 Days. Concrete strength & slump testing certificates obtained from concrete plant and submitted to Engineer.
label | Verifying Document - Mix Design Certificate
label | Frequency - 1 Test per batch/delivery, 1 Sample @ 28days.
label | Inspection Type (Visual, other) - Concrete Strength & Slump Testing
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.1.10 - Concrete Testing
label | Specification - Civil Technical Specification Section 4.4.1
label | Acceptance Criteria - In accordance with NZS 3109 and NZS 3112 Part 2 Section 9
label | Verifying Document - IANZ Accredited Laboratory Report
label | Frequency - Minimum of 1 every 50m centres
label | Inspection Type (Visual, other) - Core Compressive Strength Testing
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.1.11 - Concrete Surface Finish
label | Specification - Civil Technical Specification Section 4.2
label | Acceptance Criteria - In accordance with NZS 3114
label | Verifying Document - ITP Sign Off/Photos
label | Frequency - Every Pour
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SP
checkpoint | 4.1.12 - Construction Joints
label | Specification - Civil Technical Specification Section 4.3
label | Acceptance Criteria - Construction joints shall be installed in all kerbs and channels at 5m centres
label | Verifying Document - ITP Sign Off/Photos
label | Frequency - 1 every 5m centres
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SP
checkpoint | 4.1.13 - Concrete Docket Tally
label | Specification - As per TDS
label | Acceptance Criteria - All concrete dockets to be collected on a daily basis and provided to the Site Engineer
label | Verifying Document - Dockets
label | Frequency - Daily
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.1.14 - Asbuilt Survey
label | Specification - Civil Technical Specification Section 4.3
label | Acceptance Criteria - No discrepancies of greater than 6mm in line or level in any 3m length
label | Verifying Document - Asbuilt Drawings
label | Frequency - Straight: 10m Intervals
label | ○ Curve: 2m Intervals
label | ○ Survey every tangent
label | Inspection Type (Visual, other) - Survey Asbuilt
label | Inspection: Key - R
label | Inspection: By - SV
section | 4.2 Footpath
checkpoint | 4.2.1 - Service Location
label | Specification - As per TDS
label | Acceptance Criteria - As per project specification locate on site 4 weeks prior to construction
label | Verifying Document - ITP Sign Off/Photos
label | Frequency - Prior to the works starting
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SP
checkpoint | 4.2.2 - Footpath Location
label | Specification - As per design & Construction Drawings Sheet No: C-5111
label | Acceptance Criteria - Surveyor to set-out location of footpath for boxing and prepping.
label | ○ Dimensions as per standard detail in Construction Drawings Sheet No. C-5111: Height 100mm, Width 1.5m, Slope 2%
label | Verifying Document - ITP Sign off
label | Frequency - Prior to constructing foundation
label | Inspection Type (Visual, other) - Survey Setout
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.2.3 - Accessible Ramp Location
label | Specification - Construction Drawings Sheet No: C-5111
label | Acceptance Criteria - Surveyor to set-out location of footpath for boxing and prepping.
label | ○ Dimensions as per standard detail in Construction Drawings Sheet No. C-5111:Slope 10%
label | Verifying Document - ITP Sign Off
label | Frequency - Prior to constructing foundation
label | Inspection Type (Visual, other) - Survey Setout
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.2.4 - Subgrade Testing
label | Specification - Construction Drawings Sheet No: C-5111
label | Acceptance Criteria - Clegg testing at 10m intervals
label | ○ Subgrade CBR ≥ 6%
label | Verifying Document - Clegg Hammer Result Sheet
label | Frequency - 10m intervals
label | Inspection Type (Visual, other) - Subgrade Compaction Testing
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.5 - Foundation Preparation and Asbuilt Survey
label | Specification - As per design & Construction Drawings Sheet No: C-5111
label | Acceptance Criteria - Minimum 100mm of M/4 AP40 Basecourse
label | Verifying Document - Photos & Asbuilt Survey
label | Frequency - 10m Cross Sections
label | Inspection Type (Visual, other) - Dimension Inspection
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.2.6 - Foundation Testing
label | Specification - Civil Technical Specification Section 5.5.1
label | Acceptance Criteria - NDM testing to be carried out by IANZ accredited laboratory. Site plan to be provided to Engineer showing every test point. Minimum acceptable result shall be 95% of the suppliers specification as per approved JMF.
label | Verifying Document - IANZ Accredited Laboratory Report
label | Frequency - 10m intervals
label | Inspection Type (Visual, other) - NDM Compaction Testing
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.7 - Foundation Testing
label | Specification - Civil Technical Specification Section 5.5.1
label | Acceptance Criteria - NDM testing carried out by approved user within Downer (with approval from Waka Kotahi) Min. Acceptable Compaction ≥ 95% of Target MDD
label | Verifying Document - IANZ Accredited Laboratory Report
label | Frequency - 10m intervals with surveyed test point locations
label | Inspection Type (Visual, other) - NDM Compaction Testing
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.8 - Foundation Testing
label | Specification -Civil Technical Specification Section 5.5.2, NZTA T/1
label | Acceptance Criteria -Deflection testing shall be carried prior to kerb and channel being formed.
label | – Allowable deflections are as follows:
label | ○ 95% of readings < 2.0mm
label | ○ Maximum reading of 2.5mm
label | Verifying Document - IANZ Accredited Laboratory Report
label | Frequency - 10m intervals with surveyed test point locations
label | Inspection Type (Visual, other) - Benkelman Beaming
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.9 - Formwork
label | Specification - Civil Technical Specification Section 5.3
label | Acceptance Criteria - In accordance with NZS 3109. Finished level of formwork shall be within +-10mm of design. The line of the formwork shall be straight with the maximum deviation from a 3m straight edge along the face of 5mm with a cumulative total of all visible gaps of not more than 10mm.
label | Verifying Document - ITP Sign off
label | Frequency - Prior to pouring the concrete
label | Inspection Type (Visual, other) - Survey Setout
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.2.10 - Reinforcing Steel
label | Specification - Civil Technical Specification Section 5.2
label | Acceptance Criteria - Reinforcing steel in accordance with AS/NZS 4671 Grade 500E Steel
label | ○ Welded wire fabric in accordance with AS/NZS 4671 Class E smooth
label | Verifying Document - Dockets & Photos
label | Frequency - Per batch/delivery
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.11 - Pre-Pour Inspection
label | Specification - As per TDS
label | Acceptance Criteria - Boxing Check, Concrete Pour Inspection Checksheet completed, and Written approval from Engineer to proceed
label | Verifying Document - Checksheet: DN-QC-04 & Written Approval from Engineer
label | Frequency - Prior to pouring the concrete
label | Inspection Type (Visual, other) - Pre-pour Inspection
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.12 - Supply and Installation of Concrete
label | Specification - Civil Technical Specification Section 5.3
label | Acceptance Criteria - 20MPa at 28 Days. Concrete strength & slump testing certificates obtained from concrete plant and submitted to Engineer.
label | Verifying Document - Mix Design Certificate
label | Frequency - 1 Test per batch/delivery, 1 Sample @ 28days.
label | Inspection Type (Visual, other) - Concrete Strength & Slump Testing
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.2.13 - Concrete Surface Finish
label | Specification - Civil Technical Specification Section 5.3
label | Acceptance Criteria - U5 finish in accordance with NZS 3114
label | Verifying Document - ITP Sign Off/Photos
label | Frequency - Every Pour
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SP
checkpoint | 4.2.14 - Saw Cutting
label | Specification - Civil Technical Specification Section 5.3
label | Acceptance Criteria - Grooves to be between 1/4 and 1/3 of specified depth of slab, and any convenient width greater than 3mm. Max spacing of saw cuts shall be 3m.
label | Verifying Document - ITP Sign Off/Photos
label | Frequency - No more than 3m Intervals
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SP
checkpoint | 4.2.15 - Concrete Docket Tally
label | Specification - As per TDS
label | Acceptance Criteria - All concrete dockets to be collected on a daily basis and provided to the Site Engineer
label | Verifying Document - Dockets
label | Frequency - Daily
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.16 - Asbuilt Survey
label | Specification - Civil Technical Specification Section 5.1
label | Acceptance Criteria - In accordance with requirements of the TA Minimum cossfall of 1%
label | Verifying Document - Asbuilt Drawings
label | Frequency - Appropriate intervals to represent asbuilt footpath
label | Inspection Type (Visual, other) - Survey Asbuilt
label | Inspection: Key - R
label | Inspection: By - SV
section | Final Inspection and Handover
checkpoint | 5.1 - Construction Record Compilation
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Verifying Document - Closed-out NCR/Defects
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 5.2 - As-built Survey
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Verifying Document - As built survey record completed
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SV
checkpoint | 5.3 - Red-line As-built Drawings
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
label | Verifying Document - Signed As-built Drawings
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE,SV
checkpoint | 5.4 - Defect, Snag and Punch List
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
label | Verifying Document - Register
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PE
checkpoint | 5.5 - All QA documentation collated & signed-off
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - All signed and closed out
label | Verifying Document - Signed off Documents
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - QM