## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DG-OWR-CVSC-ITP003_v1 - Pavement for CVSC | itp |  |  |  |  | DG-OWR-CVSC-ITP003_v1 - Pavement for CVSC
section | 3.1 General Preliminary
checkpoint | 3.1.1 - Survey Setout
label | Specification - Downer Standard
label | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - SV
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Service Location
label | Specification - Downer Standard
label | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
label | Verifying Document - Service location documents
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.3 - Internal Permits
label | Specification - Downer Standard
label | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.4 - External Permits
label | Specification - Downer Standard
label | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.5 - ESCP
label | Specification - As per contracts
label | Acceptance Criteria - Prior to starting works, Ensure that ESCP plan an approved ESCP by counsil is in place and valid
label | Verifying Document - Approved ESCP plan
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.6 - Approved Construction Drawings
label | Specification - Downer Standard
label | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 3.2 Pavement Materials
checkpoint | 3.2.1 - AP65 - Source Property Tests and Sampling
label | Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991, NZS 4402 : 1986
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 per source
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - AP65 - Production Property Tests and Sampling
label | Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 3 per source initially, then 1/1000m³ (stockpile sample)
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.3 - AP65 - Testing for Layer Compaction - MDD
label | Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 per material source (stockpile sample)
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.4 - AP40 - Source Property Tests and Sampling
label | Specification - TNZ M/4: 2006 - 3 NZS 4407 : 1991 NZS 4402 : 1986
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 per source initially, then 1/1000m³ (stockpile sample)
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.5 - AP40 - Production Property Tests and Sampling
label | Specification - TNZ M/4: 2006 - 4 NZS 4407 : 1991
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 3 per source initially, then 1/1000m³ (stockpile sample)
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.6 - AP40 - Testing for Layer Compaction - MDD
label | Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.7 - Sealing Chip - Source Property Tests and Sampling
label | Specification - TNZ M/6: 2019 - 4
label | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
label | Verifying Document - IANZ Lab Reports
label | Frequency - Before Supply and Every 10,000m3 Thereafter
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.8 - Sealing Chip - Production Property Test Sampling
label | Specification - TNZ M/6: 2019 - 5
label | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 500m3
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.9 - Bitumen - Quality Testing
label | Specification - NZTA M01: 2022 - 6
label | Acceptance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test per grade supplied
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.10 - Bitumen - Supply Testing
label | Specification - NZTA Q05: 2022 - 6.2
label | Acceptance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 200 tonnes supplied.
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
section | 3.3 Cement Treated Basecourse
checkpoint | 3.3.1 - Cement
label | Specification - NZS3112
label | Acceptance Criteria - General purpose Portland cement, type GP, shall be used unless otherwise specified in the Contract documents.
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
section | 3.4 Asphalt
checkpoint | 3.4.1 - AC14
label | Specification - Pre-construction
label | Acceptance Criteria - As per NZTA M/10 specification
label | Verifying Document - Mix Design, Production Test report or Volumetric properties
label | Frequency - Per Mix
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
section | 3.5 Geotextile and Geogrid
checkpoint | 3.5.1 - Geotextile
label | Specification - Class C as per design spec
label | Acceptance Criteria - The Contractor shall submit to the Engineer for approval the details of the filter fabric they propose to use at least two weeks prior to commencement of works, including compliance certificates.
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.5.2 - Geogrid
label | Specification - TENSAR TRIAX TX160 as per design spec
label | Acceptance Criteria - The geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001.
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 4.1 Unbound Pavement Construction
checkpoint | 4.1.1 - Material Placement
label | Specification - Downer Standard
label | Acceptance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored thoughout
label | Verifying Document - Survey / Level Checks
label | Frequency - Continuous monitoring.
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SV,PS
checkpoint | 4.1.2 - Plateau Density Tests (Sub-basecourse)
label | Specification - TNZ B/02: 2005 - 7.5
label | Acceptance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
label | Verifying Document - Plateau test results confirmance
label | Frequency - Continuous monitoring.
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.1.3 - Sub-basecourse Pavement Layer Compaction (NDM)
label | Specification - TNZ B/02: 2005 - 7.6
label | Acceptance Criteria - Mean Value ≥ 95 % of MDD Minimum Value ≥ 92 of MDD
label | Verifying Document - NDM Report
label | Frequency - 1/10m each layer not exceeding 200mm
label | ○ If no clear lanes then 1 test per 50m2
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.4 - Sub-basecourse Layer thickness
label | Specification - TNZ B/02: 2005 - 5.1
label | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –25 mm +5 mm
label | Verifying Document - Survey / Level Checks
label | Frequency - 1/20m Full width
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SV or SE
checkpoint | 4.1.5 - Plateau Density Tests (Basecourse)
label | Specification - TNZ B/02: 2005 - 7.5
label | Acceptance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
label | Verifying Document - Plateau test results confirmance
label | Frequency - Continuous monitoring.
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.1.6 - Basecourse Pavement Layer Compaction
label | Specification - TNZ B/02: 2005 - 7.6
label | Acceptance Criteria - Mean Value ≥ 98 % of MDD Minimum Value ≥ 95 of MDD
label | Verifying Document - NDM Report
label | Frequency - 1/10m each layer not exceeding 200mm
label | ○ If no clear lanes then 1 test per 50m2
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.7 - Basecourse Layer thickness.
label | Specification - TNZ B/02: 2005 - 5.1
label | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –5 mm +15 mm
label | Verifying Document - Survey / Level Checks
label | Frequency - 1/20m Full width
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SV or SE
section | 4.2 CTB (Cement Treated Basecourse)
checkpoint | 4.2.1 - Pre-Stab check
label | Specification - Downer Standard
label | Acceptance Criteria - Check the temperature(between 5 °C or and 30 ºC), Wind (not exceeds 25km/hr), Rain, Time limitations(Primary compaction within 2 hr and the final trimming compaction within 4 hrs)
label | Verifying Document - Checklsit
label | Frequency - Befoore the stabilisation
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.2 - Mat testing
label | Specification - NZTA B/5: 2008 - 7.3
label | Acceptance Criteria - Every 400 m2 complete a Mat test using a 1m2 cancas. The ammount of Stabilising Agent on the canvas shall be within ±0.5 kg/m2 of the specified rate.
label | Verifying Document - Test Results/Photos
label | Frequency - Every 400 m2
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SE
checkpoint | 4.2.3 - Average usage test
label | Specification - NZTA B/5: 2008 - 7.3
label | Acceptance Criteria - Upon emptying the spreader and bulk tanker, Compare tonnes of Stabilising Agent used (from delivery docket) with measured area. Usagese shall be within ±2.5 % of the specified rate
label | Verifying Document - Calculation with Dockets and Weights
label | Frequency - Upon emptying the spreader and bulk tanker
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SE
checkpoint | 4.2.4 - Water content during compaction
label | Specification - NZTA B/5: 2008 - 7.5
label | Acceptance Criteria - The water content during compaction shall be in the range of 90% to 100% of the material’s optimum water content. The water content tests taken prior to stabilising and the water consumed per cut shall be recorded in the production plan records.
label | Verifying Document - NDM Results, delivered weekly
label | Frequency - 5 tests per 1000m2
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.5 - Control of cut depth
label | Specification - NZTA B/5: 2008 - 7.6.1
label | Acceptance Criteria - The actual depth of the cut shall be physically measured at both ends of the stabilising drum at least once every 200 m along the cut length. Maximum variation from the specified depth of cut is –0 mm and +20 mm. Unless specifically allowed in the project specification, the depth of cut shall not intrude into a subgrade layer.
label | Verifying Document - Site Records/Photos
label | Frequency - Each Cut
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.6 - Overlap on longitudinal joints
label | Specification - NZTA B/5: 2008 - 7.6.2
label | Acceptance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by minimum of 200 mm or half the layer thickness, whichever is the greater.
label | Verifying Document - Site Records/Photos
label | Frequency - Each Cut
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.7 - Continuity of stabilised layer
label | Specification - NZTA B/5: 2008 - 7.6.3
label | Acceptance Criteria - The exact location of the end of the cut shall be carefully marked. This mark shall coincide with the position of the centre of the mixing drum at the point at which the supply of the stabilising agent ceased. To ensure continuity of the stabilised layer, the next successive cut shall be started 1 m behind this mark.
label | Verifying Document - Site Records/Photos
label | Frequency - Each Cut
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.8 - Plateau Density tests
label | Specification - NZTA B/5: 2008 - 7.7
label | Acceptance Criteria - At the outset of compaction the contractor shall undertake plateau density tests for the purpose of determining the practicality of both the OWC and the MDD mix design targets, the minimum, and possibly the maximum, number and type of roller passes required to achieve the MDD for the proposed compaction plant and stiffness of lower pavement ‘anvil’ beneath the layer to be compacted.
label | Verifying Document - Plateau Density test
label | Frequency - Continuous monitoring.
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.2.9 - Compaction testing
label | Specification - NZTA B/5: 2008 - 7.7.1
label | Acceptance Criteria - The Degree of Compaction for Cement Treated Subbase shall have a Mean Dry Density of ≥ 98 % and a Minimum Dry Density of ≥ 95%. Compaction testing during construction of the stabilised pavement layers shall be carried out in lots. The area of a lot shall not exceed 1000 m2
label | Verifying Document - NDM Results
label | Frequency - 5 tests per Lot
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.10 - ITS Testing
label | Specification - NZTA T/19, Contract Specification, Section 3.6.5, Appendix F
label | Acceptance Criteria - ITS testing shall be carried out in accordance with NZTA T/19. The maximum time between mixing and compaction shall be 2 hours. The ITS test ranges shall be as follows:
label | – Dry: 150kPa - 350 kPa
label | – Soaked: 100kPa - 300kPa
label | ○ The Tensile Strength Retained (TSR) shall be no less than 75%
label | ○ If results are below the target strengths then notify the Engineer immediately.
label | Verifying Document - Test Results, delivered weekly
label | Frequency - 2 ITS (dry) and 2 ITS (soaked) for behind the hoe sampled each day of stabilisation.
label | ○ Samples are to be taken from seperate locations.
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.11 - Benkelman Beaming on Basecourse (cement modified)
label | Specification - Contract Specification, Section 3.5.5 CHAR(AMP) Appendix F
label | Acceptance Criteria - 90th percentile deflection ≤ 1.0mm. ○ No single deflection > 1.1mm.
label | Verifying Document - Test report, delivered weekly
label | Frequency - 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.12 - Construction Tolerances
label | Specification - TNZ B/5: 2008 - 7.8
label | Acceptance Criteria - Basecourse where asphalt surfacing with concrete channel
label | (i) at or close to the lip of channel –5 +5 mm
label | (ii) at other locations on pavement –15 +5 mm
label | (iii) at other locations on pavement –5 +15 mm
label | Verifying Document - Survey Records
label | Frequency - On final layer
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - C
label | Inspection: By - SV
checkpoint | 4.2.13 - Surface Finish post sweeping
label | Specification - TNZ B/02: 2005 - 7.8
label | Acceptance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
label | Verifying Document - Photos
label | Frequency - Prior to sealing
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
section | 4.3 Sealing
checkpoint | 4.3.1 - Presealing Requirements
label | Specification - TNZ B/02: 2005 - 12, Contract Specification, Section 3.6.7
label | Acceptance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 70%.
label | Verifying Document - NDM Report
label | Frequency - 1/10m
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.3.2 - Benkelman Beaming on Subbase (on AP40 CTB)
label | Specification - Contract Specification, Section 3.5.5 & Appendix F
label | Acceptance Criteria - 90th percentile deflection ≤ 1.4mm.
label | ○ No single deflection > 1.5mm.
label | ○ For CVSC, no deflection > 2.2mm
label | ○ For CTB, no deflection > 1.4mm
label | Verifying Document - Test report, delivered weekly
label | Frequency - 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.3.3 - Preseal inspection
label | Specification - TNZ P3 TNZ B02
label | Acceptance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site.
label | Verifying Document - Hold point Release, ITP Sign off
label | Frequency - Prior to sealing
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.3.4 - Spray Temperature
label | Specification - TNZ P3
label | Acceptance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
label | Verifying Document - Sealing statement
label | Frequency - Prior to sealing
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.3.5 - Chip Application
label | Specification - TNZ P3
label | Acceptance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
label | Verifying Document - Sealing statement
label | Frequency - For every spray run
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.3.6 - Post Seal Inspections
label | Specification - TNZ P3
label | Acceptance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
label | Verifying Document - Engineers Acceptance
label | Frequency - After Final Sweeping
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - H
label | Inspection: By - SE,CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3.7 - Chipseal Repairs
label | Specification - TNZ P3
label | Acceptance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
label | Verifying Document - Approved Repair Methodology
label | Frequency - Prior to Repairs
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - A
label | Inspection: By - SE
section | 4.4 Asphaltic Concrete (AC14)
checkpoint | 4.4.1 - Preparation of Area to be Paved
label | Specification - NZTA M27:2020 - 9
label | Acceptance Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected.
label | Verifying Document - Site Notes/Photos
label | Frequency - Pre Seal
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - PS
checkpoint | 4.4.2 - Ambient Conditions for Placing
label | Specification - NZTA M27:2020 - 9
label | Acceptance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C,
label | Verifying Document - Site Notes/ Weather report
label | Frequency - Pre Seal
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - R
label | Inspection: By - PS
checkpoint | 4.4.3 - Subbase check
label | Specification - as per project specification 3.7.7
label | Acceptance Criteria - Visual inspection by engineer's representative
label | Verifying Document - ITP Sign off
label | Frequency - All
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4.4 - Heavy Tack & Blind
label | Specification - Minimum Residual Bitumen of 1.2 L/m2
label | ○ As per project based pavement specification
label | Acceptance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat. Where SMA is to be spread over clean, freshly placed asphalt, the Engineer can direct the Contractor to omit the tack coat.
label | Verifying Document - Run sheet, QA from Sub
label | Frequency - Entire length of pavement
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.4.5 - Asphaltic Concrete - Surfacing
label | Specification - NZTA M10 & M27, Contract Specification 3.7.15, Appendix F, Section 10.15
label | Acceptance Criteria - 55mm of AC14
label | ○ Asphalt layers less than or equal to 55mm shall be +/- 5mm from the specified design thickness.
label | ○ The combined thickness of all asphalt layers should not be less than the specified total asphalt depth.
label | Verifying Document - Run sheet, QA from Sub
label | Frequency - Entire length of pavement
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SE
checkpoint | 4.4.6 - Asphaltic Concrete - SMA 10
label | Specification - NZTA M10 & M27, Contract Specification, Appendix F, Section 10.15
label | Acceptance Criteria - 40mm of SMA10
label | ○ Asphalt layers less than or equal to 55mm shall be +/- 5mm from the specified design thickness.
label | Verifying Document - Run sheet, QA from Sub
label | Frequency - Entire length of pavement
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SE
checkpoint | 4.4.7 - Thickness
label | Specification - Contract Specification, Section 3.7.15
label | Acceptance Criteria - Thickness as per design lift with +/-10mm (AC14)
label | Verifying Document - ITP Sign off
label | Frequency - Continuos
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.4.8 - Finished surface at joints
label | Specification - Contract Specification, Section 3.7.16
label | Acceptance Criteria - No more than 5 mm variation under a 3 m stright edge
label | Verifying Document - ITP Sign off
label | Frequency - Continuos
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.4.9 - Air Voids
label | Specification - NZTA M/10
label | Acceptance Criteria - The maximum and minimum air voids for each core shall be +3%/-2% from the mix design air voids.
label | Verifying Document - Test results, delivered weekly
label | Frequency - Continuos
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.4.10 - Level checks
label | Specification - Survey
label | Acceptance Criteria - Thickness as per design lift with +/-10mm (AC20) Thickness of 40mm with +/-5mm (SMA10)
label | Verifying Document - As-built drawing
label | Frequency - 1/20m full width
label | Inspection Type (Visual, other) - As-built
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.4.11 - Line marking
label | Specification - Set out
label | Acceptance Criteria - As per NZTA standard/ design drawings
label | Verifying Document - ITP sign off/ Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
section | Final Inspection and Handover
checkpoint | 5.1 - Construction Record Compilation
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Verifying Document - Closed-out NCR/Defects
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 5.2 - As-built Survey
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Verifying Document - As built survey record completed
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SV
checkpoint | 5.3 - Red-line As-built Drawings
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
label | Verifying Document - Signed As-built Drawings
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE,SV
checkpoint | 5.4 - Defect, Snag and Punch List
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
label | Verifying Document - Register
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PE
checkpoint | 5.5 - All QA documentation collated & signed-off
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - All signed and closed out
label | Verifying Document - Signed off Documents
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - QM