## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DG-OWR-CVSC-ITP004_v1 - 3 Waters for CVSC | itp |  |  |  |  | DG-OWR-CVSC-ITP004_v1 - 3 Waters for CVSC
section | 3.1 General Preliminary
checkpoint | 3.1.1 - Survey Setout
label | Specification - Downer Standard
label | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - SV
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Service Location
label | Specification - Downer Standard
label | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
label | Verifying Document - Service location documents
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.3 - Internal Permits
label | Specification - Downer Standard
label | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.4 - External Permits
label | Specification - Downer Standard
label | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.5 - ESCP
label | Specification - As per contracts
label | Acceptance Criteria - Prior to starting works, Ensure that ESCP plan an approved ESCP by counsil is in place and valid
label | Verifying Document - Approved ESCP plan
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.6 - Approved Construction Drawings
label | Specification - Downer Standard
label | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 3.2 Stormwater and Wastewater - Materials
checkpoint | 3.2.1 - Sand
label | Specification - As per project specification (Stormwater Swales, 3.1.2)
label | Acceptance Criteria - Sieve analysis NZS 4402 Test 4.2.8.2
label | – – – – – – – – – – – – – –
label | Grading criteria:
label | – – – – – – – – – – – – – –
label | Sieve Size ¦¦ % Passing
label | 9.5mm ¦¦ 100
label | 5.4mm ¦¦ 70 - 100
label | 2.36mm ¦¦ 50 - 70
label | 0.6mm ¦¦ 15 - 35
label | 0.3mm ¦¦ 5 - 15
label | 0.075mm ¦¦ 2
label | – – – – – – – – – – – – – –
label | Verifying Document - Test result
label | Frequency - 1 per 200m³
label | Inspection Type (Visual, other) - Visual Inspection, Document Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.2 - Drainage Media
label | Specification - As per project specification (Stormwater Swales, 3.1.3)
label | Acceptance Criteria - Single size angular stone chip no larger than 9.5mm
label | – – – – – – – – – – – – – –
label | Grading criteria:
label | – – – – – – – – – – – – – –
label | Sieve Size ¦¦ % Passing
label | 9.5mm ¦¦ 80 - 100
label | 2.4mm ¦¦ 0 - 20
label | 0.6mm ¦¦ <2%
label | – – – – – – – – – – – – – –
label | Verifying Document - Test result
label | Frequency - 1 per 200m³
label | Inspection Type (Visual, other) - Visual Inspection, Document Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.3 - Soil Media
label | Specification - As per project specification (Stormwater Swales, 3.1.5)
label | Acceptance Criteria - The media must consist of material that has:
label | ○ 5% clean organic compost from a consistent source. The source of clean organic material must have been provided to the Engineer for acceptance prior to supply.
label | ○ Locally sourced topsoil (free of weeds or contamination)
label | ○ No obvious seeds, weeds, any contamination and material > 25mm in nominal diameter
label | ○ < or = to 50% coarse sand from a consistent source to improve permeability and structure.
label | ○ < 3% clay (particles < 0.002mm)
label | ○ < 5% by volume of particles exceeding 4.75mm nominal diameter.
label | ○ A pH rangeof 7.5 - 5.5
label | ○ Well graded particle size from 0.075mm through to 4.75mm with no gaps in the grading.
label | ○ Compacted hydraulic conductivity of at least 50mm/hr and nort exceeding 400mm/hr based on the ASTM F1815-069 methodology.
label | ○ Total Phosphorus < 100mg/kg
label | ○ Total Nitrogen < 1000mg/kg
label | Verifying Document - Test result
label | Frequency - 1 per 200m³
label | Inspection Type (Visual, other) - Visual Inspection, Document Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.4 - Concrete Pipes
label | Specification - As per project specification (Pipeline Supply, 2.4.4)
label | Acceptance Criteria - Concrete pipes must be reinforced concrete rubber ring jointed pipe complying with AS/NZS 4058.
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.5 - PVC-U Pipes
label | Specification - As per project specification (Pipeline Supply, 2.4.2)
label | Acceptance Criteria - PVC-U pipes and fittings for gravity stormwater must be plain wall construction rubber ring jointed and must comply with AS/NZS 1254.
label | ○ All PVC pipes must have factory fitted, composite rings; loose Z type rings must not be used.
label | ○ PVC-U pipe diameters shown on the Drawings are the nominal diameters unless shown otherwise. Pipe classes are to be as shown on the Drawings
label | Verifying Document - Concrete pipes must be reinforced concrete rubber ring jointed pipe complying with AS/NZS 4058.
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.6 - PE & PP Pipes
label | Specification - As per project specification (Pipeline Supply, 2.4.3)
label | Acceptance Criteria - PE & PP pipe must comply with AS/NZS 5065.
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.7 - Precast Concrete Manholes
label | Specification - As per project specification (Pipeline Supply, 2.5.1)
label | Acceptance Criteria - Unless shown otherwise on the Drawings, manholes (and manhole components) must be circular precast reinforced concrete manholes manufactured in accordance with AS/NZS 4058 with cast in base manufactured to NZ5 3109.
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.8 - Manhole Lids
label | Specification - As per project specification (Pipeline Supply, 2.5.2)
label | Acceptance Criteria - Manhole lids must be precast reinforced concrete manufactured in accordance with NZS 5109 rated heavy duty (HD60) or HN-H0-72 as specified on the Drawings or as required by the local authority
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.9 - Frame and Covers
label | Specification - As per project specification (Pipeline Supply, 2.5.3)
label | Acceptance Criteria - Manhole lids must be precast reinforced concrete manufactured in accordance with NZS 5109 rated heavy duty (HD60) or HN-H0-72 as specified on the Drawings or as required by the local authority
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.10 - Catchpits and Grates
label | Specification - As per project specification (Pipeline Supply, 2.6)
label | Acceptance Criteria - Use precast single or double catchpits manufactured from reinforced concrete complying with NZS 3101 and NZ 3109. Each single catchpit must have minimum internal dimensions of 450 mm by 675 mm.
label | ○ Use grates rated to class D complying with As 3996 with
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.11 - Subsoil
label | Specification - As per project specification (Pipeline Supply, 2.7)
label | Acceptance Criteria - Unless shown otherwise on the Drawings, subsoil drains must be DN110 perforated corrugated plastic pipe complying with AS 2439.1-2007 Perforated plastics and drainage and effluent pipe and fittings, Part 1: Perforated drainage pipe and associated fittings, and be minimum SN 4
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.12 - Materials - general
label | Specification - As per project specification T-WES 00012, Section 4.8
label | Acceptance Criteria - Do not change the source of supply of materials without written approval from the Engineer - refer Section 2.1
label | Verifying Document - Approved list Verification / Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Visual Inspection, Document Review
label | Inspection: Key - R
label | Inspection: By - SE/CR
section | 3.3 Receiving Materials/Parts - Portable water
checkpoint | 3.3.1 - Water Pipes
label | Specification - As per project specification refer T-WES 00013, 2.4
label | Acceptance Criteria - All fittings shall be of the material, grade, diameter and pressure class shown on the Drawings/specifications and be on the approved material list
label | Verifying Document - Approved list Verification / Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Document Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.3.2 - Water Fittings
label | Specification - As per project specification refer T-WES 00014, 2.5
label | Acceptance Criteria - All fittings shall be of the material, grade, diameter and pressure class shown on the Drawings/specifications and be on the approved material list
label | Verifying Document - Approved list Verification / Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Document Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.3.3 - Joints
label | Specification - As per project specification refer T-WES 00014, 2.6
label | Acceptance Criteria - All Joints shall be of the material, grade and size shown on the Drawings/specifications and be on the approved material list
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Document Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.3.4 - Fire hydrant and Valve Covers
label | Specification - As per project specification refer T-WES 00014, 2.7
label | Acceptance Criteria - All surface boxes and covers over buried valves and hydrants must be rated to AS 3996 Class B (footpaths and non-trafficable areas) or Class D (trafficable areas).
label | ○ Use PVC risers and/or or concrete frames as necessary to provide access to the valves or hydrants.
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Inspection Type (Visual, other) - Document Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
section | 3.4 General
checkpoint | 3.2.13 - Embedment Materials (1)
label | Specification -As per project specification (Pipeline Supply, 2.8)
label | Acceptance Criteria - For flexible pipes, well graded processed AP20 complying with AS/NZS 2566.2 section 54.2. Any proposed alternative bedding material must meet the requirements of AS/NZS 2566.2 section 5.4.2.1 note 3 and may only be used if approved by the Engineer in writing.
label | ○ Where low-fines embedment material is specified on the Drawings, the material must be a graded AP20 with none passing the 2.36 mm sieve size (no fines material) that has the consistency and moisture content suitable for placement without segregation. Screened in-situ materials may be used for embedment
label | ○ Pea metal may not be used
label | Verifying Document - Test result
label | Frequency - 1 per 200m³
label | Inspection Type (Visual, other) - Visual Inspection, Document Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.13 - Embedment Materials (2)
label | Specification -As per project specification (Pipeline Supply, 2.8)
label | Acceptance Criteria -For concrete pipes, Material with grading limits in accordance with As/NZS 3725 and the CPAA Engineering Guideline Selecting Materials for Bedding Steel Reinforced Concrete Pipe available from the CPAA website.
label | ○ Where low-fines embedment material is specified on the Drawings, the material must be a gradec AP20 with none passing the 2.36 mm sieve size (no fines material) that has the consistency and moisture content suitable for placement without segregation It is expected that screened in-situ materials will be used for embedment. The material used is to have a Compaction Fraction (CF) of 0.1 or less as defined below
label | Verifying Document - Test result
label | Frequency - 2 per 200m³
label | Inspection Type (Visual, other) - Visual Inspection, Document Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.14 - Trench Fill Material
label | Specification - As per project specification
label | Acceptance Criteria - Before construction commences establish the maximum dry density using NZS 4402 Test 4.1.3 New Zealand vibrating hammer compaction test. Submit results to the Engineer one week before importing trench fill material.
label | Verifying Document - Test result
label | Frequency - Prior to imoport material
label | Inspection Type (Visual, other) - Document Review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.15 - Concrete
label | Specification - As per project specification (Minor Concrete Works, 2.1)
label | Acceptance Criteria - Normal concrete with the requirements of NZS 3104 and strength shown on the drawings. Where the strength us not shown, use 25 Mpa normal concrete
label | Verifying Document - Mix Design
label | Frequency - Per mix
label | Inspection Type (Visual, other) - Document Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 3.2.4 - Geotextile
label | Specification - As per project specification (Earthworks, 2.15)
label | Acceptance Criteria - Geotextile to be the grade and standards on the drawings and be on the Approved materials list.
label | ○ Non-Woven Filtration Class 1 and Geotextile Strength Class C
label | Verifying Document - Data Sheet
label | Frequency - Per delivery/Item
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE/PS
section | 4.1 Soakage swale - Construction
checkpoint | 4.1.1 - Swale - Formation and Levels
label | Specification - As per design height
label | Acceptance Criteria - Ensure the excavation is clear of roots, projections, or obstructions. If overexcavation occurs, bring the bottom back to grade using excavated material, lightly compacting it. Do not leave loose soil. Notify the Engineer if the swale contains low-permeability soils; they will assess and advise on additional excavation if needed.
label | Verifying Document - As-built check, photos
label | Frequency - Before instal the drainage media
label | Inspection Type (Visual, other) - Survey, Visual
label | Inspection: Key - V
label | Inspection: By - SV,SE
checkpoint | 4.1.2 - Drainage Media
label | Specification - As per three water specification Section 3.3.2
label | Acceptance Criteria - Carefully position drainage media in a clean, excavated area free of contaminants after removing materials. Use the media as embedment around the subsoil pipe, ensuring it is lightly tamped in the bedding zone without mechanical compaction. Avoid placing or lightly compacting drainage media in flooded excavations or saturated in-situ soils.
label | Verifying Document - Photo
label | Frequency - As progress
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By - SE/PS
checkpoint | 4.1.3 - Subsoil Installation
label | Specification - As per three water specification Section 3.3.3
label | Acceptance Criteria - Position subsoil pipes centrally in the drainage media layer per specifications and drawings. Avoid laying pipes in flooded or saturated soils; no filter sleeves for perforated pipes. Install pipes parallel to bedding, avoiding ponded water in the swale. Carefully place a minimum of 50 mm of drainage media around the pipe, using it as embedment material without mechanical compaction.
label | Verifying Document - Checksheet, Asbuilt and Photo
label | Frequency - As progress
label | Inspection Type (Visual, other) - Witness,Visual
label | Inspection: Key - V
label | Inspection: By - SE/PS
checkpoint | 4.1.4 - Sand Layer
label | Specification - As per three water specification Section 3.3.4
label | Acceptance Criteria - Place a 400 mm thick layer of uncompacted sand over the Drainage Media, avoiding compaction with construction equipment. Ensure the subsoil drain is undisturbed, and rake the sand for a level finish.
label | Verifying Document - Photo
label | Frequency - As progress
label | Inspection Type (Visual, other) - Visual, Dimensional
label | Inspection: Key - V,D
label | Inspection: By - SE/PS
checkpoint | 4.1.5 - Soil Media
label | Specification - As per three water specification Section 3.3.5
label | Acceptance Criteria - Place soil media in a single lift up to 50 mm above the Construction Drawings' finished level for post-construction consolidation. Ensure a smooth, uniform surface, lightly consolidate the soil, and avoid disturbing the subsoil drain. Rectify sediment blinding as directed by the Engineer. Do not exceed 30% moisture content to prevent poor performance. Notify the Engineer for approval; upon acceptance, commence grass sowing within seven days.
label | Verifying Document - Photo
label | Frequency - As progress
label | Inspection Type (Visual, other) - Visual, Dimensional
label | Inspection: Key - V,D
label | Inspection: By - SE/PS
checkpoint | 4.1.6 - Grass Sowing
label | Specification - As per grass sowing mix
label | ○ Pernnial ryegrass 70%
label | ○ Chewing fescue 25%
label | ○ Brown top 5%
label | Acceptance Criteria - Sow an approved bird-repellent coated grass seed mix at 1 kg/30 m² and fertilize with diammonium phosphate at a minimum rate of 1 kg per 50 m². Aim for a 90% grass strike by the end of the Defects Notification Period, promptly fixing any surface depressions.
label | Verifying Document - Photo, Docket, Mix design
label | Frequency - Per application
label | Inspection Type (Visual, other) - Visual Inspection, Document Review
label | Inspection: Key - R,V
label | Inspection: By - SE/PS
checkpoint | 4.1.7 - In-situ Infiltration Test
label | Specification - Double ring infiltrometer Test Method
label | Acceptance Criteria - Test reslt > 50 mm/hr as per project spec
label | ○ Test to complete as per project's three water specification Section 3.5.1
label | Verifying Document - Test result, Witness Engineer
label | Frequency - Two test per stormwater swale
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - W
label | Inspection: By - CR,SE/PS
section | 4.2 Subsoil Drain - Installation
checkpoint | 4.2.1 - Subsoil Drain Installation
label | Specification - Downer Standard
label | Acceptance Criteria - Subsoil drains shall be constructed to the lines, levels and dimensions shown on the construction drawings and fully comply with the dimesnional and drawing specifications
label | Verifying Document - Checksheet, Asbuilt and Photo
label | Frequency - Each subsoil drain
label | Inspection Type (Visual, other) - Witness,Visual
label | Inspection: Key - V
label | Inspection: By - SE/PS
section | 4.3 Drainge Pipe - Installation
checkpoint | 4.3.1 - Length of Open Trench
label | Specification - Downer Standard
label | Acceptance Criteria - The length of open trench shall not exceed the greater of one manhole length or 50m and when offsite this open trench shall be reduced to a maximum length of not more than 10 metres.
label | Verifying Document - Checksheet, Photo
label | Frequency - As progress
label | Inspection Type (Visual, other) - Visual, Dimensional
label | Inspection: Key - V,D
label | Inspection: By - SE/PS
checkpoint | 4.3.2 - Trench Width
label | Specification - Downer Standard
label | Acceptance Criteria - The minimum trench width shall be 300mm wider than the external diameter of the collar of the pipe being laid, providing the haunching metal is compacted under and at the sides of the pipe.
label | Verifying Document - Checksheet, Photo
label | Frequency - As progress
label | Inspection Type (Visual, other) - Visual, Dimensional
label | Inspection: Key - V,D
label | Inspection: By - SE/PS
checkpoint | 4.3.3 - Trench Subgrade
label | Specification - Downer Standard
label | Acceptance Criteria - Complete Scala testing on the trench Subgrade to a depth of 1m every 10m and when the subgrade changes appearance.
label | Verifying Document - Scala Results
label | Frequency - Every 20 m
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - V,D
label | Inspection: By - SE/PS
checkpoint | 4.3.4 - Line and Level
label | Specification - Project Specification
label | Acceptance Criteria - Pipe inverts shall be laid to ±10mm of the design vertical alignment. Pipes shall be individually aligned to grade. Gravity pipes shall not be laid at a negative grade. Pipe alignments shall be positioned horizontally within the greater of 50mm or 5% of the pipe diameter from the location specified.
label | Verifying Document - Checksheet
label | Frequency - Before backfill
label | Inspection Type (Visual, other) - Visual,Dimensional
label | Inspection: Key - V,D
label | Inspection: By - SE/PS
checkpoint | 4.3.5 - Backfill Placement
label | Specification - Project Specification
label | Acceptance Criteria - Backfill shall be placed and compacted in layers not exceeding 200mm to 95% of MDD.
label | Verifying Document - NDM Report
label | Frequency - One test every two layers per 50 m
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE/PS
section | 4.4 Manhole - Installation
checkpoint | 4.4.1 - Alignment
label | Specification - Downer Standard
label | Acceptance Criteria - Structures shall be positioned within 50mm horizontally of the location specified. All structures shall be watertight.
label | Verifying Document - Checksheet, Survey
label | Frequency - Each Manhole
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE/PS
checkpoint | 4.4.2 - Drainage Structure Foundation
label | Specification - Downer Standard
label | Acceptance Criteria - Complete Scala test on the subgrade underneath each structure to a depth of 1m
label | Verifying Document - Checksheet,Scala
label | Frequency - Each Structure
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE/PS
checkpoint | 4.4.3 - Drainage Structure Bedding
label | Specification - Project Specification
label | Acceptance Criteria - Unless specified otherwise, all catchpits, manholes and other stormwater structures shall be founded on a minimum 75 mm bedding.
label | Verifying Document - Checksheet,Photos
label | Frequency - Each Structure
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE/PS
checkpoint | 4.4.4 - Structure Backfill Testing
label | Specification - Project Specification
label | Acceptance Criteria - Backfill shall be placed and compacted in layers not exceeding 200mm to 95% of MDD.
label | Verifying Document - NDM Report
label | Frequency - One test every two layers per manhole
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE/PS
checkpoint | 4.4.5 - Pipe Penetrations
label | Specification - Project Specification
label | Acceptance Criteria - Drill holes around the intended cut line before removing the section to create pipe penetrations. Ensure that the diameter of the cutout does not exceed 100 mm beyond the outer diameter of the pipe.
label | Verifying Document - Photo
label | Frequency - Each Structure
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - I
label | Inspection: By - SE/PS
checkpoint | 4.4.6 - Benching
label | Specification - Project Specification
label | Acceptance Criteria - Construct manhole benching and channelling using 25 MPa concrete. Cast and trowel manhole benching to shape, sloping towards the channel at minimum 1:12 with a U2 finish.
label | Verifying Document - Photo
label | Frequency - Each Structure
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - I
label | Inspection: By - SE/PS
checkpoint | 4.4.7 - Corbels
label | Specification - Downer Standard
label | Acceptance Criteria - Pipes shall be haunched and surrounded with concrete to a minimum distance of 200mm from the outside of the manhole in accordance with the drawings.
label | Verifying Document - Photo
label | Frequency - Each Pipe Entry
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - I
label | Inspection: By - SE/PS
checkpoint | 4.4.8 - Pipe ends
label | Specification - Downer Standard
label | Acceptance Criteria - Pipe ends shall finish approximately 50mm beyond the inside wall and be plastered with cement mortar or encased in benching concrete in accordance with the drawings.
label | Verifying Document - Photo
label | Frequency - Each Pipe Entry
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - I
label | Inspection: By - SE/PS
checkpoint | 4.4.9 - Dewatering
label | Specification - Project Specification T-WES 00011, Section 3.5
label | Acceptance Criteria - Provide a method statement for controlling water in trenches or dewatering for the Engineers acceptance five days before construction, including:
label | – Reasons why the proposed de-watering system has been chosen.
label | – Proposed location and details of any well points/spears.
label | – Details of back-up power supplies in case there is a power failure.
label | – Details of discharging (location(s), volume and flow rate) including environmental controls.
label | – A risk assessment with respect to dewatering affecting adjacent structures.
label | – Detrails of how niose standards will be met.
label | Verifying Document - Approved Verification
label | Frequency - Prior to installation
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By - CR/SE
holdpoint | AUTHORITY HOLDPOINT
section | 4.5 Acceptance Testing and Commissioning
checkpoint | 4.5.1 - Pipeline Testing - Acceptance Criteria
label | Specification - Project Specification, T-WES 00012, Section 4.6.3
label | Acceptance Criteria - Pipelines including laterals shall be tested in accordance with one of the following methods as detailed in AS/NZS 2566.2 Section 6.4:
label | ○ Low Pressure Air Testing
label | ○ Hydrostatic Testing
label | ○ Vacuum Testing
label | Verifying Document - Test Report
label | Frequency - Each Pipline
label | Inspection Type (Visual, other) - Check, Visual
label | Inspection: Key - H
label | Inspection: By - CR,SE/PS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.2 - Pipeline Testing - Testing Record Requirements
label | Specification - Project Specification, T-WES 00012, Section 4.6.4
label | Acceptance Criteria - The Test must be witnessed by the Engineer or their representative. A record of all tests shall be made and forwarded to the Engineer within 24 hours of test completion.
label | (a) Date
label | (b) Full description of section of pipeline being tested, including pipe length, pipe diameter, class and manufacture.
label | (c) Number of sump connections or laterals on the section being tested.
label | (d) Test pressure and acceptance criteria
label | (e) The start time of the test
label | (f) The pressure at the start time
label | (g) Time taken to drop pressure by 2 kPa
label | (h) Minimum and maximum pressure in the test section and water loss over 30 minutes
label | (i) Whether the pipeline passed the test
label | (j) The name and signature of the Contractors personnel responsible for the test
label | (k) The name and signature of the Engineers nominated personnel who witnessed the test
label | Verifying Document - Test Report
label | Frequency - Each Pipline
label | Inspection Type (Visual, other) - Check, Visual
label | Inspection: Key - H
label | Inspection: By - CR,SE/PS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.3 - Flexible Pipe Ovality Test
label | Specification - Project Specification
label | Acceptance Criteria - An ovality test shall be carried out on gravity pipelines in accordance with clause 6.5 of AS/NZS 2566.2 “Buried flexible pipelines – Installation”. The test shall be carried out at least seven days after the pipe surround is laid.
label | Verifying Document - Test Report
label | Frequency - Each Pipline
label | Inspection Type (Visual, other) - Check, Visual
label | Inspection: Key - H
label | Inspection: By - CR,SE/PS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.4 - CCTV Inspection
label | Specification - Project Specification, T-WES 00012, Section 4.6.7
label | Acceptance Criteria - All completed pipelines (excluding laterals and sump connections) are to be inspected using CCTV after backfilling and leak testing is successfully completed, but prior to final surface restoration.
label | ○ The specific requirements for the CCTV inspection are found within clauses (a) to (f)
label | Verifying Document - Test Report
label | Frequency - Each Pipline
label | Inspection Type (Visual, other) - Check, Visual
label | Inspection: Key - H
label | Inspection: By - CR,SE/PS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.5 - Manhole Testing
label | Specification - Project Specification
label | Acceptance Criteria - All manholes (new and refurbished) shall be water tested. Manhole watertightness testing must be witnessed by the Engineer or their representative. A record of all tests shall be made and forwarded to the Engineer within 24 hours of test completion.
label | Verifying Document - Test Report
label | Frequency - Each Pipline
label | Inspection Type (Visual, other) - Check, Visual
label | Inspection: Key - H
label | Inspection: By - CR,SE/PS
holdpoint | AUTHORITY HOLDPOINT
section | 4.6 Portable Water - Installation
checkpoint | 4.6.1 - Trench Foundation
label | Specification - Project Specification
label | Acceptance Criteria - Shape the foundation for uniform pipe support and alignment. Alert the Engineer if unsuitable trench floor material and await instructions before proceeding with additional work.
label | Verifying Document - Scala Results
label | Frequency - Every 50 m
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - V,D
label | Inspection: By - SE/PS
checkpoint | 4.6.2 - Soft Ground faft Foundation
label | Specification - Project Specification
label | Acceptance Criteria - Refer engineers advise where the foundation fails to meet the design requirments.
label | Verifying Document - Checksheet
label | Frequency - for each event/as required
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - R,V
label | Inspection: By - SE
checkpoint | 4.6.3 - Geotextile
label | Specification - Project Specification
label | Acceptance Criteria - Geotextiles shall fully wrap raft foundations, in accordance with the manufacturer’s specification, where rafts are required.
label | Verifying Document - Checksheet
label | Frequency - for each event/as required
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 4.6.4 - Embedment Construction
label | Specification - Project Specification T-WES 00013, 3.1.5
label | Acceptance Criteria - Place and compact all filling materials in layers not exceeding 200 mm compacted thickness. For pipe embedment at least 90% of the maximum dry density (MDD)
label | Verifying Document - NDM Report
label | Frequency - NDM Every 50 m per 200mm of fill
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 4.6.5 - Laying and Jointing of Pipes (1)
label | Specification -Project Specification T-WES 00013, 3.1.6
label | Acceptance Criteria - Lay in straight lines, beginning at the lower end of the line (unless agreed otherwise in writing with the Engineer), and complete each joint before another pipe is laid.
label | ○ Lay all pipe with manufacturing codes and class markings facing upwards.
label | Verifying Document - Checksheet
label | Frequency - Each Pipeline
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - Check
label | Inspection: By - SE/PS
checkpoint | 4.6.5 - Laying and Jointing of Pipes (2)
label | Specification - General, Project Specification T-WES 00013, 3.1.1
label | Acceptance Criteria - Submit the proposed methodology for pipe laying, concrete work, jointing and backfilling to the Engineer and obtain acceptance before starting pipe installation.
label | Verifying Document - Approved Verification
label | Frequency - Prior to installation
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By - CR/SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6.6 - Thrust Blocks
label | Specification - Project Specification T-WES 00013, 3.1.12
label | Acceptance Criteria - Unreinforced Concrete Thrust Blocks
label | ○ Precast concrete thrust blocks can only be used where approved by the local authority. Arrange for the Engineer to inspect the first completed thrust block.
label | Verifying Document - Checksheet, concrete test result
label | Frequency - On the first completed thrust block
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - H
label | Inspection: By - CR/SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6.7 - Thrust Blocks
label | Specification - Project Specification T-WES 00013, 3.1.13
label | Acceptance Criteria - Reinforced Concrete Thrust Walls / Thrust Blocks
label | ○ All thrust wall steel reinforcement must comply with AS/NZS 4671. Have the Engineer inspect the thrust wall reinforcing and puddle pipe arrangement prior to pouring concrete.
label | Verifying Document - Checksheet, concrete test result
label | Frequency - On the first completed thrust block
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - H
label | Inspection: By - CR/SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6.8 - Flanges
label | Specification - Project Specification T-WES 00013, 3.1.14
label | Acceptance Criteria - Complete the flange bolting procedure as per project spec and check sheet
label | ○ Have the Engineer witness the first flanged joint completed on the PE 100 pipeline
label | Verifying Document - Check sheet, photo
label | Frequency - First flanged joint completed on the PE 100 pipeline
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By - CR/SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6.9 - Backfill
label | Specification - Project Specification
label | Acceptance Criteria - AP65 backfill shall be compacted in 200mm loose layers to at least 95% of the maximum dry density (MDD) every 50m.
label | Verifying Document - NDM Report
label | Frequency - NDM Every 50 m per 200mm of fill
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - R
label | Inspection: By - SE/PS
section | 4.7 Portable Water - Testing and Commissioning
checkpoint | 4.7.1 - Pressure Test
label | Specification - Project Specification, T-WES 00013, Section 4.5.7.2
label | Acceptance Criteria - Complete the pressure test in accordance with the project specification and the check sheet for pressure test.
label | ○ The system test Pressure (STP) is 1,000 kPa.
label | Verifying Document - Check sheet, photo
label | Frequency - Each major pipelines
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - W
label | Inspection: By - SE/PS
checkpoint | 4.7.2 - Pressure Test
label | Specification - Project Specification, T-WES 00013, Section 4.5.3
label | Acceptance Criteria - Before commencing any pressure acceptance test:
label | ○ Give the Engineer at least two working days notice.
label | ○ Provide the Engineer with a detailed work method statement (WMS) with details of how the pressure testing will be carried out at least 10 working days prior to the test, including but not limited to:
label | ○ Proposed equipment to be used, including pump/s, water meters, logging pressure gauge/s, check pressure gauge/s
label | ○ Proposed fill rate, noting the bulk fill must not be greater than the discharge capacity of any air valves and any local authority constraints relating to the supply of water
label | ○ Calibration certificates for meters and pressure gauges
label | ○ Details of qualified personnel who will be carrying out the tests
label | ○ Source/s of water proposed to be used
label | ○ Provision for backflow prevention
label | ○ Location of the pressure test rig and the proposed test pressure at that location if the elevation of the test rig is higher than the lowest part of the test section
label | ○ The test lengths proposed that will ensure that no pipes are over pressurised or inadequately tested
label | ○ Pressure test report template
label | ○ Health and safety risks and mitigation measures
label | Verifying Document - Check sheet, (WMS)
label | Frequency - Prior to pressure testing
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - CR/SE
checkpoint | 4.7.3 - Water Main Disinfection
label | Specification - Project Specification, T-WES 00013, Section 5
label | Acceptance Criteria - A resolution with a remaining free available chlorine (FAC) level ranging from 15 to 20 mg/L (ppm). By the conclusion of the disinfection period, the water expelled from the pipelines should retain a minimum FAC concentration of 5 mg/L.
label | – Prepare to submit a WMS for disinfection of potable water pipelines to the Engineer for acceptance before commencing disinfection work. The WMS must include (at least) details of:
label | ○ Swabbing all potable water pipes, valves, and other fittings (> DN 63)
label | ○ How the disinfection solution will be introduced with the initial fill water for pressure acceptance testing, if done, Note that this will be at the Contractors risk
label | ○ How the disinfection solution will be prepared and delivered reliably into the pipeline. Include calculations of dosing and flow rates, strength of the proposed liquid or powered form of hypochlorite as well as methods for checking that the required FAC is being achieved
label | ○ How it is proposed to ensure that all watermains, service pipes, valves and fittings will receive nthe disinfection solution
label | ○ How measurement of the FAC during and at the end of the disinfection process will be achieved to ensure that the system has been fully disinfected
label | ○ How the disinfection solution is to be disposed of safely at the end
label | ○ Identified health and safety risks and proposed mitigation measures
label | Verifying Document - Checksheet, (WMS)
label | Frequency - Before commissioning
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - SE/PS
checkpoint | 4.7.4 - Flushing of Reconnection
label | Specification - Downer Standard
label | Acceptance Criteria - The Contractor shall open the front outside hose tap, if available, before the supply is reinstated to any premises. Wherever possible, the owner shall be notified prior to this work.
label | Verifying Document - Checksheet
label | Frequency - Each Connection
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - SE
section | Final Inspection and Handover
checkpoint | 5.1 - Construction Record Compilation
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Verifying Document - Closed-out NCR/Defects
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 5.2 - As-built Survey
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Verifying Document - As built survey record completed
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SV
checkpoint | 5.3 - Red-line As-built Drawings
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
label | Verifying Document - Signed As-built Drawings
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE,SV
checkpoint | 5.4 - Defect, Snag and Punch List
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
label | Verifying Document - Register
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PE
checkpoint | 5.5 - All QA documentation collated and signed-off
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - All signed and closed out
label | Verifying Document - Signed off Documents
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - QM