## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DG-OWR-VMS-ITP-001_v1 - Variable Messaging Sign (VMS) Site | itp |  |  |  |  | DG-OWR-VMS-ITP-001_v1 - Variable Messaging Sign (VMS) Site
section | 3.1 General Preliminary
checkpoint | 3.1.1 - Survey Setout
label | Specification - Downer
label | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - SV
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Service Location
label | Specification - Downer
label | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
label | Verifying Document - Service location documents
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.3 - Internal Permits
label | Specification - Downer
label | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.4 - External Permits
label | Specification - Downer
label | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.5 - Approved Construction Drawings
label | Specification - Downer
label | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 3.2 Receiving Materials/Parts - VMS Foundation with Plinth and cabinet pad
checkpoint | 3.2.1 - Concrete mix design
label | Specification - 30Mpa Structural Concrete
label | Acceptance Criteria - Concrete Mix design for each mix comply with the requirements of the Project Specification
label | Verifying Document - Concrete supplier mix designs
label | Frequency - Submitted to Client Engineer for approval before construction
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - Reinforcement
label | Specification - As per Design Specification
label | Acceptance Criteria - Reinforcing bars and mesh shall comply with AS/NZS4671:2001.
label | Verifying Document - Mill Certs
label | Frequency - Each Lot
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 3.3 Receiving Materials/Parts - Shoulder Widening and Sealing
checkpoint | 3.3.1 - AP65 - Source Property Tests and Sampling
label | Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006 NZS 4407 : 1991 NZS 4402 : 1986
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m3
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.2 - AP65 - Production Property Tests and Sampling
label | Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 3 per source initially, then 1/1000m³
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.3 - AP65 - Testing for Layer Compaction - MDD
label | Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.4 - AP40 - Source Property Tests and Sampling
label | Specification - TNZ M/4: 2006 - 3 NZS 4407 : 1991, NZS 4402 : 1986
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m4
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.5 - AP40 - Production Property Tests and Sampling
label | Specification - TNZ M/4: 2006 - 4 NZS 4407 : 1991
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 3 per source initially, then 1/1000m³
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.6 - AP40 - Testing for Layer Compaction - MDD
label | Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.7 - Sealing Chip - Source Property Tests and Sampling
label | Specification - TNZ M/6: 2019 - 4
label | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
label | Verifying Document - IANZ Lab Reports
label | Frequency - Before Supply and Every 10,000m3 Thereafter
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.8 - Sealing Chip - Production Property Test Sampling
label | Specification - TNZ M/6: 2019 - 5
label | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 500m3
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.9 - Bitumen - Quality Testing
label | Specification - NZTA M01: 2022 - 6
label | Acceptance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test per grade supplied
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.10 - Bitumen - Supply Testing
label | Specification - NZTA Q05: 2022 - 6.2
label | Acceptance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 200 tonnes supplied.
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
section | 3.4 Receiving Materials/Parts - Safety Barrier
checkpoint | 3.4.1 - Barrier Mill Certs
label | Specification - NZTA M23 AS/NZS 3845
label | Acceptance Criteria - Compliance documentation
label | Verifying Document - Mill Certs
label | Frequency - Prior to commencement of works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.4.2 - Concrete mix design
label | Specification - As per Design Specification
label | Acceptance Criteria - Concrete Mix design for each mix comply with the requirements of the Project Specification
label | Verifying Document - Concrete supplier mix designs
label | Frequency - Submitted to Client Engineer for approval before construction
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
section | 4.1 VMS Foundation with Plinth and cabinet pad - Construction
checkpoint | 4.1.1 - Construction Location
label | Specification - Design Location
label | Acceptance Criteria - Proposed location of construction to be staked out to the engineer for review prior to construction
label | Verifying Document - Approval letter, Photos
label | Frequency - Prior to each foundation build
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - CR
checkpoint | 4.1.2 - Ground Compaction Test
label | Specification - Downer Standard
label | Acceptance Criteria - Compaction shall achieve a minimum Clegg Impact Value (CIV) of 20 on the first layer and 25 on subsequent layers
label | Verifying Document - Test reults, Location of Test
label | Frequency - For each Foundation
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.1.3 - Reinforcement and Hold Down Bolt Inspection
label | Specification - As per Design Specification
label | Acceptance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
label | Verifying Document - Pre pour, Photos
label | Frequency - Prior to each foundation pour
label | Inspection Type (Visual, other) - Visual Inspection, Dimensional Inspection
label | Inspection: Key - H
label | Inspection: By - CR,SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.4 - Electrical & Comms Ducts Placement
label | Specification - As per Design Specification
label | Acceptance Criteria - Compliant with the construction drawings
label | Verifying Document - Pre pour, Photos
label | Frequency - Prior to each foundation pour
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - H
label | Inspection: By - CR,SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.5 - Pre-Pour Inspection
label | Specification - Downer Standard
label | Acceptance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
label | Verifying Document - Pre pour, Photos
label | Frequency - Prior to each foundation pour
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - H
label | Inspection: By - CR,SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.6 - Delivery Dockets
label | Specification - Downer Standard
label | Acceptance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
label | Verifying Document - Dockets
label | Frequency - Each Pour
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.1.7 - Compression Testing
label | Specification - As per Design Specification
label | Acceptance Criteria - One specimen from each pour shall be tested at 28 days.
label | Verifying Document - Test Results
label | Frequency - one test per 50m³/per pour
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.1.8 - Post Pour Inspection
label | Specification - Downer Standard
label | Acceptance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
label | Verifying Document - Post Pour, Photos
label | Frequency - Each Pour
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.1.9 - Defective Concrete Finishes
label | Specification - Downer Standard
label | Acceptance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
label | Verifying Document - NCR
label | Frequency - Prior to minor repair
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - A
label | Inspection: By - SE
section | 4.2 Shoulder Widening and Sealing - Construction
checkpoint | 4.2.1 - Material Placement
label | Specification - Downer Standard
label | Acceptance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored thoughout
label | Verifying Document - Survey / Level Checks
label | Frequency - Continuous monitoring.
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SV,PS
checkpoint | 4.2.2 - Pavement Shoulder Widening
label | Specification - Design Specification, Appendix E, Section 2.1.4
label | Acceptance Criteria - Pavement sholder widening treatment will be confirmed with Engineer on site
label | Verifying Document - Approval letter, Photos
label | Frequency - Prior to construction
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - CR
checkpoint | 4.2.3 - Sub-basecourse Pavement Layer Compaction (NDM)
label | Specification - TNZ B/02: 2005 - 7.6
label | Acceptance Criteria - Mean Value ≥ 95 % of MDD Minimum Value ≥ 92 of MDD
label | Verifying Document - NDM Report
label | Frequency - 1/10m
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.4 - Sub-basecourse Layer thickness
label | Specification - TNZ B/02: 2005 - 5.1
label | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –25 mm +5 mm
label | Verifying Document - Survey / Level Checks
label | Frequency - 1/20m Full width
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SV or SE
checkpoint | 4.2.5 - Basecourse Pavement Layer Compaction
label | Specification - TNZ B/02: 2005 - 7.6
label | Acceptance Criteria - Mean Value ≥ 98 % of MDD Minimum Value ≥ 95 of MDD
label | Verifying Document - NDM Report
label | Frequency - 1/10m
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.6 - Basecourse Layer thickness.
label | Specification - TNZ B/02: 2005 - 5.1
label | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –5 mm +15 mm
label | Verifying Document - Survey / Level Checks
label | Frequency - 1/20m Full width
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SV or SE
checkpoint | 4.2.7 - Surface Shape
label | Specification - TNZ B/02: 2005 - 7.7
label | Acceptance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
label | Verifying Document - Survey / Straight edge Report
label | Frequency - 1/20m Full width prior to sealing
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.2.8 - Surface Finish post sweeping
label | Specification - TNZ B/02: 2005 - 7.8
label | Acceptance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
label | Verifying Document - Photos
label | Frequency - Prior to sealing
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.2.9 - Preselling Requirements
label | Specification - TNZ B/02: 2005 - 12
label | Acceptance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 80%.
label | Verifying Document - NDM Report
label | Frequency - 1/10m
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.2.10 - PreSeal inspection
label | Specification - TNZ P3 TNZ B02
label | Acceptance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site.
label | Verifying Document - Hold point Release, ITP Sign off
label | Frequency - Prior to sealing
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.11 - Spray Temperature
label | Specification - TNZ P3
label | Acceptance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
label | Verifying Document - Sealing statement
label | Frequency - Prior to sealing
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.2.12 - Chip Application
label | Specification - TNZ P3
label | Acceptance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
label | Verifying Document - Sealing statement
label | Frequency - For every spray run
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.2.13 - Post Seal Inspections
label | Specification - TNZ P3
label | Acceptance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
label | Verifying Document - Engineers Acceptance
label | Frequency - Prior to TM Removal and After Final Sweeping
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - H
label | Inspection: By - SE,CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.14 - Chipseal Repairs
label | Specification - TNZ P3
label | Acceptance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
label | Verifying Document - Approved Repair Methodology
label | Frequency - Prior to Repairs
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - A
label | Inspection: By - SE
section | 4.3 Guardrail - Installation
checkpoint | 4.3.1 - Guard rails - Location
label | Specification - Design Specification, Appendix E, Section 2.1.3
label | Acceptance Criteria - The Contractor will set out the guardrail location with the Engineer on site.
label | Verifying Document - Approval letter, Photos
label | Frequency - Prior to construction
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - CR
checkpoint | 4.3.2 - Guard rails - Installation & Checklist
label | Specification - As per design specification
label | Acceptance Criteria - To complete the check list along with the guard rail installer after the construction
label | Verifying Document - Check Sheet DN-QC-06 Photos
label | Frequency - For each site
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
section | Final Inspection and Handover
checkpoint | 5.1 - Construction Record Compilation
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Verifying Document - Closed-out NCR/Defects
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 5.2 - As-built Survey
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Verifying Document - As built survey record completed
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SV
checkpoint | 5.3 - Red-line As-built Drawings
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
label | Verifying Document - Signed As-built Drawings
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE,SV
checkpoint | 5.4 - Defect, Snag and Punch List
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
label | Verifying Document - Register
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PE
checkpoint | 5.5 - All QA documentation collated and signed-off
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - All signed and closed out
label | Verifying Document - Signed off Documents
label | Frequency - Post construction
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - QM