## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 379c0af0-6e80-4569-bd2d-c6e66cc6b51d |  | checklist | ITP-000 - Client Pre-Construction Checklist Rev1 | itp |  |  |  | Yes | ITP-000 - Client Pre-Construction Checklist Rev1 | 45c27f32-06c2-46b5-91df-d29a738a6220
checkpoint-group | d8996e30-3eb9-4b41-abc2-27a696afe2bd |  | section | Pre - Construction Works
checkpoint-status | 589e9fa0-afd6-4af5-95a5-5dfd2b82cf98 |  | checkpoint | 1.1 Asphalt - submission of asphalt mix design
label | df00ec6c-f513-5fb4-8dbd-91d97bd4f653 |  | note | FREQUENCY: Prior to commencing asphalt
label | 5309820f-9ae1-58c6-8d69-f9c7df46132d |  | note | ACCEPTANCE CRITERIA: Ensure the mix design/s have been registered and are approved by Superintendent prior to laying mix.
label | c8cc16b3-e36d-5992-8419-360c98469249 |  | note | REFERENCE DOCUMENTS: VicRoads Spec.Cl.407.09. RAP DoT letter from production plant
label | 7f3eb5fd-32f0-5141-bae7-787859629bd9 |  | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design from the RAP DoT Letter.
label | ce5a1eeb-b2c1-5c6c-b9c1-779963cb7ba9 |  | note | RECORD OF CONFORMITY: Superintendent approval via hold point release
label | 6b66e5b7-a7b0-5441-895e-00b98ab5f99b |  | note | HP
label | cbc7a405-e38d-541c-b1da-c17dac7c670c |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
text | 6f38fd27-9260-53bc-841d-32cbf4c44bfe |  | textbox | Date Completed:
holdpoint | afc386b5-021b-4939-8f9e-c5f3022fdee2 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | c5e00acb-8cb5-4a81-9a8f-bf85a3577763 |  | checkpoint | 1.2 Concrete - submission & approval of concrete mix design prior to commencement of project
label | 83251cf5-9c1c-593d-841f-10584cfbf8d8 |  | note | FREQUENCY: Prior to first concrete pour
label | dd91c09a-b61b-52b9-9f0e-e2494e3d1bb7 |  | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour. Mix shall contain minimum 460 kg/m3 cement content. Special 50 mPa mix is to be VS502B25MET1 with a suitably flowable design slump agreed prior to construction.
label | b83b69ce-e2c4-55d7-912c-3f7198ad7f2a |  | note | REFERENCE DOCUMENTS: CE-019-ST- 0033 VicRoads Spec.Cl. 503.04
label | 17cd50c3-0bdd-5741-a101-3d7ddeb5346d |  | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design from supplier
label | f95c40ac-f777-5278-827e-7b71612612f5 |  | note | RECORD OF CONFORMITY: Superintendent approval via hold point release
label | 58c7c014-0699-556c-a0f1-258180e3e3f4 |  | note | HP
label | 71348d06-f98a-5c88-823c-d18a59fb482d |  | note | RESPONSIBILITY: FH Engineer / Superintendent
text | f8af6051-b8e4-5bf2-8877-2979023de1c1 |  | textbox | Date Completed:
holdpoint | 254ca858-9044-42df-be83-f912c42a2b61 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | c7815010-82b6-4a0a-9980-b6c15bd7e8e4 |  | checkpoint | 1.3 Welders qualifications, competencies & work methodology
label | 288e8069-da01-5d78-9e9a-a2e9aeadc3ef |  | note | FREQUENCY: Prior to commencing works
label | ed01a1b7-040a-5221-8441-73726b149225 |  | note | ACCEPTANCE CRITERIA: Weld methodology to be submitted prior to commencement of works. Welders shall be trained and compliant in Australian aluminothermic welding competencies as outlined below;
label | 101cee86-a3db-57e0-b660-1cefcddc6092 |  | note | – TLIW2012 Grind Rails
label | aecdcb84-6f29-5370-aa14-d81b95c773cf |  | note | – TLIW3015 Weld Rails using Aluminothermic welding process
label | bffd28c7-7536-54d8-a2f0-67531f51e250 |  | note | – TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
label | 7017d770-0ff4-5339-b490-18f748c5dfb2 |  | note | REFERENCE DOCUMENTS: CE-019-ST- 0033 Appendix C
label | 06beef08-b46d-5d64-b1c7-5ae9725cfa54 |  | note | INSPECTION/TEST METHOD: Welding methodology
label | 4b945b36-3e82-53c7-82bb-e2e3b1c631c8 |  | note | RECORD OF CONFORMITY: Superintendent approval via hold point release
label | 6880c148-8766-5239-a8e3-e805f62102a1 |  | note | HP
label | acf25835-363f-5c1f-aa79-5e1f7fda8672 |  | note | RESPONSIBILITY: FH Engineer / Superintendent
text | 81a8f244-b7e3-525b-b981-4c1b7f1b4f79 |  | textbox | Date Completed:
holdpoint | c63632ac-f6b8-4f1d-b1b6-b0fe53fee217 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | a1aaa098-b751-4415-84b0-3d65d51f72b0 |  | checkpoint | Final Inspection
label | 8eb233b0-71d4-5912-b19d-4cbd6b4ba6bd |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 279e0dd0-e815-5367-821e-d2e6eb8b4226 |  | textbox | Print Name:
text | c1a17e9a-e098-5caa-8ba3-6a18b75ff2dc |  | textbox | Position:
text | e53c798b-e040-5ce7-a45a-9f1257e414ea |  | textbox | Date: