## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP001 - Pavement Rehabilitation | itp |  |  |  |  | ITP001 - Pavement Rehabilitation
section | Details
checkpoint | 1 - Survey
label | ACTIVITY TASK - Verify latest drawings
label | ACCEPTANCE CRITERIA - Latest Revision of IFC
label | CERTIFING DOCUMENTATION AND FREQUENCY - Drawing Register
label | Supervisor, Foreman or Subcontractor - R
label | Project Manager or Delegated Person - R
checkpoint | 2 -
label | ACTIVITY TASK - Set out
label | ACCEPTANCE CRITERIA - Review and Inspection
label | CERTIFING DOCUMENTATION AND FREQUENCY - Initial, as per engineers’ request
label | Supervisor, Foreman or Subcontractor - R
label | Project Manager or Delegated Person - W
label | Engineer’s Representative - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 -
label | ACTIVITY TASK - Trenching/ Potholes
label | ACCEPTANCE CRITERIA - Location, alignment and level check for existing services
label | CERTIFING DOCUMENTATION AND FREQUENCY - Checklist
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - R
checkpoint | 4 - Construction – Subsoil Drain
label | ACTIVITY TASK - Pipe Materials
label | ACCEPTANCE CRITERIA - 100mm dia slotted PVC or Polyethylene subsoil drain pipe
label | CERTIFING DOCUMENTATION AND FREQUENCY - Supplier documentation, KDC Engineering Standards
label | Supervisor, Foreman or Subcontractor - R
label | Project Manager or Delegated Person - R
label | Engineer’s Representative - R
checkpoint | 5 -
label | ACTIVITY TASK - Drainage materials
label | ACCEPTANCE CRITERIA - 20/7 “Pages” metal
label | CERTIFING DOCUMENTATION AND FREQUENCY - Supplier documentation, KDC Engineering Standards
label | Supervisor, Foreman or Subcontractor - R
label | Project Manager or Delegated Person - R
label | Engineer’s Representative - R
checkpoint | 6 - Construction – Dished Channel
label | ACTIVITY TASK - Concrete Strength
label | ACCEPTANCE CRITERIA - 30MPa at 28 days
label | CERTIFING DOCUMENTATION AND FREQUENCY - Supplier documentation, KDC Engineering Standards
label | Supervisor, Foreman or Subcontractor - R
label | Project Manager or Delegated Person - R
label | Engineer’s Representative - R
checkpoint | 7 - Construction – Pavement
label | ACTIVITY TASK - Stripped Surface
label | ACCEPTANCE CRITERIA - Visual Inspection
label | CERTIFING DOCUMENTATION AND FREQUENCY - At completion of stripping, prior to further construction
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - W
checkpoint | 8 -
label | ACTIVITY TASK - Undercutting
label | ACCEPTANCE CRITERIA - Engineer to confirm
label | CERTIFING DOCUMENTATION AND FREQUENCY - As required
label | Supervisor, Foreman or Subcontractor - H
label | Project Manager or Delegated Person - W
label | Engineer’s Representative - W
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 -
label | ACTIVITY TASK - Subgrade
label | ACCEPTANCE CRITERIA - 1. CBR > 3%
label | ○ 2. No visible deflections
label | CERTIFING DOCUMENTATION AND FREQUENCY - 1. Scala testing at 10m intervals
label | ○ 2. Proof rolling with steel drum roller
label | ○ 3. Checklists
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - R
label | Engineer’s Representative - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 -
label | ACTIVITY TASK - Sub-basecourse
label | ACCEPTANCE CRITERIA - 1. Mean 95% MDD, Min 92% MDD
label | ○ 2. -15mm below 3m straight edge
label | ○ 3. +10mm from design
label | CERTIFING DOCUMENTATION AND FREQUENCY - 1. Nuclear density as per Waka Kotahi’s Specification B/2 and KDC Engineering Standards 2011 Part 5
label | ○ 2. Surface Finish – Straight edge
label | ○ 3. Level/thickness
label | ○ 4. Checklist / As-builts
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - R
label | Engineer’s Representative - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 -
label | ACTIVITY TASK - Basecourse
label | ACCEPTANCE CRITERIA - 1. Mean 98% MDD, Min 95% MDD
label | ○ 2. -10mm below 3m straight edge
label | ○ 3. +5mm;-5mm from design
label | ○ 4. 1.4mm(90%) 1.8mm(max)
label | ○ 5. Material Approval as per TNZ M/4: 2006
label | CERTIFING DOCUMENTATION AND FREQUENCY - 1. Nuclear density as per Waka Kotahi’s Specification B/2 and KDC Engineering Standards 2011 Part 5
label | ○ 2. Surface Finish – Straight edge
label | ○ 3. Level/thickness
label | ○ 4. Benkelman Beam Testing – Deflection prior to sealing
label | ○ 5. Supplier documentation
label | ○ 6. As per technical specification section C0210 and Engineers approval
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - R
label | Engineer’s Representative - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 -
label | ACTIVITY TASK - Chip-seal
label | ACCEPTANCE CRITERIA - 1. Check tight stone Mosaic surface
label | ○ 2. Aggregate – PSV54-56
label | ○ 3. Sealing QA
label | ○ 4. Approval of materials before use
label | CERTIFING DOCUMENTATION AND FREQUENCY - 1. Visual Inspection
label | ○ 2. Test data sheet
label | ○ 3. Technical specification section C0213
label | ○ 4. Mix design as per technical specification section C0213 and Engineers approval
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - R
label | Engineer’s Representative - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 -
label | ACTIVITY TASK - Line Marking
label | ACCEPTANCE CRITERIA - 1. Visual Inspection
label | CERTIFING DOCUMENTATION AND FREQUENCY - 1. TNZ Manual of Traffic Signs and Markings
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - R
label | Engineer’s Representative - R
checkpoint | 14 - As -Builts
label | ACTIVITY TASK - As-builts
label | ACCEPTANCE CRITERIA - A complete set of as-builts shall be provided on the completion of the project. This will include but not limited to
label | ○ 1. Pavement levels
label | ○ 2. Subsoil drains, dished channel, flushing eyes
label | Supervisor, Foreman or Subcontractor - P
label | Engineer’s Representative - R