## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP006 - Concrete - In-SItu Wall Installation | itp |  |  |  |  | ITP006 - Concrete - In-SItu Wall Installation
section | SECTION 3 – RECEIVING INSPECTIONS
checkpoint | 3.1 - ELEMENT IDENTIFICATION:
checkpoint | 3.2 - Survey / Set out
label | Inspection Point: Quality Control Activity - Levels confirmed on site
label | Acceptance Criteria - Set out in accordance with design drawings or site conditions
label | Verifying Document - Visual Inspection / On Site Verification
label | Key - I
label | By - IP
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Reinforcement Installation
label | Inspection Point: Quality Control Activity - Structural Reinforcement as per Structural Design documentation / additional SDA
label | Acceptance Criteria - Shotcrete Reinforcement mesh is held firm so cannot vibrate. Steel bar installed as required, with starter bars if needed.
label | Verifying Document - Client Engineering Inspection
label | Key - HP
label | By - IP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Formwork
label | Inspection Point: Quality Control Activity - Formworks to comply with the final shape/size of the wall
label | Acceptance Criteria - Formworks match designs and will enable concrete finishes as desired
label | Verifying Document - Visual Inspection
label | Key - WP
label | By - IP
checkpoint | 4.3 - Finish
label | Inspection Point: Quality Control Activity - Finish surface of wall
label | Acceptance Criteria - Off Gun / Screed finish as required
label | Verifying Document - Visual Inspection
label | Key - WP
label | By - IP
checkpoint | 4.4 - Pre-Pour Concrete Check
label | Inspection Point: Quality Control Activity - Inspection of reo and formworks
label | Acceptance Criteria - Steel reinforcement in accordance with design documentation
label | Verifying Document - Client Inspection
label | Key - HP
label | By - IP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Concrete Pour
label | Inspection Point: Quality Control Activity - Concrete is poured to required levels and strength
label | Acceptance Criteria - Strength and finish requirement met. Finished level within tolerances.
label | Verifying Document - Visual inspection Strength Test
textbox | Supplier:
label | Key - HP
label | By - IP
holdpoint | AUTHORITY HOLDPOINT