## res_ITC 12 - R11 and R16 Stormw
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP007 - Concrete - Column Installation | itp |  |  |  | Yes | ITP007 - Concrete - Column Installation | f41499fc-e2b7-4fd9-a8aa-74cd935c27d9
checkpoint-group |  |  | section | SECTION 3 – RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | 3.1 - ELEMENT IDENTIFICATION
checkpoint-status |  |  | checkpoint | 3.2 - Survey / Set out
label | 8bb66d57-c1cf-509d-a395-f9980e643568 |  | note | Inspection Point: Quality Control Activity - Levels confirmed on site
label | a20db616-61b9-5c64-bfc1-170acd790905 |  | note | Acceptance Criteria - Set out in accordance with design drawings or site conditions
label | 1728c775-9112-509b-9413-2479bcee6e8d |  | note | Verifying Document - Visual Inspection / On Site Verification
label | 28edf8f6-51b3-5187-a373-e6c9fe37d832 |  | note | Key - I
label | 27e9f54f-83ae-52b4-b6bd-4e01ef2ca1dd |  | note | By - IP
checkpoint-group |  |  | section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint-status |  |  | checkpoint | 4.1 - Reinforcement Installation
label | c43a51fd-688c-5e36-8ba0-141834a3ee31 |  | note | Inspection Point: Quality Control Activity - Structural Reinforcement as per Structural Design documentation / additional SDA
label | 950dbd46-bc0c-5bdb-9911-a46da82757ff |  | note | Acceptance Criteria - Steel bar installed as required, with starter bars if needed
label | d380a811-f080-5fa0-afca-827e35c59989 |  | note | Verifying Document - Client Engineering Inspection
label | 885ee09c-2c49-5e51-95e5-e260738af7f3 |  | note | Key - HP
label | b13111e9-0c5c-5ccf-9052-4609e974c5f1 |  | note | By - IP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Formworks
label | 978905c7-8971-568e-b368-599ecd907c76 |  | note | Inspection Point: Quality Control Activity - Formworks to comply with the final shape/size of the column
label | 29f182f3-ae61-556e-ac3f-85e0bbb94be9 |  | note | Acceptance Criteria - Formworks match designs and will enable concrete finishes as desired
label | a324b857-648f-5c3f-9400-9bbeb637ee9a |  | note | Verifying Document - Visual Inspection
label | 7e960969-1738-556e-ac31-42abab587499 |  | note | Key - WP
label | 17601a1f-9881-553c-9012-963b75eba132 |  | note | By - IP
checkpoint-status |  |  | checkpoint | 4.3 - Finish
label | ee9a3e9d-9d8f-5713-ac63-5df76f824dc3 |  | note | Inspection Point: Quality Control Activity - Finish surface of column or off-form finish
label | e8f9ebad-18dd-57f1-9ecc-56b45fc1dc66 |  | note | Acceptance Criteria - Finished as required
label | f53fc4c8-ed9d-5df5-8e0c-0dfe422fd62a |  | note | Verifying Document - Visual Inspection
label | 570c32a8-6f97-52e7-8454-abc762864bf8 |  | note | Key - WP
label | d323b3b4-1d99-56fd-a0f9-28ceb2dc0cf8 |  | note | By - IP
checkpoint-status |  |  | checkpoint | 4.4 - Pre-Pour Concrete Check
label | 29a5e9e0-fe9a-5925-ba59-6d6f090e303b |  | note | Inspection Point: Quality Control Activity - Inspection of reo and formworks
label | d785284d-f3f1-561d-9324-0e1f661a219b |  | note | Acceptance Criteria - Steel reinforcement in accordance with design documentation
label | 09ca15d1-04bc-595c-911a-f5f607698ff9 |  | note | Verifying Document - Client Inspection
label | 8a498974-f622-5278-b800-87ad31f9bd69 |  | note | Key - HP
label | ce4f6a79-f7ce-595e-a9ad-3e7bbef27df8 |  | note | By - IP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Concrete Pour
label | 07803ecf-ad03-5e18-8ed9-dcc55254f009 |  | note | Inspection Point: Quality Control Activity - Concrete is poured to required levels and strength
label | 0ae98a9e-89a2-50d9-9696-b13821458a40 |  | note | Acceptance Criteria - Strength and finish requirement met, Finished level within tolerances
label | ba1bea15-feae-5200-9841-fc9fb46e2143 |  | note | Verifying Document - Visual inspection Strength Test Supplier:
label | d7a3dcfd-2a39-5f8b-b106-b29156cf73eb |  | note | Key - HP
label | c15571da-497b-59e0-9596-812c48b51252 |  | note | By - IP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT