## res_ITC 12 - R11 and R16 Stormw
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP105 - Civil - Concrete Stairs | itp |  |  |  | Yes | ITP105 - Civil - Concrete Stairs | 127a8915-0f4e-4fe5-8960-7f3617b92efc
checkpoint-group |  |  | section | SECTION 3 – RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | 3.1 - ELEMENT IDNETIFICATION
checkpoint-status |  |  | checkpoint | 3.2 - Survey / Set out
label | 47e36a25-879a-5f8b-9e0e-0350e6e46a10 |  | note | Inspection Point: Quality Control Activity - Levels confirmed on site
label | 08e3e1c1-870d-50c1-b27d-56b0a7b45c53 |  | note | Acceptance Criteria - Set out in accordance with design drawings or site conditions
label | 076dddb4-3af6-58d7-b71c-db76d5a8fbd2 |  | note | Verifying Document - Visual Inspection / On Site Verification
label | 7c33eefc-d78e-5bb7-8cfd-806fd249ea4c |  | note | Key - I
label | 897339df-76e1-5c2e-8d0a-0a67d43b3f92 |  | note | By - IP
checkpoint-group |  |  | section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint-status |  |  | checkpoint | 3.1 - Preparation of Subgrade/Rock Preparation
label | 987c620d-ffe3-587a-8339-af9119e55569 |  | note | Inspection Point: Quality Control Activity - Subgrade meets design requirements. FCR placed to specified thickness and compacted
label | 934376ec-04ff-5011-b20c-452587049c26 |  | note | Acceptance Criteria - No soft spots. Rock layer conforms to required thickness.
label | c0074e3e-6fbc-5bb1-98e6-6e76df078a46 |  | note | Verifying Document - Visual Inspection. Geotech test if required.
label | cdcbe620-9818-5ca7-a289-addb20b8fdab |  | note | Key - W
label | 6f1e2e7c-0eb5-5030-9b31-70adb776985e |  | note | By - IP
checkpoint-status |  |  | checkpoint | 3.2 - Steel Formwork (if required)
label | e4e5eda6-d664-5462-b12a-01509fd9a931 |  | note | Inspection Point: Quality Control Activity - Installation of Bondek, to suit stair design
label | 98dca52d-589c-5357-b556-edb131099cf3 |  | note | Acceptance Criteria - Bondek installed as per drawings
label | 81c70e5b-de89-5c46-9ff9-03dcc3e21645 |  | note | Verifying Document - Visual Inspection
label | 264e3c02-f54c-57f2-ab29-67121cb1bf16 |  | note | Key - H
label | 7a11c100-f4a1-5d6d-bfb2-874da641de9a |  | note | By - PE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Timber Formwork
label |  |  | note | Inspection Point: Quality Control Activity - Installation of stair nosing rebates, correct step heights and widths
label |  |  | note | Acceptance Criteria - Formwork confirmed with drawings
label |  |  | note | Verifying Document - Visual Inspection
label |  |  | note | Key - W
label |  |  | note | By - IP
checkpoint-status |  |  | checkpoint | 3.4 - Steel Reinforcement
label | e0bcc0c3-70d9-5e7a-8919-99dc74b60abc |  | note | Inspection Point: Quality Control Activity - Installation of steel mesh and or steel bar reinforcement as per drawings
label | 52bee4cf-9c0f-5ef5-a7f8-6eb53a7261d5 |  | note | Acceptance Criteria - Reinforcement installed as required
label | 33dadfc9-3477-57fd-b50d-a716bf01932a |  | note | Verifying Document - Visual Inspection
label | e0a16390-c5b1-5731-9355-18c510a161c4 |  | note | Key - H
label | b9be93bd-86ce-5f87-8474-b3bfb2862a7b |  | note | By - IP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Concrete Pour
label | e5258f0f-3723-5c70-92c7-fee0ceac33fb |  | note | Inspection Point: Quality Control Activity - Concrete is poured to required levels and strength
label | 70bcf5f8-f0dc-59a5-9d3b-8becb6499027 |  | note | Acceptance Criteria - Strength and finish requirement met
label | 91d8b227-6275-592d-91dd-4c7380f3dbc6 |  | note | Verifying Document - Visual inspection only Strength Test
label | 3d9b9e27-f95a-5b00-a1da-f9508a9fbf1b |  | note | Key - I
label | 62d51751-c949-5a8b-98ed-f9f81af7a1e3 |  | note | By - IP
checkpoint-status |  |  | checkpoint | 3.6 - Stair edging or surface treatments
label | feac593f-a6f5-57ad-9e27-ed916a9492b0 |  | note | Inspection Point: Quality Control Activity - Stair treatments installed as required. (stair nosing’s, edge treatments, etc.)
label | 75907d04-2d9c-57f8-ac34-7e9959b9822c |  | note | Acceptance Criteria - As per drawings
label | 21bc4fe6-af45-50ca-b9fa-2c9c83d5535c |  | note | Verifying Document - Visual inspection
label | 96f6a9ea-55ac-5c53-8a32-5fd8dd66a17e |  | note | Key - I
label | 9da86c9e-e56c-5f59-ae21-4311034b58ea |  | note | By - IP
checkpoint-group |  |  | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
checkpoint-status |  |  | checkpoint | 5.1 - Completions
label | 1e9cddd2-1604-53aa-bc3b-b27859584b02 |  | note | Inspection Point: Quality Control Activity - Inspection of works
label | 0f1f5715-2e27-5cf1-9874-7a0546c3f792 |  | note | Acceptance Criteria - Works completed to the client requirements
label | 1f09bb61-fc3c-5344-b417-c04801fa52c7 |  | note | Verifying Document - This document
label | 8060618f-21ce-5041-8913-7ec3d4cb3ccb |  | note | Key - H
label | 67c5fafd-a153-5e4f-a596-de0dde2cb158 |  | note | By - PE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | SECTION 6 – COMMENTS
checkpoint-no-status |  |  | checkpoint | Comments