## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Pre-Con
section | Details
checkpoint | Sub Review
checkpoint | Safety Induction
checkpoint | Drawings Approved
checkpoint | Site Inspection
checkpoint | Hold Point, Sup Sign & Date
checklist | Rough-in | [5 empty] | ITP-115 - Mechanical - Rough-In (Office)
section | Details
checkpoint | Check Material
checkpoint | Install FCUs
checkpoint | Install BC Boxes
checkpoint | Install Fans
checkpoint | Install Pipework
checkpoint | Install Cabling, Controls Etc
checkpoint | Install Flexible Ducts
checkpoint | Install Drains and test
checkpoint | Fire Boxes/Collars/Dampers Installed, Photos Taken
checkpoint | Install Rigid Duct and seal
checkpoint | Access Panels Marked
checkpoint | Pressure Testing
checkpoint | Hold Point, Sup Sign & Date
checklist | Rough-in | [5 empty] | ITP-115 - Mechanical - Rough-In (Basement/Ground/Roof)
section | Details
checkpoint | Check Material
checkpoint | Install FCUs
checkpoint | Install Fans
checkpoint | Install Pipework
checkpoint | Install Cabling, Controls Etc
checkpoint | Install Flexible Ducts
checkpoint | Install Drains and test
checkpoint | Fire Boxes/Collars/Dampers Installed, Photos Taken
checkpoint | Install Rigid Duct and seal
checkpoint | Install louvre Box
checkpoint | Access Panels Marked
checkpoint | Pressure Testing
checkpoint | Hold Point, Sup Sign & Date
checklist | Fit-off | [5 empty] | ITP-115 - Mechanical - Fit-off
section | Details
checkpoint | Check Pressure
checkpoint | Install Condensers
checkpoint | Terminate Drain
checkpoint | Terminate Power and Controller
checkpoint | Install Grilles
checkpoint | Pressure test
checkpoint | Vacuum system
checkpoint | Access To Equipment Checked
checkpoint | Commission
checkpoint | Model No
checkpoint | Serial No.
checklist | Level Sign Off | [5 empty] | ITP-115 - Mechanical - Final Sign Off
section | Details
checkpoint | Subcontractor Sign-off Supervisor/Date
checkpoint | Head Contract Sign-off
checkpoint | Client Sign-off