## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Construction Joint (ITC)
section | Details
checkpoint | Substrate - All surfaces flat, dry, clean, smooth and free from sharp objects, laitance, oils, grease or any foreign materials which may inhibit or reduce adhesion.
checkpoint | Commencement of installation shall be taken as acceptance of the substrate by the Applicator
checkpoint | SOPRAHOSE 13 is generally positioned in the middle of the substrate or in a position with a minimum of 100 mm concrete cover from any external edge.
checkpoint | SOPRAHOSE 13 must lay flat on the concrete surface with appropriate hose clamps mechanically fixed to the concrete substrate. HOSE CLIP should be spaced at 200 mm centres.
checkpoint | SOPRAHOSE 13 END BOX will be installed on the formwork flask with the internal side of the wall or slab
checkpoint | Where the hose ends overlap, a parallel overlap of min 150 mm is required, with the two hoses laid parallel to each other with a 30-50 mm gap between the two parallel hoses.
checkpoint | The installation length of SOPRAHOSE 13 RE-INJECTABLE HOSE, between END BOX is 10 metres to achieve an ultimate injection process.
checkpoint | The standard installation length of SOPRAHOSE 13 RE-INJECTABLE HOSE, between END BOX is 10 metres to achieve an ultimate injection process.
checkpoint | Injection Boxes to be installed at a maximum of 10m spacing.
checkpoint | Pressure Seal
checkpoint | Pressure seal conecting new membrane with existing - By Delta
checkpoint | Confirm Pressure seal steel plate width : 75mm
checkpoint | Confirm Pressure seal steel plate thickness: 3mm
checkpoint | Bolts sealed galvanised paint - By Delta
checkpoint | Bolts: 12mm wide Excalibur bolts with washers installed at 100mm spacing c/c
checkpoint | HOLD POINT - Bravada Supervisor to conduct the final review of membrane system installation and confirm compliance with shop drawing/specification.
checkpoint | HOLD POINT - Delta Group Project Manager, I have reviewed the Injection Hose Prototype with Bravada, reviewed Bravad's ITC. I acknowledge handover of the works package to Delta Group and accept all responsibility for protecting the works package.
checkpoint | CHECKLIST COMPLETE AND SIGNED
checkpoint | ITC completed