## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 01.00 - Sprayed Bituminous Surfacing | itp |  |  |  |  | 01.00 - Sprayed Bituminous Surfacing
section | Details
checkpoint | 1 - Document Submissions
label | ○ As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
label | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management
label | Check Item - Check Item
checkpoint | 2 - Traffic and Safety Controls
label | ○ Traffic and safety controls are in place (eg. PPE, daily plant check)
label | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
label | Check Item - Check Item
checkpoint | 3 - Construction Procedures
label | ○ The contractor shall documented procedures for all required processes in reference to Clause 5.2 MRTS11 to be submitted not less than 7days, these procedures and ITP shall not be implemented until permission has been granted
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - MILESTONE/HOLD POINT
label | Reference - Clause 5.2 MRTS11
holdpoint | HOLD POINT
checkpoint | 4 - Seal Design - Binder Substitution
label | ○ The Contractor shall notify the Administrator of the binder class substitution not less than 14 days prior to the commencement of spraying.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - MILESTONE
label | Reference - Clause 6.1.2 MRTS11
checkpoint | 5 - Seal Design By Principal
label | Testing shall be completed by the Contractor at the test locations and minimum test frequencies detailed in Table 6.2. (Particle Size Distribution, Flakiness Index and Avegrade Least Dimension, Texture Depth and Ball Penetration.)
label | — Test results for the cover aggregate and texture depth has been submiteed at least 7 days
label | — Ball penetration testing has been undertaken in accordance with Table 6.2 and Clause 10.1.2 and passed on to the Administrator on the day of testing.
label | — Spraying shall not commenced until Designed Spray Rate and Designed Spread Rate has been confirmed.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - MILESTONE/HOLD POINT
label | Reference - Clause 6.2 MRTS11
holdpoint | HOLD POINT
checkpoint | 6 - Seal Design By Contractor
label | ○ Where the Contractor is nominated to undertake the Seal Design, the Contractor shall inspect each site and shall select inputs and associated design factors. The seal design reports shall include all inputs stipulated in the nominated clause.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 6.3 MRTS11
checkpoint | 7 - Seal Design Report
label | ○ A seal desin report shall be submited to the Administrator at least 7 days prior to commencing bituminous spraying operations. The Seal Design Report shall include the requirements of Clause 6.3.2 MRTS11. The Administrator shall have 3 days to consider the seal design report and spraying operations shall not commence until release of the hold point
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - MILESTONE/HOLD POINT
label | Reference - Clause 6.3.2 MRTS11
holdpoint | HOLD POINT
checkpoint | 8 - Quarry Registration Certificate
label | ○ Cover aggregate shall be supplied by a registered quarry comply with TMR Quarry Registration System. Certificate to be sent to the Administrator 7 days before material supply. Material from a quarry shall neither be supplied,nor used in the Works prior to written permission by the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - MILESTONE/HOLD POINT
label | Reference - Clause 6 MRTS22
holdpoint | HOLD POINT
checkpoint | 9 - Cover Aggregate
label | ○ Cover aggregate shall not be exposed to contaminant agents and to be handle to avoid any contamination / deleterious effects. It shall be protected with a light plastic or similar material to prevent the ingress of moisture and other contaminants.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 8.2 MRTS11
checkpoint | 10 - Bituminous Materials
label | ○ Binder shall be delivered to the Works in accordance with Clause 8 MRTS17 Bitumen or Clause 8 of MRTS18 Polymer Modified Binder. Temperature at delivery to site shall be measured and recorded.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 8.3.1 MRTS11
checkpoint | 11 - Bituminous Material Heating
label | ○ Strict controls shall be applied to heating of bituminous material and in accordance to Austroads AP-G41Bitumen Sealing Safety Guide, the heating requirements shall strictly be observed.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 8.3.2 MRTS11
checkpoint | 12 - Precoating Agents
label | ○ Cover aggregate shall be precoated with one of the nominated approved products listed in Clause 2 of Annexure MRTS22.1. The Contractor shall submit to the Administrator details of the precoating agent procedures 7 days prior commencing.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - MILESTONE
label | Reference - Clause 7.1.4 MRTS22
checkpoint | 13 - Compliance Testing
label | ○ The Administrator shall receive at least 15 working days a preliminary sample of 40kg of each type of cover aggregate to be used in the contract as per the requirments of Clause 3 MRTS22.1
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - MILESTONE
label | Reference - Clause 8.1 MRTS22
checkpoint | 14 - Plant & Equipments
label | ○ On site documentation of required plant will be provided no less than 3 days prior to sealing operations and shall satisfied as per Table 9. Additional plant requirements shall apply in accordance of Clause 5 MRTS11.1
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - HOLD POINT
label | Reference - Clause 9 MRTS11
holdpoint | HOLD POINT
checkpoint | 15 - Initial Bituminous Treatments (No Existing Bitumen Treatment)
label | ○ All foreigh and loose material, including lenses of pavement material shall be removed from the surface. The surface shall be swept with a road broom. Where a Ball Penetration test result exceeds 3.0 mm, the surface shall not be sprayed until approved by Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Verify
label | Check Item - HOLD POINT
label | Reference - Clause 10.1.2 MRTS11
holdpoint | HOLD POINT
checkpoint | 16 - Availability of Cover Aggregate
label | ○ Prior to commencement of bitumen spraying operations, the contractor shall provide the Administrator with evidence there is sufficient cover aggregate for the extent of bitumen spraying work to be undertaken that day.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - HOLD POINT
label | Reference - Clause 11.1 MRTS11
holdpoint | HOLD POINT
checkpoint | 17 - Pavement Surface Temperature
label | — Spraying shall not commence until the temperature of the pavement surface is above the temperature given in Clause 6.2 of Annexure MRTS11.1.
label | ○ 10℃ for primes
label | ○ 15℃ for initial seals containing cutback bitumen (i.e AMC4 to AMC7)
label | ○ 20℃ for bitumen and polymer modified binders
label | — These limits do not apply to WP-A and SAMI treatments
label | ○ placed over an existing seal or ashalt, and
label | ○ overlaid with asphalt prior to trafficking.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 11.2 MRTS11
checkpoint | 18 - Spraying Requirements
label | ○ Spraying shall not take place during rain of if rain is likely to fall prior to spreading cover aggregate and the completion of rolling. Further, spraying shall not take place during winds of greater than 30km/hr or during dust storms.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 11.3 MRTS11
checkpoint | 19 - Time Period Between Bituminous Treatments
label | ○ The minimum period of time between bituminous treatments shall be applicable as per the requirements of Clause 11.4 MRTS11
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 11.4 MRTS11
checkpoint | 20 - Spraying
label | ○ The spraybar nozzles used shall be appropriate for each spray run and shall comply with QSC. A copy of the Queensland Sprayer Certificate shall be provided.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 12.4 MRTS11
checkpoint | 21 - Cutting Back Binder
label | ○ Incorporation of cutter oil into the binder shall be caried out in accordance with Clause 8.3.3. Prior to each operation, Seal Designer Delegate shall nominate the cutter oil adjustments, which shall be recorded.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 12.7 MRTS11
checkpoint | 22 - Spreading of Cover Aggregate
label | ○ Wet cover aggregate containing free surface water shall not be loaded into the aggregate spreader.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 14.1 MRTS11
checkpoint | 23 - Time Limit for Cover Aggregate
label | Spreading of cover aggregate shall commence as soon as possible with the time limits specified below:
label | — primerseals: 15 minutes
label | — Cutback Bitumen, Bitumen and Multigrade Bitumen: 10 minutes, or
label | — polymer modified binders including crumbed rubber binder: 5 minutes
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 14.3 MRTS11
checkpoint | 24 - Early Traficking Requirements
label | ○ The requirements of Clause 14.8 shall be complied and the road shall not be opened to traffic until the release of this Hold Point by the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Acceptance
label | Check Item - HOLD POINT
label | Reference - Clause 14.8 MRTS11
holdpoint | HOLD POINT
checkpoint | 25 - Delivery of Aggregate to Stockpile Site
label | ○ Prior to commencement of delivery of aggregate to any stockpile site, the Contractor shall obtain the Administrator’s authorisation to place aggregates on the stockpile site.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - HOLD POINT/WITNESS POINT
label | Reference - Clause 10 MRTS22
holdpoint | HOLD POINT
checkpoint | Final Verification
note | Responsible Officer
textbox | Print Name:
date | Date:
note | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 02.00 - Clearing and Grubbing | itp |  |  |  |  | 02.00 - Clearing and Grubbing
section | Details
checkpoint | 1 - Document Submission
label | ○ As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
label | Acceptance Criteria & Frequency (Project Specific) - Safety Plan, Environmental Plan and Traffic Management Plan
label | Check Item - Check Item
checkpoint | 2 - Traffic and Safety Controls
label | ○ Traffic and safety controls are in place (eg. PPE, daily plant check)
label | Acceptance Criteria & Frequency (Project Specific) - Traffic and safety Management plans
label | Check Item - Check Item
checkpoint | 3 - Areas to be Cleared and Grubbed
label | ○ Clearing and Grubbing shall be limitted to the extent of those areas required to construct the works plus an additional width of no more than the distance stated in cl 1.1 of annexure MRTS4.1 or 3m where not so stated and/or meet the specified visibility requirements.
label | *Maximum additional width for clearing and grubbing - The lesser of 1.0m from the extent of earthworks or ground treatment areas or the property boundary.
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Cl 7.2.1 MRTS04, Cl 1.1 MRTS04.1
checkpoint | 4 - Limitations on Clearing Operations
label | ○ Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked out by the contractor prior to clearing operations.
label | Acceptance Criteria & Frequency (Project Specific) - Verify
label | Check Item - HOLD POINT
label | Reference - Cl 7.2.1 MRTS04
holdpoint | HOLD POINT
checkpoint | 5 - Trees Required by the Administrator
label | ○ Any trees required by the principal for use as marketable timber detailed in cl 2.3 MRTS04.1. Handling procedure shall be in a manner avoiding damages to the trunk and branches shall be trimmed appropriately. *None*
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - HOLD POINT
label | Reference - Cl 7.2.3 MRTS04
holdpoint | HOLD POINT
checkpoint | 6 - Additional Requirements
label | ○ Contractor shall mark the extent of clearing on the ground and agreed with the administrator prior to any clearing and grubbing activities. After completion of works, contractor shall give 5 days notice to the administrator and principal's RPEQ geotechnical enginner to inspect and confirm in writing that the clearing and grubbing works are complete before proceeding to the other works on same surface.
label | Acceptance Criteria & Frequency (Project Specific) - Verify
label | Check Item - Hold Point
label | Reference - Cl 7.2.8 MRTS04, Cl 1.4 MRTS04.1
holdpoint | HOLD POINT
checkpoint | Final Verification
note | Doval Representative
textbox | Print Name:
date | Date:
note | Administrator
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 03.00 - Concrete | itp |  |  |  |  | 03.00 - Concrete
section | Concrete
checkpoint | 1 - Document Submissions
label | ○ As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
label | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management
label | Check Item - Check Item
checkpoint | 2 - Traffic and Safety Controls
label | ○ Traffic and safety controls are in place (eg. PPE, daily plant check)
label | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
label | Check Item - Check Item
checkpoint | 3 - Submission and Approval of Mix Design
label | ○ Submit details of the mix design for each specified Class of concrete to the Administrator for approval 6 weeks prior to commencement of concreting operations. The Mix Design shall include the information in Clause 15.1 MRTS70
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 1
label | Reference - Clause 9.2 MRTS70, Clause 15.1 MRTS70
holdpoint | HOLD POINT
checkpoint | 4 - Trial Mix
label | ○ Minimum volume for trial mix shall be 25% of the rated capacity of the mixer. Each trial mix shall be a witness point with a notice period of 3 days. Shall be tested for slump, workability, and strength. The slump shall meet the allowable range with Table 11(a) Refer Clause 11 MRTS70
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 15.1.1 MRTS70
checkpoint | 6 - Concrete Testing
label | ○ Concrete to be tested and meet the mix design requirements. It shall only be tested at a NATA registered laboratory. Sampling and testing shall be in accordance with AS1012
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 12.3 MRTS70
checkpoint | 7 - Temperature and Evaporation Limits for Operations
label | ○ The procedure for hot weather concreting shall be submitted at least 2 weeks prior to the first concrete pour
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - MILESTONE
label | Reference - Clause 13.1 MRTS70
checkpoint | 8 - Air Temperature Measurements
label | ○ Ambient air temperature measured at the point of placement is not to be less than 10ºC or exceeds 35ºC. If the ambient air temperature measured at the point of placement is likely to exceed 35°C during placing and finishing operations, the Contractor shall take practical precautions, approved by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 13.1 MRTS70
checkpoint | 9 - Evaporation Limits
label | ○ The predicted evaporation rate during the intended work is not to exceed 0.75kg/m2/hr. If the evaporation rate exceeds 0.75kg/m2/hr then the Contractor shall undertake practical measures described in MRTS70 Cl 13.2 are to be implemented
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 13.2.1 MRTS70
checkpoint | 10 - False Works
label | ○ False work shall conform to AS 3610, except otherwise specified. The method of founding or supporting the false work and the time, order and manner of its release shall all require approval of the Administrator. Detailed drawings of such falsework shall be supplied to the Administrator at least 4 weeks prior to commencement of erection.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - HOLD POINT 2 /MILESTONE
label | Reference - Clause 15.3 MRTS70
holdpoint | HOLD POINT
checkpoint | 11 - Formwork, Bar Chairs, and Spacers
label | ○ All formwork shall be subject to inspection and approval before the concrete is to be placed. Formwork shall comply with AS 3610 and conform to Class 2 AS 3610 surface finish except as otherwise specified. All forms shall be smooth, mortar tight and have sufficient rigidity to maintain the tolerances specifed when subjected to fresh concrete and other construction loads. Unless otherwise shown in the drawings, all corners shall be provided with 15mm x 15mm chamfers or fillets.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 3
label | Reference - Clause 15.4.1 MRTS70
holdpoint | HOLD POINT
checkpoint | Concrete Temperatures:
label | ○ Concrete shall be managed to ensure that at no stage does the concrete temperature during hydration exceed 80°C or the difference in temperature between the geometric centre of the cross section and any adjacent edge location exceed 25°C (see Clause 15.5.3 for location details).
label | ○ If these limits are exceeded, appropriate rectification or rejection of the element shall occur, and additional precautions enacted.
label | Acceptance Criteria & Frequency (Project Specific) - Nonconformance
label | Check Item - Nonconformance
label | Reference - Clause 15.5 MRTS70
checkpoint | 12 - Placing and compacting concrete
label | ○ Concrete operations shall not commence until all relevant procedures, listed in Table 5.2 have been approved by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 4
label | Reference - Clause 15.6 MRTS70
holdpoint | HOLD POINT
checkpoint | 13 - Placing Concrete - General
label | ○ No concrete shall be placed in the Works until falsework, formwork, reinforcment and stressing materials have been inspected and all foreign material has been removed from the forms and all foreign material completely removed and the compaction equipment and placement procedure has been appoved.
label | — Placing operation shall be conducted in the presence of the Administrator and Contractor shall give at leat 24 hours notice
label | — Where reinforced concrete is placed on earth or sand foundations, the earth or sand is to be compacted to 95% RDD
label | ○ If placing operation required a drop of more than 2m, the concrete shall be placed using a flexible tube reaching the base of the formwork.
label | Acceptance Criteria & Frequency (Project Specific) - Approval, Visual
label | Check Item - HOLD POINT 5/Witness Point 2
label | Reference - Clause 15.6.1 MRTS70
holdpoint | HOLD POINT
checkpoint | 14 - Sheet Seperator
label | ○ Polythene sheet separator of thickness not less than 100µm, and extending at least 300mm beyond the concrete work, to be placed between the ground/bedding and the concrete
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 15.6.1 MRTS70
checkpoint | 15 - Concrete Placement Under Water
label | ○ Prior to concrete pouring commences the application procedure shall be submitted 2 weeks prior. Placement of concrete under water shall be carried out in the presence of the administrator and comply to techniques as specified in MRTS70 Clause 15.6.3
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 15.6.3 MRTS70
checkpoint | 16 - Compaction of Concrete
label | ○ The compaction for concrete other than for concrete to be placed under water and for no-fines concrete shall be deposited in horizontal layers not more than 400mm thick. Compaction of concrete shall commence immediately after deposition by using high frequency internal vibrators supplemented as required by external form vibrators.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 15.6.2 MRTS70
checkpoint | 17 - Removal of formwork
label | ○ Forms, falsework and centring shall remain in position until the times stated in Table 15.8 MRTS70 elapsed after completion of concreting.
label | — — — — — — — — — — — — — — — —
label | Exposure Classification ¦¦ Minimum Form Retention (hours)
label | — — — — — — — — — — — — — — — —
label | A ¦¦ 48
label | B1, B2 ¦¦ 72
label | C1, C2 ¦¦ 120
label | — — — — — — — — — — — — — — — —
label | ○ For structural concrete 70% has been reached of the 28 day strength characteristic and 7 days no loading should applied
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 6
label | Reference - Clause 15.8 MRTS70
holdpoint | HOLD POINT
checkpoint | 19 - Early loading
label | ○ Concrete shall not be loaded until seven days has elapsed from placement of all elements within the load path, including foundations.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 15.9 MRTS70
checkpoint | 20 - Concrete Curing
label | ○ Contractor shall submit to the Administrator curing procedures 2 weeks prior to the first concrete pour. Curing shall continue for a minimum period of seven days. If forms are removed in less than seven days, curing of the formed surface shall commence within one hour of stripping, unless otherwise specified in Clause 15.12.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - MILESTONE
label | Reference - Clause 15.11.1 MRTS70
checkpoint | 21 - Rectification of non-compliant surfaces
label | Where surfaces fail to meet the requirements of Clause 15.12, the following actions shall be undertaken:
label | a) All pockets or honeycombed areas shall be cleaned out to sound concrete.
label | b) Small voids, not more than 150 mm in lateral dimensions or 20 mm deep, shall be filled with a registered repair mortar, vibrated as necessary. The surface of the patches shall be finished flush with the adjacent formed surface.
label | c) Large voids shall be formed and filled with vibrated concrete of the same mix design. An effective bonding agent in the mix and on the interface shall be used.
label | d) The repaired area shall be cured in accordance with Clause 15.11
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - WITNESS POINT
label | Reference - Clause 15.12.2 MRTS70
checkpoint | 22 - Surface Dressing of Concrete
label | ○ Procedures shall be established for surface dressing of concrete and shall comply to the standards established as per MRTS70
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 15.12 MRTS70
checkpoint | 23 - Construction Joints
label | ○ Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 7
label | Reference - Clause 15.13 MRTS70
holdpoint | HOLD POINT
section | Requirements for precast and precast prestressed concrete
checkpoint | 24 - Placing and compacting concrete
label | No concrete shall be placed in the Works until:
label | a) the mix design has been approved by the Administrator,
label | b) the registration status of the precaster has been confirmed, and
label | c) any project-specific requirements have been addressed regarding placement and curing.
label | Acceptance Criteria & Frequency (Project Specific) - Approval See HOLD POINT 5
label | Check Item - HOLD POINT 8
label | Reference - Clause 16.5.1 MRTS70
holdpoint | HOLD POINT
checkpoint | 25 - Rectification of non-compliant surfaces
label | Where surfaces fail to meet the requirements of Clause 16.8, the following actions shall be undertaken:
label | a) All pockets or honeycombed areas shall be cleaned out to sound concrete.
label | b) Small voids, not more than 150 mm in lateral dimensions or 20 mm deep, shall be filled with a registered repair mortar, vibrated as necessary. The surface of the patches shall be finished flush with the adjacent formed surface.
label | c) Large voids shall be formed and filled with vibrated concrete of the same mix design. An effective bonding agent in the mix and on the interface shall be used.
label | d) The repaired area shall be cured in accordance with Clause 16.7
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - WITNESS POINT
label | Reference - Clause 16.8.2 MRTS70
checkpoint | 26 - Construction Joints
label | ○ Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer.
label | Acceptance Criteria & Frequency (Project Specific) - Approval See HOLD POINT 7
label | Check Item - HOLD POINT 9
label | Reference - Clause 16.9 MRTS70
holdpoint | HOLD POINT
section | Normal Class Concrete
checkpoint | 27 - Long distance travel and extended placement times
label | ○ Where travel times are, by necessity, longer than 90 min as listed in AS 1379 Clause 4.2.5, a procedure for long-distance travel or extended placement times shall be submitted to the Administrator for approval six weeks before concreting begins.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - MILESTONE
label | Reference - Clause 17.6.1 MRTS70
checkpoint | 28 - Falsework
label | ○ Falsework shall conform to AS 3610. The design and erection of falsework, the method of founding or supporting the falsework and the time, order and manner of its release shall all require approval of the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 10
label | Reference - Clause 17.10 MRTS70
holdpoint | HOLD POINT
checkpoint | 29 - Formwork
label | ○ All formwork shall be subject to inspection and approval by the Administrator. Formwork shall conform to AS 3610 and provide a Class 2 AS 3610 surface finish, except as otherwise specified.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 11
label | Reference - Clause 17.11 MRTS70
holdpoint | HOLD POINT
checkpoint | 30 - Placing and compacting concrete - General
label | No concrete shall be placed in the Works until:
label | a) the formwork and reinforcement have been inspected, and
label | b) all foreign material has been completely removed from the forms.
label | ○ The Administrator may revert this Hold Point to a Witness Point.
label | ○ The placing operation shall be conducted in the presence of the Administrator Witness and the Contractor shall give at least 24 hours notice to the Administrator of the time that placing shall start.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 12 / WITNESS POINT
label | Reference - Clause 17.12.1 MRTS70
holdpoint | HOLD POINT
checkpoint | 31 - Removal of formwork
label | ○ For cast-in-situ concrete, forms, falsework and centring shall remain in position until 72 hours has elapsed. Precast concrete shall not be removed from the formwork or formwork stripped until 40% of f’c is attained
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 13
label | Reference - Clause 17.17 MRTS70
holdpoint | HOLD POINT
checkpoint | 32 - Formed surfaces exposed to view
label | Following the removal of formwork the following operations shall be carried out to the standard approved by the Administrator:
label | a) all fins and other unwanted projections shall be ground off to provide a smooth surface.
label | b) where specified in the Drawings, surfaces shall achieve the required surface finish to AS 3610.
label | c) where surface finish is not specified in the Drawings, a Class 2 surface finish to AS 3610 is required. Repairs shall be a Witness Point
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - WITNESS POINT
label | Reference - Clause 17.18.1 MRTS70
checkpoint | Final Verification
note | Doval Representative
textbox | Print Name:
date | Date:
note | Administrator
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 04.00 - Back Fill | itp |  |  |  |  | 04.00 - Back Fill
section | Details
checkpoint | 1 - Document Submission
label | ○ As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
label | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management
label | Check Item - Check Item
checkpoint | 2 - Traffic and Safety Controls
label | ○ Traffic and safety controls are in place (eg. PPE, daily plant check)
label | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
label | Check Item - Check Item
checkpoint | 3 - Material Conformance:
label | ○ Prior to incorporating any backfill material into the works, the contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrates the source meets the specified material requirements.
label | Check Item - Hold Point
label | Reference - Clause 19.1 MRTS04
holdpoint | HOLD POINT
checkpoint | 4 - Earth Fill Material
label | ○ Earth backfill material shall comply with the requirements of earth fill material Class A1, Class A2 or Class B specified in cl 14.2.2 except that 100% of the material shall pass 25.0mm test sieve.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 19.2.2 MRTS04
checkpoint | 5 - Select Backfill Material
label | ○ Select backfill material shall be gravel or loam and shall have material properties as specified in Table 19.2.3
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 19.2.3 MRTS04
checkpoint | 6 - Geotextile
label | ○ Geotextile shall be a material of the appropriate strength class and filtration class complying with the requirements of MRTS27 Geotextiles.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 14.2.6 MRTS04
checkpoint | 7 - Construction General
label | Check the following requirements;
label | ○ Embankment is constructed to the shapes, zones and other requirements shown on the drawings or otherwise as specified. (Refer to Clause 9.3 of Annexure MRTS04.1) Fill material shall be placed in zones as shown in Figure 14.3.1
label | ○ Earth fill material is to be placed so that it is homogeneous.
label | ○ Embankment fill material shall be either earth fill material or rock fill.
label | ○ Care shall is taken when sourcing fill material so that sufficient Class A and Class B materials are available to complete the embankment in accordance with the requirements of this standard.
label | ○ The method of construction employed shall be the compacted layer method for suitable material placed in an embankment within a height 600mm below subgrade level.
label | ○ Compaction Standard shall be as specified in Clause 15.
label | ○ Permanent embankment batters shall be finished in accordance with Clause 16
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 14.3.1 MRTS04
checkpoint | 8 - Earth Fill Homegenous and Zoned Embankments
label | ○ Cover for zoned embankments, depened on embankmnet height to subgrade level and rainfall zone. Unless shown otherwise in Clause 9.4 of MRTS04.1, the requirements shall be given in Tabe 14.3.1. Zone definitions for the cross section and rainfall are shown in Figure 14.3.1 and Table 15.3(c)
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 14.3.1 MRTS04
checkpoint | 9 - Geotextile at changes in material type
label | ○ Geotextiles requirement shall comply with MRTS27 Geotextiles (Seperation and Filtration) shall be installed at the interface where fill material changes from mechanical interlock to compacted layer method.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 14.3.2 MRTS04
checkpoint | Final Verification
note | Doval Representative
textbox | Print Name:
date | Date:
note | Administrator
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 05.00 - General Excavations | itp |  |  |  |  | 05.00 - General Excavations
section | Details
checkpoint | 1 - Survey Set Out
label | ○ Survey setout complete. Surveyor has setup reference points for width and depth of excavations.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
checkpoint | 2 - All Excavations
label | ○ General Excavation and earthworks activities shall be completed in accordance with MRTS04 General Earthworks
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 13 MRTS04
checkpoint | 3 - Construction requirements
label | ○ It shall be the sole responsibility of the Contractor to prove that material is Unsuitable Material as defined in Clause 9.2.
label | ○ Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, notify the Administrator and provide any test results required to justify such a claim.
label | ○ Within 24 hours of the above notification, the Administrator will advise the Contractor of the required treatment, if any, and the extent of such treatment.
label | ○ Methods of excavation of Unsuitable Material shall be in accordance with the requirements of Clause 13. Excavated material shall be used or disposed of in accordance with Clause 11.
label | Acceptance Criteria & Frequency (Project Specific) - Notify
label | Check Item - HOLD POINT 3
label | Reference - Clause 9.4 MRTS04
holdpoint | HOLD POINT
checkpoint | 4 - Testing and reporting of acid sulfate soils
label | ○ Testing for acid sulfate potential and reporting of test results shall be carried out on all excavated material and exposed cuttings on the site which could reasonably be expected to have a possible acid sulfate potential.
label | ○ The testing frequency and reporting shall be as detailed below:
label | ○ Visual testing undertaken by trained personnel shall be continuous throughout the earthworks phase of the Contract and shall be applied to all such areas on which work is performed including Borrow Areas.
label | b) Field pH testing for both actual and potential Acid Sulfate Soils shall be carried out (on the same soil sample) on all Borrow Material to be imported to the Works and all material excavated or exposed in the Works in areas specified as having acid sulfate potential. A minimum of one test per soil type shall be carried out. The results shall be documented and reported to the Administrator prior to such materials being used on the Site. Hold Point 5
label | c) Where materials test positive to actual or potential acid sulfate contamination in the field, the Administrator shall be notified immediately. Such soils shall not be used on the Site until the results of subsequent quantitative laboratory testing negates the results of the field testing. Quantitative laboratory testing shall be in accordance with the National Acid Sulfate Soils
label | ○ Guidance: National acid sulfate soils identification and laboratory methods manua
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Hold Point
label | Reference - Cl 10.4 MRTS04
holdpoint | HOLD POINT
checkpoint | 5 - Unsuitable Material below the lines of cuttings:
label | ○ Material which deemed unsuitable as per cl 9.2 below the finished lines and levels of cuttings, shall be removed and disposed of in accordance with the provisions of cl 9.4. backfill material to be finished surface level with appropriate fill with reference to cl 18 & 19
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Cl 13.3.2.2 MRTS04
checkpoint | 6 - Bottom of Excavation:
label | ○ When the level of excavation has reached subgrade level, contractor shall carry out the provisions of cl 18.3.3 and cease excavation until the subgrade treatment type has been determined with cl 18.3.3
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Cl 13.3.2.1 MRTS04
checkpoint | 7 - Pre-Splitting:
label | ○ Batters specified in cl 8 of annexure MRTS04.1 and batters of rock cuttings with a slope of 2V to 1H or steeper shall be pre-split prior to burden blasts to ensure protection. Spacing of pre-split dill holes shall not exceed 1000m c/c
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Cl 13.3.2.3 MRTS04
checkpoint | 8 - Berm Drains
label | ○ Berm drains shall be constructed where shown on the drawings. Unless shown otherwise, berm drains shall have a nominal depth of 100mm and shall be two metres wide. Berm drains shall be concrete lined in accordance with MRTS03.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 13.3.2.5
checkpoint | 9 - Confined Excavation:
label | ○ Protection of Excavations.
label | ○ Contractor shall take necessary precautions to protect an excavation and all personnel and equipment in or about an excavation.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 13.3.3.3 MRTS04
checkpoint | 10 - Confined Excavation: - Bottom of Excavation
label | ○ The material in the bottom of confined excavations shall comply with the density requirements of Clause 15. Where the insitu material does not comply, it shall be compacted to a depth of at least 150 mm in accordance with the requirements of Clause 15.
label | ○ Where precast concrete items (end structures, walls, kerbs, kerb and channels etc) are to be placed in excavation, a 50 mm layer of bedding material complying with the requirements of Clause 19.2.6 shall be placed and compacted to provide continuous, even support to the structure.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 13.3.3.4 MRTS04
checkpoint | 11 - Excavation for Load Bearing Footings
label | ○ Excavation for foundations of structures shall be carried out to the dimensions and depths shown on the drawings.
label | ○ When adequate material has been reached at or below the depth shown on the drawings, the foundation surface shall be trimmed toa horizontal plane or horizontal steps, completely dewatered and presented for final inspection by the Contractor's RPEQ Geotechnical Engineer. No work which will cover the surface foundation shall proceed until the Contractor RPEQ and Administrator approval. The Contractor shall give the Administrator 3 days notice of such inspection.
label | ○ If the foundation surface has deteriorated since the time the foundation was approved and before blinding concrete or backfill material has been placed, additional material shall be removed until competent material is reached as described above and then Hold Point 6 shall be re-released
label | Acceptance Criteria & Frequency (Project Specific) - Notify
label | Check Item - HOLD POINT 6 / WITNESS POINT
label | Reference - Clause 13.3.4.1 MRTS04
holdpoint | HOLD POINT
checkpoint | 12 - Excavation for Pile Caps - Excavationf or pile caps shall be caried out to the dimensions and levels shown on the drawings.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 13.3.4.2 MRTS04
checkpoint | 13 - Special Requirements for Culverts
label | ○ Widths excavation for culverts shall not be greater than those specified in SD1359
label | ○ The base material shall comply with the density requirements of Clause 15. If it is not complying the insitu
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 13.3.6 MRTS04
checkpoint | 14 - Dewatering Excavation - Shall be carried in respect to the Environmental Management Plan. Under no circumstances shall water be disposed of to sanitary sewers.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 13.3.8 MRTS04
checkpoint | 15 - Supplementary Requirements:
label | Where specified in the drawings the following work operations shall be completed in accordance with cl 13.1 of annexure MRTS04.1.
label | — Trimming batters, removal and disposal of any material including boulders,
label | — Excavation, remmoval and disposal of any existing retaining structures,
label | — Removal and disposal of loosened material as a result of scaling shall be completed.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 13.1 MRTS04.1
checkpoint | Final Verification
note | Doval Representative
textbox | Print Name:
date | Date:
note | Administrator
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 06.00 - Stripping of Topsoil | itp |  |  |  |  | 06.00 - Stripping of Topsoil
section | Details
checkpoint | 1 - Survey Set Out
label | ○ Survey setout complete. Surveyor has setup reference points for width and depth of excavations.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
checkpoint | 2 - Topsoil stripping dimensions
label | ○ Where Site topsoil is required to be supplied in accordance with MRTS16 Landscape and Revegetation Works, topsoil shall be stripped from the Site at a 75 mm (± 25mm) depth, or from areas and depths as specified in Clause 2 of Annexure MRTS04.1.
label | ○ Average depth - 300mm
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.2 MRTS04 Clause 2 MRTS04.1
checkpoint | 3 - Material considered suitable for use as topsoil
label | ○ Soil stripped from the Site which is considered suitable for use as manufactured site topsoil shall be tested and ameliorated in accordance with in MRTS16 Landscape and Revegetation Works.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.3
checkpoint | 4 - Stripping to stockpile
label | ○ Material considered suitable for use as topsoil in accordance with Clause 8.3 shall be stripped from the Site in a separate operation to any other clearing and/or stripping operation. Stripped material shall be stockpiled in the locations shown on the drawings, as stated in Clause 2.2 of Annexure MRTS04.1. Material shall not be stockpiled within the drip lines of existing plants to be retained.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.4.1
checkpoint | 5 - Surplus material
label | ○ Surplus material and material considered to be not suitable for use as topsoil in accordance with Clause 8.3 shall be assessed for use as fill or deemed to be Unsuitable Material and disposed of in accordance with Clause 11.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.4.2 MRTS04
checkpoint | 6 - Stripping limitations
label | ○ Material shall not be removed from within drip lines of existing plants to be retained except where this would otherwise result in Unsuitable Material being left beneath embankments. The root systems of existing plants to be retained shall be preserved wherever practical.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.4.3 MRTS04
checkpoint | 7 - Stockpiling of topsoil
label | Wherever practical, topsoil shall be transferred directly to placement as planting media. Where stockpiling of topsoil is required, it shall be carried out in a manner which ensures that the properties of the topsoil are not permitted to degrade such that it becomes unsuitable as topsoil.
label | To assist preservation of topsoil, the Contractor shall include the following provisions in the management of topsoil stockpiles:
label | a) limiting the height of stockpiles to three metres
label | b) limiting the width of the base of stockpiles to 10m
label | c) adopting batter slopes, protective covers and drainage which reduce potential for erosion and / or segregation
label | d) limiting the period of stockpiling to a minimum practical time
label | e) where stockpiling for greater that 12 months, the stockpile shall be revegetated with grass to provide erosion and preserve the physical and chemical properties of the topsoil, and
label | f) carrying out herbicide spraying or other treatment of the stockpile at intervals required to prevent weed growth and ensure the stockpile faces are weed-free prior to use.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.4.4 MRTS04
checkpoint | Final Verification
note | Doval Representative
textbox | Print Name:
date | Date:
note | Administrator
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 10.00 - Unbound Pavements | itp |  |  |  |  | 10.00 - Unbound Pavements
section | Details
checkpoint | 1 - Define lot size. Maximum lot size for unbound pavements is 5000 tonnes for supply and "A single continuous layer completed in one day's production" for construction
label | Acceptance Criteria & Frequency (Project Specific) - Qty per lot
label | Check Item - Milestone
label | Reference - MRTS05.1 Table A1
checkpoint | 2 - Copies of current Quarry Registration Certificate (Type 1, 2 or 3) or quarry assessment (Type 4) forwarded to the Administrator at least 7 working days before material deliveries to the stockpile / pavement are to commence.
label | Acceptance Criteria & Frequency (Project Specific) - Submission of Registration Certificate per quarry
label | Check Item - Milestone
label | Reference - MRTS05 Cl.6.2 & 6.3
checkpoint | 3 - Acceptance of construction procedure for unbound pavement works
label | Acceptance Criteria & Frequency (Project Specific) - Approval of procedure by from the Administrator
label | Check Item - Hold Point 1
label | Reference - MRTS05 Cl 5.2.1
holdpoint | HOLD POINT
checkpoint | 4 - The written permission from the Administrator to use the quarry or source is required prior to material being supplied to or used in the works
label | Acceptance Criteria & Frequency (Project Specific) - Written Permission from Administrator
label | Check Item - Hold Point 2
label | Reference - MRTS05 Cl.6.1
holdpoint | HOLD POINT
checkpoint | 5 - If more than 1 grading envelope is specified in clause 2.1 of Annexure MRTS05.1 for a single location, the contractor shall notify in writing, at least two days before the commencement of the production of materials for the works, which of the grading envelopes will be used.
label | Acceptance Criteria & Frequency (Project Specific) - Submission of test results per material type
label | Check Item - Hold Point 3
label | Reference - MRTS05 Cl7.2.4
holdpoint | HOLD POINT
checkpoint | 6 - Layer Thickness between 75mm and 250mm
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | ○ Layer Thickness: 75mm - 250mm
label | Check Item - Check Item
label | Reference - MRTS05 Table 8.3.3
checkpoint | 7 - Relative Dry Density Requirements - C.V of RDD >= 100% for Type 2/3/4 Materials
label | Acceptance Criteria & Frequency (Project Specific) - C.V of RDD >= 100% (1 test / 500m2, min 1 / prouction day)
label | Check Item - Check Item
label | Reference - MRTS05 Table 8.3.3
checkpoint | 8 - Moisture content such that the degree of saturation is less than 65%
label | Acceptance Criteria & Frequency (Project Specific) - S < 65% (1 test / 1000m2, min 4 / lot)
label | Check Item - Check Item
label | Reference - MRTS05 Table 8.2.4.1
checkpoint | 9 - No visible segregation of material. Partical Size Distribution Q103A.
label | Acceptance Criteria & Frequency (Project Specific) - As directed by the Administrator
label | Check Item - Check Item
label | Reference - MRTS05 Table A3
checkpoint | 10 - Geometric Tolerances: Vertical tolerance of ±15 mm
label | Acceptance Criteria & Frequency (Project Specific) - ±10mm when covered by AC
label | ○ ±15 mm in all other cases (1 test / 25m)
label | Check Item - Check Item
label | Reference - MRTS05.1 Cl.8.4.4.3
checkpoint | 11 - Geometric Tolerances: Horizontal tolerance of ±50mm, or -50 / +250mm for pavement edges not adjacent to any other section of pavement and not adjacent to any structure or adjoining road
label | Acceptance Criteria & Frequency (Project Specific) - ±50mm, or -50 / +250mm if not adjacent to adjoining pavement (1 test / 25m)
label | Check Item - Check Item
label | Reference - MRTS05 Cl.8.4.4.2
checkpoint | 12 - Each unbound pavement layer shall be tested for perceptable surface deformation by 'proof rolling' the pavement, in the presence of the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual, Continuous testing
label | Check Item - Witness Point
label | Reference - MRTS05 Cl.9.4.7
checkpoint | 13 - Additional Geometrics (final layer only) - The maximum deviation from a straight-edge on any layer shall be 5mm.
label | Acceptance Criteria & Frequency (Project Specific) - 5mm deviation from straight edge (1 test / 10m L&R)
label | Check Item - Check Item
label | Reference - MRTS05 Cl.8.4.5
checkpoint | 14 - Additional Geometrics (final layer only) - The crossfall shall not depart from the corresponding crossfall shown in the Contract by more than 0.5% absolute.
label | Acceptance Criteria & Frequency (Project Specific) - 0.5% deviation from crossfall (1 test / 25m)
label | Check Item - Check Item
label | Reference - MRTS05 Cl.8.4.4.4
checkpoint | Acceptance of lots
label | Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until Hold Point 6:
label | a) all testing has been completed
label | b) the surface finish of the layer complies with the requirements of Clause 8.3.5
label | c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator
label | d) the layer has been presented to the Administrator for inspection, and
label | e) the As Constructed Survey requirements of the lot have been met, as specified in MRTS56 Construction Surveying and notice of such Works has been provided to the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Check & verify
label | Check Item - Hold Point 6
label | Reference - MRTS05 Cl.9.5.1
holdpoint | HOLD POINT
checkpoint | 15 - The finished surface of any unbound pavement layer shall: - be hard and homogenous in apperance
label | — not have any loose, segregated or contaminated areas
label | — have the coarse particles slightly exposed
label | — not be affected by delamination, and
label | — not visibly deflect under load when proof rolled in accordance with Cl 9.4.6
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS05 Cl.9.1.3
checkpoint | Final Verification
note | Responsible Officer
textbox | Print Name:
date | Date:
note | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 12.00 - Hand Place Concrete Paving | itp |  |  |  |  | 12.00 - Hand Place Concrete Paving
section | Details
checkpoint | 1 - Material Requirements
label | ○ Concrete shall comply with Clause 6.1 of MRTS03
label | ○ Concrete to be pattern finished shall have course aggregate of size not greater than 20mm
label | ○ Colouring agent shall be a colour curing compound from a suitable manufacturer
label | ○ Compressible packing shall be bitumen impregnated fibre board or other suitable packing
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 30.2 MRTS03
checkpoint | 2 - Construction
label | ○ Hand placed material shall be in accordance with specified drawings
label | ○ If material other than rock on or against paving shall be compacted in accordance with MRTS04
label | ○ Concrete paving shall not be constructed before ducting, pits, stormwater drainage and any bases for traffic materials.
label | ○ Expansion joints to be at regular intervals of 20m longitudinally and 6mm thickness compressible packing
label | ○ Contraction joints shall be installed at intervals not exceeding 5m longitudinally and transversely by forming 40mm deep grooves and not more than 6mm wide
label | ○ Concrete shall be cured for a period of 7 days before commencement of further operations
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 30.3 MRTS03
checkpoint | 3 - Colouring and Finishing
label | ○ Where specified, concrete paving shall be coloured. The surface shall be uniform in colour
label | ○ Where specified, the surfaces of concrete paving shall be pattern finished. Areas not to be patterned finished shall be lightly broomed to produce uniform non-slip surfaces
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 30.4 MRTS03
checkpoint | 4 - Vertical Tolerances
label | ○ A neat joint shall be made neatly to adjacent work.
label | ○ The finished height levels shall not vary from the drawings with more than ± 10 mm
label | ○ Gaps under straight edges shall be placed 3m long anywhere on finished surface and shall not exceed 5mm.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 30.5 MRTS03
checkpoint | Final Verification
note | Responsible Officer
textbox | Print Name:
date | Date:
note | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 13.00 - Removal/Demolition of Culvert End Structures | itp |  |  |  |  | 13.00 - Removal/Demolition of Culvert End Structures
section | Details
checkpoint | 1 - General - Where culverts are to be removed or demolished are to be under contract
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 9.1 MRTS03
checkpoint | 2 - Description
label | ○ Culverts and culvert end structures shall be removed or demolished where specified in the drawings
label | ○ If existing culvert components are to be removed and re-used, they shall be removed and stacked in a manner which avoids damaging the components
label | ○ Removed components which are not to be salvaged, nor reused, shall be removed from the Site and disposed of
label | ○ Components listed in clause 2.1 of annexure MRTS03.1 are to be salvaged intact and delivered and stored as per Clause 2.2 of Annexure MRTS03.1
label | ○ Backfilling of culvert and end structure is to be reinstated the area to a safe and free draining state.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 9.2 MRTS03
checkpoint | Final Verification
note | Responsible Officer
textbox | Print Name:
date | Date:
note | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 14.00 - End Structures to Culverts including Grouted rock pitching | itp |  |  |  |  | 14.00 - End Structures to Culverts including Grouted rock pitching
section | Details
checkpoint | 1 - Cast Insitu Material Requirements
label | ○ Concrete shall comply with Clause 6.1
label | ○ Steel reinforcement shall comply with MRTS71
label | ○ Rock masonry material shall comply with Clause 39
label | ○ Concrete masonry shall comply with Clause 51
label | ○ Grouted rock pitching shall comply with Clause 40
label | ○ Steel Wire mattress material shall comply with Clause 43
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 15.2 MRTS03
checkpoint | 2 - Cast Insitu Construction
label | ○ Cast insitu end structures such as headwalls, wingwalls, aprons, and kerbs to culverts shall be provided in the locations specified in the drawings. Unless otherwise specified in the drawings, cast insitu concrete end structures to culverts shall comply with the details shown on Standard Drawings 1304, 1305 for pipe culverts and 1240, 1250 and 1260 for box culverts as applicable.
label | ○ Where insitu material on or against which structures are to be constructed is other than rock, the material shall be compacted as for material at the bottom of excavations in accordance with MRTS04 General Earthworks.
label | ○ Concrete shall be constructed to comply with Clause 6.1.
label | ○ Endwalls, wingwalls and concrete aprons may be constructed without foundation bedding if specified on the drawings. Endwalls and wingwalls shall be separated with expansion gap unless otherwise as specified on the drawings. Construction of aprons shall include the integral cut-off walls
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 15.3 MRTS03
checkpoint | 3 - Grouted rock pitching Material Requirements
label | ○ Rock (other than smaller-size rock required for wedging) shall be of size not less than 150 mm and not greater than 250 mm. Where rock pitching is constructed for batter protection, the toe rocks shall be of size not less than 250 mm and not greater than 350 mm.
label | ○ The rock shall be sound rock which does not disintegrate in water and which has been selected to match the existing rock pitching where appropriate.
label | ○ Cement mortar for bedding shall consist of one part by volume of Type GP cement to three parts by volume of clean fine sand with only sufficient water added to achieve a plastic-like texture. Hydrated lime may be incorporated into the cement mortar to the extent of one part hydrated lime to 10 parts of Type GP cement (loose volume). Hydrated lime shall be an addition to, and not a replacement for, the cement. The mortar shall be able to retain its shape and not flow like a liquid. Materials shall comply with MRS70.
label | ○ Sand bedding shall comply with Clause 19 of MRTS04 General Earthworks.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 35.2 MRTS03
checkpoint | 4 - Grouted rock pitching Construction
label | ○ Grouted rock pitching shall be constructed in the locations specified by and in accordance with the drawings.
label | ○ Where insitu material on or against which the grouted rock pitching is to be constructed is other than rock, the material shall be compacted as for material at the bottom of excavations in accordance with MRTS04 General Earthworks.
label | ○ The first row of rocks shall be placed on a sand bedding of minimum thickness 50 mm
label | ○ Rocks shall be placed so as to form irregular joints. All rocks shall be interlocked and wedged with smaller-size rock, as necessary, so that no single rock may be easily dislodged, and no large voids remain between rocks. All rock pitched faces shall be stable prior to grouting with mortar.
label | ○ The voids between rocks at the exposed surface shall be filled with cement mortar. The mortar shall be used within one hour of mixing and shall not be re-tempered.
label | ○ Exposed surfaces shall have a relatively smooth, even, neat appearance. Where rock pitching is to be trafficable, care shall be taken to provide a smooth running surface.
label | ○ Rock surfaces shall be cleaned free of any coating of cement mortar exposing the faces of the rocks.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 35.3 MRTS03
checkpoint | Final Verification
note | Responsible Officer
textbox | Print Name:
date | Date:
note | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 15.00 - Supply, Installation of precast and preformed culvert components | itp |  |  |  |  | 15.00 - Supply, Installation of precast and preformed culvert components
section | Details
checkpoint | 1 - Material Requirements
label | ○ All material supplied shall be proprietary products and comply with all requirements of Clause 11.2. Concrete box culvert components and spanning slabs shall comply with MRTS24 Manufacture of Precast Concrete Culverts.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - HOLD POINT 1
label | Reference - Clause 11.2 MRTS03 MRTS24
holdpoint | HOLD POINT
checkpoint | 3 - Construction Proceedure
label | ○ At least 14 days prior to construction, the Contractor shall submit their procedure for excavation, installation and backfilling
label | ○ This procedure shall include:
label | a) Earthworks Construction Procedure (refer Clause 5 of MRTS04 General Earthworks).
label | b) Procedure for lifting and installing culvert elements.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - HOLD POINT 2
label | Reference - Clause 11.3.1 MRTS24
holdpoint | HOLD POINT
checkpoint | 3 - Precast Culvert Construction and Conformance
label | ○ All Precast culverts shall be constucted and conform to MRTS24. All relevant documents in relation ot the constuction process shall be reviewed and verified prior to installation.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - HOLD POINT 3
label | Reference - Clause 4.2 MRTS24
holdpoint | HOLD POINT
checkpoint | 5 - General Constructions
label | ○ The construction of culverts shall not commence until the check of the construction procedure has been carried out. The construction loads on the culvert shall be determined.
label | ○ Precast and/or preformed culvert components shall be installed in the locations and in accordance with the details shown in the drawings.
label | ○ All drainage structures shall be marked with indelible ink on the inside face with the name of the Manufacturer and month and year of manufacture.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - HOLD POINT 4
label | Reference - Clause 11.3.1 MRTS03
holdpoint | HOLD POINT
checkpoint | 6 - Excavation - Excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earthworks
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 11.3.1 MRTS03
checkpoint | 7 - Bedding of Culverts
label | ○ Foundation bedding and haunch zone materials shall be placed in accordance with Clause 19 of MRTS04 General Earthworks.
label | ○ The foundation bedding shall provide continuous, even support to the culvert components.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 11.3.2 MRTS03
checkpoint | 8 - Laying and jointing culvert components
label | ○ Where possible, laying of culvert components shall commence at the outlet end of the culvert and progress to the inlet end.
label | ○ Components shall be selected and arranged to give best fit.
label | ○ The ends of components shall be free of any foreign matter at the time of jointing.
label | ○ In butt and flush joints, the culvert components shall abut one another, and a bandage cover shall be installed on the outer surfaces to seal the joints.
label | ○ The bandage cover shall consist of:
label | a) one layer of non-woven fabric
label | b) three layers of woven fabric, or
label | c) a plastic or natural rubber band.
label | ○ Fabric covers shall have a width sufficient to overlap adjacent components by not less than 45 mm, and shall not be applied until the ambient temperature exceeds 15°C. Fabric covers shall not be wrinkled and shall adhere to the outer surfaces of the adjacent components. The ends of the fabric in the covers shall be secured in accordance with the manufacturer’s recommendations.
label | ○ Plastic or natural rubber covers shall be installed in accordance with the manufacturer’s recommendations.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 11.3.5 MRTS03
checkpoint | 9 - Special Requirements for Concrete Box Culvert Components
label | ○ Box culvert components shall generally be installed in accordance with the details shown on Standard Drawings 1250 and 1260 or project drawings.
label | ○ U-shaped units laid in the ‘legs down’ position on cast in place concrete bases shall be seated on to the bases using continuous cement mortar pads.
label | ○ Holding down anchors shall also be installed to retain the units in position in accordance with the details shown on Standard Drawings 1250 and 1260 or project drawings
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 11.3.6 MRTS03
checkpoint | 10 - Cutting culvert components
label | ○ Cutting operations shall provide neat end surfaces.
label | ○ The cut surfaces of reinforced concrete culvert components shall be given two coats of a surface tolerant epoxy.
label | ○ The cut surfaces of steel culvert components shall be given two coats of zinc-rich organic priming paint as specified in AS 3750.9. The coats shall have a combined thickness at least equivalent to the thickness of the galvanised coating. Each coat shall overlap the adjacent uncut surfaces by not less than 25 mm.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 11.3.9 MRTS03
checkpoint | 10 - Backfilling of Culverts
label | ○ Backfilling of culverts shall be carried out in accordance with Clauses 15 and 20 of MRTS04 General Earthworks. To determine testing lots for compaction, a change in compaction equipment or methodology shall necessitate a division of lots.
label | ○ Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - HOLD POINT 5
label | Reference - Clause 11.3.10 MRTS03
holdpoint | HOLD POINT
checkpoint | Final Verification
note | Doval Representative
textbox | Print Name:
date | Date:
note | Administrator
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 17.00 - Subsoil Drains | itp |  |  |  |  | 17.00 - Subsoil Drains
section | Details
checkpoint | 1 - General
label | ○ Clause 22 applies to the provision of subsoil drains. The types and locations of subsoil drains to be used shall be shown on the drawings and consist of one of the following types and shown in Figure 22.1.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 22.1 MRTS03
checkpoint | 2 - Material requirements
label | ○ Perforated drainage pipes used in Type B subsoil drains and associated fittings and jointing procedures shall comply with AS 2439.1. The pipe shall have a minimum diameter of 100 mm.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 27.2.2 MRTS03
checkpoint | 3 - Construction
label | ○ Where type cross-sections for subsoil drains are not included in the drawings, dimensions shall be in accordance with the requirements detailed in Figure 22.1.
label | ○ Subsoil drains shall be installed to the grades specified in the drawings. Where the grades are not specified on the drawings the minimum grades of 0.5% shall apply.
label | ○ The bottom of trenches shall be trimmed to provide constant longitudinal fall towards outlets. Drains shall be installed with a constant fall and shall not rise and fall within the trench.
label | ○ Subsoil drains shall be joined in accordance with the manufacturer’s recommendations.
label | ○ Where subsoil drains are constructed within the subgrade, they shall extend to the underside of the lowest pavement layer unless specified otherwise in the drawings.
label | ○ Where subsoil drains are constructed outside the subgrade edge point, the trench backfill material shall be placed to approximately 150 mm of the ground or finished surface and the remaining 150 mm filled with impervious material compacted as for embankment material in accordance with MRTS04 General Earthworks.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 22.3 MRTS03
checkpoint | 4 - Cleanout and outlet pipes
label | ○ Unperforated cleanout and outlet pipes and associated fittings and jointing procedures shall comply with AS/NZS 1254. The pipe shall have a minimum diameter of 100 mm.
label | ○ Clean-outs shall be located at the heads of all subsoil drains and at subsequent spacings not exceeding 60 m for Type B subsoil drains. Clean-outs shall be constructed in accordance with the details shown on Standard Drawing 1116.
label | ○ Clean-out pipes shall be joined to the subsoil drains using oblique tee or other proprietary connections.
label | ○ All cleanouts shall have caps installed.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 22.2.2 & Clause 22.3 MRTS03
checkpoint | 5 - Geotextiles
label | ○ Geotextiles used to surround backfill or wrap drains shall comply with MRTS27 Geotextiles (Separation and Filtration).
label | ○ Where an outlet, inlet, or clean-out pipe passes through the filter fabric, a separate piece of fabric of sufficient size shall be wrapped around the pipe and flared against the main fabric to provide an effective seal.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 22.2.4 & Clause 22.3 MRTS03
checkpoint | 6 - Trench backfill
label | — For Type B subsoil drains, backfill material shall be one of the followings:
label | ○ 20 mm or 10 mm nominal size drainage aggregate that conforms to MRTS04 General Earthworks, or
label | ○ 20 mm nominal size no fines concrete that conforms to MRTS70 Concrete.
label | — Trench backfill material shall be damp when placed in the trench. The material shall be carefully placed in layers not exceeding 200 mm loose thickness.
label | — Trench backfill material shall be compacted to achieve effective mechanical interlock between particles.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - Check Item
label | Reference - Clause 22.2.5 & Clause 22.3 MRTS03
checkpoint | 7 - Flushing - Once all items above have been completed, where directed by the Administrator, after the drains are constructed, they shall be flushed. Flushing shall continue until the outlet water is clean and flows consistently.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - WITNESS POINT
label | Reference - Clause 27.2.2 MRTS03
checkpoint | Final Verification
note | Doval Representative
textbox | Print Name:
date | Date:
note | Administrator
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 18.00 - Removal/Demolition of Kerbs Channel & Concrete Slabs | itp |  |  |  |  | 18.00 - Removal/Demolition of Kerbs Channel & Concrete Slabs
section | Details
checkpoint | 1 - Scope of Works
label | ○ Existing kerbs, channels, kerbs and channels, kerb crossings and concrete slabs shall be removed or demolished where specified in the Drawing.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 9.2 MRTS03
checkpoint | 2 - Damage to Adjacent Work
label | ○ No damage shall result to adjacent work
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 9.2 MRTS03
checkpoint | 3 - Joint to Existing
label | ○ Where part only of kerb, channel or slab is to be removed or where it joins existing has been either terminated at a joint or sawn to provide a clean joint. Any resulting excavations shall be backfilled to the surface finish level.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - Clause 9.2 MRTS03
checkpoint | Final Verification
note | Responsible Officer
textbox | Print Name:
date | Date:
note | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 19.00 - Cast insitu concrete kerb, channel, and kerb and channel | itp |  |  |  |  | 19.00 - Cast insitu concrete kerb, channel, and kerb and channel
section | Details
checkpoint | 1 - General - Concrete
label | ○ All insitu concrete kerb, channel, kerb and channel are provided in the locations specified in the IFC drawings.
label | ○ This does not apply to kerbs cast integrally with structures.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 3.1 & Clause 18.1 MRTS03
checkpoint | 2 - General material and construction requirements
label | ○ The concrete strength grade and concrete class shall be as specified in the IFC drawings.
label | ○ Construction joints shall be provided only as specified in the drawings and no construction joint specified in the drawings shall be omitted.
label | ○ Concrete mix designs are to be approved prior to any concrete works.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 20.3 MRTS03
checkpoint | 3 - Construction
label | ○ Where insitu material on or against which kerbs or channels are to be constructed is other than rock, the material has been compacted as for material at the bottom of excavations in accordance with MRTS04 General Earthworks. The ground surface shall be moistened just prior to placing concrete. Manually-placed concrete shall be in accordance with Clause 6.1. Exposed surfaces shall have a steel-trowelled finish.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 18.3 MRTS03
checkpoint | 2 - Set out & Excavation
label | ○ All kerb areas shall be set out by a surveyor in accordance with the IFC Drawings.
label | ○ Excavations shall be constructed to the shapes, lines, dimensions and other requirements shown on the IFC drawings.
label | ○ The bottom of excavations shall be trimmed to the tolerances specified in MRTS03 Clause 6 and any loose material removed from the surface.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 18.3 MRTS03
checkpoint | 3 - Compaction of Bottom of Excavation
label | ○ All Earth Fill Material shall be placed uniformly in layers. The allowable loose layer thickness for material compacted using the compacted layer between 150mm to 300mm (Table15.3(a)) and shall be compacted to a 95% Standard Compaction (Table 15.3(b)).
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - HOLD POINT
label | Reference - Clause 15.3 MRTS04
holdpoint | HOLD POINT
checkpoint | 2 - Subgrade
label | ○ The Subgrade shall be constructed and tested to Subgrade Level in accordance with the requirements of MRTS04.
label | ○ Subgrage layers shall be in accordance with the IFC Drawings
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Witness Point
label | Reference - MRTS04 Clause 18.3.1
checkpoint | 3 - Compaction of Subgrade - All subgrade materialsl shall be compacted and tested, a 97% Standard Compaction (Table 15.3(b)) is required
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - HOLD POINT
label | Reference - MRTS 04 Clause 15.3
holdpoint | HOLD POINT
checkpoint | 4 - Formwork
label | ○ All forms shall be set and maintained to line and level such that the finished concrete shall conform within the specified dimensional tolerances, and to the proper dimensions and contours as shown in the IFC Drawings .
label | ○ All forms shall be cleaned and coated with the lightest practical coating of release agent prior to pour.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - HOLD POINT
label | Reference - Clause 20.4 MRTS03
holdpoint | HOLD POINT
checkpoint | 5 - Pre Wetting - Wet the bedding material immediately before laying concrete without resulting in free water remaining on the surface.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - WITNESS POINT
label | Reference - Clause 20.5 MRTS03
checkpoint | 4 - Concrete Pour
label | ○ Manually-placed concrete shall be in accordance with MRTS03 Clause 6.1.
label | ○ Concrete strength grade and concrete class shall be as specified in the IFC drawings (N32/10).
label | ○ All concrete shall be tested in accordace with MRTS70
label | ○ Slump as per Table 11.3(a)
label | ○ The temperature of the concrete is less than 10°C or exceeds 35°C
label | ○ Concrete shall be placed and compacted within the times in MRTS70 Table 10.5 from the charging of the mixer.
label | ○ All Exposed surfaces shall have a steel-trowelled finish.
label | ○ The finished kerb, channel and/or kerb and channel shall be well compacted and shall have exposed surfaces free from voids and honeycombing
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Witness Point
label | Reference - MRTS 03 Clause 6.1, MRTS70 Clause 11
checkpoint | 5 - Expansion at Joints
label | ○ Expansion joints shall be installed at regular intervals not exceeding 20 m. The joints shall be constructed by installing 6 mm maximum thickness compressible packing in the full cross-section. Where relevant, joints shall be located to line up with expansion joints in adjacent structures.
label | ○ Compressible packing shall be bitumen impregnated fibre board
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 18.3 MRTS03
checkpoint | 4 - Contraction Joints
label | ○ Contraction joints between expansion joints shall be installed at regular intervals not exceeding 5 m. The joints shall be constructed by forming grooves 40 mm deep and not more than 6 mm wide in all exposed surfaces of the kerb, channel and/or kerb and channel. All grooves shall be normal to the top surface and square to the alignments of the kerb, channel and/or kerb and channel.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 18.3 MRTS03
checkpoint | 5 - Curing
label | ○ Concrete shall be cured for a period not less than seven days before any other roadworks operations are carried out adjacent to the kerb, channel or kerb and channel.
label | ○ The curing compound shall be applied using a fine spray at the rate stated on the certificate of compliance, or at a rate of 0.2 L/m² per coat, and two coats shall be applied at the full rate.
label | ○ The time between the first and second coat shall be in accordance with the manufacturer’s recommendation
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 15.11 MRTS 70
checkpoint | 4 - Tolerances
label | ○ The horizontal and vertical alignments shall vary by no than ± 10 mm from those specified. Alignments shall have smooth lines. The overall dimensions shall nowhere be less than that specified in the drawings and controlled by means of a sensor working to a control line.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 18.4 MRTS03
checkpoint | 5 - Water Test
label | ○ Where the longitudinal grade of channels <1%, a test shall be carried out by discharging water into the channel to check uniformity of flow along the channel. After the flow has ceased, water shall not pond to a depth of more than 5 mm in any section of the channel. The test shall be carried out as soon as possible after the concrete in the channel has hardened
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 18.5 MRTS03
checkpoint | Final Verification
note | Responsible Officer
textbox | Print Name:
date | Date:
note | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 23.00 - Road Furniture | itp |  |  |  |  | 23.00 - Road Furniture
section | Details
checkpoint | 1 - Demolition List
label | ○ The items of road furniture to be demolished and disposed of are listed in Clause 3 of Annexure MRTS14.1
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 7.2 MRTS14
checkpoint | 2 - Removal of Furniture / Footings
label | ○ Existing road furniture shall be demolished and removed in a manner which avoids damaging any adjacent work. All existing footings shall be removed.
label | ○ Resulting excavations shall be backfilled and finished so as to reinstate the area to a safe and free-drainingstate. Backfilling shall be carried out in accordance with the requirements of MRTS04 General Earthworks.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 7.3 MRTS14
checkpoint | 7 - Sign Substrate Material Requirements
label | ○ As Required Sign substrate shall be manufactured from aluminium except for Regulatory Parking Sign which shall be manufactured in reference to Clause 13.3.1.6 and Temporary Sign in reference to Clause 13.3.1.7
label | ○ Other materials may be considered but evidence of the full approval to be provided to the administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 3
label | Reference - Clause 13.3.1 MRTS14
holdpoint | HOLD POINT
checkpoint | 8 - Coatings
label | ○ The class of sign material for the legend and the background shall comply with Table 13.3.3.2.1 (Class 400)
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 13.3.3 MRTS14
checkpoint | 9 - Construction Footings for Road Sign Posts
label | ○ Posts for road signs shall generally be circular hollow section or rectangular hollow section in accordance with the details shown on Standard Drawing 1363
label | ○ Holes to be excavated to minimum size
label | ○ Anchor bolts for cantilever and gantry signs shall be assembled into the positioning template which shall be held firmly in place during placement of the concrete
label | ○ Concrete shall comply to MRTS 70
label | ○ Unreinforced concrete shall not be less than normal class 20/20 and reinforced concrete shall not be less than S32/20
label | ○ For fragile support posts, TMR approved proprietary bagged concrete with 28 day compressive strength of not less than 40MPa may be applied.
label | ○ Steel reinforcing shall comply with MRTS 71
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 14.3 MRTS14
checkpoint | 10 - Project Signs
label | ○ Installation, maintenance and removal of project signs will be in accordance with Clause 15.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 15 MRTS14
checkpoint | 11 - Erection of Signs
label | ○ Signs shall be erected at the locations in the design documents or where not indicated according to the Manual of Uniform Traffic Control Devices.
label | ○ Orientation of sign shall be in accordance with Clause 1.12.5.3 part 1 of the Manual of Uniform Traffic Control Devices.
label | Acceptance Criteria & Frequency (Project Specific) - Check, Verify & Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 14.4.1 MRTS14
checkpoint | 12 - Contractor's information signs
label | ○ The location, number and legends of these signs shall comply with TMR policy. Details of signs shall be submitted to the administrator at least 14 days prior to commencement of manufacture.
label | ○ Information signs shall not be manufactured until expiration of the 14-day period.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - MILESTONE/HOLD POINT
label | Reference - Clause 20.4 MRTS03
holdpoint | HOLD POINT
checkpoint | Final Verification
note | Doval Representative
textbox | Print Name:
date | Date:
note | Administrator
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 24.00 - Landscaping & Revegetation Works | itp |  |  |  |  | 24.00 - Landscaping & Revegetation Works
section | Details
checkpoint | 1 - Topsoil Requirements
label | Topsoil may be:
label | a) manufactured site topsoil, or
label | b) imported topsoil.
label | Manufactured site topsoil shall:
label | a) be manufactured from material stripped and stockpiled during clearing and grubbing operations in accordance with MRTS04 General Earthworks
label | b) be initially tested in accordance with Clause 8.1.2.1
label | c) be manufactured in accordance with Clause 8.1.2.2, and
label | d) be tested for compliance in accordance with Clause 8.1.2.3.
label | Imported topsoil shall:
label | a) be tested in accordance with Clause 8.1.2.1
label | b) meet the requirements of Form C – Topsoil Testing, and
label | c) be certified weed free.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 7.1.2 MRTS16
checkpoint | 2 - Soil Sampling
label | ○ Subsoil Sampling shall be conducted by a soil scientist with qualifications in accordance with Clause 6.2.
label | ○ Where an accredited soil scientist is unavailable in a remote location, soil sampling will be carried out under the direction and supervision of the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.1.1.1 MRTS16
checkpoint | 3 - Weed Control
label | ○ Prior to the commencement of other ground preparation operations, the site shall be in a weed free condition. A list of weed control procedures is stated in the clause.Weed removal is to be undertaken in accordance with the EMP-C in reference to Clause 3.1.2 Annexure MRTS16.1
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 8.3 MRTS16
checkpoint | 4 - Amelioration Agents
label | Soil wetting and water holding agents
label | Soil wetting agents (surfactants) shall:
label | a) have a life of at least three months from the time of application
label | b) reduce soil water repellence / hydrophobicity
label | c) reduce surface tension of soil particles
label | d) increase water penetration to soil, and
label | e) be free from matter toxic to plant growth.
label | Water holding agents shall:
label | a) have a life of at least six months from the time of installation
label | b) hold water equal to at least 200 times their own mass
label | c) be hydrated / activated prior to installation, and
label | d) be free from matter toxic to plant growth.
label | ○ Water holding agents shall be incorporated into the topsoil
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 7.2.5 MRTS16
checkpoint | 5 - Imported Turf
label | Turf shall:
label | a) have a minimum 30 mm depth of sod
label | b) be in a healthy condition
label | c) be free from prohibited or restricted biosecurity matter, pests, diseases and matter toxic to plant growth
label | d) show signs of active growth
label | ○ Turf species, turf grade and roll width shall be specified in Clause 3.3.1 of the Annexure MRTS16.1
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 7.5.2 MRTS16
checkpoint | 6 - Application of Amelioration Agents
label | ○ Amelioration agents, shall be spread over the subsoil surface at the specified rates prior to subsoil operations.
label | ○ Ground preparation operations shall occur immediately after the application of amelioration agents
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 8.4.1.1 MRTS16
checkpoint | 7 - Subsoil Operations: Roughening
label | Roughening shall occur immediately after the application of amelioration agents as per Clause 7.2.5
label | Roughening shall:
label | a) be approximately 50 mm depth
label | b) incorporate amelioration agents into the subsoil
label | c) occur when soils are dry enough to roughen / break up / crumb the surface, and
label | d) be parallel to the contour and form keys in the subsoil to prevent subsequent material slipping down the face of the slop
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 8.4.1.4 MRTS16
checkpoint | 8 - Topsoil Installation
label | ○ Topsoil shall be installed within three days of the subsoil operations.
label | ○ Topsoil shall be spread to the minimum 75 mm depth, and allow for settlement after installation.
label | ○ The Contractor shall give at least three days notice before installation of topsoil.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 8.1.2.4 MRTS16
checkpoint | 9 - Installed Turf Requirements
label | ○ Turfing shall be in accordance with Table 8.5.2.
label | ○ Turf shall be installed within two days from the completion of the topsoil operations.
label | ○ Turf shall be delivered within one day of cutting, and installed within two days of cutting.
label | Turf shall be installed:
label | a) by spreading fertiliser over the topsoil and raking the surface smooth
label | b) to the prepared surface that has been moistened with a solution of water and wetting agent
label | c) on the day turf is delivered to site
label | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
label | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
label | ○ Turf in high profile areas shall be top-dressed to ensure there are no gaps between rolls and to correct any uneven areas. Top-dressing shall be washed and graded sand specifically produced for the horticultural industry.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 7.5.1 MRTS16
checkpoint | 10 - Establishment Period Watering Frequency
label | During the Establishment Period watering shall:
label | a) be ‘misted’ or conducted in a manner that does not cause damage, run-off or subsequent erosion or displacement of treated areas
label | b) not spray onto, flow across or pond on paved areas including roadways, bikeways and footpaths, and
label | c) be in accordance with the minimum watering schedule and watering rates of Table 9.1.1.1(a) and Table 9.1.1.1(b), unless otherwise specified in Clause 4.1 of the Annexure MRTS16.1.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Claue 9.1.1.1 MRTS16
checkpoint | 11 - Interim evaluation
label | ○ After four weeks from installation, treatments shall be evaluated against the following criteria to determine if it is on track to meet the completion criteria
label | ○ Turfing treatments - Turfing treatments shall have a healthy grass cover and show signs of growth.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - Check Item
label | Reference - Claue 9.1.1.6 MRTS16
checkpoint | 12 - Establishment Period completion criteria
label | The Establishment Period shall be completed when the lot has met the following completion criteria:
label | a) the area is weed free in accordance with Clause 9.1.1.3
label | b) seeding treatments meet the completion criteria of Clause 9.1.2.1
label | c) turfing treatments meet the completion criteria of Clause 9.1.2.2,
label | d) planting treatments meet the completion criteria of Clause 9.1.2.3, and
label | e) the lot has been established for a minimum 90 day duration.
label | ○ At the completion of the Establishment Period a Certificate of Completion of the Establishment Period shall be issued by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT
label | Reference - Clause 9.2 MRTS16
holdpoint | HOLD POINT
checkpoint | 13 - Monitoring Period
label | The Monitoring Period for each Lot shall:
label | a) be a minimum duration of 90 days, from the date of Certificate of the Commencement of the Monitoring Period, and
label | b) continue until all vegetation treatments / Lots meet the completion criteria of Clause 9.2.2.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - HOLD POINT
label | Reference - Clause 9.2 MRTS16
holdpoint | HOLD POINT
checkpoint | 14 - Monitoring Period operations
label | ○ The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.2.2.
label | Monitoring Period operations include:
label | a) watering Clause 9.2.1.1
label | b) fertilising Clause 9.2.1.2
label | c) weed control Clause 9.2.1.3
label | d) pest and disease control Clause 9.2.1.4
label | e) repair or re-installation of failed treatments Clause 9.2.1.5
label | f) mowing, slashing and brush cutting Clause 9.2.1.6
label | g) monthly program and inspection reporting Clause 9.2.1.12
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 9.1.2 MRTS16
checkpoint | 15 - Monitoring Period completion criteria
label | The Monitoring Period shall be completed when the lot has met the following completion criteria:
label | a) the area is weed free in accordance with Clause 9.2.1.3
label | b) seeding treatments meet the criteria of Clause 9.2.2.1
label | c) turfing treatments meet the criteria of Clause 9.2.2.2
label | d) planting treatments meet the criteria of Clause 9.2.2.3, and
label | e) the lot has been monitored for a minimum 90 day duration, or as otherwise specified in Clause 4.1 of the Annexure MRTS16.1 or the Contract.
label | ○ Upon successful completion of the Monitoring Period the Certificate of Completion of the Monitoring Period shall be issued by the Client.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - MILESTONE
label | Reference - Clause 9.2.2 MRTS16
checkpoint | Final Verification
note | Responsible Officer
textbox | Print Name:
date | Date:
note | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 26.00 - Contractor's Site Establishment | itp |  |  |  |  | 26.00 - Contractor's Site Establishment
section | Details
checkpoint | 1 - Document Submission: Site facilities and camp establishment is to be in accordance with MRTS01 and MRTS50.
label | Acceptance Criteria & Frequency (Project Specific) - Check that all documentation are in place
label | Check Item - Check Item
checkpoint | 2 - Location of Site Facilities
label | ○ The areas shown within Clause 1 of Annexure MRTS28.1 are available for the establishment of Contractor’s Site facilities and / or storage of plant and / or materials.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 4.2 MRTS28
checkpoint | 3 - General Requirements
label | ○ The Contractor shall supply, equip, service and neatly maintain all necessary buildings, workshops and storage areas for the satisfactory completion of the Work. The Contractor shall provide properly constructed toilets and washing facilities at the Contractor’s site facilities for the use of personnel.
label | ○ Appropriate First Aid facilities should be made available at the site facilities and camp.
label | ○ Erosion and sedimentation control measures shall be implemented during the construction and operation of the Contractor’s site facilities.
label | ○ On completion of the Works, all areas disturbed by the Contractor’s construction activities shall be restored to their original condition, or as may be otherwise acceptable to the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 4.3 MRTS28
checkpoint | 4 - QA Facilities and Meeting
label | ○ If stated in Clause 2 of MRTS28.1 Annexure, a facility for QA Auditing and meeting shall be provided. If no indication is given, a facility for meeting requirements related to QA audits and meeting on site shall be provided.
label | ○ Room Dimensions shall not be less than:6m length, 3m width and 2.4 height and be equipped with one 0.75 kW reverse cycle air conditioner,
label | ○ The room shall be furnished with two office tables 1.2 m by 0.9 m each and four office chairs.
label | ○ The room shall be equipped with computers (with internet access where possible) and printer (with photocopy facility).
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 4.4.1 MRTS28
checkpoint | 5 - Documentation for Contractor Site Facilities
label | ○ If so stated in Clause 3 of Annexure MRTS28.1, the Contractor shall also provide, Drawings of location and sizes of buildings and plant maintenance areas,waste storage areas,access roads, fuel storage locatons, emergency evacuation plan and assembly point, location of parking area.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 4.5.1 MRTS28
checkpoint | 6 - Visibility to the public
label | ○ Where so stated in Clause 5 of Annexure MRTS28.1, the site facilities established by the Contractor shall be screened from public view as stated in this clause.
label | ○ Site facilities shall be screened using an opaque material which camouflages the facilities from public view and provides an aesthetically pleasing appearance blending into the existing background.
label | ○ External lights on the facilities and camps should be positioned or shielded to minimise light overflow onto neighbouring properties.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 4.5.2 MRTS28
checkpoint | 7 - Noise
label | ○ The Contractor shall in its best endeavours to sustain the noise generated from the site facilities to a minimum and managed in accordance to MRTS51.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 4.5.3 MRTS28
checkpoint | 8 - Dust suppression
label | ○ If so stated in Clause 5 of Annexure MRTS28.1, all access roads to and from the Contractor's site facilities and compound areas shall be sealed. A water carts shall be readily available at times to prevent generation of dust.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 4.5.4 MRTS28
checkpoint | 9 - Environmental Management
label | ○ The Contractor’s Site facilities and camp shall comply with MRTS51 Environmental Management and MRTS52 Erosion and Sediment Control, including addressing the facilities and camp within the project’s Environmental Management Plan (Construction). The Site facilities and camp are taken to be included within the definition of ‘Worksite’ provided in MRTS51.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 4.5.7 MRTS28
checkpoint | Final Verification
note | Doval Representative
textbox | Print Name:
date | Date:
note | Administrator
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 28.00 - Road Surface Delineations | itp |  |  |  |  | 28.00 - Road Surface Delineations
section | Details
checkpoint | 1 - Construction Procedures
label | ○ The Contractor shall prepare documented procedures for the application of pavement markings with reference to Clause 5 MRTS50 Specific Quality System Requirements.
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Clause 5.2 MRTS45
checkpoint | 2 - Testing Frequency
label | ○ The method of testing shall follow the requirements detailed in AS4049.4 and may be varied by the testing frequencies nominated in Clause 1 of Annexure MRTS45.1. Measurements of the retroreflectivity shall be in accordance with the procedure define in AS 4049.4
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Clause 5.3 MRTS45
checkpoint | 3 - Material Requirements
label | ○ Performance Criteria: The retro reflectivity of new pavement markings shall be measured at 20 days of wear aaverage of all the readings (a minimum of 350 mcd/lux/m2) is required. Refer Clause 1 of Annexure
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Clause 6.1.1 MRTS45
checkpoint | 4 - Material Requirements
label | ○ Paint: Is to be suitable for use on roads surfaced with a sprayed sealed, hot and cold mixed asphalt and concrete. Table 6.1.2 of MRTS45 detailed the paint colour designation and in accordance with AS2700.
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Clause 6.1.2 MRTS45
checkpoint | 5 - Material Requirements
label | ○ Reflective Glass Beads: To be of Type B, B-HR, C, D or D-HR conforming with AS2009 and AP-S0042. The type to be used shall be as stated in Clause 3 of Annexure MRTS45.1
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Clause 6.1.3 MRTS45
checkpoint | 6 - Material Requirements
label | ○ Skid resistance for transverse line marking: shall have a skid resistance conforming to Table 6.1.4 MRTS45. The test method and frequency shall be as AS 4049.4. and varied as stated in Clause 1 of Annexure MRTS45.1
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Clause 6.1.4 MRTS45
checkpoint | 7 - Material Requirements
label | ○ Thermoplastic materials: Shall comply with AS 4049.2 and be an approved product from the 'Asutralian Paint Approval Scheme - Specification AP-S0041/4'
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Clause 6.1.5 MRTS45
checkpoint | 8 - Material Requirements
label | ○ Cold applied plastic materials: Shall comply with AS 4049.4 and Clause 3 of Annexure MRTS45.1 and be an approved product from the 'Australian Paint Approval Scheme - Specification AP-S0041/3)
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Clause 6.1.6 MRTS45
checkpoint | 9 - Material Requirements
label | ○ Raised retroreflective pavement markers: Shall comply with AS 1906.3 and be Type A1 either uni-directional or bi-directional. For uni-directional, the pavement markers shall be white, red, green or yellow. Whilst for bi-directional pavement markers, it shall be white or yellow.
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Clause 6.2 MRTS45
checkpoint | 10 - Material Requirements
label | ○ Non-retroreflective raised pavement markers: Shall conform with the requirements of AS 1906.3 and shall be Type B. It shall be circular, approx 100mm in diameter, and 15mm high and white in colour.
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Clause 6.3 MRTS45
checkpoint | 11 - Material Requirements
label | ○ Temporary raised pavement markers: Shall conform with the requirements of AS 1906.3
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Clause 6.4 MRTS45
checkpoint | 12 - Material Requirements
label | ○ Pavement Bars: Be manufactured in accordance with details shown on the design document, or if not shown it shall be manufactured from concrete and painted white.
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Clause 6.5 MRTS45
checkpoint | 13 - Material Requirements
label | ○ Adhesives for raised pavement markers: Adhesive to install raised pavement markers shall comply with the manufacturer specification. If not available, the requirements of AS 3554.
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Clause 6.6 MRTS45
checkpoint | 14 - Setting out of pavement markings
label | ○ The Contractor shall ensure sufficient set out is carried out to establish satisfactory alignment of pavement markings, within the specified tolerances.
label | ○ Spotting on reseals and asphalt overlay, the control line shall be installed at 20m intervals.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 7.1 MRTS45
checkpoint | 15 - Weather Conditions
label | ○ Pavement markings shall not be applied when freshly applied pavement markings may become damaged by rain, fog or condensation before they have dried or set. The surface shall be dry.
label | — Air Temperature > 15°C
label | — Relative humidity < 70%
label | — Air movement > 10 km/h
label | — Adequate protection of lines from traffic during the drying process,
label | ○ Waterborne paint must not be applied when relative humidity is above 85% and when air or pavement temperatures are below 10°C
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Clause 7.2 MRTS45
checkpoint | 16 - Surface Preparation
label | ○ The surface area in which pavement markings are to be installed must be dry, free of dirt, gravel, flaking pavement marking material and other loose or foreign material.
label | ○ Further, for new bitumen sealed surfaces which are to receive new pavement markings shall be free of volatile material and solvents. Clause 7.3 of MRTS45 defines the conditons under which the pavement marking work shall not proceed.
label | Acceptance Criteria & Frequency (Project Specific) - Acceptance
label | Check Item - HOLD POINT
label | Reference - Clause 7.3 MRTS45
holdpoint | HOLD POINT
checkpoint | 17 - Spotting
label | Spotting approval shall be obtained prior to the application of pavement markings. It shall consist of spots approximately 30mm wide and 150mm long.
label | — Longitudinal Lines: 5m intervals with 3m intervals on curves less than 50m radius
label | — Transverse Markings: To be carried out as shown on the design documents
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT
label | Reference - Clause 7.4 MRTS45
holdpoint | HOLD POINT
checkpoint | 18 - Application of paint and glass beads to new pavement surface
label | It shall be of uniform thickness and intensity.
label | — Waterborne paint shall not be heated to temperature greater than 65°C.
label | — Two coats of paint and glass beads shall be applied on longitudinal lines to new surfaces
label | — Each coat of paint for any longitudinal lines group, including glass beads, shall be applied in one pass.
label | — The first coat of paint shall be applied using Type B-HR glass beads and the second coat using the gass beads as specified in Clause 2 of Annexure MRTS45.1
label | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
label | Check Item - Check Item
label | Reference - Clause 7.5.2.3 MRTS45
checkpoint | 19 - Application Rates
label | ○ Table 7.5.2.4 details the minimum application rates for the paint and glass beads.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 7.5.2.4 MRTS45
checkpoint | 20 - Application of thermoplastic material
label | ○ Thermoplastic material shall be applied to the pavement at a temperature between 180°C and 200°C unless differ from the manufacturer recommendations.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 7.5.3.2 MRTS45
checkpoint | 21 - Application of retro reflective pavement markers
label | ○ Shall be in accordance with Clause 5.6.2 of Part 2 of the MUTCD
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 7.6.1 MRTS45
checkpoint | 22 - Protection of the Work
label | ○ Newly placed pavement markings shall be protected from damage by traffic or other causes, using acceptable traffic management procedures; until paint is dry (no pick up condition) or thermoplastic material has hardened sufficiently to prevent such damage.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 7.8 MRTS45
checkpoint | 23 - Tolerances
label | Completed pavement markings shall:
label | a) be uniform
label | b) have clean and well-defined edges without running or deformation, and
label | c) conform to the dimensions shown on the design documents or in the Manual of Uniform Traffic Control Devices (Qld).
label | ○ Longitudinal lines shall be straight on straight alignment and shall be on a true arc on curved alignment.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 7.9.1 MRTS45
checkpoint | 24 - Removal of Existing Pavement Markings
label | ○ Where required under the Contract, existing pavement markings shall be removed by the appropriate method stated in Table 7.10. Where a method is stated in Clause 1 of Annexure MRTS45.1, that method shall be used.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 7.10 MRTS45
checkpoint | Final Verification
note | Responsible Officer
textbox | Print Name:
date | Date:
note | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 29.00 - Environmental Management | itp |  |  |  |  | 29.00 - Environmental Management
section | Details
checkpoint | 1 - Document Submission
label | ○ As per Doval Safety Plan and Doval Environmental Plan
label | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety and environmental procedures and controls are in place.
label | Check Item - Check Item
checkpoint | 2 - Environmental Management Plan (Construction)
label | ○ For the duration of the Contract, the Contractor shall develop, implement and maintain an Environmental Management Plan – Construction (EMP(C)) that meets the requirements of the Contract.
label | ○ The Contractor may, with the Administrator’s deemed suitability, substitute environmental Management Measures included in this Technical Specification with other environmental Management Measures which achieve the same, or better, environmental outcomes. These Management Measures shall be documented in the EMP(C).
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 1 / MILESTONE
label | Reference - Clause 6.3 MRTS50
holdpoint | HOLD POINT
checkpoint | 3 - EMP (C) Updates
label | ○ Updates to the EMP(C) shall be undertaken by the Contractor to address changes on Site, Works under the Contract and to address corrective actions following non-conformances or Environment and Cultural Heritage Incidents. Where undertaken, updates to the EMP(C) shall be submitted to the Administrator as part of the Contractor’s Monthly Environmental Report, for deemed suitability.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 2 / MILESTONE
label | Reference - Clause 6.4 MRTS50
holdpoint | HOLD POINT
checkpoint | 3 - Notification Visits by administering authorities
label | ○ Contractor must notify the Administrator within 24hrs of any inspections, site visits and meetings from any administering authority
label | Acceptance Criteria & Frequency (Project Specific) - Notify
label | Check Item - Check Item
label | Reference - Clause 7.2 MRTS51
checkpoint | 4 - Environmental Weekly Site Inspection
label | ○ Contractor shall undertake and document daily site inspections for the purpose of verifying compliance with the EMP(C), licences, permits and approvals and the other environmental performance requirements specified within the Contract. Inspection records shall be made available within 48hours of a request for a specific Weekly Side Inspection Report.
label | ○ An environmental representative must be nominated. The nominated person shall undertake the inspections
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 7.1 MRTS51
checkpoint | 5 - Environmental Monitoring
label | ○ Contractor shall contain procedure for undertaking the various types of Monitoring including specific locations, emthod, timing, frequency, duration, parameter to be monitored, and objective / criteria measured against. Reporting shall be submitted to the Administrator within 5 business days of the end of each month.
label | Acceptance Criteria & Frequency (Project Specific) - Reporting
label | Check Item - Check Item
label | Reference - Clause 7.5 & Clause 7.6 MRTS51
checkpoint | 6 - Notification and management of environmental incidents
label | ○ Notify the Administrator of incidents involving material or serious environmental harm shall be reported on a monthly basis. Reporting requirements as per the Environmental Protection Act.
label | Acceptance Criteria & Frequency (Project Specific) - Reporting
label | Check Item - Check Item
label | Reference - Clause 7.7 MRTS51
checkpoint | 7 - Records and registers:
label | ○ Environmental records are to be included in the Quality Records under the Contract. Table 7.8 of this
label | ○ Technical Specification identifies environmental record requirements. Records and registers shall be made available to the Administrator upon request. Hold Point 3 Milestone
label | ○ The environmental records listed in Table 7.8 shall be submitted to the Administrator (electronically unless agreed to by the Contract Administrator) prior to Practical Completion.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 3 / MILESTONE
label | Reference - Clause 7.8MRTS51
holdpoint | HOLD POINT
checkpoint | 8 - Noise
label | ○ The Contractor is responsible for the management of construction noise generated from Work under the Contract. The requirements of this Technical Specification do not include management of noise in relation to noise exposure within the Workplace occupational noise). This Technical Specification does not address noise impacts on native fauna unless specified in the Annexure MRTS51.1.
label | ○ In the event of a noice complaint refer to Annexure 51.1 CL 4.4
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.5.1 MRTS51
checkpoint | 9 - Vibration
label | ○ Contractor shall undertake a risk assessment of the potential damage cause by vibration to nearby premises, building and structures or cause environmental nuisance/harm prior to commencing any work activity. The Contractor is to prepare a condition survey of the premises, buildings and structures (including those listed in Clause 4.1 of Annexure MRTS51.1) that may be impacted by noise vibration.
label | ○ Unless stated in Clause 4.2 of Annexure MRTS51.1, a registered structural engineer (RPEQ) shall carry out the condition survey.
label | ○ At least 5 working days before any work activty that cause vibration start, a copy of the condition survey shall be given to the Administrator.
label | ○ Identified vibration sensitive receptors are detailed in Clause 4.3 of Annexure MRTS51.1
label | Acceptance Criteria & Frequency (Project Specific) - Check & Reporting
label | Check Item - Check Item
label | Reference - Clause 8.6 MRTS51
checkpoint | 10 - Air Quality
label | The Contractor shall manage construction activities as such to mitigate air quality impacts that cause environmental nuissance or harm. The following management strategies shall be implemented, but not limited to:
label | — regular watering or temporary sealing of the site and access roads.
label | — avoiding works (e.g. stripping, excavation, etc.) during dry and windy conditions.
label | — fitting equipment with dust collection/suppression devices
label | — stabilising/covering all stockpiled material for longer than one month
label | — covering loads
label | — maintaining clean roadways to and from worksite
label | ○ If stated in Clause 5.1 of Annexure MRTS51.1, burning of material shall not be permitted.
label | ○ Clause 5.3 of Annexure MRTS51.1 specifies the air quality monitoring requirements for compliance. Unless stated otheriwse, air quality monitoring shall be undertaken in accordance with the Air Quality Sampling Manual, EPA, 1997.
label | ○ Construction related air quality complaints shall be managed in accordance with Chapter 7 of the Road Traffic Air Quality Management Manual.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.7 MRTS51
checkpoint | 11 - Acid Sulphate Soils
label | ○ The Contractor shall be responsible for the management of actual or potential acid sulfate soils within the Site. The Contractor's EMP(C) shall address the requirements of MRTS04 General Earthworks including the requirements concerning the management of actual and potential acid sulfate soils.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.8 MRTS51
checkpoint | 12 - Contaminated Sites
label | ○ The Contractor shall be responsible for the management of contaminated sites (e.g. contaminated soil, waste dumps, unexploded ordinances) within the worksite.
label | ○ Clause 6.1 details a lists of known contaminated site within the worksite and associated management requirements.
label | ○ The Contractor shall manage known contaminated sites in accordance with statuary requirements and any additional requirements stated in Clause 6.2 MRTS51.1
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 8.9 MRTS51
checkpoint | 13 - Fauna
label | ○ Duty of care shall be taken to not harm native fauna. A list of fauna management to which the Contractor shall followed is described in Clause 8.10
label | ○ The Contractor shall be responsible for the assessment, management and compliance of temporary Waterway Barrier Works undertaken as part of this Contract unless otherwise stipulated in Clause 1 of Annexure MRTS51.1. Principal identified Queensland Waterways for Waterway Barrier Works, as mapped by DAF13, are identified in Clause 8.1 of Annexure MRTS51.1.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.10 MRTS51
checkpoint | 14 - Vegetation
label | ○ The Contractor shall ensure a vegetation management plan within the worksite is establish. As stated in Clause 8 of Annexure MRTS51.1, a list of significant areas of vegetation and associated management requirements has been highlighted within work site. The Contractor shall ensure they implement a vegetation management strategies listed in Clause 10.10.1 MRTS51 in their management plan.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 8.11 MRTS51
checkpoint | 15 - Fauna Monitoring
label | ○ Monitoring in accordance with Section 8.10.2 of the Technical specification (MRTS 51 – Environmental Management) must be undertaken if the requirements of the Environmental Approval for Tampering with Animal Breeding Places of Least Concern Species (SMP-low risk) and Colonial breeding species (SMP) are triggered.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.10.3 MRTS51
checkpoint | 16 - Biosecurity Management (Pest Management)
label | ○ The Contractor shall ensure they consider in their management plant the lists of biosecurity management strategies nominated in Clause 8.12 MRTS51. The Contractor shall control the movement of all biosecurity matters (including invasive animals and plants) preventing their spread on and off site. Detail in Clause 10.1 - 10.3 of Annexure MRTS51.1, a lists of known biosecurity matters within the worksite and asssociated management requirements has been highlighted.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.12 MRTS51
checkpoint | 17 - Waste Management
label | ○ A waste management strategies/plan must be developed to control wastes generated during construction, inclusive of but not limited to waste avoidance, waste reuse, waste recycling, energy recovery from waste and waste disposal. The Contractor shall ensure compliance with the Waste Reduction and Recycling Act, 2011 at all times.
label | ○ The implemented EMP must accomodate the documents and/or diagram listed in Clause 10.12.4 MRTS51
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 8.13 MRTS51
checkpoint | 18 - Chemical and Fuels Management
label | ○ The Contractor shall be responsible for the management of all chemicals and fuels within the worksite so as to prevent environmental nuisance or harm.
label | ○ Further to the compliance with the requirements of the Environmental Protection (Water) Policy, hazardous substances or dangerous goods, the Contractor shall comply with AS 1940 and the Work Health and Safety Act.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 8.14 MRTS51
checkpoint | Final Verification
note | Doval Representative
textbox | Print Name:
date | Date:
note | Administrator
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 30.00 - Erosion and Sediment Control | itp |  |  |  |  | 30.00 - Erosion and Sediment Control
section | Details
checkpoint | 1 - Document Submission
label | ○ Submission of the Erosion and Sediment Control Plan (ESCP). It shall incorporated areas of disturbance such as stockpile and storage area, temporary waterway crossing etc…
label | ○ Clearing and Grubbing shall not start until the ESCP for that section until deemed suitable by the Administrator.
label | ○ Timeline for assessment os suitability of ESCP shall be as per Conditons of Contract.
label | ○ Any changes to the drainage flow or sediment treatment locations shall be updated on the ESCP accordingly and submitted to the Administrator for suitability.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 1
label | Reference - Clause 6.1 MRTS52
holdpoint | HOLD POINT
checkpoint | 2 - ESCP Plan Requirements
label | ○ ESCP has been developed in accordance of the principles of Clause 1.4 and the requirements of Clause 6.2
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 6.2 MRTS52
checkpoint | 3 - Personnel Plan Development
label | ○ The Erosion and Sediment Control Plan shall be prepared and updated by personnel who have the requisite level of training and experience outlined in Table 6.3, or as modified by Clause 5 of Annexure MRTS52.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 6.3 MRTS52
checkpoint | 4 - Installation
label | ○ Erosion and sediment controls have been installed as soon as practicale and prior to initial earthwork for the section of the works (Includes rock check, catch banks, traps and diversion drains) The completion of these activity shall be approved before any earthworks can proceed.
label | Acceptance Criteria & Frequency (Project Specific) - Visual Check
label | Check Item - HOLD POINT 2
label | Reference - Clause 7.1 MRTS52
holdpoint | HOLD POINT
checkpoint | 5 - Operation and Maintenance
label | ○ Erosion and Sediment Control is to be maintained in effective working order throughout the works
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 7.2 MRTS52
checkpoint | 6 - Decommissioning and Removal
label | ○ All temporary sedimentation control shall be removed in areas where permanent measures are in place and/or site stabilisation has occurred prior to the Final Certificate. The removal of these erosion and sediment control devices shall occur prior to the end of the Defects Liability Period or the end of the Landscape and Revegetation Works Monitoring Period whicever is the later.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 7.3 MRTS52
checkpoint | 8 - Waterways - Offsite Impact
label | ○ Erosion and sediment captured within the work site shall not cause environmental nuisance or harm outside the worksite, or to permanent water bodies.
label | ○ Releases from site must not cause scour at the area of discharge. Water must only be released at the discharge point nominated in the ESCP and as deemed acceptable by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Report
label | Check Item - Check Item
label | Reference - Clause 8.1. MRTS52
checkpoint | 9 - Contractor Inspection and Audits
label | ○ Inspection shall be documented daily for verifying compliance with the EMP. Inspection shall include visual assessment of erosion and sediment control structures,
label | Acceptance Criteria & Frequency (Project Specific) - Visual Check & Reporting
label | Check Item - Check Item
label | Reference - Clause 9. MRTS52
checkpoint | Final Verification
note | Doval Representative
textbox | Print Name:
date | Date:
note | Administrator
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 31.00 - Reinforcing Steel | itp |  |  |  |  | 31.00 - Reinforcing Steel
section | Details
checkpoint | 1 - Document Submission
label | ○ As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
label | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management
label | Check Item - Check Item
checkpoint | 2 - Traffic and Safety Controls
label | ○ Traffic and safety controls are in place (eg. PPE, daily plant check)
label | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
label | Check Item - Check Item
checkpoint | 3 - Supplier Approval
label | ○ At least 3 days before steel reinforcing is supplied, the Contractor shall submit to the Administrator the identity and address of the proposed supplier and evidence of conformance.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - MILESTONE
label | Reference - Clause 6.1 MRTS71
checkpoint | 4 - Delivery of Reinforcing
label | ○ Steel reinforcing shall not be delivered to the Site until written acceptance of the proposed supplier has been obtained from the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Acceptance
label | Check Item - HOLD POINT 1
label | Reference - Clause 6.1 MRTS71
holdpoint | HOLD POINT
checkpoint | 5 - Registered Manufacturer
label | ○ Steel reinforcement manufacture shall be certified by ACRS or a TMR approved product (Refer to Clause 1). If any reason the supplier cannot gain independent certification may be granted if compliant to Clause 6.1.2
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 6.1.1 MRTS71
checkpoint | 6 - Hot bending of steel
label | ○ Authorisation is requires where specified for the bending of steel reinforced bars on site
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 2
label | Reference - Clause 8.2 MRTS71
holdpoint | HOLD POINT
checkpoint | 7 - Placing and Fixing
label | ○ Where the bars will be tied together, the reinforcement must be tied by wiring at each intersection, using annealed wire not less than 1.6 mm in diameter. Where the bar spacing is 300 mm or less, alternate intersections only need to be tied.
label | ○ All steel reinforcement in position shall be inspected and approved before placement of concrete commences.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - HOLD POINT 3
label | Reference - Clause 7 MRTS71, Clause 7 ATS 5310
checkpoint | 10 - Substitution
label | ○ Substitution of different size, grades or ductility class of steel reinforcement so that shown on the drawings shall not be made unless approve in writing by the Administrator. The application shall be forwarded 3 weeks prior of steel placement.
label | ○ Substitution shall not proceed until the Administrator has approve the change.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - MILESTONE/HOLD POINT 4
label | Reference - Clause 13 MRTS71
holdpoint | HOLD POINT
checkpoint | 13 - Prefabricated reinforcing cages
label | All prefabricated reinforcing cages must be identified with the following information, either by tagging or a combination of labels, schedules and drawings:
label | a) the fabricator’s name;
label | b) date of manufacture;
label | c) drawing reference;
label | d) traceability of reinforcement as required by this Specification;
label | e) the mass of the cage; and
label | f) the colour and location of dedicated lifting points.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - HOLD POINT 5
label | Reference - Clause 15.1 MRTS71
holdpoint | HOLD POINT
checkpoint | 13 - Provision for lifting of cages
label | ○ Prior before lifting of large cage an RPEQ engineer needs to certify lifting points and their capacity. These must be submitted to the administrator prior to lifting
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - HOLD POINT 6
label | Reference - Clause 15.1 MRTS71
holdpoint | HOLD POINT
checkpoint | 14 - Inspection of Cage fabricated outside Australia
label | ○ Shall be visually inspected by the Administrator prior to any steel placement
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - HOLD POINT 7
label | Reference - Clause 7.1 ATS 5310
holdpoint | HOLD POINT
checkpoint | Final Verification
note | Doval Representative
textbox | Print Name:
date | Date:
note | Administrator
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 32.00 - Specific Quality System Requirements | itp |  |  |  |  | 32.00 - Specific Quality System Requirements
section | Details
checkpoint | 1 - Document Submission
label | ○ As per Doval Quality Management Plan
label | Acceptance Criteria & Frequency (Project Specific) - Check that proper quality procedures and controls are in place.
label | Check Item - MILESTONE
checkpoint | 2 - Construction Procedure
label | ○ Procedures shall be prepared for all constructions procedures, including statement of equipment utilisation. Construction procedures shall be submitted at least 14 days prior to commencement of construction procedure.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 6 MRTS50
checkpoint | 3 - Lot identification and traceability
label | ○ Works shall be divided into lots for adequate identification, monitoring, submission of works to the administrator, rejection of works and possible bonus provisions for each specific item.
label | ○ Lots shall be chosen taking into account any restrictions included in the contract.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 7.1 MRTS50
checkpoint | 4 - Inspection and Testing
label | ○ Inspection and test procedures shall be included in an inspection and test plan and shall comply with clause 8.2 of MRTS 50 and to ensure compliance with the contract requirements.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 8.2 MRTS50
checkpoint | Final Verification
note | Responsible Officer
textbox | Print Name:
date | Date:
note | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 33.00 - Signage Installation | itp |  |  |  |  | 33.00 - Signage Installation
section | Details
checkpoint | 1 - Document Submission
label | ○ Has Doval’s Traffic and Safety Management Plan been submitted and approved for use by the Principal at least 14days before commencement of its implementation (as nominated in Clause 2 of Annexure MRTS02.1)
label | Acceptance Criteria & Frequency (Project Specific) - Document Submission
label | ○ Has Doval’s Traffic and Safety Management Plan been submitted and approved for use by the Principal at least 14days before commencement of its implementation (as nominated in Clause 2 of Annexure MRTS02.1)
label | Check Item - Check Item
checkpoint | 2 - Traffic and safety controls
label | ○ Are safety controls are in place (eg. PPE, daily plant check)
label | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
label | Check Item - Check Item
checkpoint | 3 - Traffic Management Process
label | ○ All traffic control signs, devices and measures in accordance to the TGS shall be applied in order to warn traffic in advance. Refer to Clause 2.2.4 of MUTCD Part 3
label | ○ TGS shall be prepared has been prepared by a suitability qualified and experienced persons and has been submitted to the Administrator for a direction as to its suitability at least 7days as per Clause 2 of Annexure MRTS02.1
label | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
label | Check Item - Check Item
label | Reference - TGS
checkpoint | 4 - Risk Management
label | ○ The Risk Management shall foresee all safety risks likely to arise during works on road when preparing standardised plan, SWMS and the TGS
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 2.2.3 MUTCD
checkpoint | 5 - Temporary Footpaths and Pedestrian Crossings
label | ○ Where footpaths or pedestrian crossings have been partially closed or temporarily relocated, has provision been made for temporary access in accordance with Clause 2.3.8 of the MUTCD Part 3?
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 2.3.8 MUTCD
checkpoint | 6 - Traffic Management
label | Traffic Management will be developed in accordance with the TMP and satisfy the following Clauses:
label | — Safety & Convenience Clause 2.3.2
label | — Traffic through the work area Clause 2.3.3
label | — Traffic past the work area Clause 2.3.4
label | — Traffic around the work area Clause 2.3.5
label | — Night Conditions Clause 2.3.6
label | — Provision for Pedestrian and Bicycles Clause 2.3.7
label | — Temporary Footpath and Pedestrian
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 2.3 MUTCD
checkpoint | 7 - Delineation
label | ○ Appropriate delineation shall be established and illustrated which part of the roadway is available to road users or the path traffic is required to follow under all conditions. Long range or short range delineation shall be installed accordingly
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 2.4.2 MUTCD
checkpoint | 8 - Night Conditions
label | ○ Flashing Lamps may be used to draw attention to certain advance sign (Refer to Clause 3.11) Pavement marking through the work shall be retroflective. Delineating devices shall comprise or incorporate retroflectors. Barriers may require floodlighting to make them more conspicuous.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 2.4.3 MUTCD
checkpoint | 9 - Safety Barriers
label | Shall be installed in place where it is deemed to have:
label | — Inadequate safety clearance between moving traffic and workers and plant on site
label | — Hazardous traffic conflicts
label | — Collisions with hazardous fixed objects, construction works or falls into excavation closed to the travelled path.
label | — Inadequate separation of temporary footpath, shared path or bicycle paths
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 2.4.5 MUTCD
checkpoint | 10 - Vehicle Size and Load Restrictions
label | ○ Informed appropriate authority about alternating width, height or load carrying capacity of the roadway
label | Acceptance Criteria & Frequency (Project Specific) - Notify
label | Check Item - MILESTONE
checkpoint | 11 - Condition of devices
label | Check that signs and devices are examined before installation to ensure that they are in good condition and their performance is not impaired. The following checks are required:
label | (a) Mechanical condition
label | (b) Cleanliness
label | (c) Colour of fluorescent signs
label | (d) Night-time visibility
label | ○ Functional inspections are also required, see Clause 2.5.5.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 2.5.1 MUTCD
checkpoint | 12 - Positioning of Devices
label | Check that signs and devices should be positioned and erected so that-
label | (a) they are properly displayed and securely mounted (see Clause 3.3);
label | (b) they are within the line of sight of the intended road user;
label | (c) they cannot be obscured from view
label | (d) they do not obscure other devices from the line of sight of the intended road user;
label | (e) they do not become a possible hazard to workers, pedestrians or vehicles
label | (f) they do not deflect traffic into an undesirable path.
label | (g) they do not restrict sight distance for drivers entering from side roads or streets, or private driveways; and
label | (h) they are not installed using supports that could be a hazard if struck by a vehicle.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 2.5.2 MUTCD
checkpoint | 13 - Positioning of Devices
label | ○ On kerbed roads in built-up areas where signs are mounted on posts adjacent to a footpath, or where vehicle parking may occur, they should be erected a minimum of 2.2 m above the level of the kerb or footpath to the underside of the sign, to reduce interference from parked vehicles.
label | ○ Where neither pedestrians nor parked vehicles have to be considered, e.g. on a traffic island or median, a mounting height of 1.5 m may be more appropriate.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 2.5.2 MUTCD
checkpoint | 14 - Setting out and recovery of devices
label | Check that before work commences devices at the approaches to and within the work area should be set out in accordance with the traffic guidance scheme in the following sequence:
label | (a) Advance warning and regulatory signs.
label | (b) All intermediate advance warning and regulatory signs and devices required in advance of the taper or start of the work area.
label | (c) All delineating devices required to form the taper including the illuminated flashing arrow sign at the end of the taper where required.
label | (d) Delineation of the work area or side track.
label | (e) All other required warning and regulatory signs including termination and end of temporary speed zone signs. This operation
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 2.5.3 MUTCD
checkpoint | 15 - Orientation of sign
label | ○ Sign should face towards approaching traffic approximately at right angles to the line of sight from the driver to the sign.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 2.5.4 MUTCD
checkpoint | 16 - Inspection
label | ○ Inspection of signs and devices shall be carried out before and after opening traffic. This inspection should be carried out along the travelled path, and past all of the signs and devices. Night inspection is to be undertaken similarly with headlights on low beam. If arrangement is confusing or unsatisfactory it shall be adjusted and reinspected.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - Clause 2.5.5 MUTCD
checkpoint | 17 - Publicity
label | ○ May be necessary to erect special signs to inform the public of the traffic guidance scheme depending on the complexity of the traffic guidance scheme.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 2.5.6 MUTCD
checkpoint | 18 - Removal
label | ○ Relevant signs and devices are to be removed or concealed as soon the activity has been completed or a hazard ceases to exist. When all work is complete, sign and devices should be dismantled in reverse order to Clause 2.5.3
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 2.5.7 MUTCD
checkpoint | 19 - Operation
label | Appropriate measures shall be implemented throughout operations of the project, this will include:
label | — Daily routine and worksite records
label | — High visibility clothing
label | — Closure & Delays
label | — Safety audits
label | — Device maintenance
label | — Layout variation
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 2.6 MUTCD
checkpoint | 20 - Emergency and Unplanned Works
label | ○ In an event of an emergency, procedures for the safe control of traffic and the safety of road authority shall be in accordance of Appendix H. FIGURE H1 illustrates different scenarios to manage traffic throughout an incident.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 2.7 MUTCD
checkpoint | Final Verification
note | Responsible Officer
textbox | Print Name:
date | Date:
note | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 35.00 - Cast-in-Place Piles | itp |  |  |  |  | 35.00 - Cast-in-Place Piles
section | Details
checkpoint | 1 - Document Submission
label | ○ As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
label | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management
label | Check Item - Check Item
checkpoint | 2 - Traffic and Safety Controls
label | ○ Traffic and safety controls are in place (eg. PPE, daily plant check)
label | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
label | Check Item - Check Item
checkpoint | 3 - Construction Procedures
label | ○ At least 28 days prior to the date for sinking of pile shafts a detailed construction procedure has been submitted to the Administrator for review.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - MILESTONE
label | Reference - Clause 6.2 & 7 MRTS63
checkpoint | 4 - Construction Procedures
label | ○ Approval of procedure for construction, excavation, inspection, certification and concreting of piles.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 1
label | Reference - Clause 6.2 MRTS63
holdpoint | HOLD POINT
checkpoint | 5 - Fabrication of liners
label | ○ Welding shall be carried out in accordance with the provisions of AS/NZS 1554.1. A Weld Procedure Sheet shall be submitted to the Administrator for approval prior to welding liners.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 2
label | Reference - Clause 7 MRTS63
holdpoint | HOLD POINT
checkpoint | 6 - Liners driven fom top
label | ○ Liners shall be driven (hammered, oscillated or rotated), open-ended using a driving rig capable of achieving penetration of the liner to the founding level.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 8.2 MRTS63
checkpoint | 7 - Construction Limitation
label | ○ A pile which is located within 2.5 m clear distance from a newly concreted pile shall not be bored or driven until 18 hours after completion of concreting in the adjacent pile. A pile which is located between 2.5 m and 9 m clear distance from a newly concreted pile shall not be driven in the period between initial set and 12 hours after casting is completed.
label | ○ The top of a newly concreted pile shall not be in contact with the driving platform while another pile is being prebored or driven from that platform.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 8.5 MRTS63
checkpoint | 8 - Tolerances
label | The completed pile shall be located as shown on the Standard Drawings within the following tolerances:
label | a) Top of pile, in plan 75 mm in any direction
label | b) Top of pile, vertically 5 mm in height
label | c) Variation from vertical or designated rake 20 mm per metre
label | d) Bow of pile 1% of length of pile in any direction, and
label | e) Diameter of liner and socket - 0, + 5% of nominal diameter at any position.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 9 MRTS63
checkpoint | 9 - Excavation of cast-in-place piles
label | ○ When a pile is to terminate above the design level, the concurrence for this change must be obtained from the Designer, it is not just a geotechnical decision.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 10.1 MRTS63
checkpoint | 10 - Excavation of cast-in-place piles
label | ○ Temporary safety shields shall be used where manual work is carried out in unlined holes and sockets as required by the Workplace Health and Safety Act.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 10.1 MRTS71
checkpoint | 11 - Pile Sockets
label | ○ The walls shall be clean and free of smeared material. Smeared walls shall be cleaned and roughened prior to certification and subsequent concreting.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 10.3 MRTS63
checkpoint | 12 - Geotechnical Certification
label | ○ The Contractor shall forward a copy of the geotechnical certification of the foundation to the Administrator prior to concreting. Insertion of reinforcement and concreting of the pile shall not proceed prior to the Administrator's approval.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 3
label | Reference - Clause 11.1 MRTS63
holdpoint | HOLD POINT
checkpoint | 13 - Steel Reinforcing
label | ○ Steel reinforcing shall be supplied and placed in accordance with the requirements of MRTS71 Reinforcing Steel and MRTS71A Stainless Steel Reinforcing. Steel reinforcing shall be assembled as detailed on the Standard Drawings to form a rigid cage capable of being lowered into the excavation without any disintegration occurring.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - See Steel Reinforcing ITP
checkpoint | 14 - Inspection For inspection purposes, supply of a suitable camera for inspection.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - MILESTONE
label | Reference - Clause 11.9.3
checkpoint | 15 - Concreting
label | ○ All concrete shall be placed in accordance with MRTS70 Concrete except as otherwise specified in Clauses 13.2 to 13.4. The Contractor shall observe all relevant Milestones and Hold Points in MRTS70 Concrete.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - See Concreting ITP
checkpoint | 16 - Concreting
label | ○ Where there has been a delay of more than 24 hours between certification and when the Contractor is ready to start concreting or when the foundation has been observed to deteriorate significantly, the foundation shall be re-cleaned (if required) and re-certified.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 4
label | Reference - Clause 13.1 MRTS63
holdpoint | HOLD POINT
checkpoint | 17 - Concreting
label | ○ All concrete shall be placed in accordance with MRTS70 Concrete except as otherwise specified in Clauses 13.2 to 13.4. The Contractor shall observe all relevant milestones and hold points in MRTS70 Concrete. Placement of concrete underwater shall only commence after the tremie and the placing procedure have been accepted for use by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT 5
label | Reference - Clause 13.1 MRTS63
holdpoint | HOLD POINT
checkpoint | 18 - Concreting
label | The target slump of concrete shall be selected from the range below:
label | a) for concrete placed in dry conditions 150 mm to 180 mm
label | b) for concrete placed by tremie underwater 180 mm
label | ○ Slump tests on delivery shall conform to the target slump and the tolerances given in AS 1379.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 13.3 MRTS63
checkpoint | 19 - Concreting
label | ○ Prior to commencement of concreting the length of the pile from the base to the top of the liner shall be measured and the socket walls and pile base checked for cleanliness.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 13.4.1 MRTS63
checkpoint | 20 - Concreting
label | ○ To assist compaction by hydraulic head, the rate of placing the concrete shall not be less than 10 metres of pile length per hour.
label | ○ Concrete supply shall be effectively continuous with delays between concrete delivery trucks of 15 minutes or less, unless an approved specific retarded mix design has been developed to allow for longer delays, as in remote areas.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 13.4.1 MRTS63
checkpoint | 21 - Concreting
label | ○ The base of the pile shall be clean and all water removed immediately prior to placing concrete. This shall be confirmed by direct observation or by using a camera. The method of placement shall allow the following:
label | a) delivery hose or pipe to 2 m above the pile base, and
label | b) ability to lift and/or shorten the delivery hose / pipe quickly with delays no longer than 10 minutes.
label | ○ Concrete shall be dropped 2 to 3 m from the end of the delivery hose / pipe onto the concrete surface to provide compaction or shall be compacted using vibration. The delivery hose / pipe shall be positioned so that the concrete does not fall onto the reinforcement cage. For raked piles, the Contractor shall detail in the procedure for construction of piles the method of delivering concrete down the piles that minimises the risk of segregation. [Refer to Hold Point 1] The top 3 m of concrete shall be well compacted with a concrete vibrator with a minimum diameter of 50 mm.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 13.4.2 MRTS63
checkpoint | Final Verification
note | Doval Representative
textbox | Print Name:
date | Date:
note | Administrator
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 40.00 - Dense Graded & Open Graded Asphalt | itp |  |  |  |  | 40.00 - Dense Graded & Open Graded Asphalt
section | Details
checkpoint | 1 - Document Submission
label | ○ As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
label | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management
label | Check Item - Check Item
checkpoint | 2 - Traffic and Safety Controls
label | ○ Traffic and safety controls are in place (eg. PPE, daily plant check)
label | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
label | Check Item - Check Item
checkpoint | 3 - Asphalt Quality Plan
label | ○ The Contractor must develop an Asphalt Quality Plan (AQP). The AQP must be submitted to the Administrator for consideration at least seven days prior to work commencing and must be implemented.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - MILESTONE
label | Reference - Clause 5.2 MRTS30
checkpoint | 4 - Compliance Testing
label | ○ Compliance Testing shall be carried out for each lot. The Testing Frequencies shall not be less than those listed in Tables 5.4.1-A, 5.4.1-B and 5.4.1-D
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 5.4.1 MRTS30
checkpoint | 5 - Binder Class
label | ○ Contractor shall provide evidence of the binder conformance and compliance with MRTS17 Bitumen or MRTS18 Polymer Modified Binder
label | ○ The Binder Class are specified in Clause 1 of Annexure MRTS30.1 and are:
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 7.1.6 MRTS30
checkpoint | 6 - Moisture Sensitivity
label | ○ For dense graded asphalt, the tensile strength ratio (TSR) must be ≥ 80% and the average tensile strength of the freeze/thaw group must be 500 kPa for polymer modified binders and 600kPa for mixes containing all other binders.
label | ○ Table 7.2.5 is a list of accepted non-conformance strength ratio for 70% ≥
label | ○ Where a Hold Point is required to be observed, the Contractor shall investigate the causes of the nonconformance and propose corrective action to prevent recurrence of the nonconformance. The Contractor shall submit:
label | a) test results covering the same Lot for insitu air voids and all characteristics specified in Clause 9.2, and
label | b) the proposed corrective action to achieve conformance.
label | ○ The Administrator shall consider the submitted documents prior to authorising the release of the Hold Point allowing recommencement of asphalt production.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT
label | Reference - Clause 7.2.5 MRTS30
holdpoint | HOLD POINT
checkpoint | 7 - Asphalt Contractor Prequalification & Operation Procedures
label | ○ At least 7days before asphalt is incorporated the Contractor shall notify the Administrator in writing of the identify and address of the PAC (Prequalified Asphalt Contractor) and their operation procedures.
label | Operation procedures
label | a) laying program and rolling pattern
label | b) details of any required placement trial and Technical Standard, MRTS30 Dense Graded and Open Graded Asphalt Main Roads Specifications and Technical Standards
label | c) Inspection and test plan.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - Check Item
label | Reference - Clause 6 MRTS30
checkpoint | 8 - Mix Design Submission
label | ○ At least seven days before asphalt is to be incorporated into the Works, the Contractor shall submit to the Administrator a copy of the mix design certificate(s) for each nominal size and type of asphalt mix to be incorporated into the Works.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - MILESTONE
label | Reference - Clause 7.3.3 MRTS30
checkpoint | 9 - Asphalt Mix Design Registrar
label | ○ The process is written in Technical note 148 Asphalt Mix Design Registration. The certificate shall be sign the Contractor mix designer certifying the mix complies with MRTS30 and shall be submitted 28days prior to asphalt being incorporated.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - Check Item
label | Reference - Clause 7.3.2 MRTS30
checkpoint | 10 - Asphalt Mix Design Acceptance
label | Asphalt shall be produced by a registered asphalt manufacturer from the nominated asphalt plant in accordance with the nominated mix design for the Works. Asphalt shall not be incorporated into the Works until the Contractor has demonstrated to the Administrator that the underlying lots conform to the specified requirements or have been accepted by the Administrator for utilisation at a reduced level of service, and the following documents have been received and reviewed by the Administrator:
label | a) identity of the PAC(s) who will undertake the asphalt production, placement and compaction and the address of the asphalt plant that will produce the asphalt (refer Section 6)
label | b) the mix design certificate, which holds current registration with TMR, for each conforming mix design to be used in the Works (refer Section 7.3) or conforming revised mix design submissions (where applicable) (refer Clause 7.3.3)
label | c) the Contractor’s AQP (refer Section 5.2)
label | d) the Contractor’s Aggregate Production Procedure (refer MRTS101), and
label | e) the Contractor’s RAP Management Plan (where applicable).
label | ○ These documents shall be submitted to the Administrator not less than seven days prior to the commencement of asphalt being incorporated into the Works.
label | ○ Any subsequent changes to any of the above documents will require re-submission and re-release of the Hold Point.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT
label | Reference - Clause 7.4.1 MRTS30
holdpoint | HOLD POINT
checkpoint | 11 - Nonconforming Mix Design
label | ○ Nonconforming mix designs, that hold current registration with TMR, shall not be incorporated into the Works unless otherwise accepted in writing by the Administrator prior to the commencement of asphalt production.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT
label | Reference - Clause 7.4.1 MRTS30
holdpoint | HOLD POINT
checkpoint | 12 - Preparation of Pavement
label | ○ The surface of the pavement base/bridge deck or existing substrate shall not be wet, and shall be thoroughly swept using a rotary broom to remove any loose material or other deleterious material which may be present. Any deleterious material, which still adheres to the surface after sweeping, shall be removed by other means.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.2.2 MRTS30
checkpoint | 13 - Crack Filling
label | ○ In areas shown in the Drawings or stated in Clause 2 of Annexure MRTS30.1, cracks greater than 2 mm wide shall be filled prior to placement of any asphalt. The Contractor shall mark out in the presence of the Administrator, the extent of crack filling to be carried out.
label | ○ Cracks shall be filled level with the surrounding surface with a polymer modified sealant approved by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 8.2.3 MRTS30
checkpoint | 14 - Strain Alleviating Fabric Strips
label | ○ In the areas shown on the Drawings or stated in Clause 3 of Annexure MRTS30.1, strain alleviating fabric strips shall be applied to existing cracks prior to placement of asphalt or sprayed sealing.
label | ○ The Contractor shall mark out, in the presence of the Administrator, the extent of the strain alleviating fabric strips to be applied.
label | ○ Where directed by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - WITNESS POINT
label | Reference - Clause 8.2.4 MRTS30
checkpoint | 15 - Method of Placement
label | ○ A self-propelled paving machine equipped with the ability to be operated with automatic thickness control and automatic joint matching facility must place the asphalt.
label | ○ Hand placement of asphalt is only permitted for minor corrections of the existing surface and in areas where placement with a paving machine is impractical.
label | Acceptance Criteria & Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - Clause 8.3 MRTS30
checkpoint | 16 - Nominated Layer Thickness
label | ○ The binder details are specified in Clause 1 of Annexure MRTS30.
label | ○ The nominated thickness of a layer of Asphalt shall be within the limits specified in Table 8.6.1
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.6 MRTS30
checkpoint | 17 - Tie-ins to Existing Pavement
label | ○ For Tie-ins, the Contractor may be required to a implement a layer thickness that does not conform with Clause 8.6.1. The Contractor shall detail the work methods to be adopted in the AQP.
label | ○ Placement of asphalt in a nonconforming layer thickness shall not occur until Administrator approval.
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT
label | Reference - Clause 8.6.2 MRTS30
holdpoint | HOLD POINT
checkpoint | 18 - Pavement Temperature
label | ○ The pavement surface temperature shall be measured and recorded at the point of asphalt placement on a regular basis during paving operations. The Contractor shall document the method of measuring and recording pavement temperatures in the AQP. Unless otherwise accepted by the Administrator, asphalt placement shall not commence or continue, unless the pavement surface temperature complies with the requirements of MRTS30 Table 8.7.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - HOLD POINT
label | Reference - Clause 8.7 MRTS30
holdpoint | HOLD POINT
checkpoint | 19 - Paving and Compaction Temperatures
label | ○ Contractor AQP must document the temperatures at which the asphalt is placed and compacted to achieve the insitu air voids requirements specified in Clause 9.2.1. The contractor shall nominate in the AQP the listed of requirements described in Clause 8.8.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.8 MRTS30
checkpoint | 20 - Tack Coat
label | ○ Tack coat is to be applied to a clean, dry surface immediately prior to the placement of asphalt. The AQP shall state the bituminous emulsion grade and proposed tack coat.
label | Acceptance Criteria & Frequency (Project Specific) - Visual Check
label | Check Item - Check Item
label | Reference - Clause 8.9 MRTS30
checkpoint | 21 - Joints
label | ○ Construction of asphalt joints shall be described in the AQP and shall follow the procedures described in Clause 8.10
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 8.10 MRTS30
checkpoint | 22 - Placement Trial
label | ○ If specified in Clause 6 of Annexure MRTS30.1 and prior to commencing work, the plant and personnel proposed for use for the Works must be subjected to a placement trial.
label | ○ The Contractor shall submit a copy of the completed inspection and test plan and all relevant test results and records from the placement trial. Prior to further placement of the Contractor’s nominated mix(s) in the works, the Administrator shall review the outcomes of the placement trial. No further work shall be undertaken until the Administrator has given approval to proceed. N/A
label | Acceptance Criteria & Frequency (Project Specific) - Approval
label | Check Item - HOLD POINT
label | Reference - Clause 8.11 MRTS30
holdpoint | HOLD POINT
checkpoint | Final Verification
note | Responsible Officer
textbox | Print Name:
date | Date:
note | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off