## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
dff49ebe-0123-48ac-bb16-364b1cf941ad | checklist | 02.01 - Traffic Management | itp | 02.01 - Traffic Management
1acd4417-855b-439b-bdbd-c4ddf47c1017 | section | Details
b376f788-5fba-4498-b9a8-ef2f365f49df | checkpoint | The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
bf17b1c3-aacf-5ed8-b523-1bf236b530aa | note | Acceptance Criteria and Frequency (Project Specific) - Accreditation Supplied to Administrator
a9741a63-11be-5166-b259-60d90c1e0ab0 | note | Check Item - Check Item
6b1e2a3d-cfe3-5270-8bc8-c91a898cffcc | note | Reference - MRTS02 Cl. 5.2
429a2722-a949-47a8-9270-bdf23d86b03a | checkpoint | No traffic rearrangements shall be carried out until after the Administrator has advised the Contractor that the submitted, and amended as directed, TMP is approved and suitable for use.
279ceba4-e83b-5379-a134-91218da8900f | note | Acceptance Criteria and Frequency (Project Specific) - Approval via Contract Notice - Per NTO
5b98b8a3-bd2f-5ac4-a76c-29db6553678c | note | Check Item - Hold Point 1
c526fdb5-77b2-56b6-8c73-87916f4ca6f1 | note | Reference - MRTS02 Cl. 5.3
a43a5bf7-9beb-45a8-8296-651f80d9564e | signoff | HOLD POINT
ede7bde8-adb9-45c3-8b89-c8692c501361 | checkpoint | All traffic control devices inspected and records kept in accordance with the specification
8511e79c-0f0a-5a91-9f88-6d39d70443b8 | note | Acceptance Criteria and Frequency (Project Specific) - Site Records - Daily
130035bf-14e5-5926-8a66-318b1adad814 | note | Check Item - Check Item
a1565179-b15c-5e86-bc27-40ab3fe4bb80 | note | Reference - MRTS02 Cl. 5.6.4
a1d69ce6-641b-44e6-9509-75c6fee6a242 | checkpoint | In the event of a traffic crash/incident within the site, the Contractor shall record the date and take time and date stamped photographs of the signs/devices in the vicinity of the crash.
251b971f-cf69-5964-b923-125a5fdfa912 | note | Acceptance Criteria and Frequency (Project Specific) - Incident Report - Per incident
f65b68a1-6bc1-5adb-8b3e-d42184b315ea | note | Check Item - Check Item
ec11eddc-a5aa-5da5-b792-70e4f65108cd | note | Reference - MRTS02Cl. 5.6.5
705a66dd-d266-4166-a644-16a2f53fc5bd | checkpoint | The minimum number of lanes to be maintained on midblock sections of road will be determined as per the method (a), (b) or (c): As Mentioned MRTS02.1 Cl .3.2, 3.3, 3.4, 3.5
9359dcd4-86d5-5619-ada2-f5e93e5038e6 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
fdc4ba9d-2905-528c-801b-fb6f414b8b4c | note | Check Item - Check Item
dc0920ff-9f2d-5701-a10d-bb971ae0b4bc | note | Reference - MRTS02.1 Cl. 5.7.3
3b78273e-5765-4ddf-86f5-8b7474bb8c5d | checkpoint | Traffic may be altered from its existing route via the following Cl 3.8 MRTS02.1
04187e7f-a1f2-5aff-a6c0-8215a3bd0d5c | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
84662d53-d987-58a9-8fff-78296a8b53b9 | note | Check Item - Check Item
7f45e7bb-ad5f-5c5b-9eb6-d5de4bffd0b2 | note | Reference - MRTS02.1 Cl. 5.7.4
c3e2c9a9-ce24-487f-8d33-39f22d0e9561 | checkpoint | All TGS's prepared by a suitably qualified person and submitted to the Administrator for review and shall be accompanied with a specific risk assessment. Innovations, alternatives and departures from standards shall be certified by a RPEQ.
c11658ad-8847-5c07-b789-2f9f71654bb5 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
3019a9f4-4bd0-556e-8929-0e728a3d8310 | note | Check Item - Hold Point 2
6a229267-a896-52d8-ad6e-b8c15975c894 | note | Reference - MRTS02 Cl. 6.2
07612779-899d-4b6f-8ab2-8d1696c8e23b | signoff | HOLD POINT
64ff5557-8de1-4113-a5ca-96b3449c6d58 | checkpoint | The Contractor shall provide a minimum of two VMS (one in each direction) for the works under construction on Gatton Helidon Rd. VMSs shall be in place a minimum of 2 weeks prior to the commencement of the works on site to provide advance warning to the road users of the impending works. The requirements of Clause 6.5.2.1 of MRTS02 shall apply with regards to their use
09bec48e-21ab-5a7f-8e28-e5915cae032e | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
4d2e5e58-638a-5dfc-8ed0-9c8e44cf5c88 | note | Check Item - Check Item
45597c8a-b04e-575a-a3bd-569f51973569 | note | Reference - MRTS02.1 Cl. 6.5.2.1
e79584ee-def0-4888-bcfc-20a90a70bc77 | checkpoint | The Traffic Management Inspection report to the Contractor for action, together with documentation of any actions taken in regard to findings.
cdd0c2cd-ee83-5437-8f81-a7ff74385af5 | note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
66ae341a-aa91-577b-9699-08bb2716a079 | note | Check Item - Milestone
3cb10352-c441-5e4e-b09f-76bb10f10f8f | note | Reference - MRTS02 Cl. 7.5
7c48bce0-dcb7-4800-ac70-ed56cf2b939c | checkpoint | The following requirements for side tracks shall apply as Stated in MRTS02.1 Cl 5.7
4a26579d-8342-5860-b3bb-9f2190be4ddb | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
8303cc34-1bd8-521a-bf24-c6c3707542dc | note | Check Item - Check Item
348d71ec-f49c-5388-a97a-426ac88f5d1e | note | Reference - MRTS02 Cl. 6.5.3.3
4f0e05ea-077c-463c-987f-678daed7aa89 | checkpoint | The following additional control measures are required to mitigate end of queue crashes as stated in MRTS02.1 Cl 5.8
8b37cd22-93e6-5710-acff-0f480792872a | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
f7cb455d-e617-5835-a2a0-bd87c5afe5a2 | note | Check Item - Check Item
9f701448-b843-51a5-a909-b232b7d84c86 | note | Reference - MRTS02 Cl. 6.5.7
4f49d603-3aea-49dc-9a36-7c2085c52c72 | checkpoint | On asphalt and bituminous surfaced pavements, when permanent linemarking will not be in place outside working hours, temporary raised pavements markers (Stick and Stomps) are to be installed and maintained on centre lines, lane lines and edge lines at spacing of not greater than 25 m (except for side-track tie-ins where spacing shall not exceed 5 m). Temporary pavement markers shall only be in use for a maximum of 48 hrs and shall be replaced by linemarking after such time. If the Contractor is unable to complete line spotting by the end of each day’s work and the road is to be trafficked, the Contractor shall delineate all separation and lane lines as above. Existing longitudinal lines are to be removed by abrasive blasting or approved other method approved in writing by the Administrator when temporary lanes are in place
a56a0e1c-d8b6-5fcc-aa84-7b9cae3617e3 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
b9a473e5-36bc-5057-ba46-11a2b86036bb | note | Check Item - Check Item
61bb94e8-690c-5bc3-9630-e3ffd3560c5e | note | Reference - MRTS02 Cl. 6.5.8
aa03fb01-81f5-4653-b871-59375c3f56e0 | checkpoint | Temporary road lighting shall be installed in accordinance with MRTS02.1 Cl 5.12
2ce05393-7f02-558f-83f8-ca8da032e851 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
b0658b25-df37-575b-aac5-47c99e5d978b | note | Check Item - Check Item
c6a39b34-8028-5bc7-8dc2-6bb1fa545ad9 | note | Reference - MRTS02 Cl. 6.5.13
c71f7f13-7be5-49e2-af90-e508328d6f85 | checkpoint | In addition to the requirements of Clause 7.1, there is a need for an independent review to establish conformance with the approved TMP and TGS and with the performance requirements of MRTS02 – Provision for traffic
e932f20a-cfae-552b-9c11-4d4d17452643 | note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
c602855d-b09d-5c55-9853-22cfaef61e87 | note | Check Item - Check Item
2c6ae606-fc35-59c7-918b-5ca16cdcd8c2 | note | Reference - MRTS02 Cl. 7.1
531a87de-cd9d-4c41-b14e-180527dc9dce | checkpoint | Supplementart Requirements completed as per MRTS02.1 Cl 8
27fa7f58-fb87-5046-991f-7f2d1aff70eb | note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
1734f09b-8222-5a5c-ad7e-41408ed0c9bd | note | Check Item - Check Item
d96bfe7d-2e06-574e-b020-06f00d6a087b | note | Reference - MRTS02 Cl. 9
5ec7b0ec-770d-4fb8-b2c6-83d8a9732ff8 | checkpoint | Supplementart Requirements completed as per MRTS02.1 Cl 9
fb82fad0-a29b-5c8c-9b04-26cff560d18f | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
c7004869-3d2c-5a0e-ada1-8b14574e1f1d | note | Check Item - Check Item
05aba69a-7e41-54f3-bae9-8015163dedfc | note | Reference - MRTS02.1 Cl. 9
69661642-ca7e-4c0f-b822-c4803dd52bdb | checkpoint | Final Verification
0ea433dc-828a-5552-a380-7982f0f51159 | note | Project Manager Verify that the Above has been Constructed according to Specification
0cd4d813-f913-57a9-8a74-983adf5fb242 | textbox | Print Name:
0015f4e6-0c38-5960-8839-7d2c588f9fe2 | date | Date:
6afbbc11-f0d8-5d66-9a7b-6b5e4e56fe09 | note | Client Verify that the Above has been Constructed according to Specification
2e89b3f4-468a-544e-8313-587cb39ee4a1 | textbox | Print Name:
530c0272-a7e8-583a-bafa-c948dd143177 | date | Date:
63db548a-62b0-4b95-a14e-a0e7ff3dfe82 | signoff | Signature
1ca660f3-1170-4c08-a59e-f3d4cc4f55ca | checklist | 03.01 - Removal of Existing Drainage Structures and Concrete Slabs | itp | 03.01 - Removal of Existing Drainage Structures and Concrete Slabs
0d9907df-7de4-401d-a18c-98a17c04bff6 | section | Details
8ab6b7b4-9abf-4a28-8149-2ea7321dcee0 | checkpoint | Culverts and culvert end structures shall be removed or demolished where specified in the drawings.
e75b4b0a-9612-57b1-a809-9d3cce577f17 | note | Acceptance Criteria and Frequency (Project Specific) - Culvert Removal - Per Culvert
0ba588d0-1302-554b-8287-def4d886eb88 | note | Check Item - Check Item
26781bfe-0d9b-5693-b9c7-0fa5b534322e | note | Reference - MRTS03 Cl 9.2
3b864a02-779e-4cb4-97e3-bc79e067a7df | checkpoint | If existing culvert components are to be removed and re-used, they shall be removed and stacked in a manner which avoids damaging the components.
7d9e649f-0b63-5ad6-b58a-2f063725954f | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
f8c4a37f-7531-5690-a319-c78a84ed5d82 | note | Check Item - Check Item
4b814481-3193-5524-a7b0-2832c0e33120 | note | Reference - MRTS03 Cl 9.2
fb5788a7-566b-4ada-bea3-afb2ebbb820b | checkpoint | Removed components which are not to be salvaged, nor reused, shall be removed from the Site and disposed.
e96258da-a7df-5dc3-a7af-6dae93a54588 | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
128d11b6-18f4-5751-8b56-559560f0875f | note | Check Item - Check Item
2707c736-fa83-5010-9d48-86c5fae995b3 | note | Reference - MRTS03 Cl 9.2
bf165e4f-720a-49f7-940e-912d0a4bfa17 | checkpoint | Excavations carried out and the void left by the removed culvert or end structure shall be backfilled to reinstate the area to a safe and free draining state.
4b039abd-5426-59c7-8618-0ee1dc5150b4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
e7520c07-f3f0-5bea-a557-b0444a2b7a10 | note | Check Item - Check Item
bcadb5ee-a64f-5b57-85ca-06194b167c5c | note | Reference - MRTS03 Cl 9.2
6124e4f9-fcff-49d0-b7c8-e99c0f7894e3 | checkpoint | Existing kerbs, channels, kerbs and channels, kerb crossings and concrete slabs shall be removed or demolished where specified in the drawings.
5a2708db-10ed-5fb3-989d-171b5bb02c93 | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Kerb
daf455ea-8255-5ef3-bc69-461b8a24e633 | note | Check Item - Check Item
66cebcaf-80b6-576f-ba31-ab14f5021a7f | note | Reference - MRTS03 Cl 9.4
19d8f9d1-d403-4c0a-93f9-c97851b9f497 | checkpoint | Any Kerb and Channel or concrete slab to be removed is saw cut at removal extents or removed to existing joint (or removed in its entirety) where specified in the drawings and no damage shall occur to adjacent work
6e3a810a-febf-5fda-b561-38b44887c7d2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9d1315c1-78d4-544f-b0e5-9429b7f48ce2 | note | Check Item - Check Item
d28c9619-0007-5e01-bb28-383aa9887792 | note | Reference - MRTS03 Cl. 9.4
bf08bbf7-ef04-4926-83a2-e204f11ee97a | checkpoint | Kerb excavations backfilled to flush with the surrounding area.
dd940738-a121-5fa1-8609-a6dc3a78bbd6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
37ac7cee-6a3b-55c6-b844-729e11f8fe4f | note | Check Item - Check Item
c022b1f6-ec1e-5c40-a986-eb2049ce5769 | note | Reference - MRTS03 Cl. 9.4
1f69c1de-eadf-4b8b-9205-87188e818b31 | checkpoint | Final Verification
b2ef1278-e587-5ba0-859a-85fb63d84692 | note | Project Manager Verify that the Above has been Constructed according to Specification
ef3d26d4-09d3-5654-9749-fa108a9c11fb | textbox | Print Name:
3caa2030-3c4b-5b56-8458-ea2f430a0834 | date | Date:
96d66129-fbb5-5203-874a-8194159d5114 | note | Client Verify that the Above has been Constructed according to Specification
a9a6296e-ec14-522d-8a58-3ffebaffbdf8 | textbox | Print Name:
7c0249de-e720-55e3-926e-a18e97404534 | date | Date:
7cfb3d92-86dd-45a2-8d7b-4cea382ecc57 | signoff | Signature
e5672de8-5dcf-47fd-940f-9d0aa45316a5 | checklist | 03.02 - Supply and Installation of Precast Concrete Pipe | itp | 03.02 - Supply and Installation of Precast Concrete Pipe
62c6ca12-d784-4448-aad4-5daed7ac5d02 | section | Details
618171bb-c2ef-4dc4-a7f0-00bfd2353784 | checkpoint | Contractor shall set out installation as shown on the drawings. The Administrator will determine the design appropriateness of the set out with regard to the actual site conditions.
09533698-3ace-57ad-9e6b-47a328db81df | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b52df3f3-d982-58f1-9941-fd3ca7db1bdb | note | Check Item - Hold Point 1
c252ffbf-1799-537c-8a77-2972457c8b96 | note | Reference - MRTS01 Cl. 8
f5a3e4ad-cff3-4843-a911-0d3b3870c827 | signoff | HOLD POINT
cec883af-7c44-4433-8e23-2f5609f63965 | checkpoint | Concrete Pipe culvert components comply with MRTS25/26 Box Culverts Comply with MRTS24
75cf078f-e6a9-5692-bc46-71d3a769c810 | note | Acceptance Criteria and Frequency (Project Specific) - Manufacture and Test Certificates
05d7fa1e-fe60-580d-b27a-2bbe74b6cf39 | note | Check Item - Check Item
2de9ed6f-62e3-570b-abaa-b07a87d664bd | note | Reference - MRTS03 Cl10.2, MRTS25, MRTS26, MRTS24
be3f1bf4-3618-4e48-abfb-50916139955d | checkpoint | Component size, wall thickness and class is as specified in the drawings
935222a3-d4b0-5688-a70c-e7b3f33d7ed3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
854077a9-fa37-581f-8978-be52e6f4d9f3 | note | Check Item - Check Item
8daf6276-07cc-5ac3-ad56-9fac506627d6 | note | Reference - MRTS03 Cl11.2
0bb44160-d365-457a-a3e8-f6f88d81cfe8 | checkpoint | Bandage Covers are a Proprietary Product, either: Synthetic or Rubber Band, samples inspected by administrator
f0db1677-0bd3-5440-91e0-ea37d25d8868 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2b61788a-9e7c-55c1-abb3-231501e0cf1e | note | Check Item - Hold Point 1
8f62b1c4-9c5a-5ec5-802a-4a03f79b20ba | note | Reference - MRTS03 Cl11.2
3e0d8609-9b45-4943-9bb5-d37fc77c82c8 | signoff | HOLD POINT
70ea8348-c309-493a-b520-dce02fea6798 | checkpoint | Procedure for excavation, installation and backfill submitted 14 days prior to works.
4c549994-a455-5a57-b9b0-037600baa015 | note | Acceptance Criteria and Frequency (Project Specific) - Written
a34e6a37-099b-5d23-9c70-6389347a4831 | note | Check Item - Milestone
e8f9f818-e11c-58a3-913b-7f06283e3f83 | note | Reference - MRTS03 Cl11.3.1
abd78722-7beb-4821-8cdc-3f89f3c413ac | checkpoint | Culvert Construction Procedures accepted prior to commencement of Installation
297729b7-3fd7-531a-a29b-2a7004a1a11f | note | Acceptance Criteria and Frequency (Project Specific) - Written
cf643934-106c-5a9a-871e-fa4ead5989de | note | Check Item - Hold Point 2
e190751f-0a5e-58c0-8a26-6bdfccde5296 | note | Reference - MRTS03 Cl11.3.1
52b23f1e-c218-4453-bbb4-92b71412653d | signoff | HOLD POINT
de6fc886-3682-4292-9343-dcadb278de6d | checkpoint | Components installed in the locations and in accordance with the details as shown on the drawings
c4653604-93b0-5121-ac1e-3fad926cf53f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bd77112a-fae2-5716-a91d-762a68f5da22 | note | Check Item - Check Item
60c9e9c9-ac8d-58a0-bfcb-1eac2e9b0520 | note | Reference - MRTS03 Cl11.3.1
c5f8c296-53bd-4500-847a-60605bd11e92 | checkpoint | Excavations completed as per MRTS04
7236b158-33cf-51ac-87f5-1ab16e3e9773 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
b43cab27-5fef-5325-8d2e-15afaf965f29 | note | Check Item - Check Item
769b36ac-4a10-5df9-bd9b-f0fb621d8dc0 | note | Reference - MRTS03 Cl12.3.1, MRTS04
d9a4f4e0-bbeb-4af8-b167-9657991c2f40 | checkpoint | Foundation bedding and Haunch zone material placed in Accordance with MRTS04
2a8550ea-1f85-5573-9934-9d1c3806dd35 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ecbd2777-7373-54ce-97c9-0dc672f6128d | note | Check Item - Check Item
c83a1427-ec11-5f15-a022-aeea09ed10dc | note | Reference - MRTS03 Cl11.3.2
267e23a9-b87f-4db4-8e93-b9d813f55938 | checkpoint | Components are assembled as per manufaturers specifications
b5641949-23d5-56e6-9e31-6e495aa0757f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3dc79f64-17e6-5dfa-8f2d-01c30ed5f56d | note | Check Item - Check Item
468cc84a-a0c8-5365-9e8c-4c1457e84124 | note | Reference - MRTS03 Cl11.3.3
c4e87d05-290b-4de3-b824-1a8a2f13da15 | checkpoint | If Possible, Contruction commenced at outlet. Ends of components free from foreign matter.
8bd6d019-c8fb-5e3b-84d2-76c04b927fb6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
47cf2cac-d1f1-5027-a8c0-8542619a08ca | note | Check Item - Check Item
5d541902-df1e-529a-89f0-b61f5c4fe017 | note | Reference - MRTS03 Cl11.3.4
e7980a60-3380-4e2a-9064-826fc00dbef2 | checkpoint | Placed with external groove or spigot end facing outlet with minimum of 50mm bedding material
d528fa2a-58fb-5911-9285-69c87968be52 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0e5e6ef2-304e-5414-bddb-5c707784c226 | note | Check Item - Check Item
f5b3c4e0-c14a-5aee-bb1c-1416a448e618 | note | Reference - MRTS03 Cl11.3.5
f5bb3558-e455-4d9e-b5a3-843cc40c6b8b | checkpoint | Pipes laid with the word 'TOP', where marked, or lifting hole facing the top. Lifting holes plugged after the pipe is installed.
afa1e54b-3831-5700-8d1c-736cb6f811be | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5f19e4d4-87d8-55f5-8a10-fc8697145cb9 | note | Check Item - Check Item
cff598de-c532-549e-aad7-825028b05021 | note | Reference - MRTS03 Cl11.3.5
631eed5a-2ff7-479e-b873-d35d129b78eb | checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator.
94ac57e7-5893-58bc-831c-c5dacd19a02f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
df7def97-9f52-5a5d-bc64-c609c0335166 | note | Check Item - Hold Point 3
52056e31-c1bc-5585-9b69-228e7e682b55 | note | Reference - MRTS03 Cl11.3.5
4e5d2fbe-4180-4f64-ba8d-0a7319a9eacb | signoff | HOLD POINT
ee7c71bf-ffeb-495f-8a66-a714d973eb5a | checkpoint | Where RCP's are required to be cut, the cut surface shall be given two coats of a surface tolerant epoxy.
ba210702-7dfb-5c7d-b48e-f3e292ad8ab3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d8dcd1c1-2eaf-5342-a657-ec23887eeedd | note | Check Item - Check Item
1802af1b-22ab-54bc-bf17-a3f4cf19fe6b | note | Reference - MRTS03 Cl. 11.3.9
f8cc4384-f8ba-43b9-9d60-bfa2099667af | checkpoint | Backfilling of culverts shall be carried out in accordance with Clauses 15 and 20 of MRTS04
3be6f427-35ee-569e-9b8d-17c1eb230e82 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
bea5563f-d02f-5e7f-84b7-4414d72fa627 | note | Check Item - Check Item
92fda4b6-87b2-5d9c-ad58-afa2decb1a1f | note | Reference - MRTS03 Cl. 11.3.10
51abe8eb-f67e-42d8-a018-15a85c531c67 | checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met.
927f3e96-d556-5099-a711-e1ed5a02f184 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6618586e-1dcc-5b37-8458-d308ad7a29ef | note | Check Item - Hold Point 4
778ae0d5-eec0-5e02-a87e-7925283dfb7f | note | Reference - MRTS03 Cl. 11.3.10
0b25e96a-3ee3-4d2e-b614-301cb12c87cb | signoff | HOLD POINT
113b05d5-532d-4347-892a-8574a1471d70 | checkpoint | Survey Requirements: All points (inlets and outlets) shown on the drawings.
d0f5598f-2f77-54ea-bbde-aa530136f960 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6300c5b6-975e-59db-8051-8836430362bf | note | Check Item - Check Item
31411ec2-22d2-5d2d-bb03-2af43a64fd9c | note | Reference - MRTS03.1 Cl. 1
44f88768-28e8-4324-81ff-e59fe3ed6392 | checkpoint | Supplementary Requirements Completed as per Clause 52 MRTS03 & MRTS03.1 Cl 6
fcd88919-b695-59ca-ace5-f197a2f2d14b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
15dfc87c-90e1-5ac4-aa53-4873fd902bc9 | note | Check Item - Check Item
9a0e5ba3-6e8c-5648-b62b-d7924f89f8ef | note | Reference - MRTS03.1 Cl. 6
6255f21a-d2ab-4828-a9c8-ac164e56d6be | checkpoint | Final Verification
68f5a7e1-0371-59cc-a833-09b381f51341 | note | Project Manager Verify that the Above has been Constructed according to Specification
70c301e7-7e6d-5a35-9d21-728290045d18 | textbox | Print Name:
5cc996ee-b6ee-587c-99bc-e37a515bd795 | date | Date:
58f06015-dab8-589d-b787-d4035a0e094f | note | Client Verify that the Above has been Constructed according to Specification
9cf2e5fa-7785-5aeb-a497-1f23de1b74a4 | textbox | Print Name:
ee33a170-a3ff-5f63-9e56-124dbdbf8485 | date | Date:
b5028509-07d2-40e4-8e63-e211703e6e68 | signoff | Signature
3744b1eb-4370-45c8-8db6-d0ed24317cd0 | checklist | 03.03 - Cast Insitu - Culvert Component/End Structure | itp | 03.03 - Cast Insitu - Culvert Component/End Structure
266ad6b8-4381-40eb-bae0-3983c1a9e733 | section | Details
2e3925b0-7f69-4cbf-96ed-24d943856058 | checkpoint | Concrete Conforms with Cl 6.1 (MRTS 70), Concrete Mortar conforms to Cl6.2, Steel Reinforcing conforms to MRTS71, Rock Masonry conforms to Cl33, Grouted Rock Pitching complies with Cl 34, Steel Wire Matresses comply with Cl 37
8408c3f3-9676-5aa5-b6d3-201f9cbca4c7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS70 ITP
4943d6a6-7a54-578c-82fa-32a0b9b20157 | note | Check Item - Check Item
d4318bb7-6b19-5b23-aa1e-bbc508a85515 | note | Reference - MRTS03 Cl 14.2, Cl 15.2, Cl16.2
920d8d45-a561-40b2-a595-0750b2a1787c | checkpoint | Cast-in-situ end structures such as headwalls, wingwalls, aprons and kerbs to culverts constructed in the locations specified on the project drawings and comply with standard drawings 1304, 1305 for pipe culverts and 1240, 1250 & 1260 for box culverts as applicable
d2740b0c-c959-5f77-a740-f2755dd3549b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9bbf22bc-1bc6-5fec-bf4b-c5bc7a3381b4 | note | Check Item - Check Item
fa85cf8e-b5d8-506c-9885-a3ad93c16677 | note | Reference - MRTS03 Cl 15.3
49cd631e-c6d6-4479-88f3-13e4e6527ec0 | checkpoint | Where material on or against which culvert bases are to be constructed is other than rock, the material is compacted as per bottom of excavations in accordance with MRTS04 General Earthworks.
bd6a250b-fb50-5cc9-bc67-0e281c8a50c6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, ITP
3ffa1ad0-b3aa-55a8-a49d-03364e6c8eca | note | Check Item - Check Item
43e4408d-1c3b-5a75-8ee0-743ce228dc85 | note | Reference - MRTS03 Cl 15.3
0523d559-8335-437a-a87a-43b57229b4a9 | checkpoint | Endwalls, wingwalls and concrete aprons constructed without a foundation bedding unless specified otherwise in the drawings.
e7dfa60e-f28a-594e-8c23-fa5dc125a733 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
02c561aa-e858-59d8-9a61-59903a5aa156 | note | Check Item - Check Item
90a3e280-277d-55f6-8866-b1d31b618510 | note | Reference - MRTS03 Cl 15.3
762a3cee-2bfa-4cf7-8665-7e2f7b21b4e6 | checkpoint | Endwalls and wingwalls seperated with an expansion gap unless otherwise specified on the drawings.
e3a759ec-3f9c-5896-b012-2d18d8164925 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
beed135b-98fb-5723-af00-59ab67bebe02 | note | Check Item - Check Item
533fc31c-7281-5d59-a885-0bf616af864f | note | Reference - MRTS03 Cl 15.3
d35a3815-29e4-47cd-bbf6-601d681f0039 | checkpoint | Supplementary Requirements Completed as per Clause 52 MRTS03 & MRTS03.1 Cl 6
ba8bebb0-349b-5d0e-8725-0d4a271bc3f7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
872f496b-b2fa-5dd1-9e40-b322b882defd | note | Check Item - Check Item
f535485c-135d-5cf6-a2ab-643edf915892 | note | Reference - MRTS03.1 Cl. 6
cc7fe153-4a8b-4b49-817c-7509b75d0eeb | checkpoint | Construction of culvert base, walls or endwalls shall include the construction of integral nib or cutoff walls where relevant
1890f90d-83e3-50b3-b98d-41bc4b79adb7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6d51179e-8d60-5262-868f-6397d1ee969f | note | Check Item - Check Item
22ac02fc-c63d-5016-aad6-71809d437f48 | note | Reference - MRTS03 Cl 17.3, Cl 18.3
6dee30ff-ac8f-4670-a70c-d35ff3e2a031 | checkpoint | Construction of culvert base, walls or endwalls shall comply with the Geometrics Section stated in Clause 1.5. MRTS03.1. For Each Structural Element, testing requirements must contain: Dimensional, Positional, and Relative Position
08073dc9-bbe5-5ed7-9f7a-587db8408805 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d9d79b52-e5ed-5c0a-bb43-7d785e14a15c | note | Check Item - Check Item
84adfa2b-8d1e-5db8-a81d-7f942fbe2133 | note | Reference - MRTS03.1 Cl 1.5
7f120d10-7356-4d45-be8e-13f3b57be865 | checkpoint | Final Verification
2fdeb2d4-109d-550a-8cc0-c3ffdd9c43f2 | note | Project Manager Verify that the Above has been Constructed according to Specification
8dbe4385-4cd4-5704-855f-3ce9ffc0b789 | textbox | Print Name:
f1ef7df6-665f-56e3-9f5e-2d31871da44c | date | Date:
929c963d-0c67-5e5d-b00c-2ddebb482733 | note | Client Verify that the Above has been Constructed according to Specification
fa9ef91d-ea7f-5155-a4c7-96ff423b3cdf | textbox | Print Name:
1c92bd2a-cfb3-59ab-b493-f2ae2ae7c076 | date | Date:
e0ff55dd-800a-4332-8785-268fc44b59b4 | signoff | Signature
d580af58-64ef-48f2-a2cc-876166cec272 | checklist | 03.04 - Pre Cast - End Structure | itp | 03.04 - Pre Cast - End Structure
6e47912e-c9b6-42e4-b1ab-caee521aa3a0 | section | Details
ac175a4a-0d4d-40ff-aecf-13a3337caac5 | checkpoint | Precast end structure conforms to Cl6.6, Concrete Mortar conforms to Cl6.2
ac313e14-6422-5546-82fa-add8a52b9b68 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7da72c48-2e87-5292-b1d3-8c011700f1f6 | note | Check Item - Check Item
4f50fa97-5a92-500a-ad03-d411709f0827 | note | Reference - MRTS03 Cl 16.2
9f4849a4-c319-4e30-b4a3-3e8e8f0a7de1 | checkpoint | Constructed in the locations specified on the project drawings
2e99842b-eaf7-5f67-a05f-4273afd571f2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
aae64bb1-4617-5413-a248-b22b2be0510c | note | Check Item - Check Item
32f2f489-0057-56ed-97d8-b2bb61951228 | note | Reference - MRTS03 Cl 16.3
eeac43e0-a623-4c6d-8588-6c42db4a212c | checkpoint | Where material on or against which end structures are to be constructed is other than rock, the material is compacted as per bottom of excavations in accordance with MRTS04 General Earthworks.
8eec556d-61b2-59ad-b9d7-cf6a09a65de0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, ITP
7f35f1c0-fc20-5cda-b01c-152bad51ae94 | note | Check Item - Check Item
e0bdc3d9-d34c-5060-9c1a-9d50c007f801 | note | Reference - MRTS03 Cl 16.3
de1a3bc7-c4cf-4a5c-950b-b29419688d82 | checkpoint | End Structures laid on foundation bedding which provides continuous even support
407f1497-4c48-58c9-a409-4570ddd5581b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
12949672-0f48-5c50-bf99-e6dd8bd0f36d | note | Check Item - Check Item
d7d2f513-4f78-54ad-959d-a5a98864b12a | note | Reference - MRTS03 Cl 16.3
63f9c743-3b76-4d50-a67e-3f504f469358 | checkpoint | Joints between end structure and culvert in addition to any holes and recesses are filled with cement mortar and finished smooth and uniform and cured for 48hrs
32eea183-f48a-5bc1-886e-4b73be474bca | note | Acceptance Criteria and Frequency (Project Specific) - Visual
82e55f48-25f6-5c7f-b578-989a15cb6e43 | note | Check Item - Check Item
6df6640d-066e-5b4c-be16-710dfc9231b2 | note | Reference - MRTS03 Cl 16.3
b9e91f94-349b-411f-94e1-eba684b908f3 | checkpoint | Backfilling operations not undertaken during curing period and complies with MRTS04
f8a06bcd-c7af-5e56-8bfe-f5a76c637cb8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, ITP
285a6605-4d40-5f6b-9169-b5511ffa3090 | note | Check Item - Check Item
dbb58008-5559-5481-a525-21d7944b8d78 | note | Reference - MRTS03 Cl 16.3
9ba440b6-0e99-4c27-be8a-37957ac2f1f0 | checkpoint | Geometrics: All points for which levels are shown on the drawings
02db5b03-ad7d-54a6-86ee-75ed3b3f419f | note | Acceptance Criteria and Frequency (Project Specific) - Horizontal: ±100mm, Vertical Invert: ±10mm
c433f4da-a69a-57a8-9ea1-2f77f68bc4cb | note | Check Item - Check Item
5d47d16d-b9be-5f9c-b8a6-d892c65167cd | note | Reference - MRTS03.1 Cl. 1
632e458d-bdf7-491a-9eda-db6c64d0a8d8 | checkpoint | Final Verification
ed16ecbb-2559-5612-9e06-eab723cc28c8 | note | Project Manager Verify that the Above has been Constructed according to Specification
b7995103-d043-525c-89bc-e67b1f0499f6 | textbox | Print Name:
7f713191-40c8-5e75-ba3a-fadb8143a256 | date | Date:
205d62b2-a88f-5263-949e-bf4dd54ab63d | note | Client Verify that the Above has been Constructed according to Specification
ef7acecf-6307-522a-8002-0d66ada11919 | textbox | Print Name:
97eb32a7-0f0d-59f0-b021-6e46e4512f4e | date | Date:
c3a6632c-1ac2-48b2-bb60-ed265c4b3865 | signoff | Signature
5aebc1be-7d9f-49af-83c2-ebe1ac9572e6 | checklist | 03.05 - Supply and Installation of Precast Box Culverts | itp | 03.05 - Supply and Installation of Precast Box Culverts
44813817-fbdf-4fba-b1de-8c68c3f0aa9c | section | Details
39939f34-c03f-43de-9999-a31f4836b623 | checkpoint | Contractor shall set out installation as shown on the drawings. The Administrator will determine the design appropriateness of the set out with regard to the actual site conditions.
5a74fe6c-16c0-5879-889b-4cbf1031dd4f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
11edbe1f-56bc-5989-8be4-4fea98aa0edf | note | Check Item - Hold Point 1
14408d8c-5046-53ae-9390-ee8d5cd332c2 | note | Reference - MRTS01 Cl. 8
a3a5c75f-93cb-45f0-9720-e53b23b0c217 | signoff | HOLD POINT
ee188997-15e7-4c17-90b1-480bc5503f0b | checkpoint | Concrete Pipe culvert components comply with MRTS25/26 Box Culverts Comply with MRTS24
d30f207b-5efe-5a28-a08f-38b0c83b1d5a | note | Acceptance Criteria and Frequency (Project Specific) - Manufacture and Test Certificates
70d0ea09-0550-526a-8db8-271851cd10b6 | note | Check Item - Check Item
fcdeeba9-b4d2-5baf-98a4-ec05a99e71c9 | note | Reference - MRTS03 Cl10.2, MRTS25, MRTS26, MRTS24
8a9397d7-ff15-46d3-bdb4-5865c71add87 | checkpoint | Component size, wall thickness and class is as specified in the drawings
4ea2c7fc-2cbc-5fc8-a0b0-cef69fddbbd3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e7501818-d288-5247-87aa-b0dddc8fbe47 | note | Check Item - Check Item
7d91e9e1-cba2-5146-8a2c-bbfb044de824 | note | Reference - MRTS03 Cl11.2
fec238dc-6960-4c38-8b74-e1af2dfef047 | checkpoint | Procedure for excavation, installation and backfill submitted 14 days prior to works.
2e3426dd-b484-506e-bbae-f4b4e6fb370a | note | Acceptance Criteria and Frequency (Project Specific) - Written
7b66c171-2d34-53d1-a9b1-d1308f6b63b7 | note | Check Item - Milestone
0fdc7391-db9d-5c6a-965b-f7bc48c630fc | note | Reference - MRTS03 Cl11.3.1
a5b8852f-279b-49ad-ad4a-fd23271d71c1 | checkpoint | Culvert Construction Procedures accepted prior to commencement of Installation
d20f18a1-6e09-5c8c-ba5b-f986ff7572a8 | note | Acceptance Criteria and Frequency (Project Specific) - Written
32b694c5-2b7d-5f20-b19b-3ce1dd892828 | note | Check Item - Hold Point 2
266bdd68-b026-5508-a108-f68562cfa079 | note | Reference - MRTS03 Cl11.3.1
a938cac7-6802-4ec4-a0a6-2aac2fc0a79d | signoff | HOLD POINT
865752ef-a312-4c7c-ab85-2854c77b8d8c | checkpoint | Components installed in the locations and in accordance with the details as shown on the drawings
c7be7600-daf5-5ab5-b187-bd6eeec1da04 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6448e1b7-ee68-5a2a-8050-4cd69c90c229 | note | Check Item - Check Item
8dde1634-b7b0-54df-a310-403a728bd091 | note | Reference - MRTS03 Cl11.3.1
a99db4e6-9ed9-4fe8-985a-01b0dccd5ef4 | checkpoint | Excavations completed as per MRTS04
82e839f4-4df8-52cf-b44f-33c925fd7648 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
5ac0ef62-cfb3-524b-9759-af96f94cb2b6 | note | Check Item - Check Item
c1fd2bd8-fc5f-5f9e-9034-9c7c379c03d1 | note | Reference - MRTS03 Cl12.3.1
1de597eb-4999-4c4d-b000-ddde828b0339 | checkpoint | Where material on or against which culvert bases are to be constructed is other than rock, the material is compacted as per bottom of excavations in accordance with MRTS04 General Earthworks.
c8143d10-af0e-558f-be8d-92c10b7666f4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
283c959d-744f-5016-be85-ea8227275e0a | note | Check Item - Check Item
e82fe028-69aa-593f-9cbf-7f67c54e3f31 | note | Reference - MRTS03 Cl14.3.1
8527c2ce-fc54-46fd-965f-c04bcd034f51 | checkpoint | Cast in-situ concrete bases, footings, infill floors and box culverts constructed without a foundation bedding unless specified otherwise in the drawings
33a6c8cf-6c40-59fe-83a1-520339ffb6e5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5b40e117-f44a-5241-8ad1-bfd87a3db550 | note | Check Item - Check Item
6e723eba-52bd-5e8d-aa3f-b14ad624905d | note | Reference - MRTS03 Cl14.3.1
935d0765-b306-47d7-9cc1-30c4925f2fc9 | checkpoint | Construction of bases, footings, infill floors and box culverts include the construction of nibs and integral cut-off walls
f47f43f4-2879-5337-bf9b-de5ef3c5f116 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
89e42d1a-a6a1-501c-b16e-165911553cb2 | note | Check Item - Check Item
ae76729c-299d-591c-b4ab-7dc835eb9e27 | note | Reference - MRTS03 Cl14.3.1
b39dcfc6-b7f7-4bdf-9d57-72df39af2225 | checkpoint | Components are assembled as per manufaturers specifications
9347d2c0-d6c2-553b-abb6-39bae15cb93d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d201f72e-8982-5966-ac06-31ff41f52944 | note | Check Item - Check Item
f89bd21c-3d20-52b0-aa03-8d7b27ecdcc5 | note | Reference - MRTS03 Cl11.3.3
8355b35c-be0a-46ed-92cb-a9a653ef0c42 | checkpoint | If Possible, Contruction commenced at outlet. Ends of components free from foreign matter.
ad3c29e2-090f-5acc-9cd7-0eaddf87fabd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
57d41f49-6b8a-5956-af95-1700aefbf949 | note | Check Item - Check Item
07e29e19-1464-5307-a380-e2393629cc66 | note | Reference - MRTS03 Cl11.3.4
72966390-60bb-477a-b079-40d9cb190f8e | checkpoint | Box culverts installed in accordance with Standard Drawings 1250 and 1260 or project drawings.
3056bfc2-4ee9-5578-9cee-4f5e60ca1752 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f3898e4d-1d20-5844-b361-c2655d21e8ca | note | Check Item - Check Item
9c5c2616-b97e-5348-8330-d17b564395ee | note | Reference - MRTS03 Cl11.3.6
0810ba15-1359-417f-8b01-00cd7960e26f | checkpoint | Holding down anchors installed to retain the units, where specified, as per the details on STD DWG 1250 and 1260.
56100136-b2f3-5b60-b5a7-12511917e7ce | note | Acceptance Criteria and Frequency (Project Specific) - Visual
76558777-ef57-5756-9bdd-e2b9723ec0dd | note | Check Item - Check Item
bb92813f-e0e8-59e5-be19-e8718c014951 | note | Reference - MRTS03 Cl11.3.6
34e21fcc-ff86-4180-a6bb-5f58dd32d951 | checkpoint | Where spanning slabs are installed, locating dowels installed in the tops of the units and the spanning slabs seated on continuous cement mortar pads on the adjacent unit.
5573cb8b-a19c-5e46-a9c1-61e52a3343d0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
093cc24d-34fa-555d-93ca-11239186fa5e | note | Check Item - Check Item
224a8a70-edfe-5b70-bbce-8301bd6151f1 | note | Reference - MRTS03 Cl11.3.6
bcf4f050-7e2a-4e34-bf04-153cd9e4ddaa | checkpoint | In multiple cell culverts, the gaps between the lines of installed cells shall be a minimum of 40mm wide and filled with 1:10 leanmix with max 10mm aggregate.
5f6be076-f75b-582e-a6d1-66e6a56193c7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e8d65945-5ae9-5638-8937-08e7b084b9e5 | note | Check Item - Check Item
1d747db0-12c0-54f1-85dd-3983fe5f9231 | note | Reference - MRTS03 Cl11.3.6
eefab2b6-892c-4229-8c9e-642a75964240 | checkpoint | Where spanning slabs are installed, the space between the slabs is filled with lean mix concrete.
844497b7-8119-51e0-9eec-0db58800df7c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a55f9a0a-7a66-5cbd-893e-c37853b0a778 | note | Check Item - Check Item
f1053b79-e8b8-56ab-b26d-52080619edfc | note | Reference - MRTS03 Cl11.3.6
109587c9-1454-4aca-8f47-e47a5c380f62 | checkpoint | Lean mix backfill cured for 24 hours before any other backfill material is placed over the culvert.
86c3382b-2f4e-5305-8990-9f21f647df13 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3d3f38f3-c81a-5053-b5fc-15bef05f44ac | note | Check Item - Check Item
d1500755-06eb-537f-a088-2ecd95dba711 | note | Reference - MRTS03 Cl11.3.6
13dceaea-83a2-407b-99b3-e754086ed040 | checkpoint | Backfilling of culverts shall be carried out in accordance with Clauses 15 and 20 of MRTS04
fc6a7791-e7e9-50cf-9267-1613e7689f71 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
5ae406fe-acc1-5f00-9d29-5008a5633cf2 | note | Check Item - Check Item
38631222-7dc1-5496-aad3-fadd49270162 | note | Reference - MRTS03 Cl. 11.3.10
9ca7c6c5-2389-4923-8011-d00186616cf7 | checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met.
b187c419-02c7-58ea-af3c-15a6eb35b19f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1493dc09-b550-598e-885f-cdfb0126e4ea | note | Check Item - Hold Point 4
2e7be154-5a06-501d-8ce6-83dccc00244b | note | Reference - MRTS03 Cl. 11.3.10
dfc7011c-d418-484b-97ab-ff5d64b19134 | signoff | HOLD POINT
62bc7a1e-245c-47fb-9d95-0b488fb0341f | checkpoint | Supplementary Requirements Completed as per Clause 52 MRTS03 & MRTS03.1 Cl 6
93180f71-5bfc-536d-a343-0b75c420b5f0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ff984901-30e7-5c91-ba58-ec39540fa975 | note | Check Item - Check Item
36bbc599-674d-59b1-a5fb-b51d469c3f9a | note | Reference - MRTS03.1 Cl. 6
d6597563-e1ea-4a01-97e1-72d38c3cec64 | checkpoint | Survey Requirements: All points (inlets and outlets) shown on the drawings.
a35093da-986b-5df6-b064-ee39b7f16416 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ec2ec0df-04d0-522b-8b8f-af1a0f932498 | note | Check Item - Check Item
56fb6a31-f602-5adb-88ab-9e447a2a4b65 | note | Reference - MRTS03.1 Cl. 1
21cf06a5-1ee2-4cf0-b741-b699b6e82f6d | checkpoint | Final Verification
a263eefe-f170-5909-b08f-71cf88f3681b | note | Project Manager Verify that the Above has been Constructed according to Specification
62cbf493-c5bb-59d3-b29a-60c8aba7390e | textbox | Print Name:
be26cacd-1256-5d3a-9455-989d7d6df2ee | date | Date:
a7e526dc-f0a6-5353-951e-88a651f1bad0 | note | Client Verify that the Above has been Constructed according to Specification
32292d98-417c-5c15-ab21-06589a0806f3 | textbox | Print Name:
52be656d-cbcb-52cd-afc0-dd6de456711c | date | Date:
e53d965f-3538-4b2a-9705-c4bf89babb52 | signoff | Signature
5ccce51a-597f-44d8-b90f-fee10d050ca2 | checklist | 03.20 - Kerb - Cast Insitu/Extruded | itp | 03.20 - Kerb - Cast Insitu/Extruded
d09e935b-0d7a-4d1b-ab50-38ff451de0fc | section | Details
c6e7629e-4f2d-460f-bac5-350ffcb19d4e | checkpoint | Supplied Concrete complies with MRTS70/71. MRTS70 and MRTS71 ITP completed.
63b3690b-8a96-5191-a620-7b0eba6b1052 | note | Acceptance Criteria and Frequency (Project Specific) - ITP 70.01
dd5cbaec-966f-54e4-a766-68e37661175c | note | Check Item - Check Item
3722277e-96ea-5701-837c-33f72c3b2c00 | note | Reference - MRTS03 Cl 18.2
a44c6251-5dd4-4fd3-a5a6-3023752899a6 | checkpoint | Cast-in-place concrete kerb / channel constructed in the locations shown on the Drawings and in accordance with the details shown on Standard Drawings (1033)
12e81f6e-acc9-584e-820f-d6580bec4e3c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
22fbddaf-532d-510a-9544-ad766b35c162 | note | Check Item - Check Item
82f6c5c3-e0fd-5462-8d1f-03105595f706 | note | Reference - MRTS03 Cl18.3
c5dac546-e226-4689-a606-6c1162c9415f | checkpoint | Excavations / foundation preparation in accordance with the requirements of MRTS04 General Earthworks. The ground surface moistened just prior to placing concrete.
a0e0b378-d7c7-5476-8fee-b6d9e281ead9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3de85438-788a-55de-9e6a-8bef4af49bed | note | Check Item - Check Item
bde68f82-7b8b-5e58-ad0c-d3de49571190 | note | Reference - MRTS03 Cl18.3
e623ce79-5703-481d-b31f-6cf2cf82b080 | checkpoint | Exposed surfaces of manually placed concrete to be steel-trowel finished.
236df2f2-9b46-567c-971d-1f2547980a7e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0efb1523-f0b5-52ad-9018-46e930dec5d4 | note | Check Item - Check Item
2343006a-5151-56c9-8e15-52dbaf7fffd4 | note | Reference - MRTS03 Cl18.3
df63cb29-6149-4bde-a761-8e1104f33c4d | checkpoint | Expansion Joints shall be installed at regular intervals not exceeding 20m. The joints shall have a compressible packing with maximum thickness of 6mm covering the full cross section.
f67c1533-6c77-5e16-8cec-a6366ebd178f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9a5d31b9-d349-5a55-a935-ab4d1c0c9b7c | note | Check Item - Check Item
1389d339-7341-55a1-9d48-cb639160793d | note | Reference - MRTS03 Cl18.3
ff683d2e-0174-47e0-b55b-afc121fab93c | checkpoint | Contraction Joints shall be installed at regular intervals not exceeding 5m. They shall be constructed be forming grooves 40mm deep and not more that 6mm wide.
fa3c702d-54de-5752-b08c-f20ac06555ad | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d68a7917-5f30-5d06-8ed4-4e04a438dc56 | note | Check Item - Check Item
9d044838-961f-5a5d-8d29-b5cca31e403f | note | Reference - MRTS03 Cl18.3
ae16863e-c3d7-4c8d-b9d6-d598e6934a1f | checkpoint | Concrete shall be cured at least 7 days before any other roadworks operations are carried out adjacent to the kerb / channel.
6f5b8ee1-f3db-57cc-8c7a-d4f4f6b32d53 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
eba090b9-2a82-57cc-8d7f-7149ea61526c | note | Check Item - Check Item
4226d44b-04ff-5737-ab04-94c5490c8198 | note | Reference - MRTS03 Cl18.3
dfbd592e-42d5-4c33-bf54-8ea838233e51 | checkpoint | The Horizontal and Vertical alignments shall vary by no more than ±10mm from those specified. Alignments exhibit smooth lines. Overall dimensions are at least equal to that shown on the Drawings.
54e3db7c-5a10-5dfc-a7cc-046307d88d8e | note | Acceptance Criteria and Frequency (Project Specific) - ±10mm from Drawings, 1 test per 10m (invert levels)
46deac02-6f06-51fd-bb5e-772eca040ae3 | note | Check Item - Check Item
ed5ea68d-b9f9-55d9-8069-2f22ec895b13 | note | Reference - MRTS03 Cl18.4
8adce60a-2b45-43be-9031-c3fc7d517d67 | checkpoint | WATER TEST: (on channels where the longitudinal grade is less than 1%). The test carried out as soon as possible after the concrete in the channel has hardened and water shall not pond to a depth of more than 5mm
994a4c4a-faf9-5056-bdef-53793dc12e48 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1b973345-c480-5f3a-8a3f-6db0abc55058 | note | Check Item - Witness Point
6af20874-2c95-5d72-96e1-0e646f634096 | note | Reference - MRTS03 Cl18.5
921c909e-ad5a-4593-bda7-e76fa5234a03 | checkpoint | Final Verification
7c8863ca-1b4e-5184-a4d7-5d5c628b5e9c | note | Project Manager Verify that the Above has been Constructed according to Specification
f6df43e6-5e41-5ef2-a2e3-17875bd53497 | textbox | Print Name:
d4c79224-71b9-5bf7-b437-7552fb22d9eb | date | Date:
d2cd5bc6-d9c6-5eeb-b7c2-42965b71bb77 | note | Client Verify that the Above has been Constructed according to Specification
7eb62c61-b180-58a3-90f8-24915ab716a1 | textbox | Print Name:
9f7d0c0d-a870-5caf-9943-0737ac3e9a8e | date | Date:
9a33bcb4-3481-4a8d-b8f3-da9d0e4950a0 | signoff | Signature
3ccf5e24-997b-4c10-8726-9c1a1a197fd8 | checklist | 03.41 - Rock Protection | itp | 03.41 - Rock Protection
999fa06e-4a34-4147-93ba-e00c3f18d297 | section | Details
8fb127a2-b471-4090-96fc-133fbb6fb663 | checkpoint | Rock complies with size requirements specified on drawings, otherwise shall be not less than 150mm and not greater than 500mm. Rock shall be well graded with not less than 50% larger than a size twice the minimum specified
8275a9a7-3327-512e-a65d-cf14b555162a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
17def2bf-d5ab-59f6-bf26-379836eb609e | note | Check Item - Check Item
f27320f9-dd08-578c-9347-94fb5f6c276d | note | Reference - MRTS03 Cl. 35.2
b8f66273-01ce-4967-9c75-e324d47a3362 | checkpoint | Rock shall be clean, hard, dense and durable igneous or metamorphic rocks. It shall be resistant to weathering, free from overburden, spoil, shale and organic matter.
ffbf869a-56b2-5355-bd72-76f64274e5f5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a827551a-196f-5fb1-9237-b97961237095 | note | Check Item - Check Item
4d900b79-3475-51ea-8341-8edc71b7fa36 | note | Reference - MRTS03 Cl. 35.2
917a77bc-988d-4bbe-a225-d2a2914a6dad | checkpoint | Rock Protection constructed in the locations and in accordance with the drawings
d4a079a6-cdc1-5676-8d36-c6cfcf96ffcb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9a86f4c7-87d9-5738-a09f-4ceaa164c655 | note | Check Item - Check Item
89e47063-8bdf-54ac-8352-6881b37b5e86 | note | Reference - MRTS03 Cl. 35.3
79e600d7-7673-4913-96fe-260bf0d303fe | checkpoint | Rock Protection is uniform in appearance and does not have noticeable veritical or horizontal irregularities
8747ac42-6b2b-5a8e-a7c1-a0aec8726507 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a7dda7bc-2ed8-5c34-beb8-c04e9eeb9019 | note | Check Item - Check Item
63a058d8-bad4-56dd-ac17-870bb56dd52e | note | Reference - MRTS03 Cl. 35.3
2cbbf5b8-c4b7-4d84-b5da-3724a863a24b | checkpoint | Rock material shall be placed such that larger rocks are uniformly distributed throughout the rockwork layer with smaller rocks filling the voids.
7db83682-ae59-51c0-84b7-0f8451e36caa | note | Acceptance Criteria and Frequency (Project Specific) - Visual
81355c86-3fbc-564f-92dc-4f96d5f393a5 | note | Check Item - Check Item
bdaa0ee6-5a98-5456-9d08-1931e3c0b61b | note | Reference - MRTS03 Cl. 35.3
dca52b90-e768-4add-966c-0c3747852d5e | checkpoint | Where constructed on an embankment, rock protection is constructed concurrent with the embankment with no more than 1m vertical height of open embankment above the completed rock protection
227cc05e-84d8-540e-986c-a079330eaa64 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
19b2c3d9-6d1c-5da5-bed6-f9d044bf1038 | note | Check Item - Check Item
8eb72170-2cf9-5aea-88f3-a6ee68bd4ba5 | note | Reference - MRTS03 Cl. 35.3
0482f2d7-72ad-4869-aeb3-e5b982ff814f | checkpoint | Cement mortar shall consist of one part Type GP cement to three parts fine sand. Materials shall coply with MRTS70
6bedd9d4-5800-5e99-8fcd-609d77e9d7e1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fb2d9d54-0d0d-5d7f-94d9-ca4b83802500 | note | Check Item - Check Item
3e33c542-a3e9-5fe7-9d26-2604111ba86a | note | Reference - MRTS03 Cl. 35.3
aa321503-d55c-4855-bbb9-d990f641f7f8 | checkpoint | Final Verification
a7bda85e-0721-59f7-b9e7-203ffe9fa5bf | note | Project Manager Verify that the Above has been Constructed according to Specification
b801b900-cfaa-53bb-a359-5a110ad4bf88 | textbox | Print Name:
a2f08d51-68f0-5a4b-b860-be271d86c013 | date | Date:
6a2cb6db-51cd-54dc-a705-55eab2b0ef96 | note | Client Verify that the Above has been Constructed according to Specification
63e473f2-04c2-5fa7-ba72-c1532ff2d3c5 | textbox | Print Name:
7001291f-d501-5c2d-8f73-af0bddec5356 | date | Date:
7d927144-8aad-4f88-aaa1-86fe652a730e | signoff | Signature
3f951f41-ad97-4662-be02-cd630ae84e0b | checklist | 04.01 - Clear and Grub, Stripping of Topsoil | itp | 04.01 - Clear and Grub, Stripping of Topsoil
a8b21b0c-f2b8-4ed1-9582-8906fe461f8f | section | Details
c5178cba-2fdd-4528-8594-cfb64af1aa7e | checkpoint | Extent of Clearing has been checked and marked according to the Vegetation Removal Notification nu the Project Arborist
97a49081-b8fb-5146-ba4f-508096325b62 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
46743f0e-f4b5-5be0-9659-17a759ee22c4 | note | Check Item - Check Item
54d8576b-021d-52cc-8da0-975c5e98f438 | note | Reference - MRTS04 Cl 7.2.1
2f2d168f-4bc9-4a5d-ad5a-b1b32f511bb6 | checkpoint | Tree Protection Zones installed as per Arborists recommendations
e0006847-2e7f-5352-8c98-0701ece50ac5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f91b42a7-b760-5db2-947e-4f1fb1ec0798 | note | Check Item - Check Item
8d45d53c-ba54-55ec-91b8-10f09b234429 | note | Reference - MRTS51.1 Cl 9.1
e2afe414-4fe3-4f43-8367-52e0f5bbf797 | checkpoint | Clearing operations and other environmental operations to be supervised by Project Arborist, SQP Contaminated Land and environmental representative where required
7e08e2e7-913c-5dc9-aa78-1788c112a991 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1993f37a-9280-5818-a631-8eb8ff10880f | note | Check Item - Check Item
92e5325d-c5af-5444-9f2e-6aff89b7bd11 | note | Reference - MRTS51.1 Cl 9.1
282fed67-ef21-46f6-a41a-fbf32b332934 | checkpoint | Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked prior to clearing operations reaching the areas concerned.
bf194349-3488-5a3c-b3f6-4242adc30185 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d9eb6bcd-f1af-588d-9c76-0e867049d17f | note | Check Item - Hold Point 2
f62d493d-8011-5500-9a0e-17e7336e7379 | note | Reference - MRTS04 Cl. 7.2.2
ee2637ab-f347-466d-86f6-8deb83304e7a | signoff | HOLD POINT
9e25ce4b-8c79-4e09-8060-13bd6aeae1a2 | checkpoint | Any trees required by the Administrator for use as marketable timber shall be as nominated in Clause 2.3 of Annexure MRTS04.1. Such trees shall be clearly marked by the Contractor prior to clearing operations reaching the areas concerned
6728b055-75c7-5624-a33d-cd640ca7ec17 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1b45c1c0-7ca2-55de-8fe9-947d95c2cb41 | note | Check Item - Hold Point 3
a98dc43e-5e9d-59bb-b02d-384bbab6adf3 | note | Reference - MRTS04 Cl. 7.2.3
d6623c4f-c679-4c1c-9da2-3d3ae49c1fca | signoff | HOLD POINT
813127b3-4cfd-48f3-aa6b-c3af5a39cb9a | checkpoint | As soon as practicable and prior to initial earthworks operations (clearing and grubbing) for any stage or section of the Works, erosion and sediment controls associated with drainage paths flowing through the Works area is being installed.
c3de5e9a-73fc-5c44-990a-e162a8fa4ce8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
78c83cce-853f-5459-b953-c8ef91913ff8 | note | Check Item - Hold Point 2
173c5e98-7015-5bc8-b4b1-16656fbd8b47 | note | Reference - MRTS52 Cl. 7.1
7aaaadd1-39d1-42c0-a517-c761062c7a3f | signoff | HOLD POINT
d988ea9e-adcf-4af8-b2b7-f82db14b3516 | checkpoint | Hollow timber which is identified as being suitable for fauna habitat logs relocated to areas clear of construction activities
895a13db-6a61-51e1-ac25-d520e3717e4d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d89808f3-c036-54a7-ad8e-da96e3042cdb | note | Check Item - Check Item
7cbb4879-cca2-529a-bb8c-80b4f2fa0b68 | note | Reference - MRTS04 Cl. 7.2.5
2cd21a60-35d5-47af-8f97-d5594875f91c | checkpoint | Cleared and grubbed material other than that mulched under Clause 7.2.4 shall be disposed of in any areas stated in Clause 5 of Annexure MRTS04.1 to this Technical Specification. If no such disposal instructions are stated, the cleared and grubbed material shall be removed from the Site and disposed of in accordance with all relevant statutory requirements, including the requirements in MRTS51 Environmental Management. Cl. 7.2.7
a5894760-6c75-5b8f-af7a-6d244b83755e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e71d13b5-2f5c-53cd-90cb-07c55443c20b | note | Check Item - Check Item
d8cb3e97-dd40-5f4d-8842-63358ce3e899 | note | Reference - MRTS04 Cl. 7.2.7
c1f07f55-02dd-495d-8c8b-3d6c244b9c76 | checkpoint | The scope of clearing and grubbing shall include the items as per Annexure MRTS04.1 Cl. 1.2 & Cl. 1.4
098a8a03-13cb-58eb-8d8a-bd571d04f588 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9e7d2530-daac-582e-881f-9a28a7ea5beb | note | Check Item - Check Item
2e329bef-179d-563b-8a0c-0dc526387d21 | note | Reference - MRTS04 Cl. 7.2.8, MRTS04.1 Cl 1.2 Cl 1.4
536eb762-16ab-4b0a-9546-b5a1748f0f6d | checkpoint | Trees shall be clasified as a Mature Tree if they have a diameter greater than 100mm diameter. Diameter of trees may be checked by Adminstrator to confirm if Mature.
9f1bec79-578d-507c-9ef7-cd95fdbfd362 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8eb29c25-dbc4-5c12-b563-d1e4301a0b49 | note | Check Item - Check Item
5fbc35c1-dc07-52eb-9d20-b16acee2e790 | note | Reference - MRTS04.1 Cl13.1
fd0ec405-5adb-4f78-a2f8-129a8f796ffb | checkpoint | The additional width for clearing and grubbing is 1.0m from toe of embankments as per Annexure MRTS04.1 Cl. 1.1
68a05e0e-2203-55eb-9052-1f8e83ece7e0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d231774f-5809-5e7b-8ffc-8c80b200a5fe | note | Check Item - Check Item
08bc446d-a90e-5da5-926e-20a058f72bd1 | note | Reference - MRTS04.1 Cl. 1.1
5f18898d-f95b-4923-b0e6-90dd16a276e1 | checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
13cc2388-9c18-5f7a-8563-6a7b71ad24ce | note | Acceptance Criteria and Frequency (Project Specific) - Visual
df0f4c4b-cb92-5039-964f-eeed8a624441 | note | Check Item - Check Item
3fac256c-c225-579e-bcce-97ddc6559d92 | note | Reference - MRTS04 Cl. 8.4.3
380bf527-2e65-42b8-ae8e-1b9744aadcbc | checkpoint | Additional Requirements for Clearing and Grubbing AS Per MRTS04.1 Cl 1.4 have been followed
a4e1d5a0-cb4a-593d-b1d5-f2b85e56738a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
17296ddd-7045-513c-888b-f90a0c985cd6 | note | Check Item - Check Item
baeb3ab7-116d-5b10-80bf-c6de35d57476 | note | Reference - MRTS04.1 Cl 1.4
752b3183-c41e-4473-839f-7deba5ff169c | checkpoint | Final Verification
27dd9dcd-701e-54c3-8021-aa8d8f6b3461 | note | Project Manager Verify that the Above has been Constructed according to Specification
24415c07-ebe3-5f2d-a71f-68a96c05c8ca | textbox | Print Name:
4c2e2020-ff12-5f50-8bb1-79454b0cf650 | date | Date:
3e5adbd3-b780-578f-bd83-5f0d1858c218 | note | Client Verify that the Above has been Constructed according to Specification
c8f94fc1-085a-521c-94e9-6afcbcad5097 | textbox | Print Name:
488efe44-10c9-5932-8652-5d694e45b5ee | date | Date:
fe4874a9-5c98-4422-82e1-260f09a7d47d | signoff | Signature
10d1adf4-58e7-4a51-bd53-2843e94fdd57 | checklist | 04.04 - Ground Surface Treatment | itp | 04.04 - Ground Surface Treatment
6e5f6ce1-201f-43d8-949e-c2c5473d70bb | section | Details
09bd6dda-7d13-4fc5-b470-ead6f4835ba2 | checkpoint | Ground Surface Treatment carried out on all areas beneath road embankment/pavement (except where special treatment or subgrade preparation is required)
7e757185-6662-571e-adf2-daf20b9b351a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
018fcbbb-0dfb-5c64-a078-2f022c2d7ff1 | note | Check Item - Check Item
a1ddae94-28d6-59c4-beed-5713de6bbd53 | note | Reference - MRTS04 Cl12.2.1.1
f13ad48f-2fc8-42fa-8af4-39ae79cc609d | checkpoint | Holes and local depresions filled with similar material and compacted in accordance with Cl15
d4d3c8bb-0e9d-58fc-9373-639fc135aa14 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
37fe00f7-c612-5dc7-8ad2-6804a8cb4b86 | note | Check Item - Check Item
ef895449-509d-5510-89ff-ce19d54ac314 | note | Reference - MRTS04 Cl12.2.1.2
94d31c4e-ea2b-4b1a-b549-7532ddc25ec0 | checkpoint | Existing surface scarified >150mm deep and compacted in accordance with Cl15. If material is too wet or too dry to compact and does not classify as unsuitable, moisture content adjusted to a depth of 300mm using appropriate methods.
66d13b83-4a16-5d58-add6-7a2e8a1fb2cd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2d3d4583-9a56-57c7-88e9-db1938880191 | note | Check Item - Check Item
9657afb1-4e82-535c-968e-848380796dc2 | note | Reference - MRTS04 Cl12.2.1.3
d8200748-a6bf-4592-a8eb-5efc9c4185d4 | checkpoint | Construction Testing Requirements: Test Method
4be37e63-912e-5041-9dff-751071c46329 | note | Acceptance Criteria and Frequency (Project Specific) -
059ba0f7-225d-5ad9-bdbb-5ad0ffa190e9 | textbox | Max. Lot Size
30606a35-022a-5121-98fd-3d776cf87717 | textbox | Min. Testing Frequency
f9cdc081-4875-5a2a-b9fb-cdde4fba07a3 | textbox | Min. No. of Tests
d761c7dd-6615-5a54-a731-336feb9b0c06 | note | Check Item - MRTS04
6f7dd0cd-e47e-5be2-821b-a32c4d0652fc | note | Reference - Table A1
8059a8ec-c560-4abd-ac45-53e7da094d7c | checkpoint | Compaction: Q140A, Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
df5edb0a-9115-541d-94a7-c4f3553c03b8 | note | Acceptance Criteria and Frequency (Project Specific) - Max Lot Size: 5000m2
711876af-0422-52c1-b51d-27c90f25e691 | note | ○ 1 per 500m2
0fc4dc2d-85c1-5530-885f-e1ec238700ad | note | ○ 1 per lot
cbf81d4f-cc40-5e90-9747-2da4f108ad6d | note | Check Item - Check Item
37e23d73-1793-52ef-a43d-be083832f8ba | note | Reference - Table 15.3b
974e0ae1-7918-4862-b2a0-7a0196b1ea80 | checkpoint | Final Verification
eaa0ffa2-9e00-5de3-ba42-8a78c55bce59 | note | Project Manager Verify that the Above has been Constructed according to Specification
0167bd25-3c19-5158-9b96-4e69e5ace49c | textbox | Print Name:
e4b9a0c9-f7a6-590d-9bad-de55d8e4bd18 | date | Date:
f5bbec47-e187-5e23-869d-a241bad6dca3 | note | Client Verify that the Above has been Constructed according to Specification
eb20af17-83a6-5488-86e2-63be2e26daf7 | textbox | Print Name:
30ce25f1-b0c4-5969-9347-efe59ea85b81 | date | Date:
69cf2601-ce5e-496b-aeda-6ebbbc6cf465 | signoff | Signature
9278f333-f6b2-4445-91a6-db8bcfa84c0f | checklist | 04.05 - Embankment | itp | 04.05 - Embankment
113835d4-ca5a-458c-ade4-71ba2dc8fd41 | section | Details
ee228bac-1c10-4de4-8fa7-b426d9d62dbf | checkpoint | General fill material used for the construction of road embankments sourced from general excavations on site or imported. Where embankments are zoned (ref Table 14.2.2 / Clause 14.2 - Annexure MRTS04.1), material is suitable for each zone.
473b03eb-c54d-5319-8bb6-a9259a92efc6 | textbox | General Fill Class:
b722ac44-811d-54e0-ae7f-4698d5b173f3 | note | Acceptance Criteria and Frequency (Project Specific) - General fill material Class A
1d7117cd-16cb-57a8-8c21-f86a1d39f387 | note | ○ WPI< 1200, PI>= 7,
4d1ba61a-337b-5f8b-8c6c-aad7e6d1a0e2 | note | ○ % passing .075mm 15 - 30
3d10ad50-c38a-57fe-985d-69b9c6b56aa7 | note | General fill material Class B
e5d27c1a-6c4d-5c05-86e9-116e553525e4 | note | ○ 1200 < WP < 2200
580ff605-e0e2-5146-afb4-685df262be83 | note | General fill material Class C
3ce7426d-1919-544b-9803-2f764643d257 | note | ○ 2200 < WP < 3200
0344c42a-c677-5f61-bbbf-e16a54973029 | note | General fill material Class D
c89d0fc6-3348-592f-bcdb-4ba31cf2dcf0 | note | ○ 3200 < WP < 4000, PI <=50
dbbdb2ed-7bfe-5b99-853b-0f2717288b60 | note | – CBR as Specified
cc9bc20f-a213-5752-a143-0d6831ecfbef | note | Check Item - Check Item
539822f7-5e24-5d66-b6ef-ec0182a507ee | note | Reference - MRTS04 Cl14.3.1 Table 14.3.1
4fcdd637-7e84-497b-a8a3-c6941145b0af | checkpoint | Rock Fill shall consist of sound igneous, metamorphic or sedimentary rock or combination of these rock groups that will not disintegrate in water or when exposed to the weather. Rock Fill shall be free from overburden, Spoil, shale, clayey materials and organic matter. Rock Fill shall be either sourced from a quarry (or quarries) registered under Transport and Main Road's Quarry Registration System (QRS) or any other suitable source and shall comply with the properties stated in Table 14.2.3. Rock shall be angular in shape and the least dimension of the rock shall not be less than half its greatest dimension
8c8e5c9e-19f8-5990-9bb2-3a4fc93b69a8 | note | Acceptance Criteria and Frequency (Project Specific) - Table 14.2.3
9541a1f5-06a8-524f-ad9a-b57c861d2fef | note | Check Item - Check Item
d319e6b8-6278-5f6f-9173-9e5ec6b3e646 | note | Reference - MRTS04 Cl14.2.3
5a159526-6e8d-4d54-8706-eb0d3cd142ab | checkpoint | Where embankments are to be constructed on or against any slopes or batter of existing embankments (including batters resulting from the partial construction of Embankment, for example, Core Zone), steps shall be cut as follows:
79027fdc-c9e8-56f7-bf06-a0ba10bab414 | note | a) where the ground surface has a slope steeper than 1V to 8H and shallower than 1V to 4H, a series of horizontal steps not less than 300 mm high shall be cut into the ground surface to be covered by the Embankment.
cd9e73bd-26dd-5fa3-a7da-4ee9e71d72d4 | note | ○ Such steps shall be constructed both longitudinally and transversely (refer Figure 14.3.3(a))
1295308c-e767-5c38-8bca-8676e8027fee | note | b) where the existing slope or batter has a slope steeper than 1V to 4H, a series of horizontal steps not less than 600 mm high shall be cut into the ground surface to be covered by the Embankment
8e59de48-d1c1-5bc2-8ef2-826a7db44f34 | note | Check Item - Check Item
d00e2bf6-05bc-456b-ade0-ee5d7c79bbad | checkpoint | Compaction methods suitable for material type
3a44179a-a70e-5dae-8b40-3ed6c5725461 | textbox | Compaction Method:
50333499-ae5b-53ec-a6b2-a5d5b910c360 | note | Acceptance Criteria and Frequency (Project Specific) - Table 15.2
be5668ce-c367-5a14-85c8-3ee52fefb032 | note | Check Item - Check Item
3b2c3b2c-ebb2-5106-8778-8a4b99b9d03f | note | Reference - MRTS04 Cl15.2
5aea0c89-6631-407b-9458-4bd3bc89518d | checkpoint | Compacted Layer Method: Embankment compacted to required density (by characteristic Value). Refer to Table 15.3-B MRTS04 for more information. Fill material placed uniformly in layers. Uncompacted layer thicknesses;
08f88763-23b3-5c31-b44b-ad8893eabe59 | note | – General Fill 150-300mm
048ae09b-e044-5789-8042-3323b485911e | note | – Fill in Water Retaining Fill 150-200mm
1e948b32-7176-5fef-a646-171cd87f009f | note | – Subgrade 100- 200mm
03938c83-1f4c-5c5e-a1c6-c1611f29562d | note | – Backfill except Sand 100mm-100mm
fc282e18-c47a-5149-850f-3ad29b199eb3 | note | – Sand 150-300mm
b6b0ede2-1452-52b0-9872-c1d29cb54c98 | note | Acceptance Criteria and Frequency (Project Specific) - RDD%
ffd523c0-c79f-5a50-b3ae-c17a2e9966fa | note | ○ Insitu - >95%
2b0fc839-bd25-5d61-bf77-8cef180d33a6 | note | ○ Bottom of Excavations - >95%
4603b40e-459f-5244-91a7-8bf9217905a5 | note | ○ Subgrade (A/B) - >97%
71f8da16-d5ce-5cb7-955a-1548bd492867 | note | ○ Subgrade (C/D)' - 90>96% Subgrade (C/D)* - > 95%
3c56efbd-9ef9-53fe-9877-1e36b71ba1dc | note | ○ Road Embankment(A/B) ->95%
508cf608-4549-53cd-ba05-80278f2ced19 | note | ○ Road Embkmnt(C/D)' -90<96%
a35866d2-3de6-589f-95ec-55ad4b6df391 | note | ○ Road Embkmnt(C/D)* ->95%
b63fdfd1-8f6c-5511-a3f1-3604397b339c | note | ○ Levee Embkmnt(A/B) - >97%
a4414d24-9bdb-57b4-91cb-d06643c79e83 | note | ○ Backfill(Sand) - >70%
1b5d414a-bcc5-58df-a339-4f57fca90037 | note | ○ Backfill(Not Sand) - >95%
070f6fdc-3e59-51f7-bfd2-c9ddd56a33db | note | ' High Rainfall Zone
644725f7-68d9-5837-9283-70d059c88607 | note | *Low Rainfall Zone
ea0e5fdf-ec61-56ac-b821-bb40ebda5106 | note | Check Item - Check Item
59fa73e3-12bb-5c01-bd4c-a72b0a2acc25 | note | Reference - MRTS04 Cl15.3
7c2bfe09-54be-4e44-9503-5c456bf4a314 | checkpoint | Compacted Layer Method: Embankment moisture content within ranges specified
d2e9996a-6ac2-5066-9e38-397e4c38431d | textbox | Rainfall Zone:
a486fbb7-0309-5a68-a4a2-b896bc2d685f | note | Acceptance Criteria and Frequency (Project Specific) - Table 15.3C
8c6f44be-d17c-5484-8447-72aea045ffb9 | note | Check Item - Check Item
d8763ac1-2d0e-5824-b627-612785adcb00 | note | Reference - MRTS04 Cl15.3
bbfd6e20-3bc9-436b-89d9-6b45c4c76518 | checkpoint | Where required, each layer rolled with the mechanical interlock method until no further permanent visible lowering of the surface occurs and layer thickness no greater than specified in Table 15.4
2eb67fea-941c-52c6-8fc1-b423682ac8b4 | note | Acceptance Criteria and Frequency (Project Specific) - Table 15.4
301eb66f-051d-5d9f-b2eb-99597ba58c38 | note | Check Item - Witness Point 4
2241dc51-e7b5-5212-84c0-8d0088485f01 | note | Reference - MRTS04 Cl15.4
de796450-4554-4e77-b00f-53aa846b3ea2 | checkpoint | Geotextile placed at interchange between compaction methods
4e4efefd-6379-5586-9745-dbd8f1f79613 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
35bfd285-8f4b-5b0e-8d1b-ab2d2f6bda67 | note | Check Item - Check Item
39e5793a-4bb3-5e94-b312-2fcd52c0a340 | note | Reference - MRTS04 14.3.2
eef8071b-4176-441c-b32d-f772012aed4b | checkpoint | Within Geometric Tolerance
1c3aa2f6-a9dc-57a7-88aa-3c6fceaab025 | note | Acceptance Criteria and Frequency (Project Specific) - MRTS04.1 Cl1.2
e53a2c6d-0696-5e4b-bdf6-92a33fce16fd | note | Check Item - Check Item
28b4820e-f167-575f-abdc-36dff4773577 | note | Reference - MRTS04.1 Cl1.2
0328d5a6-1c55-4357-8700-1979a316e5cc | checkpoint | Construction Testing Requirements: Test Method
83ce6564-4d59-5646-acf7-cfc89f44c78b | note | Acceptance Criteria and Frequency (Project Specific) -
d8331b65-ee3e-5e3e-a4a5-4c9e7d930b0c | textbox | Max. Lot Size
fed4fb46-2898-5606-bc68-59d23f4aaa4a | textbox | Min. Testing Frequency
535a125b-e9b7-515e-9aa3-a22296195c8f | textbox | Min. No. of Tests
53f90cec-eccf-52f1-b577-33078eb7018e | note | Check Item - MRTS04
dafbcc69-64da-5b26-ab94-f9a0b0c9e991 | note | Reference - Table A3
db5368eb-75a5-555f-be49-ba7a14851893 | note | Note - Table 15.3A: Layer Thickness, Min: 150mm & Max: 300mm
a8143a96-3677-4187-9212-05f77eb9629b | checkpoint | Relative Moisture: Q250, Rainfall zone: Medium (500mm - 1000mm), Class A1 & B1: 70% - 90%
9b93b222-9bc4-5716-b9f7-61f266ba10d9 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
1f28105d-c3c0-529e-a3cb-c705f1dc7fde | note | ○ 1 per 500m2/per layer
80d1dffa-d7a1-5f6d-9771-497e8a135dd7 | note | ○ 4 per lot
26ad6218-4aab-51e0-a94e-6769dbba4f17 | note | Check Item - Check Item
25a24815-f109-5941-9d1c-2ec4870f6561 | note | Reference - Table A1
9f50bb47-b597-40f7-a9e3-6f66e2267ef7 | checkpoint | Relative Compaction: Q140A, Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
a47bf565-94b1-5472-afee-cae54afc8e30 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
3a39efa5-f768-5682-8f92-329bc2a1c948 | note | ○ 1 per 500m2/per layer
0d9e0da6-04b3-5b31-a922-99c3acc3ae72 | note | ○ 4 per lot
936b58db-651f-58e4-a7ec-4ec7b593eb75 | note | Check Item - Check Item
0038edd9-d958-5d2d-9236-7bfb670326c2 | note | Reference - Table A1
e566d6c7-0c27-426c-ac1e-d85edaae3aae | checkpoint | Grading: Q103A
8ca451da-0efa-5349-8981-d755281663f0 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
7facc403-212a-505f-a5b3-65e06917ee8e | note | ○ 1 per 1000m2/per layer
f86a3668-2da0-5723-9fae-ddc714ffb467 | note | ○ 2 per lot
16b55612-7a60-5a96-aa3a-92ac106fc8cd | note | Check Item - Check Item
585f19c3-7c98-57ef-92aa-c5827ab41102 | note | Reference - Table A1
4d2de5ab-3cbe-45f0-8244-2225805f7370 | checkpoint | Plasticity Index: Q105
25c38bd2-422c-5ebc-a286-ef7f1881e694 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
f1a416f9-4437-5356-adae-2fc8fe70fad0 | note | ○ 1 per 1000m2/per layer
8119d800-4145-5570-a95b-b139a59a78c6 | note | ○ 2 per lot
b86f7d80-4845-5e36-9c1a-8c12f44d401b | note | Check Item - Check Item
8c735be5-fcb0-5064-a38a-fc2a13a896c0 | note | Reference - Table A1
cc9caace-dddb-4dd2-9a63-209e3c096dac | checkpoint | Stockpile Testing Requirements: Test Method
397436ad-ef0b-506f-9535-c262ded9de2c | note | Acceptance Criteria and Frequency (Project Specific) -
a9394613-7a39-5cde-a9c8-2ceefe1dd844 | textbox | Max. Lot Size
88c6a89d-4db6-504a-ac43-406c54880f08 | textbox | Min. Testing Frequency
de12bb1f-b1da-5cb6-8291-016f45181b28 | textbox | Min. No. of Tests
0fd1674d-24bd-5fdd-88fe-3b87f9b357d1 | note | Check Item - MRTS04
5cda8af4-0010-57ea-81bc-167fbbbbea80 | note | Reference - Table A3
830ef988-aeb7-4771-b928-8e3be7db91a7 | checkpoint | Grading: Q103A
1c2ce5dc-cdb5-54e2-a499-ffb57a44ea78 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m3
cefa7315-9bd8-54ed-9493-736f84fc7c6e | note | ○ 1 per 1000m3
9c20973a-7cbd-5839-820b-abfa91b0d90f | note | ○ 2 per lot
3af80db9-8e10-550b-9c7c-b2f5780afdd3 | note | Check Item - Check Item
3e5b0f47-03c5-53c7-a50d-3f9dfe6f9a8b | note | Reference - Table A1
766a9557-6d5e-4697-8ed3-489035411527 | checkpoint | Plasticity Index: Q105
a1889d4f-e57f-53cc-9f95-1e10a7a60e03 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m3
e86aa3e4-0a39-5888-bfb4-aee04e3b38b5 | note | ○ 1 per 1000m3
6e23194d-6d98-5d99-ae74-c37959c25b65 | note | ○ 2 per lot
dcd5aa84-3c02-5228-aa56-4736192f68de | note | Check Item - Check Item
be4c0c5e-411d-5b43-849d-e261514518ad | note | Reference - Table A1
21227912-4c2b-46c4-957a-6c2dde2a5a3e | checkpoint | Emerson Class Number: As 1289.3.8.1
3ff3bc3a-358f-57c6-b07a-3c3d90452e33 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m3
f498e6a6-08ba-57ac-8a49-d857a00a4024 | note | ○ 1 per 1000m3
8d96a3fc-57b2-51aa-be41-71d398a63a9a | note | ○ 2 per lot
95d4f08f-852b-59f4-913f-4ccab376af44 | note | Check Item - Check Item
0b2d835f-1ae1-5d17-ae20-457001fcdce0 | note | Reference - Table A1
c2ee1f3d-411a-4291-ae5c-78981b983493 | checkpoint | Prior to incorporating any Earth or Rock Fill Material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements
3cbf3ab5-166b-58c7-b8a3-d7e05a8a08a6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
23fd0aee-e706-53ca-a302-baaf1030a8d8 | note | Check Item - Hold Point 8
28a624e5-0177-5a75-9428-8d9f1d42df5c | note | Reference - MRTS04 Cl. 14.2.1
dc62431e-4f9c-45a6-ba38-5cd73ce44e84 | signoff | HOLD POINT
d735cc52-3f69-4092-941c-3c622d143ac8 | checkpoint | Final Verification
7e3bcec9-6dbc-5d2d-8768-551dfe4c7c1c | note | Project Manager Verify that the Above has been Constructed according to Specification
eba308d1-cff2-502e-9b3b-5ca291ad00c5 | textbox | Print Name:
26f87a02-d3fd-51a9-ae40-ce14c8ca5b90 | date | Date:
20cd6789-57d3-5ddb-8728-a4a3fa038346 | note | Client Verify that the Above has been Constructed according to Specification
3875f28c-c56b-57f3-90ea-1af5636be530 | textbox | Print Name:
08b9f912-c62a-5dff-bc0a-6fe7ba92afab | date | Date:
58bbab86-4187-4204-afcb-9ae01ea0ad89 | signoff | Signature
16f29f71-b11c-4567-8f0d-9223fc46abef | checklist | 04.06 - General Excavation | itp | 04.06 - General Excavation
66c77375-8ff5-4958-9549-9107055171c8 | section | Details
9df235b5-48a1-4911-aa4c-498585739322 | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially Unsuitable Material is encountered on site, the Contactor shall, before proceeding to remove or cover such material, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl.11
404b67d2-2d8e-5061-91fb-a6dcab7216b9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
83219c84-a9c2-541c-a8c6-612c7d1e21aa | note | Check Item - Hold Point 4
699a5dee-3e07-5754-a404-4841abb88fe5 | note | Reference - MRTS04 Cl. 9.4
a1456f57-46d7-4481-99cb-df25cdb083b6 | signoff | HOLD POINT
2795d16f-ad93-4640-b901-03d240be702a | checkpoint | When the level of excavation has reached subgrade level, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the subgrade treatment type has been determined in accordance with Clause 18.3.3.
f37c4e1c-4b01-53de-9570-5938481ffd04 | note | Acceptance Criteria and Frequency (Project Specific) - Annexure MRTS04 Clause 13.3.2.1
7aea7c45-1096-5ea8-9a39-0dac8387f196 | note | Check Item - Hold Point 6
68078bb5-bba8-599a-bf5f-1f98ceb9e2ab | note | Reference - MRTS04 Cl. 13.3.2.1, Cl. 18.3.3
03d4c93a-3703-4822-b111-2d2b25b1ab4b | signoff | HOLD POINT
adf0d237-58c1-49da-9f90-96c366991656 | checkpoint | Material below the finished lines and levels of cuttings, which is Unsuitable Material in accordance with the provisions of Clause 9.2, shall be removed and disposed of in accordance with the provisions of Clause 9.4. Backfilling of the excavation shall not commence until an As Constructed Survey of the excavation have been met as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
784b0870-aed7-5d9d-82f4-433588b2e520 | note | ○ Where Unsuitable Material has been removed, the excavation shall be backfilled to the finished surface level with appropriate Fill Material as specified on the drawings or in accordance with Clause 18 and Clause 19. Technical Specification, MRTS04 General Earthworks Transport and Main Roads Specifications, November 2022 30.
59dcced9-8544-511c-9d6f-dd83f40b19f0 | note | ○ After backfilling of the excavated area has been completed, an As Constructed Survey shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator
8cde8787-fb44-5aad-8639-366de8ddbdee | note | Acceptance Criteria and Frequency (Project Specific) - Annexure MRTS0 Clause 13.3.2.2
1eb52628-98da-5418-ab63-0279f92d81fc | note | Check Item - Hold Point 6
44536c86-cff5-5d5c-9ddb-c14991b7f6af | note | Reference - MRTS04 Cl.13.3.2.2
ebae4aea-971d-43f2-9b3e-ae0432beb504 | signoff | HOLD POINT
17bf2964-e36f-47dc-8dba-58aeda884098 | checkpoint | Excavation completed to the shapes, lines and dimensions and other requirements shown on the drawings and tolerances specified
10b35d98-8196-5d1e-bd0d-4f2131d4ef7e | note | Acceptance Criteria and Frequency (Project Specific) - MRTS04 Clause 6
fbb1d72c-6005-533c-9e8f-c57cfe9ff8f5 | note | Check Item - Check Item
ece21ed5-e519-59da-bf5d-d5a275d30503 | note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
5d3460e1-8e41-48d1-ad0c-e3ce83ffe045 | checkpoint | Protection of excavations in accordance with MRTS04 Cl.13.3.3.3
4273321b-bb75-5cf8-8af7-452952e308b5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bcdb12c8-44a9-5f14-823e-769e0df2a6cc | note | Check Item - Check Item
f3f71d5e-bd72-5ef9-8c45-9213105dff83 | note | Reference - MRTS04 Cl. 13.3.3.3
fa4e282b-a51a-41da-8b44-44292290fa7b | checkpoint | Dewatering of excavations shall comply with requirements of EMP
e7bed4e2-1fbb-587a-8000-684a550a8376 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4cc03454-fa4d-5b06-b7e9-a208e6023898 | note | Check Item - Check Item
34e51c4d-569c-5dde-945f-86d585bb5375 | note | Reference - MRTS04 Cl. 13.3.8
73fa91b8-3adf-4c5e-b821-c259065fe8a0 | checkpoint | Batters in cuttings shall be free of loose material and shall be trimmed neatly to the shapes specified.
23076678-33da-5ff0-8e0f-605390c06478 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
18067994-304e-5cb5-ab35-ea224e8fce9f | note | Check Item - Check Item
0d1a3b48-1b1a-5004-97fd-0350ce45665e | note | Reference - MRTS04 Cl. 16.1
29e045d1-1b37-42bd-af27-29ed5eada50e | checkpoint | If any section of a batter has been over-excavated beyond the tolerance limit specified, the Contractor shall re-form the batter to the average batter slope shown on the drawings, using an approved rectification method
799fa67e-52ab-52b4-b053-f4b25cc25f26 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3efc7381-4ad9-5ed6-97b2-115c61544bef | note | Check Item - Check Item
78b0952d-8d2c-594e-b4eb-2b23d3b2c520 | note | Reference - MRTS04 Cl. 13.3.2.4
efa9031f-6b98-4293-bad4-21990771586d | checkpoint | Trench excavations and excavations for structures shall be carried out to the dimensions shown on the drawings or, where not so shown, to the minimum dimensions necessary to construct the Works accurately and safely under the Contract. Prior to any excavation Works or trench excavations, an assessment is to be undertaken to identify cadastral marks that may need protecting as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator
5b83aa4b-1494-5cf3-84d4-a04eb07d7fca | note | Acceptance Criteria and Frequency (Project Specific) - Visual
14e4a5db-624f-5cc2-a3a6-894d4f198c62 | note | Check Item - Check Item
eef638db-64af-5165-aebe-ab9144ec032c | note | Reference - MRTS04 Cl. 13.3.3.1
b3236068-ac88-41b1-81a7-f86c498e68c7 | checkpoint | Material which is Unsuitable Material in accordance with the provisions of Clause 9.2 shall not be reused in the Works but shall be removed and disposed of in accordance with the provisions of Clause 9.4
96052ad1-4aea-5537-8814-f5c688dfde91 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8f61fee6-9977-5579-b4fa-453e14bccb3d | note | Check Item - Check Item
f515d738-7425-57fa-9dcc-b4eab7b6c277 | note | Reference - MRTS04 Cl. 13.3.3.2
dda912a2-1095-4234-a412-a0ea7fc45319 | checkpoint | Final Verification
87ab955f-d740-50ac-b22f-f08ed68c7ad7 | note | Project Manager Verify that the Above has been Constructed according to Specification
a73c9de1-abed-5d88-8607-3adcdb0b4984 | textbox | Print Name:
ff6be535-bdda-5169-aeae-540d979f58bb | date | Date:
4ad7ea4c-1c33-5bcf-b1c8-881f50191833 | note | Client Verify that the Above has been Constructed according to Specification
9fb416d9-40a0-5267-ac7a-ba3d2d3cb3cf | textbox | Print Name:
dd67a663-69df-52dc-9fce-35dc31bc0d15 | date | Date:
5dffb753-d618-42d2-b515-212141978d7e | signoff | Signature
836429eb-7390-4642-a04f-3407d59deb86 | checklist | 04.07 - Structure Excavation | itp | 04.07 - Structure Excavation
0fba01d5-cd26-4f7b-8f4d-cde9be718ce0 | section | Details
10e7aaa2-9f7a-444a-b772-61eca6e13603 | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or pottentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.3 and CL11.3
3fd4d6c6-9660-5c26-81d1-737314dd0022 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
af028db2-c013-5df2-9df8-04474d58463a | note | Check Item - Hold Point 4
d1b24a6b-186c-56a1-b1a6-b2d5ea7326ba | note | Reference - MRTS04 Cl9.4
87b07762-59cd-45d5-b319-a247f68906f7 | signoff | HOLD POINT
4373a250-c6cd-4927-8a13-a8477e79ed44 | checkpoint | Where material can be reasonably be expected to contain a possible acid sulphate potential, the test results shall be documented and reported to the Administrator.
e9b5bc9a-05d3-5c7a-8688-c2dde8c36a2f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
90f9061a-9876-5393-a971-2a667f51dab9 | note | Check Item - Hold Point 5
e8b6b4dd-1ef4-5ad6-8466-45de25c4f1f6 | note | Reference - MRTS04 Cl10.
77fd57df-f309-4593-a8e6-2594d1f8a46f | signoff | HOLD POINT
96c3e275-2637-4108-b6bb-161485612fda | checkpoint | Where shown on the drawings or specified elsewhere, a layer of blinding concrete shall be placed over the foundation material as soon as practical. The top surface of the blinding concrete shall be screeded neatly to the shape and levels shown on the drawings
9030603f-6124-5900-80ae-50dd3b6acb10 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b1a31d1c-2430-5835-bd09-8a6ce8a3ae01 | note | Check Item - Check Item
148f7f22-ce4c-5f88-a1dc-2f7a84a1106c | note | Reference - MRTS04 Cl13.3.4.1
d458f239-7d5f-448d-a975-f758a7eeba9e | checkpoint | The widths of excavations for culverts shall be the minimum necessary for their construction and placement of backfill against them, provided that nowhere shall such widths be more than those shown on standard drawings 1359.
0fb5ceb5-5082-5e09-9117-9cf8504df464 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
880e5d42-f039-5305-9e72-d7cdc7755437 | note | Check Item - Check Item
e28c5fb0-ffa8-5272-ab9c-1bb91f718b08 | note | Reference - MRTS04 Cl13.3.6
01330213-0632-42b2-b273-815b4560b307 | checkpoint | The material in the bottom of excavations shall comply with the density requirements of Clause 15 and compacted to a depth of at least 150mm.
b8380115-f87d-5202-8c41-3bb4fe7998a0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
16946e2e-1d09-5fcf-b5d2-8b332c8a5595 | note | Check Item - Check Item
9cf999ac-7363-57a7-a8cc-e3f096d2e8cb | note | Reference - MRTS04 Cl13.3.6
aa1ca57d-3762-4c7a-81c4-8af8d3fb64f0 | checkpoint | Compaction: Q140A, Bottom of excavations = 95%
6aed601e-5153-52d3-a4b5-393ecd503422 | note | Acceptance Criteria and Frequency (Project Specific) - Max Lot Size: each culvert or end structure
dde27f0c-abc7-5c81-91f6-ee3c80591be0 | note | ○ Min. Test Frequency: 1 per 50m2
6ca7877c-5553-5f1a-9c33-7fa62b193a80 | note | ○ Min. no of Tests: 2 per lot
785594dd-1db1-598b-b008-f394e23603a9 | note | Check Item - Check Item
43364aee-47ae-531b-810b-9df615fffd45 | note | Reference - Table A2 No. 2.6
7b36dc8c-82b4-40a3-a0d3-bbfa91a02aea | checkpoint | Supplementary Requirements as per Clause 22 MRTS04. The material used in backfilling unsuitable material excavations, in addition to the requirements specified in Clause 18.3.4.2 of MRTS04, shall satisfy the minimum CBR requirements of Clause 3 of this annexure.
3ccc56b8-7112-5c3b-ae48-f9cd43591dd4 | note | Acceptance Criteria and Frequency (Project Specific) - Testing requirements
0259ea1f-def3-564b-9b24-8c2f259b357d | note | Check Item - Check Item
587e7709-0cb7-5d61-a444-5d7786e2f416 | note | Reference - MRTS04.1 Cl. 13
10faa625-5ba1-48a1-936a-45bb08c155bc | checkpoint | No areas on Site are available for the disposal of excess and Unsuitable Material. If no areas are indicated, all such material shall be removed from the Site
e44ce380-41c7-518b-bf0d-b42d5fc6b383 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8b1717d0-cd9e-5b93-b25c-fcf22500c8c0 | note | Check Item - Check Item
8daa9ef8-d39e-5939-9133-d905def8d938 | note | Reference - MRTS04.1 Cl. 5
aacefcf6-d92d-43eb-9d49-5051b792bb4c | checkpoint | Final Verification
8236ba66-a4cf-5585-9404-9b69fafec20a | note | Project Manager Verify that the Above has been Constructed according to Specification
5c94bbe0-c208-506a-b1f8-45b425519344 | textbox | Print Name:
cf1f6b61-2a0d-5ef1-8794-56f6e217f73a | date | Date:
185c2a21-b202-5813-846d-d485caa69187 | note | Client Verify that the Above has been Constructed according to Specification
d10d9404-3369-5ef0-aa56-667dc87a9167 | textbox | Print Name:
4e6c8f61-1217-5c13-af76-a1da554e3467 | date | Date:
ada6151e-9cd2-4567-945a-22d3160c85b8 | signoff | Signature
488f932e-2325-4e3e-b07d-5afe7193f4b1 | checklist | 04.08 - Stripping of Topsoil | itp | 04.08 - Stripping of Topsoil
e6928cf2-b868-4952-944a-6073c93fab18 | section | Details
906254c1-7a5f-4d35-a7f6-158818d7bc31 | checkpoint | Where site topsoil is required to be supplied in accordance with MRTS16 Landscape and Revegetation Works, topsoil shall be stripped 100mm (+/-25mm) depth, or from areas and depths as specified in Clause 2 of Annexure MRTS04.1
02fa2b14-f6e9-5dc3-89ab-b19792559815 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
165696b8-385c-5b16-a76d-826c8e5e37c6 | note | Check Item - Check Item
69da89d3-c1d2-5d46-a37d-79799850ef97 | note | Reference - MRTS04 Cl. 8.2, MRTS04.1 Cl. 2
8968e17a-bf07-4eb1-bc9f-476a6a8bf7bf | checkpoint | Soil stripped from site which is considered suitable for use as a manufactured site topsoil shall be tested and ameliorated in accordance with MRTS16 Landscape and Revegetation works
c9c74ae0-942b-5e10-9757-d28277e5b748 | note | Acceptance Criteria and Frequency (Project Specific) - Insitu topsoil - 1/2500m2, min.1/soil type
4c3645df-03c1-5f34-981f-684f9cff4890 | note | ○ Stockpile Topsoil - 2/500m3, min.1/soil type
a4bae6d1-9581-5973-8392-b18ee3c9cc1c | note | ○ Manufactured Site Topsoil Compliance - 2/500m3, min.1/soil type
e0f6ecda-82e5-5ae5-ba04-bb8352caadc4 | note | Check Item - Check Item
2079ba3f-33d8-5aca-8915-0862eaebc9a3 | note | Reference - MRTS04 Cl. 8.3
e3c02fd5-d0eb-4e55-92ae-04ab94c218c8 | checkpoint | No areas are available within the limits of the site for the disposal of excess and unsuitable material, with the exception of excess topsoil. Excess topsoil may be uniformly distributed on cleared and grubbed areas which are outside the road embankment formation.
be4d60f5-68c1-5ff7-83e7-2f8fab97d04e | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
647a8b68-2ccb-51a4-9837-7b078e9c0778 | note | Check Item - Check Item
c930d9ca-5392-5340-a5b6-931e3911a65f | note | Reference - MRTS04.1 Cl. Cl. 5
02a038f6-6318-4479-ab34-236593043f68 | checkpoint | Stockpile site locations are to be nominated by the Contractor and approved by the Administrator. The Administrator is not obliged to approve any stockpile site location within the road reserve. Stockpile sites shall not be placed within 50 m of a watercourse or within the 20% Annual Exceedance Probability (i.e. Q5) flood zone of a watercourse, unless approved by the Administrator. No native vegetation shall be cleared for stockpile sites located outside the area defined under Clause 7A of Annexure A (Contract Details) to the General Conditions of Contract, unless approved by the Administrator.
17576dfa-85cc-5ee8-a90a-f38604b20dc8 | note | ○ Stockpile sites shall not be placed within the Tree Protection Zone defined in Clause 9.1.2 of Annexure MRTS51.1.
8e696693-c418-5df9-ae30-98882c040e41 | note | ○ Preference should be given to existing stockpile sites or existing cleared areas. No guarantee will be given as to stockpile site suitability, condition or availability. In the event that the establishment of stockpile sites requires clearing, grubbing or earthworks to be undertaken, a Cultural Heritage risk assessment and environmental survey must be undertaken prior to any works being undertaken. The Contractor shall advise the Administrator of any such requirements HOLD POINT. No clearing or works beyond the defined project extent may proceed without approval from the Administrator and the TMR Environmental Officer.
e3b1780d-9944-5fd8-b2b8-220ac446e811 | note | ○ All costs associated with undertaking necessary earthworks activities required for stockpile sites shall be deemed to be included in the Contractor’s schedule unit rates for the corresponding earthworks items.
4417377c-4b8e-53d2-9665-898db7ec9be9 | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
a9485ed1-e919-5f92-88d8-1059ba0c1759 | note | Check Item - Hold Point
90d8c22f-d921-56c6-a958-60e747be34c5 | note | Reference - MRTS04.1 Cl. 2.2
f0ca8dda-574a-4eda-a9b0-b2544febf494 | signoff | HOLD POINT
0cc2da0e-4b54-4887-a4ac-f83ef60170c8 | checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
7bc4fb1e-c822-52bf-b944-32a240a1e173 | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
1427bcb6-9d28-5994-8089-46ec3f9793d2 | note | Check Item - Hold Point
b2401d23-6af5-507b-8eea-39fd1f89e079 | note | Reference - MRTS04 Cl. 8.4.3
cd981cff-6e51-4f6e-a226-1fdb1de95132 | signoff | HOLD POINT
e0c8872b-4b2e-460b-942c-bea9d51a8c52 | checkpoint | Stripped material shall be stockpiled in the locations nominated by the Contractor, as stated in Cl. 2.2 of Annexure MRTS04.1.
14592a68-10e8-5184-8c6c-96b58cd92a5c | note | Topsoil Stockpiles are;
66d46e4d-7655-5a45-a769-2417753966c9 | note | ○ Less than 3m High
d48a87c5-4de5-548d-b189-ed8232372c94 | note | ○ Less than 10m wide
074adc40-f4d8-5992-95c7-4f7a44568466 | note | ○ Appropriately battered, drained or otherwise protected to prevent erosion and segregation
ed3afd24-c108-53dd-a645-845c5b9d6f18 | note | ○ Stockpiled for the minimum duration
78c765ef-3884-5ecd-91b9-cdf34b617689 | note | ○ Stockpile sites shall not be placed within 50m of a watercourse or within the Q5 flood zone of a watercourse.
66dcfb17-c13f-5633-b96f-591e8ed6f6c4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5ae611ee-517e-5cf2-8964-e9e2ad51cf2c | note | Check Item - Check Item
f50c1836-970e-5919-a0fb-c35674b1624b | note | Reference - MRTS04 Cl. 8.4.1, MRTS04.1 Cl. 2.2
83fe9078-0ec0-4ac9-b30b-1138a18eef32 | checkpoint | The Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area prior to earthworks.
d238ecd9-a1d6-5d87-8a21-2c560a62147f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2f65a6f7-9843-50ee-8bbb-3fdcd9300666 | note | Check Item - Hold Point 2
f81195be-a535-501a-bc92-27cc7af1229a | note | Reference - MRTS52 Cl. 7.1
692bff3b-56b0-444d-9890-66a55eead92b | signoff | HOLD POINT
d9f6316a-835e-4eb7-b96a-7a9c4f140344 | checkpoint | All stripped areas, other than areas beneath road embankments or above road cuttings, shall be left in a neat, free-draining condition with side slopes not steeper than one in four unless otherwise specified. They shall be treated to conform with the landscape, revegetation and environmental requirements of the Contract.
e177abc3-410e-54d4-9da9-c11c4918ca40 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8bca25e7-2857-5bf5-8ebe-adc589ab321c | note | Check Item - Check Item
710a0ff4-6f3e-5bf9-a8c6-9455045941ff | note | Reference - MRTS04 Cl 8.4.5
4949fdc4-b739-4c31-a08c-9a3dab0f9bfc | checkpoint | Prior to any further Works over the stripped area, an As Constructed survey of the stripped area shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
da798cf0-9bd9-5de8-b248-03b730523afb | note | Acceptance Criteria and Frequency (Project Specific) - As Constructed Survey
95ed54d5-d923-5bb1-b3a0-8a7db689fe36 | note | Check Item - Survey Report
8200147a-c3bd-5dfe-98de-1b3a1e13d94e | note | Reference - MRTS04 Cl 8.4.5
19f57b05-0e42-49e3-af4d-445477de575b | checkpoint | Final Verification
5fd874b2-dafa-5026-8e84-33a240b427d6 | note | Project Manager Verify that the Above has been Constructed according to Specification
0d9742a2-4f53-532b-a3b5-01e54527f4d4 | textbox | Print Name:
da236f7c-b516-56ff-83bb-92a40df6fe92 | date | Date:
6632fd47-da24-5097-ba24-6fe3f7b76c8a | note | Client Verify that the Above has been Constructed according to Specification
8cbd5b4b-333d-519d-91da-f233ab288c07 | textbox | Print Name:
d25e0647-2c4e-5498-8235-3b8c38fad110 | date | Date:
7000e8eb-b558-47ab-882a-f1dea87aa317 | signoff | Signature
1f7def73-500d-4a4a-92a0-ff540e8fb271 | checklist | 04.09 - Subgrade | itp | 04.09 - Subgrade
f1868dc8-5765-4947-aa35-7004a77d0368 | section | Details
62ac137c-aebb-4001-9285-2975351005ce | checkpoint | CUTTINGS: Tests conducted in accordance with MRTS04 Cl 18.3.3.2
cc1268e1-433f-5dcf-b891-9f8b841ae44c | note | Acceptance Criteria & Frequency (Project Specific) - RDD
b2723e5a-df80-5b55-ac5d-de48f35d83c0 | note | Check Item - Check Item
afcf2545-5d0a-501d-a80a-6fb1cc4c1af5 | note | Reference - MRTS04 Cl 18.3.3.2
6a96f6ee-dc3d-43e1-b9ba-900e3e103e35 | checkpoint | Work stopped when excavation has reached sugrade level. Contractor shall carry out the requirements of the relevant provisions of Clause 13.3.2.1
46e3b67e-0959-52a9-abc5-69252095a183 | textbox | Specified Subgrade Treatement (A-K):
d9757ef2-5d88-5565-a90d-c91403fc18a8 | note | Acceptance Criteria & Frequency (Project Specific) - MRTS04 Table 15.3-A, Table 15.3-B
dea5769a-cef8-52b6-a433-bee27caed8e4 | note | Check Item - Hold Point 8
261a6841-dd23-5577-9bbb-a353c6a5ea75 | note | Reference - MRTS04 Cl13.3.2.1 Cl18.3.3
c1d961bb-b5e6-4f7d-9020-d125b1aae6f0 | signoff | HOLD POINT
8a87aa8c-ab63-462e-a9d5-dfdf955aa94c | checkpoint | General fill material used for construction of subgrade where embankment or cutting treatment using general fill, if used in road embankments must comply with Cl 14.2.4
9b221c59-86ed-5d55-9973-4ef62aeaa1d1 | note | Acceptance Criteria & Frequency (Project Specific) - MRTS04 (Embankment ITP or Related Lot)
56205f12-8077-56ae-9eb7-5ef4475813ae | note | Check Item - Check Item
b0f8f9f2-569f-5104-b2b5-77bf05b40346 | note | Reference - MRTS04 Cl 18.2.1
20b82577-ff35-465f-b56f-4c61966fec07 | checkpoint | Unbound pavement material shall conform with the requirements of MRTS05 Unbound Pavements and shall be at least of the subtype specified in Clause 12.1 of Annexure MRTS04.1, or where no such subtype is specified, at least subtype 2.4.
c58ea179-2c82-5d82-9a25-e666547e3180 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6676fe18-9bd4-57b8-a455-d41655324bc9 | note | Check Item - Check Item
b1872bdd-b77d-572c-89ab-1d50b5d380b8 | note | Reference - MRTS04 Cl 18.2.2
f0116637-417a-49d5-84e1-43871299c5d6 | checkpoint | Quarry Registration Certificate submitted to Administrator 7 days prior to sourcing high permeability drainage materials.
ae512ada-dc32-5e08-8c95-7912268ea56d | note | Acceptance Criteria & Frequency (Project Specific) - Written
f09daf10-9c86-5784-a6f3-0930e0577bce | note | Check Item - Milestone
449d3911-cc2b-53ae-b50e-2d765f399b0f | note | Reference - MRTS04 Cl18.2.4.1
46c9cb6b-69a4-46c7-a23c-a87e2d639eca | checkpoint | A mix design shall be submitted atleast 14 days prior to commencement of subgrade stabilisation
081cd03a-3e9d-51d2-9e97-265875c7e3e3 | note | Acceptance Criteria & Frequency (Project Specific) - Written
cd81489f-6715-5be2-8dbf-8b65eb3e8fdc | note | Check Item - Hold Point 11
503537e7-50f7-5973-900b-a2303f746772 | note | Reference - Cl18.2.5.4
ddf53bb3-72ef-442f-bf6a-589923564ec2 | signoff | HOLD POINT
d2a25c26-c2ac-4533-8a5f-3cab07391eda | checkpoint | Subgrade and underlying work tested and conforming prior to placement of pavement.
0f2761d3-3784-5051-a423-896155ef05d9 | note | Acceptance Criteria & Frequency (Project Specific) - ITP
3e49d730-33e4-52f0-bfb6-92ecd0dd497d | note | Check Item - Hold Point 12
f879c848-8c32-56ad-822c-bcac1211e0b2 | note | Reference - MRTS04 Cl18.3.1
272b749f-2e46-4f9c-bd5a-cc8f99a6064b | signoff | HOLD POINT
c92de848-0a67-4a7d-a548-992f930a4987 | checkpoint | Subgrade material provides a stable dense surface displaying no vertical movement under proof roll
fd679c94-5a9f-52c5-8921-be55eb90ce1d | note | Acceptance Criteria & Frequency (Project Specific) - Visual, No Delfection, Continuous
9cca0e6a-5e14-5815-9c32-7bc6ad0ae143 | note | Check Item - Witness Point 8
0188773e-4962-5018-b82b-efa3858acc04 | note | Reference - Cl18.3.2
e29fd581-af7e-4359-95d7-a8aa467de000 | checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
71ac6048-7390-5f48-b8e3-db4172090a01 | note | Acceptance Criteria & Frequency (Project Specific) - Visual, Tolerances: Table 6.3.1, Subgrade (individual results) = +25mm, Subgrade (average) = +10mm
ef969346-13be-5169-ab53-d888d80a81c8 | note | Check Item - Check Item
9ac89419-90f7-574f-a40f-86a1f46013ba | note | Reference - Cl 18.3.3.1
b5613bdf-fdf8-40d2-9274-dffcaa29f162 | checkpoint | Quality Verification Requirements Test Method
d22f8f0b-51f5-5ca6-8f96-b9a59799ff18 | note | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size, Min. Testing Frequency, Min. No. of Tests
2ddd15af-a1c9-52b2-b4fb-3765199959c0 | note | Check Item - Check Item
bb0a85f5-e70c-569c-a326-c24224256ac2 | note | Reference - Table A.2
7b23f6f3-6ef3-45e8-b73d-a372f2f33f8a | checkpoint | Compaction/Moisture Ratio: AS1289.5.4.1 or AS1289.5.7.1
d2c4a9ec-7ce7-5a1e-8a9c-14b258d07afc | note | Acceptance Criteria & Frequency (Project Specific) - 2000m2, 1 per 500m2 (per layer), 4 per lot
45fbffd5-5c51-52de-9a0c-251ddd09d4d1 | note | Check Item - Check Item
c1ce05de-2225-5a73-a8c1-d529491738ff | note | Reference - MRTS04 Table A.2 No. 2.11
42d97b04-27a4-4d0f-ad1c-2f2b6b6c867f | checkpoint | Grading (AS1289.3.6.1), PI (AS1289.3.3.1 or AS1289.3.3.2), WPI (Q252)
28798cd3-7fc2-552a-8484-f7cc25d3a417 | note | Acceptance Criteria & Frequency (Project Specific) - 2000m2, 1 per 1000m2 (per layer), 2 per lot
1467daf5-0572-589e-8b8b-7189df876526 | note | Check Item - Check Item
4ba7edd1-5a9a-5749-b1d3-3556f9323c95 | note | Reference - MRTS04 Table A.2 No. 2.11
fa786ed7-0403-4b64-b594-fdedd2b8b39f | checkpoint | Geometrics, Horizontal Position
51450897-4edd-5aff-a5e3-a84fcbd3112a | note | Acceptance Criteria & Frequency (Project Specific) - All edges and interfaces (at 20 intervals)
2c9bccf3-b869-5779-9448-f069e94692a9 | note | Check Item - Check Item
3420ebbb-c37d-5e70-8fe5-4430d6911043 | note | Reference - MRTS04 Table A.2
876cb2fb-73b9-42b3-a7fb-8d455fcdfb82 | checkpoint | Geometrics, Vertical Level
974c0a55-aa61-5e15-9ae3-41a58c815a51 | note | Acceptance Criteria & Frequency (Project Specific) - All edges and interfaces (at 20 intervals)
92a38a81-b80d-50f4-9910-96cc09804dd4 | note | Check Item - Check Item
0aedfbba-528d-5f91-9673-3ef5f18e0fb0 | note | Reference - MRTS04 Table A.2
528f957a-0287-4188-b37b-dd03cf86a04d | checkpoint | Geometrics, Deviation from a straight edge < 25mm
88192551-4641-506a-9495-56f3c81e02bc | note | Acceptance Criteria & Frequency (Project Specific) - All edges and interfaces (at 20 intervals)
3b6cea40-986b-5fdd-bb85-f6444762f930 | note | Check Item - Check Item
07864920-07e9-51a5-9552-890d6a81de59 | note | Reference - MRTS04 Cl 6.3.2
c2698fb7-7d0c-462f-9af6-a2a8e45f93ea | checkpoint | Final Verification
72bb748e-1b10-5023-b168-fbaa2169fa8e | note | Project Manager Verify that the Above has been Constructed according to Specification
c6a6b917-8b06-5500-bb4b-92ed9698dc75 | textbox | Print Name:
fb3b2b3b-9d91-5127-a7da-84c22fc14624 | date | Date:
e42795f2-9054-5248-8f2c-8efadbef6b89 | note | Client Verify that the Above has been Constructed according to Specification
80a5f1fb-8eb7-5cea-90ce-b7ed6b8b09bf | textbox | Print Name:
2906761d-5528-5cb2-8a3f-5022b2d9fc7a | date | Date:
be5042b7-9cc0-4705-81fb-62a8a46747ad | signoff | Sign ITP
913a9da1-fcb6-40c6-bba0-6d420a905a5f | checklist | 04.10 - Backfill | itp | 04.10 - Backfill
a825a4a5-beb9-4a5e-94c0-2e180642b8c7 | section | Details
f3fc2ecf-8baf-4fd2-8838-f9c1c1420db2 | checkpoint | Prior to incorporating any backfill material, stockpile or source test results as specified in Appendix A shall be submitted demonstrating material meets the specified requirements.
abeafeaf-51d6-5c63-abba-72275e49a6ae | note | Acceptance Criteria and Frequency (Project Specific) - Written
3e1eda18-5326-52ef-81a6-0222daa2d535 | note | Check Item - Hold Point 11
66762d31-1006-5af4-8b83-60df2d1a5a62 | note | Reference - MRTS04 Cl19.1
d8137485-4c3b-4792-9fc7-63f1be2defe9 | signoff | HOLD POINT
a515066d-ec1d-470a-b14b-37d8e8749c96 | checkpoint | Material for backfill shall be as shown on the drawings or as specified elsewhere in the Contract. Where not so shown or specified, material shall be earth backfill material complying with the requirements of Clause 19.2.2. Earth Backfill Material shall comply with the requirements of Earth Fill Material Class A1, Class A2 or Class B specified in Clause 14.2.2 except that 100% of the material shall pass 25.0 mm test sieve.
f8361e55-2814-59e8-81dd-f8a98e8dc766 | note | Acceptance Criteria and Frequency (Project Specific) - Grading
f57056de-1abb-5d15-86ce-dac9ed9454cf | note | Check Item - Witness Point 6
b4ba23a6-ab93-53b5-bcdf-1318e775cc2a | note | Reference - MRTS04 Cl19.2.2, Cl19.3.1
1a8c40b6-be39-4936-91e6-82c21b747aed | checkpoint | Unless specified otherwise in Clause 19.3 or elsewhere in the Contract, backfill shall be compacted using the compacted layer method of construction in accordance with the requirements of Clause 15, except as may be modified by the requirements of Clause 19.
2405146b-5b5e-5620-a00b-48e5cc7a673f | note | Acceptance Criteria and Frequency (Project Specific) - RDD 1/500m2/300mm Lift - min 4/lot
012bbc24-2f8c-5ab7-a705-cf9e36903d1a | note | Check Item - Check Item
26e9bbbc-0c02-5597-a470-7114d37bc949 | note | Reference - MRTS04 Cl19.3.1
4ac3eeaf-0e40-4eec-b069-6fe3cd9c4422 | checkpoint | Backfill around In Place units (pipes, culverts, pits and so on) not placed until completed and inspected by Administrator and any curing period has elapsed.
d6178134-ae33-5267-879f-fd049d80250e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bdf3d3e4-33c7-5a8b-aa1f-99665a6ae37f | note | Check Item - Hold Point 12
9e74f228-10a8-58b2-bea4-de52f865ff87 | note | Reference - MRTS04 Cl19.3.3
b1170b78-30b9-4a1a-b704-d23d6f750a7b | signoff | HOLD POINT
920fdde8-6b9c-4930-8d9a-bcc16246dee8 | checkpoint | Where material is placed on opposite sides of a culvert, structure, conduit etc. the difference in level of compacted material on opposing sides shall not exceed 150mm, unless shown otherwise on the drawings.
ab851254-0fe5-5bfd-b0f9-02dc416827a3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cd7bc715-9248-5e5b-8437-e0aea9c70ecd | note | Check Item - Check Item
6b587614-5692-50ad-8384-d67c42bcb16b | note | Reference - MRTS04 Cl19.3.3
df0a45df-350c-4e97-a510-cba08a60aa37 | checkpoint | Foundation bedding, haunch, side and overlay zones for concrete pipe culverts shall be as per standard drawing 1359.
41b3436c-8f8c-58c4-83b8-dca063be449e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2f13dacd-090c-5d49-9f07-eb59d1114842 | note | Check Item - Check Item
02daeedb-9f66-5997-864b-df456347cc5f | note | Reference - MRTS04 Cl19.3.4
812dad98-67ff-40fe-ab32-ec0f6921c146 | checkpoint | Construction Testing Requirements: Test Method
6ec73f3f-fae7-5e1c-83fd-09729d324508 | note | Acceptance Criteria and Frequency (Project Specific) -
afed8d10-4bc9-53e9-999f-fc9d98e0bd6a | textbox | Max. Lot Size
848b82d0-ce96-5260-9c29-065ce7b1cad7 | textbox | Min. Testing Frequency
02b4e699-c9a1-5804-8928-dfbcf9cbfc3f | textbox | Min. No. of Tests
a46c9bb4-de62-559b-8139-57e1dedb2687 | note | Check Item - MRTS04
3d3fa59b-3116-5d55-8e5e-48a6ff86ca6b | note | Reference - Table A3
9055ef24-2ba2-4175-88ef-b63ed9bfd2e2 | checkpoint | Relative Moisture - Rainfall zone: High (>1000mm), Class A1/A2: 70% - 100%, Class B: 80% - 110%
3c6f69bd-df56-5399-8ed6-4f3ae9763f84 | note | Acceptance Criteria and Frequency (Project Specific) - Each culvert/structure
f0e6504e-417f-5024-b67f-77a8ae1c4abe | note | ○ 1 per 100m3
fc6f7e55-b4c3-5647-b248-231239030d79 | note | ○ 2 per lot
a4aa2a81-9a5d-549a-9b0c-796e44e50d41 | note | Check Item - Check Item
7aed6eba-c3fa-5c03-a369-b4841194824f | note | Reference - Table A1
1dcc4544-8b52-4035-be13-b5b289eb33ad | checkpoint | Relative Compaction - Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
887a8571-b985-5732-8496-a73750514e4a | note | Acceptance Criteria and Frequency (Project Specific) - Each culvert/structure
8885e066-3b8c-5344-b2cb-61c792d35c39 | note | ○ 1 per 100m3
d16d1a81-5809-52dd-84bf-b0aa1e5cb0c6 | note | ○ 2 per lot
4b5e485d-d943-50d6-9016-890b6196b8fa | note | Check Item - Check Item
39312952-ba9b-5ac7-97e8-3930ed52970a | note | Reference - Table A1
b659db86-4594-41e4-8bef-061ac5a446f4 | checkpoint | Stockpile Testing Requirements: Test Method
c18cae72-200e-537e-b450-e0ad419edcbe | note | Acceptance Criteria and Frequency (Project Specific) -
63465e3a-d918-5526-a767-665b0f25c348 | textbox | Min. Testing Frequency:
a6740e33-cf6d-5da7-b3eb-705e710056b2 | textbox | Quarry Source
be0963f9-50ad-58a2-b537-7791cc5bbc66 | textbox | Other Source
b76a7a08-5d23-53a4-8f36-78f1ee0f6e6f | note | Check Item - MRTS04
2ab19636-a499-59b1-a515-d3c51717fae5 | note | Reference - Table A3
28e79144-0acc-46c3-837f-6322102af451 | checkpoint | Grading
0043bbb8-ef92-5a97-a360-740f9372c83a | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
47da7248-a7c7-58d5-9637-78ef1eb86087 | note | Check Item - Check Item
f826bf78-1eef-53aa-a564-889fbde9ae30 | note | Reference - Table A1
c1fd6d35-f4ea-41e7-9e2e-fe93b93ece5c | checkpoint | Plasticity Index
8e63c655-a3c6-5cc2-98c2-b84f42e12ea0 | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
c468a97b-17e9-5c06-820c-1a16c4d8b7ab | note | Check Item - Check Item
3603eeaf-c025-5cc0-9c73-89d57a7bf20f | note | Reference - Table A1
e4942fd4-ba94-4f8a-a65d-13adaa3bf942 | checkpoint | Linear Shrinkage
bd91c95e-108f-5025-8bf5-28d06c3f3f62 | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
4e4a34fc-6e5e-520a-8d19-67d4d894d7c6 | note | Check Item - Check Item
1b9ca419-a873-55b7-bc5c-e9516d3a7612 | note | Reference - Table A1
bc456d12-9b85-46e0-b4e1-d5f6f57b3b74 | checkpoint | Emerson Class Number: AS 1289.3.8.1
dd40cc80-56a3-5b0e-ae20-1a472783f42c | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
31ec665a-a150-56d8-b6eb-2262983b2284 | note | Check Item - Check Item
11405e46-38ce-5db8-ae2a-79cb044e836d | note | Reference - Table A1
40cc7aad-1e4d-4fe7-8b38-02dad7014734 | checkpoint | Soaked CBR and Swell (For earth backfill in subgrade only)
bcb43521-9251-5b69-a136-05b3b75e6b68 | note | Acceptance Criteria and Frequency (Project Specific) - 4000t, 200m3
5dabe55f-6aa9-5252-8339-d1b93b59b32c | note | Check Item - Check Item
feb90165-ad2c-5f4d-a016-89a5db200566 | note | Reference - Table A1
9a72646e-8d31-4a0e-9bb0-760bcb0bb699 | checkpoint | Final Verification
6c27cc87-0011-508c-ad6e-1e596c266633 | note | Project Manager Verify that the Above has been Constructed according to Specification
5339089d-d538-5702-8856-4459c614c49d | textbox | Print Name:
cf8ce7d3-d875-53e5-9feb-999949f341d1 | date | Date:
148b2be7-dc8d-5b57-b9fa-d6c47da9b0b9 | note | Client Verify that the Above has been Constructed according to Specification
61b4cca6-d459-51fc-867e-c89b8bd4220a | textbox | Print Name:
ac870449-603d-5301-b0de-31abb9078564 | date | Date:
5a40762a-db3d-4d3e-9812-2542320ef9fa | signoff | Signature
ff03fd9b-ba80-48fa-beef-18471a497395 | checklist | 04.18 - Subgrade Testing | itp | 04.18 - Subgrade Testing
0b28c2be-77e2-4f79-96b6-4365856c1dc7 | section | Details
d804e1d7-e8fc-41eb-90bb-1104ba36b574 | checkpoint | All sampling shall be undertaken by the Contractor, in the presence of the Administrator, unless directed otherwise by the Administrator
d8cbb1ee-cb60-5a3d-9508-fe44a264cad7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
229cf4d9-9bcf-557d-8f57-500cad1507ba | note | Check Item - Witness Point 5
8921a0b6-d9ae-5b05-a335-029546603642 | note | Reference - MRTS04 Appendix B.3
9d68a7db-813f-4ded-a35b-dd1818fc9925 | checkpoint | Each different material encountered within this depth in Clause 18.1 shall be sampled and tested in accordance with this Technical Specification unless otherwise approved by the Administrator.
7a2f3cb8-d71f-5cdf-b5e6-c5003d29341f | note | Acceptance Criteria and Frequency (Project Specific) - Testing
9dd89e81-1578-5814-b3d4-f1d28abdd28a | note | ○ 1.5m below subgrade in CUT
698a91f6-40c1-58c9-bb9d-d7b50ce4fc61 | note | ○ 2.0m below subgrade in EMBANKMENT
5da4d3b2-c0ae-5639-b31e-c69636a019fc | note | Check Item - Check Item
e4531230-efcb-52f0-a3e1-aa14bdcbfcb6 | note | Reference - MRTS04 Appendix B.3
90d168a6-ecd1-43f5-8e4c-3bbf81a5c5cf | checkpoint | Untreated subgrade material shall be sampled from their natural location in accordance with AS1289.1.2.1. Untreated subgrade materials that break down under environmental and service conditions due to weathering shall be pre-conditioned by artificial weathering in accordance with RMS Test Method T103
5023d477-40dc-5d39-a98b-b02b14b09ef6 | note | Acceptance Criteria and Frequency (Project Specific) - Testing
91f7904f-3775-5853-9bae-f457715de7bf | note | Check Item - Check Item
537f346a-69f9-561d-8ce4-08ea6bbf1c38 | note | Reference - MRTS04 Appendix B.3.1
2029525e-0838-4287-81bf-e1fcaf87d7c1 | checkpoint | Fill Materials from Stockpile:Materials which breakdown, degrade or fracture during construction, such as highly and extremely weathered rocks, shall be pre-conditioned prior to compacting the specimens for testing. Preconditioning may include: – Lab preconditioning, – Field compaction using construction methods propsed for the works. The pre-conditioning method shall be recorded in the in the submission of the test results detailed in MRTS04 Clause B.5.
8d3ef1b9-950b-5437-bc94-54fc48c7fa46 | note | Acceptance Criteria and Frequency (Project Specific) - Pre-Conditioning
c5c77901-390f-5905-9d2d-ea01bd10a263 | note | Check Item - Check Item
c802f0ec-64dc-5729-b6b6-d513082c5dad | note | Reference - MRTS04 Appendix B.4
0048c31b-6497-46e0-bf94-0807e734efe4 | checkpoint | Fill Materials after Field Compaction: Obtain samples from the completed fill (after compaction and proof rolling) in accordance with AS 1289.1.2.1. Samples shall be taken over the full depth of the compacted layer.
3ca7c605-da3b-566a-b09e-b777b080af70 | note | Acceptance Criteria and Frequency (Project Specific) - Test Reports
49f933e6-8523-5772-bb47-0801e445e56b | note | Check Item - Check Item
c7d5b1b1-993b-54ca-81c9-530fba4eb386 | note | Reference - MRTS04 Cl. B3.2.2
a1ac1816-d797-4a65-bd89-41f5085d10ac | checkpoint | All testing shall be undertaken by the Contractor, in the presence of the Administrator, unless directed otherwise by the Administrator
6ebb0f68-930f-5132-bfb0-ec2723f1e0b8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6e6d93cc-4804-5398-9c12-cae63f9d31b1 | note | Check Item - Witness Point 6
db46f236-30be-5283-aa7d-492dfbe2fed1 | note | Reference - MRTS04 Appendix B.4
cc6a16d6-a0cf-4c43-baf5-5c28d3a1d3a5 | checkpoint | Each untreated subgrade material sampe and each fill material sample shall be tested for: laboritory CBR, swell, PSD, maximum aggregate size of fill materials, liquid limit, plastic limit, plasticity index, weighted plasticity index, insitu moisutre content
0568f0af-504d-5255-9eec-0fcc232479a2 | note | Acceptance Criteria and Frequency (Project Specific) - Testing per material type
ec2fd525-b434-54ab-b23a-18337effae6b | note | Check Item - Check Item
3179a825-5386-5ae4-9570-c4f722fb562a | note | Reference - MRTS04 Cl. B.4 & MRTS04.1 Cl 3
6e9ba0ba-1079-4f8a-a0c6-17e9f641ec62 | checkpoint | Final Verification
e7e6b16c-b644-5e97-afb9-656846188451 | note | Project Manager Verify that the Above has been Constructed according to Specification
02c7929b-2e3e-5ab5-8967-1b7db284467e | textbox | Print Name:
f53f8c54-60b9-5a8f-9550-4671fb15d9d1 | date | Date:
231135ac-2b7c-5629-987d-c4442ee22dfc | note | Client Verify that the Above has been Constructed according to Specification
11c9e42c-6139-52bc-9c5b-c3a0ddff44b1 | textbox | Print Name:
64830cc8-56fa-51e3-9797-da166d981e78 | date | Date:
e643ad40-6022-4801-ab08-44103a2eacbe | signoff | Signature
477ffcd9-d602-41e3-b03e-1502af88aef5 | checklist | 05.01 - Placement of Unbound Pavement | itp | 05.01 - Placement of Unbound Pavement
3d575801-7a04-4389-a67d-721030a0f57b | section | Details
b6e6f8e9-c2ec-4d01-9107-f16aa51363d7 | checkpoint | Layer Thickness between 75mm and 250mm in accordance with table 8.3.3
17623837-684d-5052-9f9a-3d7db62e6e25 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8f596a18-9e29-5869-b4d6-d09dc5b49f11 | note | ○ Layer Thickness: 75mm - 250mm
7ce7541e-1b76-524e-a0b1-cac6d9ee8e36 | note | Check Item - Check Item
a8682212-d376-505b-84f0-a550f622f320 | note | Reference - MRTS05 Table 8.3.3
6d9483ec-2e7f-41d8-9610-d1731995862a | checkpoint | Relative Dry Density Requirements: C.V of RDD >= 100% MDD for Type 1 Materials, = 100% SDD for type 2.3, 2.4 and 2.5
a89ed846-ca3a-5be6-bd28-b508e881efdf | note | Acceptance Criteria and Frequency (Project Specific) - C.V of RDD >= 100% MDD (1 test / 500m2, min 1 / production day, min 4 per lot)
e60069ae-90b1-5a2a-982e-249e1cdc2e5c | note | Check Item - Check Item
e9e15438-d92e-5bfe-b9dc-f381f9c4a085 | note | Reference - MRTS05 Table 8.4.3
bab37bf3-8d1f-4dbd-b1e4-f7b1aa69426d | checkpoint | Unless agreed otherwise, a trial placement of materials of a minimum size of 1000m2 is required.
736d77a4-0260-53ff-a298-ec62fc148339 | note | Acceptance Criteria and Frequency (Project Specific) - All tests as described by this ITP and MRTS05
cee25575-5595-5191-9367-9e73f98d1806 | note | Check Item - HOLD POINT 3
a42adb9d-39dd-566a-80fd-5282f1dc8915 | note | Reference - MRTS05 Cl. 8.2
e1a0524f-3f2f-4692-a8b0-08f42b3f4fef | signoff | HOLD POINT
dedef4dd-ac14-4c1a-b362-1b7c7826ddb5 | checkpoint | Moisture content such that the degree of saturation is less than 60%(modified). The administrator may accept a higher level of moisture up to a maximum of 70%.
f6f95914-83c4-5017-9660-00f3dd3536aa | note | Acceptance Criteria and Frequency (Project Specific) - S < 60% (1 test / 500m2, min 4 / lot)
d5cda34d-21bd-5b5a-9417-5fdd0138966a | note | Check Item - HOLD POINT 4
fb2117f1-a0bd-5c24-af3e-25933aed3174 | note | Reference - MRTS05 Table 8.3.4.1
46d89c82-1dd0-4707-9ea5-de02879268ae | signoff | HOLD POINT
5202eda2-ac9b-4488-8b89-7f9484537c53 | checkpoint | No visible segregation of material. Partical Size Distribution Q103A.
dc72d859-13b1-5e56-94e2-601b91430440 | note | Acceptance Criteria and Frequency (Project Specific) - Min 1 per lot
34be4df1-39fd-53b0-87ad-4b7805a584d2 | note | ○ Additional tests as directed by the Administrator
6adfdd86-8b0d-5986-82b3-74bd3304d254 | note | Check Item - Check Item
5c86464e-35eb-591c-84fa-a97bcaac362c | note | Reference - MRTS05 Table A3
e3b4210b-05f3-428f-abf4-998c61ad2faf | checkpoint | Geometric Tolerances in accordance with MRTS05.1 Cl.8.4.4.3
996ca10d-b4cd-5627-871e-16dcade8a439 | note | Acceptance Criteria and Frequency (Project Specific) - ±10mm when covered by AC
bfc29acb-0c25-5318-904c-82d770315eb8 | note | ○ ±15 mm in all other cases (1 test / 20m)
78d6027f-d5cc-5f09-84df-b701c0b08bc5 | note | Check Item - Check Item
4fe2a0d1-c222-522b-bbc1-359f7206272b | note | Reference - MRTS05.1 Cl.8.4.4.3
e4b399a7-2769-4cdd-98c5-663f72458cf3 | checkpoint | Geometric Tolerances: Horizontal tolerance of ±50mm, or -50 / +250mm for pavement edges not adjacent to any other section of pavement and not adjacent to any structure or adjoining road
78e09efa-2e31-5820-b489-08ee17b2e9e5 | note | Acceptance Criteria and Frequency (Project Specific) - ±50mm, or -50 / +250mm if not adjacent to adjoining pavement (1 test / 25m)
932840c1-b54d-5ab1-a0b2-5d056df5d58a | note | Check Item - Check Item
8b5b5002-73ea-5ed5-895a-30a967e1c6f5 | note | Reference - MRTS05 Cl.8.4.4.2 Table A4
41c5a5c7-c05c-4edd-a150-417f683e7311 | checkpoint | Deviation from a 3m straight edge shall be less than 5mm.
7bcb9b4c-ff63-505c-8c2c-af3b675fd894 | note | Acceptance Criteria and Frequency (Project Specific) - Straight Edge Test
87ac0d18-2e34-5941-adad-c80245fbaa52 | note | ○ Less than 5mm
08311682-164b-5aa6-b1e9-27408a02aa17 | note | ○ 1 test per 20m
78e7c279-fa6c-5fcd-9b04-2b116dad0792 | note | Check Item - Check Item
dc040428-b4eb-516a-93c9-2140996a7fc5 | note | Reference - MRTS05 Cl. 8.4.5
2327117c-696d-4a50-a7fd-f50969d6802f | checkpoint | Each unbound pavement layer shall be tested for perceptable surface deformation by 'proof rolling' the pavement, in the presence of the Administrator.
312542e7-1a80-53fd-a54b-6a59617105dd | note | Acceptance Criteria and Frequency (Project Specific) - Visual, Continuous testing
6336e622-8845-56bf-9551-dafd8eab6245 | note | Check Item - Witness Point
7b96e1e6-1666-5241-98d1-4392885cafbb | note | Reference - MRTS05 Cl.9.4.7
99706f2e-fe7d-4f97-80b2-40633deaeefe | checkpoint | Additional Geometrics (final layer only). The crossfall shall not depart from the corresponding crossfall shown in the Contract by more than 0.5% absolute.
09a7f2a8-6b5f-5a3e-aa49-8b5d873c231e | note | Acceptance Criteria and Frequency (Project Specific) - 0.5% deviation from crossfall (1 test / 25m)
27adc136-2d40-5928-a869-8256f13ccb98 | note | Check Item - Check Item
15cad4b1-7243-58da-ae1d-6bdd050d7eaf | note | Reference - MRTS05 Cl.8.4.4.4
cd641982-a271-476f-a2d7-09a944a66b37 | checkpoint | The finished surface of any unbound pavement layer shall: – be hard and homogenous in apperance, – not have any loose, segregated or contaminated areas, – have the coarse particles slightly exposed, – not be affected by delamination, and, – not visibly deflect under load when proof rolled in accordance with Cl 9.4.6
1c047261-7471-524e-9fcf-04c3f91b3d68 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c3ea0f58-d55a-598e-97d8-43d3a226b8bc | note | Check Item - Check Item
f2a4eed6-58aa-5161-86f7-915693e28ca7 | note | Reference - MRTS05 Cl.8.3.5.1
47bcf7c3-9a65-4936-bc21-1078f9feb42c | checkpoint | The Contractor shall not incorporate materials into the work unless it has demonstrated that the material complies fully with the requirements of this Technical Specification before delivery of the material to site
64d18683-0d45-5c70-8429-f23eeab49950 | note | Acceptance Criteria and Frequency (Project Specific) - Test Results per lot
e9967e78-a500-5479-9a4d-c94e7374fdb4 | note | Check Item - Hold Point 5
5160cff6-2288-5149-b085-13f4b525ae81 | note | Reference - MRTS05 Cl.9.1
8d32b118-39ac-4e0a-863f-e605c1a198d7 | signoff | HOLD POINT
09a09197-218e-49fd-8765-3776f160f912 | checkpoint | Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until Hold Point 6: a) all testing has been completed, b) the surface finish of the layer complies with the requirements of Clause 8.3.5, c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator, d) the layer has been presented to the Administrator for inspection, and, e) the As Constructed Survey requirements of the lot have been met as specified in MRTS56 Construction Surveying and notice of such works has been provided to the Administrator.
48fe93ee-017a-5eda-bf33-4ed493ad26e0 | note | Acceptance Criteria and Frequency (Project Specific) - Adminstrator Acceptance
af96d217-df59-5f40-a76f-249bb41dd76d | note | Check Item - Hold Point 6
ca4b4252-b4dc-5cf5-84c9-564539a40b6b | note | Reference - MRTS05 Cl.9.5.1
e35ba4ca-41dd-47c1-ad9e-76a76dcd3837 | signoff | HOLD POINT
0e6cb33e-e85d-4a2f-93ff-50b6e0f39119 | checkpoint | Final Verification
0f8acf3a-cf0b-5f12-8c70-d7508a56c46b | note | Project Manager Verify that the Above has been Constructed according to Specification
08922ac6-fc64-5974-9d8a-8d5849bf8d20 | textbox | Print Name:
ba8e4ce9-4ff6-5e5a-a7e6-0e186f88a64e | date | Date:
bdc43317-affb-516a-a702-e3a2b0480cb1 | note | Client Verify that the Above has been Constructed according to Specification
8b082f89-dd33-5d16-b6e7-556fc5e834ec | textbox | Print Name:
148da89f-7055-5284-ab37-4b75e0b6db51 | date | Date:
9f3ac309-4c90-4e11-8cad-63442dfc9231 | signoff | Signature
7df555e1-d26e-4784-87b9-8b07a8bef1d6 | checklist | 05.02 - Supply of Unbound Pavement Material | itp | 05.02 - Supply of Unbound Pavement Material
3e86a2b0-05e8-44d9-8203-862b98feb55c | section | Details
1a6ce208-dbf6-4f14-9be2-98365c7e972b | checkpoint | No unbound pavement works shall commence until all relevant construction procedures have been accepted by the Administrator.
fcaee8dd-a302-5ad6-86b9-1c7fe564be9b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
450d739c-3f06-5ed0-88c8-182071822fbd | note | Check Item - Hold Point 1
db0e47c9-0d1e-5f17-a7b1-4dd107080c71 | note | Reference - MRTS05 Cl. 5.2.1
0c2bf31e-bfe4-45b6-b8f3-24631350ad89 | signoff | HOLD POINT
99b8c26c-982f-4680-b5f2-c34be5bfa659 | checkpoint | The aggregate production procedures shall be submitted to the Administrator at least 7 days prior to commencement of material production
2b8829cf-1bed-535b-8d1c-af31abeb043e | note | Check Item - Milestone
eb57178d-e75e-5a64-8803-fa766310f0e3 | note | Reference - MRTS05 Cl. 5.2.2
2e65c0b6-6ebe-472c-b0a3-6c6c07755541 | checkpoint | The unbound pavement construction procedure shall be submitted to the Administrator at least 14 days prior to the commencement of unbound pavement works
2adc13ed-c5cb-54bf-9b96-97726cf40bf4 | note | Check Item - Milestone
b78b72db-7b32-51df-bde4-da67df6d36a8 | note | Reference - MRTS05 Cl. 5.2.3
d71d7ad0-16fb-423b-b4c2-9178270996b4 | checkpoint | The current TMR Quarry Registration Certificates for Type 1, 2 and 3 materials, shall be submitted to the Administrator at least 7 days before a material's supply or use.
9faf5ced-c689-5f1c-9483-8338610e7bf2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6d15eb48-4ce0-5165-90a2-b3931d578a91 | note | Check Item - Milestone
679323c7-f9c0-59d7-9d26-bbe87127013b | note | Reference - MRTS05 Cl6
f9cd7983-2574-4717-b636-e983941376e2 | checkpoint | Material from a quarry shall not be used until the quarry has been approved by the administrator.
fa9ac45d-9430-5cf3-b509-99a401e9f376 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
53effcd5-4efe-5819-975a-4d5e004838e4 | note | Check Item - Hold Point 2
fb9177ae-9419-5f2c-a4c7-f06cd2da9551 | note | Reference - MRTS05 Cl6.1
38d5a6a0-35d5-4bcf-a587-b881e83c69b0 | signoff | HOLD POINT
9b4d8e48-d89c-4a51-81a6-e3f511d730e5 | checkpoint | Type 1, Type 2, Type 3 and Type 4 materials to comply with the respective material properties from clauses 7.1 to 7.4.
c587eed8-1fea-5a4a-a167-6f2fe8451f32 | note | Check Item - Check Item
4eeaf9d3-3518-5238-9681-cd6aa04839c5 | note | Reference - MRTS05 Cl. 7.1 - Cl. 7.4
18b68350-54cd-42e6-bf79-1e2f18669643 | checkpoint | All pavement material incorporated into the finished pavement shall be free from sticks, organic matter, clay lumps and other deleterious material or contamination.
1eacac4d-2da0-57c0-857b-270da09898c0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
19ce02a8-4eb2-5358-bfb0-dde3302d8b71 | note | Check Item - Check Item
7154b57a-df08-55d1-b43c-537570297b8c | note | Reference - MRTS05 Cl7.5
9dc3fbde-1305-4944-b146-77ddb32ebcb7 | checkpoint | Stockpiles located as specified in MRTS05.01 Cl. 2.4 or if not specified, on clear, even, firm, well drained ground where it can be clearly identified with individual stockpiles separated by at least 2m.
31ac98da-a4e7-5371-802a-633185964ff2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e6f7790e-4485-5ff8-a33d-ada6c46a7abc | note | Check Item - Check Item
2c2d8332-c9df-5081-92d7-a0d3d94e7120 | note | Reference - MRTS05 Cl7.7
8df2cabe-82f6-451b-8833-08c2bb4f6371 | checkpoint | Separate stockpiles for each production lot, or stockpiles incrementally created from a single material subtype with each added lot tested and approved prior to subsequent lots being added.
232944d9-0811-501c-a49b-8f8c6a9acf74 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c4e40951-6fc5-51a2-949e-c6c90be3147f | note | Check Item - Check Item
af5ff043-934b-5f04-956b-45459e8fed9f | note | Reference - MRTS05 Cl7.7
e1683adc-974d-498a-9e5a-1fc8c6b13082 | checkpoint | Final Verification
1f041e38-2d33-575d-9783-f86c4b45da57 | note | Project Manager Verify that the Above has been Constructed according to Specification
004eb277-813f-53d0-a288-91be932eff35 | textbox | Print Name:
be286db0-3fe8-5d1c-819b-e93e6a3964c6 | date | Date:
f0f9fd29-2f5f-5750-a8a7-a4eda74a57d2 | note | Client Verify that the Above has been Constructed according to Specification
c1f50c57-c9fe-5db5-8d7f-4f24678ffb4d | textbox | Print Name:
764cbc97-a5fc-543f-8872-bb0359848e76 | date | Date:
fa506a21-32dd-47fb-a988-e27f4fdec6fc | signoff | Sign ITP
d9d9e8b4-682b-4ce1-834d-55a62be4b117 | checklist | 10.01 - Plant Mixed Lightly Bound (Cemented) Pavements | itp | 10.01 - Plant Mixed Lightly Bound (Cemented) Pavements
4d1175d5-6a5b-4e50-a9b8-a4129d81c0b4 | section | Details
cb2063d8-bdf7-4797-a477-ef0c8b7e647d | checkpoint | No lightly bound pavement works commenced until all relevant construction procedures have been accepted by the Administrator.
82c5a005-8bc4-5fc1-991e-b6f19e78288a | note | Acceptance Criteria and Frequency (Project Specific) - Written
72abe28b-82bb-55b1-bc96-a147f176cf1e | note | Check Item - HOLD POINT 1, Milestone
d009e04a-ca4f-597a-bcca-5240198b0a9c | note | Reference - Clause 5.2 MRTS10
ca62e491-49b3-49da-b886-9416cb31870e | signoff | HOLD POINT
6e886dbb-8096-4d84-9173-d30c5a9ea578 | checkpoint | Lightly Bound Pavement Constution Procedure submitted to Administrator at least 14 days prior to commencement of pavement works.
fb37eb42-6de9-5fd0-b416-e5582b95b90d | note | Acceptance Criteria and Frequency (Project Specific) - Submitted 14 Days Prior
29c35c16-f252-50ad-8151-8bf5a18d24cf | note | Check Item - Milestone
4c03ce3e-4a8f-5d27-8665-97bdcd220558 | note | Reference - MRTS10 Clause 5.2.1
8fb18215-2e45-4a61-b83f-dadea19617d9 | checkpoint | The unbound pavement material to be used as part of the plant-mixed lightly bound pavement conforms to the requirements of MRTS05.
f3ecdc79-7d16-5a78-803b-7c4e10a134a2 | note | Acceptance Criteria and Frequency (Project Specific) - Written
800eedd4-701e-5d29-874d-bbeea65a4e6e | note | Check Item - Hold Point 2
dd6b5c3d-3753-541b-b0f1-0758edf7fcc7 | note | Reference - MRTS10 Clause 6.1
12c1b90d-0d03-4097-bcb6-e5f05f8090b1 | signoff | HOLD POINT
8231016b-9bd4-466b-b404-9c7a1ebc1452 | checkpoint | Regsitered mix design and terget content of stabilisation agent nominated and submitted to Administrator along with: 1. Stabilised Mix Design Certificate, 2. Quarry Registration Certificate
dcb0538b-8745-54d3-b991-9b370599f7a7 | note | Acceptance Criteria and Frequency (Project Specific) - Submitted 14 Days Prior
0ded1b53-941a-570d-8f92-cbfd6dde7508 | note | Check Item - HOLD POINT 3
f23651aa-be32-5fd1-94eb-2800e95831ae | note | Reference - MRTS10 Clause 7.1
dbb283b2-496d-4a35-bfaa-6c0735f065f7 | signoff | HOLD POINT
c337a71b-0ea3-41d0-bad7-998be990e931 | checkpoint | A trial of the manufacturing and laying operations shall be caried out prior to commencement of the work.
1edea30e-bc41-51c7-9625-0b9e68733ffd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4b0760f4-57f7-5e8f-8d2c-befb0e4a09f6 | note | Check Item - WITNESS POINT 1
ba03d49b-cb53-5df8-a53b-15710bf03626 | note | Reference - MRTS10 Clause 8.1
38c11b4b-310d-4ca8-8ac0-05bcf4570917 | checkpoint | Prior to continuing works after completion of the trial, records which demonstrate compliance submitted to the Adminstrator for acceptance.
f38e9af8-72f0-5a14-b699-c932b2006313 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8c2eeccf-c751-5d18-8f44-8f72389ad472 | note | Check Item - Hold Point 4
7be06de6-0c4e-5eb1-adb6-148dae7dfd66 | note | Reference - MRTS10 Clause 8.1
6806c540-6395-4860-95c8-80cc1458df0b | signoff | HOLD POINT
bd9561f2-39e3-46a4-8091-d40846ce097d | checkpoint | Each supply lots shall be sampled and tested for compliance in accordance with the testing frequencies specify in MRTS05. No material shall be incorporated into the work unless it has demonstrated compliance fully with the requirements of MRTS05 and MRTS10
5bdce606-6d01-54e7-9572-bb8d4f95598d | note | Acceptance Criteria and Frequency (Project Specific) - Written
33d44ad8-1be4-524a-b9cf-aac0639531d0 | note | Check Item - Check Item
1adfa717-df82-555e-9e42-45133dbd74d0 | note | Reference - MRTS05 Clause 7
01bd9516-0327-4100-a7c9-9ef076b0f3e5 | checkpoint | Equipment as specified in approved construction procedure.
4620a0fc-ea14-57ed-a6a5-5d9f26458aa5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c1c12877-ae89-54a5-8470-67f0ed2bea29 | note | Check Item - Check Item
0cc78ff2-506f-5ae2-b385-a062532f8bca | note | Reference - MRTS10 Cl.8.2.1
b82c0a41-4c7c-4b3f-9b13-62f12416092d | checkpoint | The time between the commencement of mixing the stabilisation agent into the unbound material and the completion of compaction of a single layer is less than the allowable working time. The allowable working time for the plant-mixed lightly bound pavement is to be the lesser of the following a) Tested working time shown on the mix desing certificate, b) Four hours
b5f28607-1918-59be-bc40-6b78e745fe26 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ad3284cc-c32b-5a61-ab10-0387ddb4470f | note | Check Item - Check Item
70619f52-1f05-5bc7-920c-e6786b343884 | note | Reference - MRTS10 Clause 8.2.3
1fc81fbe-b61b-4455-a56a-218350877a2b | checkpoint | Lightly bound pavements not constructed when: a) air temperature is less than 10°C or greater than 40°C, b) during rain or when rain is likely to fall during placement, c) evaporation rate due to the combined effect of air temperature, wind and relative humidity may result in excessive drying of the pavement layers
eeef7673-173d-573f-b6dd-cbdf7160fd2c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
25d7c612-986f-5f77-b8a9-6f1fe566661b | note | Check Item - Check Item
ec16d64f-7216-5208-8fa9-986f674b80ce | note | Reference - MRTS10 Clause 8.2.4
26ebacd2-78a2-4e2c-9919-d6e82c8e771d | checkpoint | Individual compacted layer thicknesses in accordance with Table 8.2.7.1. Minimum - 125mm, Maximum - 250mm
cafe8a4f-56f8-5818-beed-72d5f4a6e6a1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d2082d0d-05a2-5d38-b081-d3a5a02aa1c9 | note | Check Item - Check Item
0dd829cc-66a0-5048-a056-f5a693aff962 | note | Reference - MRTS10 Clause 8.2.7.1
7fe40aac-5522-4f81-8cac-f1914d0b15a3 | checkpoint | Where a lightly bound pavement layer is to be overlaid directly with another lightly bound pavement layer, the finished surface is hardcut to uniformly roughen the surface across the full width of the layer.
1f961cf2-99aa-562e-bb1f-0041261c6c05 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5c46c5cc-7403-5b8a-8446-f92183dec77c | note | Check Item - Check Item
5008942d-e439-54e9-8da7-428d05011532 | note | Reference - MRTS10 Clause 8.2.7.2
396dd2da-a2d8-41db-aef0-410717f15603 | checkpoint | Unless constructed in the same shift, a cement slurry is applied to the hard-cut surface prior to placing the next lightly bound pavement layer.
fab63421-aa2a-52ec-bb53-4df6a49eba29 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
64d85476-b9db-54e7-9c4a-84dd86706919 | note | Check Item - Check Item
ee5023d5-25ee-5c90-94f3-1287c05539c1 | note | Reference - MRTS10 Clause 8.2.7.2
bed467a7-2e21-45ff-9ba6-d742d74baad8 | checkpoint | Each layer of lightly bound pavement cover with the next layer or bituminous surfacing within seven days of placement. Lightly bound layers not covered with a sprayed seal or prime within 48 hours of placement.
14edba6c-b377-59c4-9a57-0ff96ebe871b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
58d3f850-85f5-51ba-9397-45e41b44cd05 | note | Check Item - Check Item
69a5a87e-389d-587a-83ba-24843764676e | note | Reference - MRTS10 Clause 8.2.9
8b862865-5b1d-433e-add9-c495dd0aa8e7 | checkpoint | Longitudinal joints offset by a min. 150mm from joints in underlying layers, located away from wheel paths and in the final layer coincide with the lane-marking or change in crossfall. Transverse joints offset by a min. 2.0m from joints in underlying layers.
79c9dd4c-433a-5cfa-ac15-edc83a77f118 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
57cea377-e557-51ef-9a8b-bd4db596c2be | note | Check Item - Check Item
4fa1446a-9b3a-5955-af78-70c8ff7d6f7e | note | Reference - MRTS10 Clause 8.2.10
0e636de1-ad51-42ca-9156-b8754dbe6b18 | checkpoint | For fresh joints between adjoining or adjacent run, the outside 300mm of material from the first run shall be left uncompacted until the adjacent run is ready for compaction.
92fed8fe-9fe1-5b53-8f41-6b202b2c64c7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a9ff54d0-4d45-59d6-be20-ef8c4c4c1036 | note | Check Item - Check Item
1855d947-f424-5f2b-9a3b-481e82b2b171 | note | Reference - MRTS10 Cl. 8.2.10.1
e9ba2a72-5c6e-49db-83f7-42674f060d19 | checkpoint | Joints that are not fresh shall be cut back to form a neat, clean vertical face. Cutback distance shall be a minimum of 150mm and before placing the adjoining layer or adjacent layer, the cut back edge of the existing layer shall have a cement/water slurry at a rate of 2kg/m2. The slurry cement/water ratio to be 0.6 and 0.7.
44fe9629-8809-5b16-b2f5-bce2ffee3fab | note | Acceptance Criteria and Frequency (Project Specific) - Visual
de14e583-598d-50f1-94b7-a52fd857e29b | note | Check Item - Check Item
b6071967-3552-5f93-954e-0c3441d5897d | note | Reference - MRTS10 Cl. 8.2.10.2, Cl.6.4
73530a20-0281-4afd-af10-38efe4c6cb27 | checkpoint | With the exception of vehicles directly involved with curing, compliance testing, sealing operations and construction of overlaying pavements and subsoil/pavement drains, lightly bound layers not opened to traffic until the lost has been tested and passes proff rolling.
3998b2d3-b300-5ab3-9c7e-da91892c1901 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
14a7d297-5a1e-5f8a-aa56-f675869d0cbd | note | Check Item - Check Item
8bbf330a-8df9-5d8f-b7c3-76777ba36a5e | note | Reference - MRTS10 Clause 8.2.11
cf9fbbbc-c00c-405f-9f48-12817e4969e5 | checkpoint | The actual content of stabilising agent for each lot complies with the requirements in Table 8.3.2. Min/Max Value = Target Content +/- MPV (Mixing-Plant-Variability)
9d477b81-2d79-5a7d-a02b-59a99a54c348 | note | Acceptance Criteria and Frequency (Project Specific) - Written
bf6f054a-c7d0-5726-a532-4eec3526651d | note | Check Item - Check Item
6acfeb54-871c-5005-a239-bad6164a6fe0 | note | Reference - MRTS10 Clause 8.3.2
10da3f6d-0990-4f65-9bdd-ff52467eb800 | checkpoint | Unconfined compressive strength between 1 - 2MPa
34a29b7e-32a9-530e-aa7d-ea096120885c | note | Acceptance Criteria and Frequency (Project Specific) - Written
c23e7226-912e-5760-8826-2aa5d6fb552a | note | Check Item - Check Item
a801da86-bb25-59e5-9834-435438bc6e7d | note | Reference - MRTS10 Clause 8.3.3
34565d55-ac11-41eb-bebb-0ef478ed8fdf | checkpoint | The characteristic value of relative compaction shall not be less than 100%, except for the upper most layer of lightly bound base which shall not be less than 102% Compaction testing will be conducted at the 4hrs working time after batching.
a8a8f8e8-d840-572a-ab82-35b058b6ca13 | note | Acceptance Criteria and Frequency (Project Specific) - Written
b080eae0-c528-560f-bc90-58a4e0f10764 | note | Check Item - Check Item
82ebe2fb-aa7a-59c2-ada8-d9b6c4076b29 | note | Reference - MRTS10 Clause 8.3.4
1357c53b-6d07-4906-ad25-5bf32b3eb341 | checkpoint | Horizontal tolerances shall not be more than ± 50mm except for the following: a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm, b) Where alignment of the pavement with an existing structure is necessary
1e993305-c87a-5b31-950b-6ca85ef96845 | note | Acceptance Criteria and Frequency (Project Specific) - Written
967d3fa2-1f0d-5478-9b1d-1105cb4a0d97 | note | Check Item - Check Item
539f5bbe-ba32-5a5a-a149-3b6451b52f42 | note | Reference - MRTS10 Clause 8.3.5.2
ac789c7c-e478-4656-a7ca-20223288161f | checkpoint | The primary tolerance for the Lightly Bound Layer shall be ± 10mm. Further, the total thickness of the constructed Lightly Bound Layer shall be within -20mm, +unspecified of the specified thickness.
7ef1153f-9a43-5909-98da-3a77ffa16697 | note | Acceptance Criteria and Frequency (Project Specific) - Written
7ace5335-812a-5259-8665-628939784054 | note | Check Item - Check Item
a3a0ffa8-a087-5558-b7f6-b28f78c90078 | note | Reference - MRTS10 Clause 8.3.5.3
158d4221-ae01-4911-9312-19de35204ff5 | checkpoint | Deviation of a straight edge placed anywhere on the surface shall not exceed 5mm over 3m
cc403ae5-73dd-54ec-b118-e87fa2f7970f | note | Acceptance Criteria and Frequency (Project Specific) - Written
5dcb88bc-bae1-5ee3-b0cf-078717f259d0 | note | Check Item - Check Item
8d202486-7405-58db-84d6-d335a0a280e6 | note | Reference - MRTS10 Clause 8.3.6
fb68a5ce-f66d-4c3c-952e-c36a25f875a6 | checkpoint | Crossfall shall not differ from the designed crossfall by more than 0.5% absolute.
5412dfda-4235-5a19-8884-25c87ed8d08a | note | Acceptance Criteria and Frequency (Project Specific) - Written
1a1699ce-7c83-5189-820c-42e96a35a48e | note | Check Item - Check Item
43bcfd97-1ca8-5880-951b-59b4a46a9638 | note | Reference - MRTS10 Clause 8.3.5.4
99e36672-bd86-4876-9f13-980c34a6a6e5 | checkpoint | Horizontal tolerances shall not be more than ± 50mm except for the following: a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm, b) Where alignment of the pavement with an existing structure is necessary
d443c4f0-237b-56c2-8de6-a3020060445b | note | Acceptance Criteria and Frequency (Project Specific) - Written
34d09c45-a090-5d4a-b655-693daae04b8d | note | Check Item - Check Item
2c2a7f6b-df7a-53a9-936a-a652ea8c4bf9 | note | Reference - MRTS10 Clause 8.3.5.2
b9ce57a0-e937-4c31-9ca2-ad3d99e7f260 | checkpoint | The Maximum Road Roughness shall not be greater than (Rs) "2.31m/km"
5ee75377-a798-573e-a88d-6cfb2ff06a20 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b6e6679b-c95a-58bf-9c94-08eb72831549 | note | Check Item - Check Item
484bfacb-6e3d-563d-9fa3-54ebd2de6873 | note | Reference - MRTS10.1 Clause 8.3.7
7b2a9d0c-7e91-4ebb-9376-6936a5019272 | checkpoint | For lightly bound layers that are to be covered by a sprayed bituminous surfacing, the maximum ball penetration is less than 3mm
b658def3-cef2-59a6-8398-6ce905233166 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ed3221db-b75b-50ab-a934-f847b83b3042 | note | Check Item - Check Item
4eae329e-692f-5e6b-9180-839ba2438194 | note | Reference - MRTS10 Clause 8.3.8
185381d1-d9df-46b9-b43a-bc62d05d7de0 | checkpoint | The perceptible surface deformation test shall be undertaken in the presence of the Administrator
fb9ae6f6-8c11-5bad-8a5b-b2e3a351e613 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
24a2a232-1bc2-547b-b134-ef7f8acd8c1a | note | Check Item - WITNESS POINT
72a37038-00c6-5eaf-9e44-ed5ebe10959b | note | Reference - MRTS10 Clause 9.4.10
6eaf3117-97e7-497a-a4e0-295bff6a2d7a | checkpoint | No lightly bound layer shall be covered by a subsequent layer of pavement or surfacing untill all testing has been completed, the surface finish comlies with Clause 8.2.7 and the layer presented to the Administrator.
7d550aa2-db22-5f80-88a5-c1479cef587b | note | Acceptance Criteria and Frequency (Project Specific) - Written
11db3e8a-745b-57eb-8b5d-1e58bbff229b | note | Check Item - HOLD POINT
48eea678-b8ff-524b-b70c-e4fd2f235936 | note | Reference - MRTS10 Clause 9.5.1
4ba72d2c-5d0c-45dd-9df0-8fa07466fa56 | signoff | HOLD POINT
3d7a4685-49d1-4a6f-9670-fb1eec84bb7a | checkpoint | For each lightly bound pavement lot, the Contractor shall submit control charts in the ITP appendixc which show the following properties for that lot and all previous lots of the same lightly bound material produced under the Contract: • Liquid limit • Linear shrinkage • UCS • Stabilising agent content, and • Actual moisture content (sampled at plant)
bac240ea-cbe6-565b-b16f-cd79d1065f5b | note | Acceptance Criteria and Frequency (Project Specific) - Written
76d56ca6-09f4-51f9-a7e2-8005ed4c3c85 | note | Check Item - Check Item
198588d0-59e5-53b8-a2df-f32860e82af4 | note | Reference - MRTS10 Clause 9.5.2
fa1988c5-b25e-4b87-a3d1-7cfcb66eb43e | checkpoint | Final Verification
7ceada8e-f1e0-548c-915b-dee45617e65a | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
832b511b-9d99-5ddd-9c48-9335b4863662 | textbox | Print Name:
00b2420f-cd17-5508-a571-267b438d8370 | date | Date:
24d00ae0-e968-5a36-856c-c52c0b35d0ed | note | Project Manager Verify that the Above has been Constructed according to Specification
b0806b10-6477-530f-8518-20471deb4a1a | textbox | Print Name:
3fa6cac3-f56e-5ac0-8ff7-483233918571 | date | Date:
0b5fc44e-2779-4d2d-907a-2f79bf388b76 | signoff | Signature
0a59eb97-cf65-4d95-a576-f1ef0ea31010 | checklist | 11.01 - Sprayed Bituminous Surfacing | itp | 11.01 - Sprayed Bituminous Surfacing
d5647e0e-4f0f-4b93-ad4c-90c86365f9bf | section | Details
c08ac8ef-b2c8-4cb6-8cfd-027f425b7919 | checkpoint | Construction procedures for sprayed bituminous surfacing shall be submitted not less than 7 days prior to commencement of works
b429d5f1-e8ef-54e0-97c4-8493868bb0da | note | Acceptance Criteria and Frequency (Project Specific) - Written
7f155534-5b63-5fa4-9d4b-92ff629c6596 | note | Check Item - HOLD POINT 1, Milestone
c88f1a9f-872b-52c4-834d-34c77bd72d59 | note | Reference - Clause 5.2 MRTS11
92bca366-d609-4b4e-bc84-93b4ed9d6fcf | signoff | HOLD POINT
f39e4ab1-b0a8-421c-a1d7-def9d91a8238 | checkpoint | Seal design - Binder substitution, Ther contractor shall notify the administrator of the binder class substitution not less than 14 days prior to the commencement of spraying
97c958fe-7680-5210-8f86-d8670bbaaf6b | note | Acceptance Criteria and Frequency (Project Specific) - Submitted 14 Days Prior
21e78b37-17f4-55d4-8a98-a54b1b6f249b | note | Check Item - Milestone
be6e1238-2a1b-524f-b23d-73a6aaf90cc2 | note | Reference - MRTS11 Clause 6.1.2
2fa65851-6c83-4158-aba3-694a953efd5b | checkpoint | Seal Design by Contractor - Where the Contractor is nominated to undertake the Seal Design, the Contractor shall inspect each site and shall select inputs and associated design factors. The seal design reports shall include all inputs stipulated in the nominated clause.
14ccfe08-9678-503f-944c-9e48e4220fb9 | note | Acceptance Criteria and Frequency (Project Specific) - Written
15fa3ee8-f867-5bea-9706-35e476ae5fad | note | Check Item - Check item
9bf8506e-64b3-5b4c-91dc-ae0ef53eaf9d | note | Reference - MRTS11 Clause 6.3
68edbd18-3608-4db5-963f-136a8515083a | signoff | HOLD POINT
1a89c537-e9b6-4e75-b250-d3a792a369b5 | checkpoint | Seal Design Report - A seal desin report shall be submited to the Administrator at least 7 days prior to commencing bituminous spraying operations. The Seal Design Report shall include the requirements of Clause 6.3.2 MRTS11. The Administrator shall have 3 days to consider the seal design report and spraying operations shall not commence until release of the hold point
80711dd8-ae75-5040-b5fa-072f6b36b21b | note | Acceptance Criteria and Frequency (Project Specific) - Submitted 7 Days Prior
ec7818c8-0c17-59fa-a213-395314fcdc64 | note | Check Item - MILESTONE/HOLD POINT
4fa2187f-42b7-56cf-bea2-8aed80c9fd76 | note | Reference - MRTS11 Clause 6.3.2
e87641db-ac8b-4e12-b7af-37c58172bf64 | signoff | HOLD POINT
75101ee3-35aa-4b71-9198-05c2987f29b5 | checkpoint | A trial of the manufacturing and laying operations shall be caried out prior to commencement of the work.
3b0cdba9-7e1d-53c3-a245-d9c50eabde32 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c0097594-ed12-5c51-9380-5ede06268f30 | note | Check Item - WITNESS POINT 1
036f2ff1-ea63-52df-ace4-66a752430f9d | note | Reference - MRTS10 Clause 8.1
dd95d93c-dee1-4932-811d-55002970964c | checkpoint | Quarry Registration Certificate - Cover aggregate shall be supplied by a registered quarry comply with TMR Quarry Registration System. Certificate to be sent to the Administrator 7 days before material supply.
4c577798-94d1-524f-9d98-e53e0acca14e | note | Acceptance Criteria and Frequency (Project Specific) - Submitted 7 Days Prior
a57578aa-5368-50af-8c00-b4a6048d32a5 | note | Check Item - Milestone/Hold Point
45cef267-186d-50db-8796-c55759281dbc | note | Reference - MRTS22 Clause 6
165ee230-544c-4bff-b8a1-ba677df27da1 | signoff | HOLD POINT
c5f6a899-f440-4ec6-b159-e4a6d2205fc1 | checkpoint | Cover Aggregate - Cover aggregate shall not be exposed to contaminant agents and to be handle to avoid any contamination / deleterious effects. It shall be protected with a light plastic or similar material to prevent the ingress of moisture and other contaminants.
5338a7f9-4aa3-59cf-a49e-3046ef36fbc5 | note | Acceptance Criteria and Frequency (Project Specific) - Written
edb3db14-dc26-56b7-914d-097904689a83 | note | Check Item - Witness Point
b0e15c52-7ffc-5041-a297-84e16e56a510 | note | Reference - MRTS11 Clause 8.2
a9dde629-b035-4c5e-a776-ac21985b796b | signoff | Witness Point
12d7a5ed-5a6b-4aaf-a2ef-39e1328c6ef1 | checkpoint | Bituminous Material Heating - Strict controls shall be applied to heating of bituminous material and in accordance to Austroads AP-G41Bitumen Sealing Safety Guide, the heating requirements shall strictly be observed.
6842ea85-146f-553b-846a-731590f4a68e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d4a92e63-f9ee-5c8e-b638-f6c9767f2dd3 | note | Check Item - Witness Point
dea616ff-f928-5bd8-b53d-b54dc3a08ae8 | note | Reference - MRTS10 Cl.8.3.2
c244e207-dace-4e24-957f-c7f654519e6d | checkpoint | Precoating Agents - Cover aggregate shall be precoated with one of the nominated approved products listed in Clause 2 of Annexure MRTS22.1 The Contractor shall submit to the Administrator details of the precoating agent procedures 7 days prior commencing
ae725015-0dc7-511f-a544-e642820fd440 | note | Acceptance Criteria and Frequency (Project Specific) - 7 days prior
b1d4f8a5-3254-5f7d-b8e8-4650384cb8b3 | note | Check Item - Milestone
798480b1-a6b7-58cf-a437-e9c60f9c2dec | note | Reference - MRTS22 Clause 7.1.4
228fadd8-5e1d-4993-a813-a610b8b3c0a6 | checkpoint | Plant & Equipment - On site documentation of required plant will be provided no less than 3 days prior to sealing operations and shall satisfied as per Table 9. Additional plant requirements shall apply in accordance of Clause 5 MRTS11.1
c430282d-65bd-5764-aa39-28d940616405 | note | Acceptance Criteria and Frequency (Project Specific) - 3 days prior
cca4976c-8d1b-5c9a-b10b-6c1ccf267f71 | note | Check Item - Hold Point
d0a207bd-5ddd-51d7-a054-39434b5f73ed | note | Reference - MRTS11 Clause 9
dec1d00a-70e9-47f3-9b50-16273842b2d4 | signoff | HOLD POINT
fde76039-a499-4825-a57c-22b289e8d4a3 | checkpoint | Initial Bitumenous Treatments - All foreigh and loose material, including lenses of pavement material shall be removed from the surface. The surface shall be swept with a road broom. Where a Ball Penetration test result exceeds 3.0 mm, the surface shall not be sprayed until approved by Administrator.
9fd45bc8-5701-5a36-a438-721fd455304b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
21ecb39b-b402-5f16-8c39-7b4db52f17d4 | note | Check Item - Hold Point
2fd6399a-af69-50de-b8e4-f38215c7bc67 | note | Reference - MRTS11 Clause 10.1.2
e9e463b4-4a4e-4199-81a9-9a06370e5202 | signoff | HOLD POINT
cc9238b9-e94d-49e1-b702-64f0cb3b7fe3 | checkpoint | Availability of Cover Aggregate - Prior to commencement of bitumen spraying operations, the contractor shall provide the Administrator with evidence there is sufficient cover aggregate for the extent of bitumen spraying work to be undertaken that day.
bd36402f-aae0-5157-9c12-6b31ed439b0d | note | Acceptance Criteria and Frequency (Project Specific) - Written
a0177a40-ae60-5b68-95fe-3312f0970a4d | note | Check Item - Hold Point
6cee6762-01b8-567c-8498-d0bdb2454448 | note | Reference - MRTS11 Clause 11.1
b64e7ec9-f540-40e6-b277-23c9e7bb8e9b | signoff | HOLD POINT
ca30cb9c-edb2-4f90-acff-e659d52e2e8b | checkpoint | Pavement Surface Temperature - Spraying shall not commence until the temperature of the pavement surface is above the temperature given in Clause 6.2 of Annexure MRTS11.1.
553ca393-74da-54c7-b790-2b09be3e8167 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d650104d-7e7f-56b9-807d-e5a3463dfbbc | note | 10℃ for primes
56c90766-0b26-57bd-a186-84f184b73d28 | note | 15℃ for initial seals containing cutback bitumen (i.e AMC4 to AMC7)
fa65b41a-dbb0-5176-bd99-63597db46ace | note | 20℃ for bitumen and polymer modified binders
f4785123-4d16-55dc-bdd6-df524f6bf553 | note | Check Item - Witness Point
b8497a48-7fad-5881-9fdb-a54acfae0438 | note | Reference - MRTS11 Clause 11.2
a1010f0e-36be-4cbc-a29e-c8921effff66 | signoff | Witness Point
c532b8fa-bf41-4202-925d-cffc1bc06896 | checkpoint | Spraying Requirements - Spraying shall not take place during rain of if rain is likely to fall prior to spreading cover aggregate and the completion of rolling. Further, spraying shall not take place during winds of greater than 30km/hr or during dust storms.
d4d13b46-5e3d-5381-a7e9-61876cbb41e9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
34930f5c-4b85-5e28-8566-cb458712c95f | note | Check Item - Check Item
6519be9e-68a2-52e6-a43b-2ccf7c83bd6c | note | Reference - MRTS11 Clause 11.3
88514757-741f-463f-be07-89bbcb3e06c8 | checkpoint | The minimum period of time between bituminous treatments shall be applicable as per the requirements of Clause 11.4 MRTS11
3f10ded7-0d13-5acc-af11-5478bb033ace | note | Acceptance Criteria and Frequency (Project Specific) - Visual
95e70d6a-f814-51a2-ad45-25b87b02e1d0 | note | Check Item - Check Item
d71dab9c-137d-5399-9d1a-93e662c1ca9b | note | Reference - MRTS11 Clause 11.4
845305ca-fc28-47fe-bfa6-0c21141fe51a | checkpoint | The spraybar nozzles used shall be appropriate for each spray run and shall comply with QSC. A copy of the Queensland Sprayer Certificate shall be provided.
802376b4-fa34-5606-b76d-9132395abe03 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
64885289-8b04-5873-951d-e3d6a724b3b5 | note | Check Item - Witness Point
7b863b5b-9069-5d78-b24b-357b5be8e4ac | note | Reference - MRTS11 Cl. 12.4
ce1cef5f-a84a-41f5-8fc6-ee98a78b5273 | signoff | Witness Point
a3f462df-3aea-467f-a968-29d8fb0ae322 | checkpoint | Cutting Back Binder - Incorporation of cutter oil into the binder shall be caried out in accordance with Clause 8.3.3. Prior to each operation, Seal Designer Delegate shall nominate the cutter oil adjustments, which shall be recorded.
3bccdf82-c8d6-57f8-9027-ff1dbf23519c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c014a270-5171-5672-bfac-cd4467af5b6e | note | Check Item - Witness Point
d13361f5-74fb-549a-81a1-d6a44c2a5761 | note | Reference - MRTS11 Cl 12.7
681ba2eb-cc23-43a8-b480-673748b6fa18 | signoff | Witness Point
bdb6a811-bfa5-4d60-bb97-08af4f3245ce | checkpoint | Spreading of Cover Aggregate - Wet cover aggregate containing free surface water shall not be loaded into the aggregate spreader.
69ed54b3-ceec-56cb-b611-fe44f2b427e8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f2e02d98-4d12-59f0-a50b-b64c2154c7df | note | Check Item - Witness Point
7a98c6c9-7e0d-5d20-acc9-d0cae6b2ab49 | note | Reference - MRTS11 Cl 14.1
2403312d-8484-46f7-b12d-3c12006bec10 | signoff | Witness Point
8c7ee463-f143-4c1b-8441-0a6aefff3e69 | checkpoint | Time Limit for Cover Aggregate - Spreading of cover aggregate shall commence as soon as possible with the time limits specified below:
a019a614-299c-56d7-9ce0-84de6282b340 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
57262a1d-ecc5-53a1-ae00-f31adf059e1e | note | primerseals: 15 minutes
62222d36-354b-581c-bfd1-b97e364e8221 | note | Cutback Bitumen, Bitumen and Multigrade Bitumen: 10 minutes, or
39372d3d-417d-5336-a4da-883a4cceab7a | note | polymer modified binders including crumbed rubber binder: 5 minutes
ef4b832d-e0c4-5b8d-82d6-da34ec77ee77 | note | Check Item - Check Item
b5e3eb2d-90d8-5412-86b0-576d6ecdbb9b | note | Reference - MRTS11 Clause 14.3
9428711f-3a60-42f1-9f21-547570b3403e | checkpoint | Early Trafficking Requirements - The requirements of Clause 14.8 shall be complied and the road shall not be opened to traffic until the release of this Hold Point by the Administrator
26d233e4-a6d6-5b04-bb03-8022b0159b60 | note | Acceptance Criteria and Frequency (Project Specific) - Written
2cb0be53-3861-5c14-9a8b-e3a9ee0c080e | note | Check Item - Hold Point
891ea436-9fe7-5347-b095-ff3025b5d4a1 | note | Reference - MRTS11 Cl 14.8
f8af3334-2bb4-4fac-a86b-a9f78ead5056 | signoff | Hold Point
e82784d2-1161-4e99-bcb9-a5a5365dcab4 | checklist | 14.08 - Road Furniture | itp | 14.08 - Road Furniture
52acc3c2-5459-4058-8439-aa385891388d | section | Details
9a7c2676-7504-43aa-b2ca-9ba9d17c845b | checkpoint | Road furniture to be removed are as listed in MRTS14.1.
72c10496-3efe-5eb2-9d82-18b0db15b7e2 | note | Check Item - Check Item
ab70e1f0-82f6-5ad8-838e-bc162d66efb3 | note | Reference - MRTS14.1
500b6474-dd5c-46a7-bc0f-ff2ecd04f449 | checkpoint | Existing road furniture demolished and removed avoiding damage to any adjacent work.
ec4569b1-776f-5d61-87c3-c642caac9482 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6ffc4a5f-51fa-57db-bcb5-a6f9d86029c1 | note | Check Item - Check Item
e520b0fe-6652-50c3-b04f-6f6ad4be1520 | note | Reference - MRTS14 Cl.7.3
e79e3497-04e9-440c-815c-08f959da7bb4 | checkpoint | Resulting excavations are backfilled and finished so the area is in a safe and free-draining state
0f66d0e6-7bd4-5843-a91f-d444cb3a1319 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
30ccab13-69d3-5cf5-bdff-dc0c3f6bc4bd | note | Check Item - Check Item
43fa8252-6f14-52e8-ae44-a42b5ed60561 | note | Reference - MRTS14 Cl.7.3
b222317d-5edf-4374-abdc-c69b466516e9 | checkpoint | Milestone - Dismantling and removal shall not commence until expiration of the seven day period. Hold Point 2
41ee4fe7-efbb-5a2f-b303-8ac56f7622e1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8329f156-87cf-52d1-b511-bd30e3d464af | note | Check Item - Milestone
0cd0193b-52e8-5ebc-9f63-ef8057738d89 | note | Reference - MRTS14 Cl.7.3
6f6f57e2-0662-4026-98d0-dd66574e7efb | checkpoint | The items of road furniture to be removed and re-erected shall be as listed in Clause 4 of Annexure MRTS14.1. Not less than seven days prior to commencement of dismantling and removal of any road existing furniture, the Contractor shall submit a schedule of items of existing road furniture to be dismantled for re-erection in accordance with the provisions of the design documentation.
92ea3c70-c917-5b08-a6dc-4b96742f2006 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ac1078e5-5a84-52be-88d6-1717d0866514 | note | Check Item - Hold Point 2
43324c9c-9372-5d3d-885a-4f4fbc6aa361 | note | Reference - MRTS14 Cl.9
a3905749-04f0-4b32-b71c-7e4de4a32dbf | signoff | HOLD POINT
5249c5e9-5946-42e3-8433-0b1cf31e9a18 | checkpoint | Final Verification
f40b92aa-46aa-59cb-a9ef-994dbb58c09a | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
4cf75d79-ea33-51a0-9459-7289e6936cad | textbox | Print Name:
d0ce47bd-3661-5339-8321-6eef7f12ad34 | date | Date:
474f1a3a-f9fb-5e94-9291-e764754b51be | note | Project Manager Verify that the Above has been Constructed according to Specification
a7e96844-fa7e-557f-87cf-7db97585d19c | textbox | Print Name:
ce80e0f4-c0b2-53cf-8b60-748e8704eb4c | date | Date:
5858fd20-613d-48ac-8048-5e3179011cb1 | signoff | Signature
e3c818ac-28d8-4bc3-80ea-bc5018e07b30 | checklist | 14.11 - Fencing and Gates | itp | 14.11 - Fencing and Gates
2e6daf4a-e407-43d8-800e-ec195c125f9a | section | Details
bb01758c-90d1-4c91-9502-67735ee1ff2e | checkpoint | Material Requirements are as per the design documentation or as shown on Standard Drawings: 1600, 1601, 1602, 1603 and 1604.
b44a65f5-bd40-547e-8d53-9d4346920803 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
99f12d5d-2ed9-568e-9899-ff3bb897dd0e | note | Check Item - Check Item
4e1b86bf-0ed8-57f9-9780-5fe0a0f114e7 | note | Reference - MRTS14.1 CL.11.3
1f2089bc-68b7-4dd5-b9de-bc8b57010e56 | checkpoint | Fencing is constructed in the locations and to the details shown in the design documentation
c763f651-c7b2-5e7f-849b-9623a9aa8b13 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fbd4b63a-b446-5c37-9a9e-65ddb408fd88 | note | Check Item - Check Item
ed757fcd-0342-5828-ae14-19603242cea7 | note | Reference - MRTS14 Cl.11.4
ad4d1fdd-a85f-4c03-b9f5-a7adce1ccecb | checkpoint | Where possible, in undulating country the fencing has been erected so that the post tops follow a smooth line
b27a5e09-1ce4-5895-b818-79370d12ecd8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
037e91ae-6d8b-5ac2-ae2d-4c61a4b713cc | note | Check Item - Check Item
458a1210-46ef-5139-b4f0-2a48370adc13 | note | Reference - MRTS14 Cl.11.4
3b2e0d47-a3a9-482e-b16b-4656557cbb21 | checkpoint | Gates are installed in the locations shown in the design documentation or as shown on Standard Drawings: 1600, 1601, 1602 & 1603.
540786fa-7973-5866-9e46-93480f9a0b18 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b8e02c90-4d16-5a28-8e61-3f68dc069ee6 | note | Check Item - Milestone
98657bab-59c9-5855-9cdb-b137f2ac7f84 | note | Reference - MRTS14 Cl.12.4
52002e47-1309-430f-a9da-4efc3b80c6de | checkpoint | Final Verification
3ff56bb6-08ab-5d4e-9093-be8a298562d9 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
b9f84334-a26c-566e-9625-f66aa9d47f6f | textbox | Print Name:
85087746-2bcc-591f-81a0-a39954e1ae8d | date | Date:
a9bfb289-3096-54ee-a3a6-b90623b4595b | note | Project Manager Verify that the Above has been Constructed according to Specification
1ca05c7e-c9dc-5327-8e93-008e4a57ca2e | textbox | Print Name:
5e28e4af-3624-5c95-aa5f-7461b1723b4f | date | Date:
97ec299e-f0b1-44a4-a796-105a96cc1e0b | signoff | Signature
7227dd46-be3e-4533-9b09-2db219fff263 | checklist | 14.13 - Supply and Installation of Road Signs | itp | 14.13 - Supply and Installation of Road Signs
89f6e6b6-6b5f-4aac-9b88-727b5b311fe6 | section | Details
f6a3abef-f5bf-49c1-9ae1-de54df229088 | checkpoint | Dismantling of items to be salvaged
adb55ecb-279e-5949-8b8a-20f01ce81814 | note | Acceptance Criteria and Frequency (Project Specific) - Submission Schedule
dd5c2728-88cc-5591-abcc-05fc08f1d61c | note | Check Item - Hold Point 1
672d2ac4-e584-5245-8360-1ddf89441f9a | note | Reference - Cl8.2
6bb42f3c-fee6-499d-b1b2-c279843ffb1f | signoff | HOLD POINT
bc863126-feb5-49e7-90c7-c35d3987ee8e | checkpoint | Dismantling of items to be re-erected
001b31da-3a96-5c84-9ccb-2bcdd7b2a9f8 | note | Acceptance Criteria and Frequency (Project Specific) - Submission Schedule
b8af1307-8c64-5f98-8ae4-24f0e9e18010 | note | Check Item - Hold Point 2
19e599b7-8950-584f-9b0c-c72e6fb92984 | note | Reference - Cl9.2
1adcab3b-2924-4291-9c1f-f2d438153d23 | signoff | HOLD POINT
dbb153ea-941c-464b-b8a5-2f6758dd4a8f | checkpoint | All legend elements, including letters, numerals, symbols, colours and borders in all sign faces conform to the MUTCD and project drawings
c7e94163-4f02-570d-91c7-914296d1d38c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a392e520-12ca-5919-8331-9c24f9c6052b | note | Check Item - Check Item
08c52c5f-d96c-539e-ac35-c1959e6e3bf3 | note | Reference - MRTS14 CL 13.2
024a93b5-1ae9-479d-a9eb-536ce2b45728 | checkpoint | Dimensional Tolerances conform to the requirements detailed in AS1743 and legends and lettering conforms to AS1744
b036c918-f1dc-5777-a602-d0417fa6b113 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cdfe1dc3-8850-5bd0-8505-2e0d3416f771 | note | Check Item - Check Item
07dc8dfb-d424-5eb4-80df-460ddb27e336 | note | Reference - MRTS14 CL 13.2
ff083e48-45ec-4a3e-97d8-16bbeddb9555 | checkpoint | Other materials may be considered but evidence of the full approvalof the department will be provided to the administrator prior to their use.
24bc8d57-eef0-51a1-bfa5-74660955446e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
262b3792-87a5-5b57-876f-fe0fa1f2ee9c | note | Check Item - Hold Point
bddd6b31-e4fb-5d14-a1f9-10b7180a4dea | note | Reference - MRTS14 CL 13.3.1.1
9be13392-e873-4eae-a5c4-3783d863726f | signoff | HOLD POINT
4d6b318e-72a1-467b-8b2d-98750c4a4336 | checkpoint | Sign Material conforms with the requirements as set out in Cl 13.3
02007814-73b9-51ab-8e24-1ba89fee2123 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
92623894-121b-5673-8bd0-f9cde91d4947 | note | Check Item - Check Item
f12acfd1-cc95-5505-9b89-0453eb2a5c3d | note | Reference - MRTS14 Cl 13.3
7adc6804-c6e0-41f5-a6fa-958794c3e22d | checkpoint | Sign faces are fabricated in accordance with the requirements of the Design Guide for Road signs to the size specified in the contract
48bec370-3f53-5284-8a4d-36a06b935bb6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bce4066a-89d9-5aae-ad06-0cae6ceebfa0 | note | Check Item - Check Item
5029059d-c828-52b3-9699-3502a59c3d9d | note | Reference - MRTS14 Cl 13.4
ea1e2c65-4445-4fa8-b3f7-5367fa3a4996 | checkpoint | Sign posts shall be circular or rectangular hollow sections unless specifically shown otherwise in the design documentation.
8df83fe8-f39b-5254-b540-599949db9392 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
60d8fd72-56b9-5a70-8a6a-65483726a192 | note | Check Item - Check Item
44e0f4a4-b54a-5aec-bfb1-ce2d24df291f | note | Reference - MRTS14 Cl 14.2.3
4d04895d-a133-43c3-92bb-dfce1b560ba2 | checkpoint | Post sizes and spacings shall conform to the design documentation with slip bases and fuse plates as required
0a8c0a56-25dd-5065-8ced-f7e8c422774c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1b2c3682-44f4-517c-83bb-0dcf16aad888 | note | Check Item - Check Item
60fb6f59-fc9c-5fca-b748-b9143eaad957 | note | Reference - MRTS14 Cl 14.2.3
bc98ee4d-2b57-4b78-ae56-68c629c23440 | checkpoint | Concrete footings shall conform to MRTS70 and to the dimenesions shown in the design documentation.
105a059f-67ed-542d-9b97-7a84a9b91997 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f3479f7e-5b38-50fa-aa83-37abcffeefea | note | Check Item - Check Item
3fa80d48-c2e5-52e8-883a-9ea145e1d6f4 | note | Reference - MRTS14 Cl 14.3
787f5594-8d62-477b-9126-d7a9fbf72a33 | checkpoint | Erection of Road Signs
21e38ed5-24bb-53ea-a0ac-94b9d2b3bcc3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
791f2c9c-d4ac-5da0-82bb-1a9ebe166712 | note | Check Item - Witness Point
7e221424-b643-5cab-8958-b4ad52c8b780 | note | Reference - MRTS14 Cl 14.4
f16f610c-b9ef-49df-bfd3-34022be35f49 | checkpoint | Signs erected at the locations shown in the design documentation and the orientation shall be in accrodance with the MUTCD
ab46311a-ca7d-57a3-b8e1-60e9585a980b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
df50c5b0-86c2-5b2a-943e-ab958589973b | note | Check Item - Check Item
910b6db0-66cf-5a0b-931a-d3785b374f68 | note | Reference - MRTS14 Cl 14.4.2
5458ee60-01cf-48cb-8e2c-9f6d2757581f | checkpoint | Sign faces installed on the posts and/or frame once all other erection is complete
594b47b7-7c79-5506-83a6-cc349bc1172e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3b13a533-8e86-5a84-9790-e40c10083b91 | note | Check Item - Check Item
3dc41b4a-2bf8-5d8c-8d0b-8f5c4b016170 | note | Reference - MRTS14 Cl14.4.5
e752048b-a4d5-4cd8-a567-7a3b50e093fa | checkpoint | Final Verification
da0f9f63-ddf7-5c46-a50c-021261837a83 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
a4bf7ddb-2473-5782-ab3f-9b5065875c28 | textbox | Print Name:
726fbe50-6882-5c27-b0cc-22a9d6d0f275 | date | Date:
eac6ef37-a25c-5ecd-a333-c375072a51ed | note | Project Manager Verify that the Above has been Constructed according to Specification
a41bb73e-7e9c-5ec9-babe-cc876c7074b3 | textbox | Print Name:
309ce4fc-9c11-5b99-aecc-203518ff481e | date | Date:
59574f10-5f60-44f8-9c92-8659f493bd17 | signoff | Signature
cde808f3-a39e-43f4-8431-592c6d4b9fb5 | checklist | 14.21 - Installation of Steel Beam Guardrail and End Treatment | itp | 14.21 - Installation of Steel Beam Guardrail and End Treatment
f66b309c-2168-463c-a864-2a94dbce124e | section | Details
f142a964-f054-44d7-9141-c2ff1510b53f | checkpoint | Proprietary road safety barrier systems and/or end treatment shall be manufactured, fabricated and assembled in accordance with the design and specifications provided by the system and/or device designer.
0602477d-1c2d-5a13-ac5e-720a44684ca6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8f14f92b-2b80-584d-85e2-2c9b93dbbd34 | note | Check Item - Check Item
79bd266f-3ed0-5354-b0e6-c0325ab4b687 | note | Reference - MRTS14 Cl21.2
29d34f9d-1db9-429b-b4ab-fca0947a210a | checkpoint | The installer of proprietary road safety systems shall provide the required quality documentation in accordance with clause 21.2 to the Administrator.
4bd2a8c7-4a21-597f-810d-f5f1948a70b3 | note | Acceptance Criteria & Frequency (Project Specific) - Written
2a2afb92-c764-5a97-96bd-de3b682a6cc1 | note | Check Item - Hold Point
69b9f43f-b846-5952-8f3e-41bcb49ea308 | note | Reference - MRTS14 Cl21.2
59f58f31-386c-4543-b15d-a0bc4af4472e | checkpoint | Proprietary barrier systems shall be installed as shown in and required by the design documentation and in accordance with the requirements of the installation manual.
54b58da7-70ea-5978-812f-3c1018d96319 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4d03e66e-0da3-5d9a-8712-0dbfd65f5050 | note | Check Item - Check Item
7912e6f7-c3f1-5063-be47-56cf14b534cb | note | Reference - MRTS14 Cl. 21.4.1
223e499b-0b67-4f69-97b6-c87782c80226 | checkpoint | Where the design of the system is provided by the Contractor, the design, installation drawings, specifications and evidence and conditions of acceptance for use on state-controlled roads in Queensland shall be provided to the Administrator prior to commencement of installation.
2ebdbfd3-03aa-51dd-9654-3bc18ce08bdd | note | Acceptance Criteria & Frequency (Project Specific) - Written
c11130e6-f9b2-5bec-b9a1-b27c80110a7f | note | Check Item - Hold Point 12
59932b10-72b9-5312-96d4-a203e9be6a13 | note | Reference - MRTS14 Cl. 21.4.1
9f75de4b-9739-47e4-a248-e58f3bdb2c79 | signoff | HOLD POINT
4bb80f65-5135-486a-9972-c03229409066 | checkpoint | Delineation shall conform to the requirements of Clause 10.2.4 of MRTS14 and shall be installed in accordance with Part 2 of the MUTCD.
4261c202-af0c-5840-a7b3-687b1309ccfd | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4cd416f7-df9f-59da-b92b-d421eb984dfe | note | Check Item - Check Item
8e7a8c21-d017-5dbd-8315-9eea8ce3341a | note | Reference - MRTS14 Cl. 21.4.5
6603f795-e5c5-47ba-8083-269cfe50ffd2 | checkpoint | Proprietary systems shall be installed in accordance with the tolerances specified by the supplier. Where not specified, the alignment shall not deviate from the design by more than 20mm and the height shall not deviate by more than 10mm from the design.
864448f4-6498-57ad-8389-d4875007890f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c3635128-9e42-584f-9a65-c81eac7971f0 | note | Check Item - Check Item
c5554b96-5cc0-5170-9693-2cd9cc200058 | note | Reference - MRTS14 Cl. 21.4.6.2
0c17ca6a-bba1-40dc-9031-0ab03435a57c | checkpoint | The quality records of proprietary systems shall include: - Evidence and conditions of acceptance for use on state-controlled roads in Queensland - Supplier's instructions or procedures for the installation and ongoing maintenance and repair - Details of the country of manufacture of all components - Quality documentation showing the supplied components are in accordance with the supplier's specification - A copy of the detailed design (where not provided by the Principal)
60f054c1-5691-5744-997e-2d9627d28f40 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
75e3f95b-ba4d-525e-a852-e0c8229e88b5 | note | Check Item - Check Item
45e37dad-190a-514b-92f4-e01d0065a67e | note | Reference - MRTS14 Cl. 21.4.7
ca603406-aff5-46bb-963e-8a9f6f042efe | checkpoint | Final Verification
56c3366d-a659-537e-8e97-24029d3573e4 | note | Project Manager Verify that the Above has been Constructed according to Specification
3421cf47-db80-51da-8994-dc8c90d47764 | textbox | Print Name:
97bd400d-f653-5af4-a661-f9f92a458eba | date | Date:
c58812c3-22d7-59ec-956c-a316d9b47b70 | note | Client Verify that the Above has been Constructed according to Specification
9fbd2024-fe60-5307-801d-2822382e31cd | textbox | Print Name:
1432c396-5758-5984-be17-20d27623ae13 | date | Date:
f5ac292c-3ddc-4736-ba5e-36c1b30af3d0 | signoff | Sign ITP
ebf9341b-c153-4081-acaf-db37df559234 | checklist | 16.01 - Landscape and Revegetation Works | itp | 16.01 - Landscape and Revegetation Works
857daac9-cef2-4f71-8266-0a9bc1b04139 | section | Details
ef659d39-f2cf-486b-8e6e-7c7ccbbc933d | checkpoint | Soil Management Plan prepared in accordance with Form A of Appendix MRTS16. Construction and regular Updates submitted to the Administrator for approval
619c9136-d1b9-530c-bd35-1f8291d33ffe | note | Acceptance Criteria and Frequency (Project Specific) - Written Acceptance
cd5f9047-53f3-58ac-9afa-f8543b9da72a | note | Check Item - Hold Point 1
e59ab9ce-7ca2-5b6f-abb2-0fd4e4ec8769 | note | Reference - MRTS16 Cl 5.2.1
b056bbd2-4a71-4a65-9aea-fcea2f50b5f0 | signoff | HOLD POINT
d1b5efc7-a618-4b25-8a3f-805a2ba70319 | checkpoint | Non-Potable Water Plan and permits submitted to the Administrator
9fffca0b-33ab-59a0-a2d2-5e66fa158080 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
a500d3ef-ac7c-5951-bdda-a517f038285d | note | Check Item - Hold Point 2
e3f8f12c-8700-5a26-b587-cab9ce5058e2 | note | Reference - MRTS16 Cl 5.2.2
fcccd911-b1e4-456c-a7e9-3cb3e9a82e19 | signoff | HOLD POINT
e1eea601-ec9d-4061-bd61-15e13a48f7fa | checkpoint | Seed Supply Proposal submitted to the Administrator within 30 days of Possession of Site
61f923ec-7572-5efc-aa06-5c379c28e2c1 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
116fcbce-e48e-5526-a8f0-0ae9c9c57b22 | note | Check Item - Hold Point 3
fd7f5b82-d3bb-5c69-989e-1e30c36e88ed | note | Reference - MRTS16 Cl 5.3.1
5ea00576-c823-425d-85d0-67647261eed2 | signoff | HOLD POINT
e7113d07-5835-447e-8d65-86b288053869 | checkpoint | Plant Supply Proposal submitted to the Administrator within 30 days of Possession of Site
1455a844-e8b7-5ada-b5c4-8b0718bb63e0 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
c7887f5f-16fa-57f5-b73e-e2578c135878 | note | Check Item - Hold Point 5
36b3ad02-5579-5113-85ce-28b7b5fc5cae | note | Reference - MRTS16 Cl 5.3.3
17047927-c61c-4a3d-8f6e-b2807c9f74ac | signoff | HOLD POINT
9622567d-5376-4077-98ab-2cb650eb6b4b | checkpoint | Plant Harvesting Proposal submitted to the Administrator prior to harvesting plants
6aa541f9-6145-5d5b-a264-09c0c7be0c3f | note | Acceptance Criteria and Frequency (Project Specific) - Plan
7c914a68-9da5-5a14-9fed-a2314f94f8d3 | note | Check Item - Hold Point 6
e3cc705f-79a8-5c60-9d47-0c3507cc33bf | note | Reference - MRTS16 Cl 5.3.4
70615e9a-4777-4d57-8987-3f7fd02d6b5d | signoff | HOLD POINT
311dfea7-feae-45b9-92e0-1099afa30560 | checkpoint | Materials imported to Site shall be free of prohibited or restricted biosecurity matter
b2be25ed-1463-5599-afe5-04887ef0517d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
630de01d-9037-5b6a-b366-32fd39d0ad67 | note | Check Item - Check Item
bad3b87d-ab0e-5d92-9e9f-4282c620bc21 | note | Reference - MRTS16 Cl 7
3a778011-4115-449d-8e0e-798af608807a | checkpoint | Materials are stored to ensure no deterioration or contamination occurs
78dd6eeb-c3ae-57e5-9645-0a6d69c9b8ba | note | Acceptance Criteria and Frequency (Project Specific) - Visual
882016ab-c41a-5a8c-aee7-899cfe370e89 | note | Check Item - Check Item
b3815507-b297-5cb2-957a-b0b654ff8bce | note | Reference - MRTS16 Cl 7
5e612c55-c73f-475e-bc41-5aad941c930d | checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
6a39cbcc-9d23-588e-9dfe-7554b8ebc214 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bed6f8c1-96b7-5333-a65e-8914a74f607a | note | Check Item - Check Item
4546e59b-f664-5cbb-90f4-b24aa1535043 | note | Reference - MRTS16 Cl 7
4ccbd21d-7ed2-45c1-bbaa-9dac2e8a8670 | checkpoint | containerised plants and ex ground stock in accordance with MRTS16 Cl. 7.6.2
b4644035-8cd7-5e3d-a5d1-bef2b12f23a1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6a472163-34b6-5602-9cdf-494d0531a01d | note | Check Item - Check Item
a54e341f-914e-5229-80c2-aca5d549cb92 | note | Reference - MRTS16 Cl 7.6.2
64632e50-e8f9-4565-a1a1-a20de6e9c6f4 | checkpoint | The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings
10c72c95-3268-5164-a9c3-88a199f78b35 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8aaea422-32de-5ca4-8b44-8621fc7f4c84 | note | Check Item - Check Item
d932d550-9045-5f8f-8857-2f36451088c8 | note | Reference - MRTS16 Cl 8
6d82f420-3ed5-42a4-9a1a-493ef33b3133 | checkpoint | Ground preparation works carried out within the drip line of retained vegetation, 300mm of paths, kerbs, road furniture or structures and in accordance with TMR Standard Drawings 1644 and 1646
ca679bd8-9178-5153-9a50-906b827b43bc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b6fab82a-3021-561e-80e4-32747bdc5ac1 | note | Check Item - Check Item
5075d6fd-4e1e-56cd-83c8-c8b4fb29a8df | note | Reference - MRTS16 Cl 8.4 TMR SD 1644
8f95c2c7-beb0-48db-8d0b-508fe5c42ee1 | checkpoint | Site is weed free prior to ground preparation operations
c0b6f2af-c761-5a2c-b7a4-4576907efa34 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
95349d99-bf2c-5309-9509-1276a56fae87 | note | Check Item - Witness Point
9202d51a-fc55-5dee-93d2-0409b266539c | note | Reference - MRTS16 Cl 8.3
f4fc01d5-26f3-49a3-8b79-3142c8d89d1c | checkpoint | Administrator notified at least 3 days before each of the following: application and incorporation of amelioration agents, ripping, cultivation, roughening
558f41d1-bdb4-59b1-84b8-8562751bcc35 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d81cefcc-23b9-5bdf-ba70-7750837cc440 | note | Check Item - Witness Point
1fbcdb04-e143-57cf-abd0-cb45e76e0737 | note | Reference - MRTS16 Cl 8.1.1, Cl 8.4.1.1, Cl 8.4.1.2, Cl 8.4.1.3, Cl 8.4.1.4
101e122e-e157-435f-8e06-46f879a91f50 | checkpoint | Stockpiled topsoil is in accordance to Form D - Manufactured Site Topsoil Compliance Testing prior to being used
58e0b657-d7c9-5f28-ae84-ad54508ff535 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8eebbb1d-15a7-5472-b593-a96964030da8 | note | Check Item - Hold Point 7
589f619d-89d1-527e-bead-5bc8b217c453 | note | Reference - MRTS16 Cl 8.2.1
095dbdba-06f7-4379-bde2-bbfcbf5507e1 | signoff | HOLD POINT
7979a40b-725d-4d79-8376-9edec9805e47 | checkpoint | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
b4250c15-a1d1-5533-95c3-7bb85d21bb8e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
791424e2-1b8d-56b3-9ff4-9dce2acb670e | note | Check Item - Hold Point 8
85f9c0d8-b3b4-5070-b412-5f5cde24bc55 | note | Reference - Cl 8.4.1.1
58dfc624-a660-419b-aa3d-cbe6d7cec3f4 | signoff | HOLD POINT
e15cfb6f-5409-450e-80f8-8d588c439444 | checkpoint | The contractor shall submit 1kg samples (plus test certificates) of proposed amelioration agents 4 weeks prior to use for direction as to their suitability.
586263c7-14e0-56e2-a7a2-d7e1bd9cb7c3 | note | Acceptance Criteria and Frequency (Project Specific) - Test Reports, Samples
9107a650-ff91-5416-a204-8f6259ca3f0b | note | Check Item - HOLD POINT
49cccb39-14d3-5e0a-a42d-07229042caa2 | note | Reference - CTS16 Cl. 3.1.6
241f270d-e231-4925-8fbf-df70a0ada0b3 | signoff | HOLD POINT
cb88ae71-73fb-418a-b220-3d19d1e33418 | checkpoint | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
6cfd355b-b21f-5b2a-b4dd-0cdba59319d6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a6bb6ab0-638c-5646-85c2-fc4be94cb4b6 | note | Check Item - Witness Point
9d5b71f6-19a3-572d-9f37-f2e856873a61 | note | Reference - MRTS16 Cl 8.4.2.1
47ad3c95-2216-413c-a162-ec29e9bd8452 | checkpoint | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by spreading fertiliser over the topsoil and raking the surface smooth
ba835fb3-9f7a-5cd2-a2d5-d8d40e7b267e | note | b) to the prepared surface that has been moistened with a solution of water and wetting agent
4c4a0ae4-f3b6-5ade-801a-6b4795297f15 | note | c) on the day turf is delivered to site
21fa4d02-8699-505e-993c-8f9ae1d6801c | note | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
1bc0a827-e3fa-5169-872e-b174b97ce8c1 | note | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
a7e80c1f-a7c2-565d-82ec-f68d8ce19cea | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5ee61eeb-cd29-5b7a-bfbe-a452335cff9a | note | Check Item - Check Item
3269058f-6bc4-5036-9478-04d94996b052 | note | Reference - MRTS16 Cl 8.5.2.
1ec29bf8-2896-4d7f-9dc9-9e649c4efa07 | checkpoint | Hydromulch Seeding installed in accordance with Cl 8.5.1.3, with equipment producing a uniformly applied, homogenous slurry that is applied indirectly, and from at least 2 directions with no watering on the day of installation.
c544538d-67db-5531-9933-9dbc02b60002 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2cb40f42-9a41-509c-906b-9f3ce7ddad94 | note | Check Item - Check Item
5804505c-43a0-5e3f-9a68-a7d1c55b60c6 | note | Reference - MRTS16 Cl 8.5.1.3
5ae4487d-0d21-4b5d-9e26-76c0c8b07cf5 | checkpoint | Single Pass Hydromulch Seeding installed in accordance with Table 8.2.1.4
27129e1b-5195-576c-95f7-c39df24ec506 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
01f7f472-7b9c-5d4c-a869-f0a03af8abec | note | Check Item - Check Item
cc5d765c-4cc5-567e-9ce8-a59cca0709ed | note | Reference - MRTS16 Cl 8.2.1.4
714f499b-65a5-4703-b495-dfe6efca3376 | checkpoint | Fertilisers are broadcast evenly over topsoil in accordance to manufacturer's recommendation and the prepared surface has had a water and a wetting agent applied
90c032e0-3eef-5936-8bbb-23a222798e3f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
01c58120-87d2-57a1-b1c1-4d277cf2136a | note | Check Item - Check Item
f2d1af4b-1d7f-545e-8d21-102a7d4f18dd | note | Reference - MRTS16 Cl 8.5.1.3
32065d2b-e978-4174-97b8-158591fd4911 | checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
6d4fa6b2-67be-5a7a-bc2d-3fa5c07d91cd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
57dc91bb-bc53-5d80-8a09-3f7171237a92 | note | Check Item - Check Item
f37e242d-d01a-5a29-b1bd-185e3ed84183 | note | Reference - MRTS16 Cl 8.5.2
acd2afda-e871-449b-8d5e-c9d1f1c9add9 | checkpoint | Mulching be manufactured in accordance with Clause 8.2.2
8e53722a-b090-5e6f-baa0-565ef0c7ea26 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
54bf2eb9-33c7-52e8-9b1d-a4d7f7a8b298 | note | Check Item - Check Item
5e778126-93a8-5610-9d9a-5d365a46dd48 | note | Reference - MRTS16 Cl 7.6.3.1
bcd620e1-75e8-47ae-93ef-40f2f1ab72a8 | checkpoint | Matting shall be installed in accordance to 8.5.1.7 and according to manufacturers recommendations and in accordance with TMR Standard Drawing 1648.
622f54eb-74c3-567b-bf18-2f93fe9acb4b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4faa3490-70a8-53c9-9b25-191f210a528a | note | Check Item - Check Item
2ec4b71c-6d73-55ba-9468-10b2567ed0ff | note | Reference - MRTS16 Cl 8.5.1.7 TMR SD 1648
a4d545d3-d37d-4b34-8872-902a63aa754d | checkpoint | Plants installed within 5 days of mulch or matting and within 48 hours of delivery with initial watering on the day of installation, as soon as practical after planting and in accordance with Table 8.5.3.1 and 8.5.3.2
11cdd365-01c4-5be7-9f90-6fef32457e5b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0527f9ea-cd49-5d8b-ae59-e7cba81dae53 | note | Check Item - Check Item
09354007-560c-52d5-9a83-950376952862 | note | Reference - MRTS16 Cl 8.5.3.2
2522c063-4058-4f50-a41f-e43f0e07aadb | checkpoint | Administrator notified of plant delivery to allow for inspections
228ffe23-7946-5176-a040-97aba258a04b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c2007e27-4029-511f-a718-e3555bcca29c | note | Check Item - Witness Point
341cf0f4-1262-56eb-8039-e59328b30e38 | note | Reference - MRTS16 Cl 8.5.3.1 & Cl8.5.3.2
de4dc2c8-0e3d-4b47-b42d-9b520442e4f4 | checkpoint | Prior to installing plants, plants shall be set out in accordance with Clause 8.5.3.3 The Contractor shall give two days notice prior to delivery of plants to allow inspection of the plants
670d5c6a-7d24-5c76-9deb-fd769b9b8bea | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bc213491-ce22-52b7-95dd-83fe0183ad54 | note | Check Item - Hold Point 11
42604560-8e35-55b4-bef5-55660326eeaf | note | Reference - MRTS16 Cl 8.5.3.3
30b788c8-83a5-4cc3-99b1-ef4e75c7df7c | signoff | HOLD POINT
ad15cfbf-8c1e-4cff-9dbb-ba9524d3458c | checkpoint | <25L Container Plants installed as per Cl 8.5.3.1 and Table 8.5.3.1 while ≥25L container plants installed as per Cl 8.5.3.2 and Table 8.5.3.2
87af9746-0c1f-51ad-b19d-d8068aa7dd47 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
157726ae-a73f-51f1-bcab-f5b81b4941cc | note | Check Item - Check Item
044b3012-8c7e-519f-94d7-afaeb8070c3e | note | Reference - MRTS16 Cl 8.5.3.2, Cl 8.5.3.1
29672571-1660-461e-baf8-591a75c6b513 | checkpoint | Plant mats installed in accordance with TMR Standard Drawing 1647, type of organic matting shall be as specified in Clause 3.4.3 of the Annexure MRTS16.1
43771664-97f8-5e1d-85e7-abc5cc627f9b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
41f3ceac-a87d-5ebf-9361-ff5db24a089e | note | Check Item - Check Item
1bb89247-cc8e-5624-901f-7ef6adf62c91 | note | Reference - MRTS16 Cl 8.7.6.4 TMR SD 1648
f685cc59-08c7-4bc3-9439-419a18be1aa2 | checkpoint | Stakes and guying shall be in accordance with Table 7.6.5 TMR Standard Drawings 1653 and 1655 while Guying shall be installed with containers ≥200L, ex-ground and transplanted trees and in accordance with TMR SD 1656
3ccfbe60-93af-561e-91e7-dce1bc599ead | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ed65150e-a400-5e02-877a-f890cdf3eb64 | note | Check Item - Check Item
6d17e3f4-3e9d-56dd-a2fa-373e4790a72c | note | Reference - MRTS16 Cl 7.6.5 TMR SD 1653, TMR SD 1655, TMR SD 1656
a1d8edd6-bc31-4a23-887f-20f6f5e94110 | checkpoint | Certificate of commencement of landscape and revegetation works establishment period issued and is a minimum of 90 days
b2394869-5367-5a36-998c-3fe7ba0d6248 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
03883e96-e4c0-5ea3-a917-a2b099ef4e16 | note | Check Item - Milestone
5721b1ef-ce27-539d-8d96-f771955d632e | note | Reference - MRTS16 Cl 9.1
870a91aa-336f-48e8-8182-b28716577deb | checkpoint | The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.1.2
9a56a05f-ece5-5c1d-a91c-2224610056ee | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bf50ef94-5efe-53f3-981a-8f9ee729bb14 | note | Check Item - Check Item
2e3a9f7c-faad-5f7d-8f8f-dc88cbf8cbf4 | note | Reference - MRTS16 Cl 9.1.1
1730c9e4-1374-40ce-9676-314a3cdf4683 | checkpoint | If a plant failure is determine to relate to the species, a substitute species has been proposed and submitted to the administrator for suitability
d7bb3cc1-0f44-5479-9d27-b9d71adb2003 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
05966fd5-109e-58f6-a234-c7b793f62b80 | note | Check Item - Hold Point 10
a9a072b4-7d67-5a0c-9cdd-36c961f23ac8 | note | Reference - MRTS16 Cl 9.1.1.5, Cl 9.2.1.5
b19b25d3-3cdd-4477-8de2-db3451d899b2 | signoff | HOLD POINT
0979cdf3-69b1-4178-b92d-a634545b5d28 | checkpoint | Certificate of commencement of landscape and revegetation works monitoring period issued and is a minimum of 90 days unless otherwise specified in Clause 4.2 of the Annexure MRTS16.1
1e8e2c01-ca89-5f4c-88f8-9ea40b9fe51e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7cff5aae-4c4a-5d82-a8d7-5c30dd5eb9d2 | note | Check Item - Milestone
0f94e70c-ec70-584f-b078-c519bd2eeda5 | note | Reference - MRTS16 Cl 9.2
b7c1ecd9-ebc0-4f6d-97ec-3b61b21266ec | checkpoint | All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1
adc4ae81-32da-5d00-a71b-cfd17a0dfa93 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d7beaafe-837f-57c3-b9b0-ed67bffad9cc | note | Check Item - Check Item
47260382-8325-5cdb-b5f6-811b60fa943e | note | Reference - MRTS16 Cl 9.2.1
488d3d3e-47c8-461a-a636-8e1956a7a363 | checkpoint | Certificate of finalisation of landscape and revegetation works monitoring period issued
9a737d10-595e-5c55-82ba-0bb7e06f843e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5917c38f-8ef8-5899-a562-05ca19bb2990 | note | Check Item - Milestone
e1f5e326-6e80-544c-bdde-86ac5dbca012 | note | Reference - MRTS16 Cl 9.2
d0642156-df1c-4e58-94ce-a63d4d68bed9 | checkpoint | Final Verification
e8f5b393-9859-53e8-b620-49c58fa6f24d | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
ec411baf-60a2-5328-bb11-7847a2b47b6e | textbox | Print Name:
e0260515-6211-58ea-b014-37a86e58e94c | date | Date:
b382f383-6f11-552f-a389-552d92583fff | note | Project Manager Verify that the Above has been Constructed according to Specification
60867466-0afd-56ee-a295-d78546b384d4 | textbox | Print Name:
b26c0ed0-863f-5806-91e4-41b955d640d0 | date | Date:
b8ab4d74-c023-416e-8315-520ec5e46e04 | signoff | Signature
9e605acc-b62a-4f02-be04-424169ad97b6 | checklist | 16.02 - Installation of Turfed Areas | itp | 16.02 - Installation of Turfed Areas
f21d50b7-971d-4821-b48e-e5c2ca989e6a | section | Details
c280152f-fd4e-4b8f-b636-11eefc3aacaa | checkpoint | Installation of Turf Shall Comply with Project specific Requirements listed in MRTS16 Annexure.
85dd8dc9-3c5f-527b-a15f-2cb1560bff8c | note | Acceptance Criteria and Frequency (Project Specific) - Written Acceptance
4244d77f-e3f0-5505-99a4-885b727712be | note | Check Item - Hold Point
f97d01d6-7058-5634-b6de-a916562c4263 | note | Reference - MRTS16.1 Cl 3.3.1
8de319ec-fe77-470d-a045-5254133a24d3 | signoff | HOLD POINT
99cf3904-3e2d-4bf7-9ac5-88488d3a3bc0 | checkpoint | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
30c9ab4d-048c-519e-ad91-927e11057958 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
5077be70-31ba-5af0-a9eb-55c067b13c28 | note | Check Item - Hold Point 8
23605cef-6f15-5348-846c-1f40b1598b5e | note | Reference - MRTS16 Cl 8.5.2 & MRTS16 CL 8.4.1.1
d2ce5754-4d1f-4f7a-859b-1a9ea18203d4 | signoff | HOLD POINT
3b54d9d3-51e7-4f22-984d-39b2c7031cb5 | checkpoint | Topsoil shall be installed within three days from the completion of the subsoil operations. Topsoil shall be spread to the required depth. (75mm)
19032704-e915-51aa-aa77-a5805311c991 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
97b78655-c189-5c09-b19d-e21c43a584ea | note | Check Item - Witness Point 6
a95563d3-c424-52fb-920b-625fb8ca39c3 | note | Reference - MRTS16 Cl 8.5.2
a5693c12-b07c-4b83-8cd0-8897f7cad5e1 | checkpoint | Subsoil operations shall occur immediately after the application of amelioration agents. As per Table 8.5.2
d46a8bfc-7c1d-5d19-b032-f841eb676540 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
b3f146eb-9ed5-5ae5-ab1f-d6f740e1c6b1 | note | Check Item - Witness Point 3,4, or 5
772089c2-5893-5569-900d-b255e62c274e | note | Reference - MRTS16 Cl 5.3.3
7fb71a3a-15e3-4706-8119-f77f62605279 | checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
f13db80f-06ea-521e-8302-0f9b1f3d48df | note | Acceptance Criteria and Frequency (Project Specific) - Visual
28108e32-da74-579c-b5eb-c5e703ffb6e9 | note | Check Item - Check Item
deffee25-105e-5a30-a1c5-b71cec704a1f | note | Reference - MRTS16 Cl 7
c4517d9c-a34e-4f51-9538-828c511e8b88 | checkpoint | Stockpiled topsoil is in accordance to Form D - Manufactured Site Topsoil Compliance Testing prior to being used
f35589d4-7b5d-5dfb-b81c-615f063d887c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
56ca1609-dad3-5c42-b96d-57137453f009 | note | Check Item - Hold Point 7
ec7f5b3f-d2a4-50b7-90a4-4e5cbbb4e0e4 | note | Reference - MRTS16 Cl 8.2.1
e71b424d-c606-46d0-985e-c732dce2d1ec | signoff | HOLD POINT
da8e743d-91e5-4aaa-ab4f-4cf5ff162c9f | checkpoint | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
26c7090e-372f-5ca7-b165-551d083c82d2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
997c1086-09bb-58fd-8a08-7be20832bd6f | note | Check Item - Witness Point
23110c6a-b9e7-5f16-ae9e-d5fdc9a00706 | note | Reference - MRTS16 Cl 8.4.2.1
7abe6cb3-5f3c-486a-b1ee-97091714e3e2 | checkpoint | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by spreading fertiliser over the topsoil and raking the surface smooth
87ef3d15-139e-5666-8c8c-c65ed42e5064 | note | b) to the prepared surface that has been moistened with a solution of water and wetting agent
0609a339-0f58-53fa-91d3-7c064d0b39ce | note | c) on the day turf is delivered to site
2ef5c86b-9813-534c-b44a-18ef745ac8ca | note | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
25779142-2c54-52a3-8a8f-f5a5fecbb63b | note | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
ed199df2-98db-50bf-82bb-31048e949a4f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
62cfabeb-5acf-5bf1-ac07-939a9ed9cbe3 | note | Check Item - Check Item
30f290a1-be16-5ae6-bb2b-12532523b547 | note | Reference - MRTS16 Cl 8.5.2.
cfca9699-7dc2-4f17-aebd-2e1f9133f2e2 | checkpoint | Subsoil Testing Requirements Completed as per requirements of Form D & Form E
20cefb40-76e5-5371-9060-fa74ee0d47f3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8775dc45-d149-500e-869b-ab310def4c6f | note | Check Item - Check Item
b9774671-6631-5985-a194-ff7740bab04a | note | Reference - MRTS16 CL 4.1
c675cf93-6b48-46c9-bd81-d481fbad343d | checkpoint | Hydromulch Seeding installed in accordance with Cl 8.5.1.3, with equipment producing a uniformly applied, homogenous slurry that is applied indirectly, and from at least 2 directions with no watering on the day of installation.
957873e3-2bc2-5ef1-844b-2c8d0cab6673 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
61f20b36-0259-58d0-b950-a2d1f8adcd6b | note | Check Item - Check Item
64101707-76ad-50a8-aaa7-38a319ecf935 | note | Reference - MRTS16 Cl 8.5.1.3
4154b1a6-d3d9-4a67-b384-8ab04add3076 | checkpoint | Single Pass Hydromulch Seeding installed in accordance with Table 8.2.1.4
5c4d16af-5309-5b3f-afc4-471dca69fa91 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b99614ef-bfbf-532d-9e68-38b3966b1c3f | note | Check Item - Check Item
f90c7a8d-f9e1-5bf6-899d-6a465ab3a821 | note | Reference - MRTS16 Cl 8.2.1.4
d6a254fe-522d-499a-b667-996dd730ac5b | checkpoint | Fertilisers are broadcast evenly over topsoil in accordance to manufacturer's recommendation and the prepared surface has had a water and a wetting agent applied
63bab8cb-0927-5de5-b1fd-b8b9bfbf9620 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ba63d972-8694-5d88-8e21-4ed8cc1f112f | note | Check Item - Check Item
c7e9213e-84c4-56c7-b9dd-52f867eb5927 | note | Reference - MRTS16 Cl 8.5.1.3
8d2d32b2-ad43-48c5-b51a-3cb0e74f5b20 | checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
7f791faf-d8df-58b1-8c3e-c9756a744a00 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0b0e53c2-b097-56be-bf57-e86d32d8445d | note | Check Item - Check Item
42e80521-9eb8-5385-bfd7-c0529086688a | note | Reference - MRTS16 Cl 8.5.2
37335e95-1ce2-44ea-bfa3-d1d170eaf104 | checkpoint | Certificate of commencement of landscape and revegetation works establishment period issued and is a minimum of 90 days
cce62900-e654-5235-8422-b9becbb63a05 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e9c6cf11-5c15-5066-a549-54f878367b54 | note | Check Item - Milestone
58fb58f2-0557-506d-909d-9ddea730697e | note | Reference - MRTS16 Cl 9.1
0902e157-cd76-4451-b049-aacd06b8de4d | checkpoint | Certificate of commencement of landscape and revegetation works monitoring period issued and is a minimum of 90 days unless otherwise specified in Clause 4.2 of the Annexure MRTS16.1
a4415627-1993-5cb7-9b8f-5b2e146ba9f4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5a2dd256-c485-54a6-a223-74714c6620fd | note | Check Item - Milestone
84e17a1e-9226-5fbd-8b9d-f513bcc9b3e6 | note | Reference - MRTS16 Cl 9.2
08e38290-e581-443c-bebf-b7febfff2ae1 | checkpoint | Final Verification
8a583262-d4e9-514a-a8b9-2796c6ab8817 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
42b8d66f-ffa3-5b93-919e-1fc8f7c36c48 | textbox | Print Name:
7ad4b78c-fcfb-5650-ae05-1edd40c703a5 | date | Date:
06f750e9-34e0-5fe6-950e-4791c3e112bd | note | Project Manager Verify that the Above has been Constructed according to Specification
da2ac463-012f-5438-a133-05e6433780ca | textbox | Print Name:
3b1b44ac-1e6b-5a35-a26a-081d20087757 | date | Date:
b94d907d-79e0-4199-9387-d2ad6983f9f3 | signoff | Signature
22e4ead3-235b-4ef7-926c-30efc36d0500 | checklist | 27.01 - Geotextile | itp | 27.01 - Geotextile
49f0b7c7-1644-4be5-92fe-e268d652ae3c | section | Details
7814fe1e-7bc3-43c5-ad92-fcc573bc669d | checkpoint | Geotextile strength and filtration classes as specified on drawings or within MRTS27
3c171b28-2519-55e2-902d-eafd449642ca | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d9acea9b-4c34-53de-93c3-c75d7c4df568 | note | Check Item - Check Item
17f3a7cd-2387-516d-8ab7-5753c02350f8 | note | Reference - MRTS27 Cl6
69d7430d-e4b4-42fb-a1d4-e98635912789 | checkpoint | Geotextile stored on site under protective covers, off the ground and in a manner unaffected by heat. Rolls clearly marked with manufacturer, type and batch.
3c0c0e63-6270-5d2b-a835-538c469e5d17 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ba8d7be6-a06c-5711-a995-75c96b1aa9d9 | note | Check Item - Check Item
f6acc799-8316-552d-bb25-069d21bdc1af | note | Reference - MRTS27 Cl7
7bdedd8a-600d-4649-b402-e6f7fcedc2e3 | checkpoint | Proposed Geotextile submitted to and accepted by Adminstrator for acceptability to Cl6.
d360320b-eca2-5fc5-9cea-cd8788a5fd95 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f9a02fbb-ca4a-5f97-97ad-8e2d8910653b | note | Check Item - Hold Point 1
31d76ecc-d0d5-5bec-907b-a9492aa4ea63 | note | Reference - MRTS27 Cl8.1
6b20fba5-5013-485c-8958-627d5b481891 | signoff | HOLD POINT
6cdd3be4-335d-4a83-8909-06ffbb839dea | checkpoint | Geotextiles installed as specified in the contract
d1bb1379-b9b4-538e-b09c-13ce04f115e7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
cf3cd015-624f-54f3-84c2-b89463cd09a5 | note | Check Item - Check Item
ac0ce6a3-74d1-5782-881b-2a9b747efecf | note | Reference - MRTS27 Cl9.1
886c2503-7196-4566-a44b-f32b7f7204f7 | checkpoint | Area cleared and graded with all sharp objects and large stones removed and covered within 48hours of being placed
7d762e63-331f-52bc-80bd-2a0acc4271c0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
016298f5-8135-5a44-8b38-6b11592d62ff | note | Check Item - Check Item
aec6e1d8-5c9f-5c2e-852b-a9b257641562 | note | Reference - MRTS27 Cl9.1
ba7f46ae-7fc3-4ae4-9a4d-b109b99299e1 | checkpoint | Initial uncompacted layer thickness for fill material placed over the geotextile shall be not less than 200mm of D85 of the fill material, whichever is greater.
7c2d3610-adb4-5a6a-9483-f8b1136170f8 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4835d9f3-9e0d-5517-a790-5770e0d57563 | note | Check Item - Check Item
669f7ff6-3d97-5e8d-b456-698511f3f24d | note | Reference - MRTS27 Cl9.2
6ecd78d2-d1e4-4846-80dd-89746690e6bd | checkpoint | Jointing of geotextiles in accordance with clause 9.3. If overlap is not specified, it shall be a minimum of 500mm. If used to line subsoil drainage trenches, the geotextile shall fully envelop the drainage material with a minimum 300mm overlap at the top of the trench.
a27c41a0-49ed-5922-866c-c097b59334a1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3c075019-7f45-5c4e-93e4-63191c287602 | note | Check Item - Check Item
706da57a-305c-55e7-a178-eef55bdb39c2 | note | Reference - MRTS27 Cl9.3
5cf7d684-b3c6-493d-a538-85187ff19c38 | checkpoint | Filling over installed geotextile shall be in accordance with clause 9.4. No construction equipment shall stand or travel directly on the laid geotextile. Rock placed directly on geotextile shall be placed with a drop height not exceeding 1.5m.
b4213715-1e2f-52bf-9bac-9183763db510 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7b23377d-e044-54a5-949c-06f3dc4a7e78 | note | Check Item - Check Item
b7399fa4-48de-5de1-9e45-0917fe646211 | note | Reference - MRTS27 Cl9.4
bd2c6f70-6d4c-4069-878a-3d0131fec9df | checkpoint | Where batch size is <5000m2, sampling and testing need not be undertaken, provided the nominal strength of the material supplied is 20% higher than the requirements and the filtration properties are 20% lower than the requirements stated.
e7e52cd3-7c34-5f1b-8566-c254649c787f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e6c5ecc4-258f-5eba-9135-3387943b3063 | note | Check Item - Check Item
08097c91-d313-54ee-b32f-3fe5ddc3d593 | note | Reference - MRTS27 Cl10.2
50a4df6f-554a-4b8d-b71e-54022c7b1c42 | checkpoint | Where directed, a testing sample shall be cut and provided to the administrator
23aa9e5f-b1f2-51c7-b7e2-2e5096caf905 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e86c2d49-6158-5c6f-ba29-4c0a6de79bd3 | note | Check Item - Witness Point
e194c3cd-e202-572e-b19e-da9a59418e9e | note | Reference - MRTS27 Cl10.2
08fec3c4-22a2-4ac2-8b04-676c178d7c74 | checkpoint | Sampled geotextile shall be tested by the Contractor for the range of properties specified in Table 6.2 and Table 6.3 in accordance with the requirements of Clause 10.3.
e6475532-e585-51e6-ae25-cbc21a772cc4 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ea8eba36-bd68-5af3-a64e-0d46f687f77f | note | Check Item - Check Item
c99d6cd6-1ba4-53cf-8a5f-e6fee5d829d5 | note | Reference - MRTS27 Cl10.3
652c68a2-3486-4648-9eb9-8fd5d0c98b8f | checkpoint | Geotextile not placed until administrator accepts test results
7e7f45bf-cf7e-541f-92e8-1618f938289b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1699d47c-7f73-5ca7-acae-ad7d14c7b1aa | note | Check Item - Hold Point 2
a42b4d1a-f9f1-5b3e-b495-024e7c9e516b | note | Reference - MRTS27 Cl10.4
bce99035-012b-4a1d-9149-6ac36c2555b4 | signoff | HOLD POINT
3cd07878-f974-440d-bec8-b8e8c1ba2a10 | checkpoint | The administrator may select samples from the site for audit testing.
df61b610-0371-5256-8e75-42c2e1b7ba79 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1329fb77-2ae8-500a-b581-848dc0823d70 | note | Check Item - Check Item
9a049918-ea0d-53e9-83b3-56344bdcbf2a | note | Reference - MRTS27 Cl10.5
57d89801-96ba-4937-802e-200de23ec18c | checkpoint | Final Verification
396832d4-c921-5944-9618-3d0bd204d98c | note | Project Manager Verify that the Above has been Constructed according to Specification
9f3e88aa-c7f0-539c-82f9-9258a8d03a1b | textbox | Print Name:
da416904-5215-5a32-9a4a-4a3d3bf9a5f6 | date | Date:
b6316505-743f-5c7d-bccf-90a23423581a | note | Client Verify that the Above has been Constructed according to Specification
69941ccc-8cb7-53a7-a929-79f313d1f32a | textbox | Print Name:
9417a060-9882-5ad8-8c9e-1fa3d8ea4720 | date | Date:
6cb94084-9f18-4ad0-a38c-9dd21cbb2dc1 | signoff | Sign ITP
a16c3172-0500-4cd8-8fd1-f0b576701e93 | checklist | 28.01 - Contractor's Camp and Site Facilities | itp | 28.01 - Contractor's Camp and Site Facilities
f952a7dc-b99f-449d-9ab9-4cd67411c14b | section | Details
5e9e5fff-8cc4-4665-aa7f-f39550130e0e | checkpoint | Location of facilities within areas given in MRTS 28.1 Cl. 1 or through private arrangements.
eb5f2161-5ed5-59cb-b12b-8437e657c0c5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7e7ee4e5-96e6-520b-9bfe-16a7daff182a | note | Check Item - Check Item
c27a935e-8e10-5a95-ac81-80c3042120e0 | note | Reference - MRTS28 Cl. 4.2
a7d9eeac-3d41-4e54-8e78-3189b107e296 | checkpoint | Properly constructed toilets, rubbish receptacles and wash facilities provided. The Contractor shall supply, equip, service and neatly maintain all necessary buildings, workshops, first aid facilities, parking areas and storage areas for the satisfactory completion of the Work.
62202fb6-9686-58fb-97e8-33a761f75c30 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
73875fb6-ee3f-5021-b0c0-d888310a59d4 | note | Check Item - Check Item
156e04ad-df20-5e0d-ae8b-abf362676150 | note | Reference - MRTS28 Cl. 4.3
2da7e5c4-eac9-48dc-a225-a476b5647f45 | checkpoint | If so stated in Clause 3 of Annexure MRTS28.1, the Contractor shall provide a separate room for the Administrator within the Contractor’s site facilities. The office accommodation is for exclusive use of the Administrator during Work Under the Contract and the size and any amenities required to be provided by the Contractor as stated in the Clause 3 of Annexure MRTS28.1. To encourage collaboration between all parties, the room shall be in the same building with the rest of the Contractor's staff and is to enable private meetings as required between the Administrator and the Principal.
0530d9f8-0e62-581c-bfba-b633aabd4e57 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c68dd7fc-3b61-500f-a64a-8760e316c435 | note | Check Item - Check Item
8a1932d5-ce7a-535d-8bca-989442a3f009 | note | Reference - MRTS28 Cl. 4.4.2
99e3bb8d-56de-41c3-b905-74e16b38acec | checkpoint | Contractors camp complies with all requirements of MRTS52 and included in the E&SC plan.
ed309aa1-2a46-5716-a5f9-de21b8e68e63 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2d984048-35a1-5216-9717-68e4a8b9284a | note | Check Item - Check Item
9f18db1c-f1b4-5a40-8624-b4a642a578f2 | note | Reference - MRTS28 Cl. 4.5.7
d69ffe31-895d-48e6-81ea-4f230f173c77 | checkpoint | Contractors camp complies with all requirements of MRTS28 a with a proposed site facility layout submitted to the administrator.
00c6d659-2f6e-50e7-a7d5-51b1430eaa3b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b3c7a6bd-b681-5321-bc42-5eeb32926c5e | note | Check Item - Check Item
0598f772-8238-5e39-92a5-1266ce919033 | note | Reference - MRTS28 Cl.4.5.1
1957534a-7dd7-4355-9af3-e53615f8f141 | checkpoint | Contractors camp complies with all requirements of MRTS28.1 Annexure
1905db80-a272-5cda-94fc-b843282cf9a6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0a161d60-e784-5dae-b077-9d614746b925 | note | Check Item - Check Item
77968b16-a804-5bde-a040-e4bc47e6f820 | note | Reference - MRTS28.1, C.l 3
112d28b7-d186-4d86-a151-50061975cf8e | checkpoint | Supplementary Requirements completed as per C.L 8.1 & 8.2 & 8.3
c529116f-ba1d-5c56-934b-57650dd45857 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c87eabbb-cd3b-5ef2-945c-2d61a78b0535 | note | Check Item - Check Item
b033ca0c-7fe1-56a5-bc00-2e98bb6f8e22 | note | Reference - MRTS28.1 Cl. 8, Additional Obbligation Documents
4d984593-4bdf-4a01-a4f2-c62c9a4aa2a0 | checkpoint | Final Verification
e8f779b6-d861-5816-85df-8b1fb7e66a7b | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
be275628-41eb-584e-bec4-184931b8d64f | textbox | Print Name:
c814c84f-105c-5b9a-97fd-e09c256d335a | date | Date:
dc29bea7-6e81-55a0-8d93-0deb64362fec | note | Project Manager Verify that the Above has been Constructed according to Specification
ea707607-3bfb-533a-9af8-0fbef1100bd0 | textbox | Print Name:
79a24376-9600-5dba-9b8c-6afcde695570 | date | Date:
cb83a514-1448-4f49-b5b5-b5702dc5525a | signoff | Signature
0b66831f-cfbf-4065-bf85-27110d1c9d39 | checklist | 45.01 - Road Surface Delineation | itp | 45.01 - Road Surface Delineation
8f93f3c6-d6dd-42d0-bc68-c20981cdadd1 | section | Details
3451ad10-7056-4dc3-8282-0c32aafd7ac5 | checkpoint | All material conforms to requirements set out in Clause 6 of MRTS45.
9466ddba-0e71-52c0-97a8-83af3004b01d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3796db5e-c37d-5153-b7d1-5ac7be593570 | note | Check Item - Check Item
845ddbee-3403-5a8c-a106-0b6c24e5a07f | note | Reference - MRTS45 Cl 6
64d104f5-73d8-4d5e-af52-f383be4648be | checkpoint | Installtion of Pavement Markings conforms to requirements set out in Clause 7.
7e4c991f-3fed-5914-ae56-2b0a5c03e30d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
425418a5-82d9-543b-93ec-e0cca2db8585 | note | Check Item - Check Item
9c1e4585-3427-51f1-91d4-69e163069fd6 | note | Reference - MRTS45 Cl 7
56f86d59-cba3-4266-b3d8-7d38414026b3 | checkpoint | Pavement markings not applied when freshly applied pavement markings may become damaged by rain, fog or condensation before they have dried or set.
ee2cdf5c-efe9-5add-9e25-a0649259d143 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
90883f46-9a05-507e-bfb2-390bdc091643 | note | Check Item - Check Item
aa56d38a-af60-586f-8c9e-ff69fb334e59 | note | Reference - MRTS45 Cl 7.2
643147e2-9150-4d88-b702-6c960bddfdde | checkpoint | Pavement surface is thoroughly dry and free from all dirt, loose material and other contaminants immediately before applying the pavement markings
73880a5d-c017-5fd6-b00f-db717f5e3ad3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1c03e2fb-03b1-5b50-9854-38b56305e87a | note | Check Item - Check Item
e2678627-9383-521f-b956-bb0ad6cf9fef | note | Reference - MRTS45 Cl 7.3
df49fcd0-d016-4f08-a1c9-d11fb04e30c2 | checkpoint | In addition to Cl. 7.3, new bitumen sealed surfaces which are to receive pavement markings shall be free of volatile material and solvents.
dd5a92e9-7c59-57f9-82e0-72ee0d61d97a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
45ea1948-0c28-5051-a979-d1bd8a1ce92c | note | Check Item - Hold Point 1
d3296576-4c2f-501e-afce-287d799298c1 | note | Reference - MRTS45 Cl 7.3
dc5d5004-53db-407a-b40e-3b810b633bd2 | signoff | HOLD POINT
f1627a66-14f1-4547-a28b-4734f467b14c | checkpoint | Spotting approved by the Administrator prior to any application of pavement markings
badd3066-72fc-5ca6-8b14-129edaccde9b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
81a8fb77-a4c0-536a-a4b0-7d6dd7a74ccb | note | Check Item - Hold Point 2
c53110cc-1d72-5672-8230-806c3326d84f | note | Reference - MRTS45 Cl 7.4
31b6ec0f-62d9-45d5-a4ba-a67525b477e7 | signoff | HOLD POINT
9f2c1f5a-aa68-475e-a3fd-c9598797b97a | checkpoint | Construction procedure for application of pavement markings submitted to the Administrator
24c193db-1f3a-518a-9c46-ef3e44776ae7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
232e4318-98cb-5fd8-8bef-6b0b1c8bea7a | note | Check Item - Check Item
fafabfcd-fc42-594c-8c7e-fcdab22c3b4f | note | Reference - MRTS45 Cl 7.5
a491f103-c1b3-431d-a81a-f94b594becbe | checkpoint | All Markings are of uniform thickness and intensity
1e6c41e3-fbcc-5891-b4d6-96cff4b28e27 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b22f9377-117f-5841-b7f0-5ebc21c6b43b | note | Check Item - Check Item
54567e4d-3e87-575f-80bd-48095bb2d8aa | note | Reference - MRTS45 Cl 7.5.2.3
03050c03-f36c-42e4-926a-8c35342ea6bc | checkpoint | Waterborne Paint not heated to greater than 65°C and consists of two coats of paint and glass beads with application rates for the paint as per Table 7.5.2.4
398c2063-95ce-5dff-8dad-8b89cd689868 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, Table 7.5.2.4
8ec8f481-bfc9-5845-9257-c1ff9cd2d252 | note | Check Item - Check Item
693cd775-64ff-583d-839c-32c152e02a02 | note | Reference - MRTS45 Cl 7.5.2.3, Cl 7.5.2.4
aa43ddec-db0f-4077-9c82-726c53fafe83 | checkpoint | A primer was placed just prior to thermoplastic materials as per manufacturers specifications
065496ee-db33-52fc-8f40-4653532243a5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4f1a5138-9fcc-5f14-aabc-85b512fcadc9 | note | Check Item - Check Item
33114c19-099e-5f7f-946a-a33894091938 | note | Reference - MRTS45 Cl 7.5.3.1
77ec1f4d-73b5-438f-8b4e-c2350f8fec8a | checkpoint | Thermoplastic shall be applied at a temperature as per the manufacturers specifications
43f70bdf-4969-5ab4-9bf8-3304df5524a7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0a68b7bf-219b-5621-9486-9741f82adde0 | note | Check Item - Check Item
9c1b2d2a-af2c-5e4f-b2d2-f4b8f02699cf | note | Reference - MRTS45 Cl 7.2, Cl 7.5.3.2
b09041f8-0fe5-4fd3-b669-455a882f1090 | checkpoint | Thermoplastic applied at a minimum of 2mm thickness
9ae1a5aa-af58-56e6-ae4d-3e91d0a39a30 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
789973ca-332c-5fad-a916-8a6c407e4e3a | note | Check Item - Check Item
eb9f23a9-8d84-554f-9f4f-a6655c05e534 | note | Reference - MRTS45 Cl 7.5.3.3
44cdb10a-de81-42c0-8d84-a0ef364a3946 | checkpoint | Raised Pavement Markers installed in accordance with Cl 4.6.3 of the MUTCD
a42a603b-9a0c-5dae-993b-552170b6b493 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1f93d4c0-7bb2-59c2-9d3c-788a67444a7c | note | Check Item - Check Item
8f07e6fd-0fcc-5974-b0f7-bf1b07193151 | note | Reference - MRTS45 Cl 7.6
cbd3eac5-c128-49e9-8498-d8c734f1b1d3 | checkpoint | Material complies with luminance and retro-reflectivity requirements
7e750592-99a6-5052-abc2-85c936dfbf63 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
303479d0-16f3-5c8b-9483-c0368ecb6aa6 | note | Check Item - Check Item
a79c92a4-45d3-51da-9478-39f5fa067239 | note | Reference - MRTS45 Cl 7.7.6
303017fe-3597-49df-bf31-9e91d9ff7337 | checkpoint | Material protected from damage by traffic or other causes until paint is dry and thermoplastic has hardened
b2e9f6df-63e5-5f8f-b306-a42724f4c919 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
61e2d6f3-a88e-5c49-bbbd-192d69e05239 | note | Check Item - Check Item
3ddaff33-f76f-5e9b-b3df-5dc0c689ec26 | note | Reference - MRTS45 Cl 7.8
a8124777-391a-452f-89dd-5832666ae1ff | checkpoint | Completed Pavement Markings are uniform, clean and well-defined edges with deformation and conforms to dimensions as set out in the MUTCD
687ea173-08db-546f-8c5b-25f112b0218a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bb5d1d35-34ba-5bff-8200-dcad2c06743f | note | Check Item - Check Item
92548e78-1027-52ab-b254-e7d87d3f64ed | note | Reference - MRTS45 Cl 7.9
906d94d8-e19f-4339-8226-4bf6f8a2e960 | checkpoint | Pavement Markings conform to all tolerances
e7c116b2-9640-576e-a5ff-3f4750cd3149 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
94b74b9f-c69b-52c5-bd58-d344bd12cae3 | note | Check Item - Check Item
dbd724ce-17d3-5aa5-8830-1f1d2bc1ea67 | note | Reference - MRTS45 Cl 7.9
757b99cb-0b0d-421b-b73a-58edfe4a5ce4 | checkpoint | Quality Verification Requirements, Test Method
0a57399b-51a4-5d6d-bb2a-3037fba8558c | note | Acceptance Criteria and Frequency (Project Specific) -
c6c92950-8ad2-51cd-854d-35cbbd32b99c | textbox | Min. Testing Frequency
5116eb4f-e78f-51dd-93c7-b5157a6beedb | textbox | Min. No. of Tests
60fa6336-a512-5c55-970d-aded0e067758 | note | Check Item - MRTS45
982e1503-de11-507b-aaad-7b02e9b0295a | note | Reference - Annexure
4107ce29-adb4-4829-acf8-1523bbceda40 | checkpoint | Materials
0b50d7bd-fc25-5359-a6bd-137f7887faec | note | Acceptance Criteria and Frequency (Project Specific) - 1 per batch, 1 test
67db4d9c-a9e0-5713-a991-3a2fd049b82e | note | Check Item - Check Item
d37c7ec7-0636-5894-8f23-c097588579b2 | note | Reference - MRTS45.1
cd464a7d-4524-4588-b19f-a53bd27c39b6 | checkpoint | Thickness of Pavement markings: Longtitudinal lines, Transverse markings
ee3baa4e-cdb5-5ac2-9698-97fdb94c79b0 | note | Acceptance Criteria and Frequency (Project Specific) - 1 per lot/ 1 test
e7ce5d73-48c1-5d20-b4df-bc63f1b155a3 | note | ○ 1 per lot/ 1 test
7894b63f-ded8-5b50-89e7-f5b4452eca59 | note | Check Item - Check Item
36758c4d-70a5-5e54-a1ca-8ad7741e0248 | note | Reference - MRTS45.1
9c08f019-6120-43fc-859d-8b46f9cc7de5 | checkpoint | Dimensions of Pavement markings: Longtitudinal lines, Transverse markings
95894486-a5ad-5b9c-868e-167efa51ec11 | note | Acceptance Criteria and Frequency (Project Specific) - 1 per 200m/ 1 test
6b004189-beb6-5179-a395-795e3481658c | note | ○ 1 per type/ 1 test
d8bdf163-ac8c-5391-a0bd-eefd0d95e1cc | note | Check Item - Check Item
976aca7c-4555-5c80-961c-9a64e06c6b88 | note | Reference - MRTS45.1
098abdc4-389f-4a30-92f3-518b154623e8 | checkpoint | Dimensions of raised pavement marker placement
14d7dee1-6e8c-5e41-a738-6e2c076b5c87 | note | Acceptance Criteria and Frequency (Project Specific) - 1 per 50 / 1 test
6797e5df-d828-5983-aa51-1d248bef77b2 | note | Check Item - Check Item
a34d76e2-8283-568d-8b8d-7af10cc4932e | note | Reference - MRTS45.1
abd56b30-cf00-4dc4-8a4a-714fcbefe4ad | checkpoint | Retroreflectivity
c2b11651-60b0-5f37-a669-2fc15aa1ba4f | note | Acceptance Criteria and Frequency (Project Specific) - 1 per lot / 1 test
5cb66c7a-95b9-5266-8c42-420c182b6f54 | note | Check Item - Check Item
f5095545-b662-57ff-8905-57a2dc433c40 | note | Reference - MRTS45.1
5bcc1261-2761-4507-8d1d-b61b30c9db7e | checkpoint | Skid Resistance
407e98b3-af00-5f78-9013-207943ba2b3f | note | Acceptance Criteria and Frequency (Project Specific) - 1 per batch / 1 test
121f8b8c-58bf-54c7-ac84-f95721eb2311 | note | Check Item - Check Item
fab2aca9-e721-52a2-a2e5-0240835e7188 | note | Reference - MRTS45.1
7d4a7b9a-e86c-4347-822f-5236d2a4900a | checkpoint | Final Verification
d259064e-7f62-5ae3-b358-4dc3b50e8d04 | note | Project Manager Verify that the Above has been Constructed according to Specification
21f43310-a06f-507b-a8b0-2c75d00bcad2 | textbox | Print Name:
c7f6ee48-fcaf-567a-a32a-ad33ddba89fe | date | Date:
ba1091a5-99e5-511a-bb7a-a7694ea6339b | note | Client Verify that the Above has been Constructed according to Specification
7b93f963-fd15-5c4c-91d6-a5d096c3b3a7 | textbox | Print Name:
8aad0cc6-a7d0-5896-ae5d-5bd1752f440f | date | Date:
8fdb4443-0206-4e55-b9f6-7906cbb359e0 | signoff | Signature
6898fa9e-250d-40b2-91fb-df47f7002489 | checklist | 51.01 - Environmental Management Systems | itp | 51.01 - Environmental Management Systems
aa896dd9-fcdc-435d-9e6c-924868e14ce1 | section | Details
f8dcf9c3-a6fe-4176-84b7-d8e87145636e | checkpoint | Environmental Management Plan (Construction) EMP (C) submitted in accordance with Conditions of Contract.
51c83d72-c10a-50b4-a6cb-a615c570612f | note | Check Item - Milestone
61780373-70b5-5214-9b93-89574d3163c0 | note | Reference - MRTS51 Cl. 6.3
5051a95f-2ae9-4d0a-9e57-f7d470bfabfd | checkpoint | Works under the Contract shall not start until the EMP (C) is assessed for suitability by the Administrator.
0d5ad50d-3acb-50da-9295-b216ca2ad9b8 | note | Check Item - Hold Point 1
da63b070-f5f8-5eb5-924d-f3178151054a | note | Reference - MRTS51 Cl. 6.3
1669c12f-1fd5-4fa6-8ffc-9476cfd48164 | signoff | HOLD POINT
59d0661c-db0e-4c37-be0a-c578af3d0321 | checkpoint | Any amendments to the EMP (C) shall be submitted on a monthly basis and be assessed for suitability by the Administrator.
2c10af80-3b08-5946-a8ee-4029828c5fc3 | note | Check Item - Hold Point 2
a50f45fe-ee9d-5d97-b054-dd4fcefb80d8 | note | Reference - MRTS51 Cl. 6.4
09286340-dc3d-404b-8e48-a4c0d0fff852 | signoff | HOLD POINT
c01a4c21-b07a-48b7-b130-8bf6354a6c61 | checkpoint | Environmental site inspections to be conducted daily against all licences, permits, approvals and other environmental performance requirements. All Inspection to be documented with records being submitted to the Administrator on a Weekly basis.
d61bd5cd-dea6-51c0-9103-d248dada34da | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a9c167dd-21fb-5d0a-8fdb-652511b1cf3e | note | Check Item - Check Item
81c297ae-25df-52aa-8f3a-90d903c9856d | note | Reference - MRTS51 Cl. 7.1
96683c2c-454f-4401-a801-027696b5a92f | checkpoint | The Contractor shall be responsible for the management of the below inline with the requirements outlined within the Additional Obligation Documents and MRTS51.1:
92239298-dfe2-51ff-a63c-0212a315597b | note | ○ Landfill Gas Requirements
8690afac-12f5-5e18-9429-aa25ccc040c3 | note | ○ Contaminated Land Requirements
a6f9b0e0-ef69-51c8-9df8-1ca63921cd33 | note | ○ Water Quality Requirements
e20da56b-9222-517c-837e-b0cb43d41607 | note | ○ Bio Security Requirements
82a15250-e61f-5e8f-a785-39a9b8170a67 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dc68fe37-e22b-54d1-a51e-23986b513fb4 | note | Check Item - Check Item
6140bf28-1f3c-560c-b81c-3f44bc803f19 | note | Reference - Contract Documents
3a836890-da73-4486-98da-43c9f0334c1b | checkpoint | The Contractor shall be responsible for the management of Indigenous and non-Indigenous cultural heritage artefacts, sites and values within the worksite BCC organised Cultural Heritage Training completed and applicable inspection where required
cfe44a0d-6690-59fd-9be5-c6be749de626 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
15aeab28-15a9-5205-88bf-8fcfb201f85c | note | Check Item - Check Item
eb3f7f7d-7591-5caa-9737-91f32f01abb9 | note | Reference - MRTS51 Cl. 8.4.1
885092b4-0495-4ee4-b7b5-f51f01baf3e9 | checkpoint | The contractor shall at all times take measures to assist in minimising noise associated with construction activities so as not to cause environmental nuisance or harm.
271b193f-6a56-561e-9059-20d8f538b39b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
36be3b0d-9ecb-577e-9472-d1f145839b3c | note | Check Item - Check Item
6da166ca-a81c-52b2-bdbf-58628f01020b | note | Reference - MRTS51 Cl. 8.5.2
a7378f41-1c25-4d88-9dca-05e8a83a03d4 | checkpoint | Project records shall include all noise monitoring results if required
9e1ca160-617b-53e9-8f72-70f65d32509b | note | Check Item - Check Item
9f180e3f-df9f-501e-bf24-682cb8925f8c | note | Reference - MRTS51 Cl. 8.6.3
0f924e61-483d-4844-8a0d-72501849780e | checkpoint | Condition survey may need to be conducted prior to commencement of activities as per Annexure MRTS51.1 Cl. 5.5 Copies of condition survey to be forward to Administrator 5 working days before any works that cause vibration start.
c52e4239-e6b2-5156-bdcd-5e582331789f | note | Check Item - Check Item
7cae3398-6c98-5aba-9459-28c9094a7887 | note | Reference - MRTS51 Cl. 8.6.2.3
c9735db2-4717-471c-870b-27c7b433100e | checkpoint | Where identified in Cl. 4.3 of Annexure MRTS51.1 the contractor shall undertake vibration monitoring at vibration sensitive receptors.
1afd0c80-9e5e-53d6-806e-ccb9d72ddaf4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
db51009a-65b7-54ff-875c-5befb0840554 | note | Check Item - Check Item
335f52e7-3559-52b9-beb1-5b2db2496f0d | note | Reference - MRTS51.1 Cl. 8.6.1
42de2680-891c-480a-b9b9-f6d8113a12b5 | checkpoint | Project records that show compliance with the VMP and shall include all noise monitoring results (if required)
d83db729-c2a1-570f-9bdc-051f8a90d386 | note | Check Item - Check Item
b3fec6f3-e9ad-5bf0-9514-625134ab0827 | note | Reference - MRTS51.1 Cl. 8.6.2
829d5b10-c98b-43d5-9360-abbf33ae74dc | checkpoint | The contractor shall ensure that construction activities do not result in air quality impacts that cause environmental nuisance or harm. Burning of material shall not be permitted
2e49da29-e190-5b89-b30e-77e6aa1f0a49 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1fa1622f-4ae8-59b7-bedc-7c0a8e4bb226 | note | Check Item - Check Item
8abb38d5-165c-5d7c-aaf0-46e6651c861a | note | Reference - MRTS51 Cl. 8.7.3
88501032-1e91-42ff-93b8-bb0db42686c8 | checkpoint | The contractor shall be responsible for the management of acid Sulphate Soils and shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
e39168b0-9649-5daf-9444-b66162a51921 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d48a4e7b-c2a0-5f07-80a7-7a7255451dcb | note | Check Item - Check Item
41b64e8e-4a1e-50c0-a640-d3569ee9effe | note | Reference - MRTS51 Cl. 8.8
ddd75a0e-cbdc-477c-a157-5d7410f980dd | checkpoint | The contractor shall be responsible for the management of contaminated sites ( contaminated soils, waste dumps, unexploded ordinances ) within the worksite . The contractor shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
795a0c67-5359-582c-8e64-0674251f7748 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
aa10e0eb-e0a7-5672-b474-c329b9d4f8e5 | note | Check Item - Check Item
3ff1b63b-f34e-5e90-b035-b5ab8d572041 | note | Reference - MRTS51 Cl. 8.9.1
a778fdc4-db6b-4897-809d-f917b6ae8614 | checkpoint | The contractor shall take all due care to not harm native fauna. Areas of significance and related management requirements are stated in Cl. 7 of Annexure MRTS51.1. Contact details for emergency wildlife care shall be included on project emergency contact list. Carry out Dawn and Dusk Frog Calling prior to Clearing works and other requirement Frog management where required inline with additional obligation documents
b97f9ad8-381c-5dcc-bbf1-0b7c198499ed | note | Acceptance Criteria and Frequency (Project Specific) - Visual
880ca0ac-4b14-56ff-99ff-6975b1451f8f | note | Check Item - Check Item
46f9a798-9eca-575f-a017-106a22e9bc19 | note | Reference - MRTS51 Cl. 8.10.1
d2b71e09-326d-44a8-9b05-c6e3ebc6c739 | checkpoint | A pre-clearing and post clearing report must be provided by the koala spotter.
6130987a-063a-5877-a87a-d158739d9693 | note | Check Item - Check Item
847fef69-54fb-5f76-8e74-890595d4e9ae | note | Reference - MRTS51.1 Cl. 8.10.3
b428cf52-9d24-4006-9476-38322f16c7e2 | checkpoint | The contractor shall be responsible for the management of vegetation within the worksite. The daily site inspections shall include visual assessments of vegetation management measures.
efd9deed-2131-5e30-baae-99567cb539b5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
444064ee-5ec7-5e73-a949-0f05f803529c | note | Check Item - Check Item
c11164ae-f5cc-5269-acc8-7dee253c85e7 | note | Reference - MRTS51 Cl. 8.11.1
4ba36584-62a1-479f-846c-782735dcc0ec | checkpoint | All declared pest known to occur within the worksite and associated management requirements are stated in Cl. 9.1 of Annexure MRTS51.1.The contractor shall manage all declared pests (Animals and Plants ) within the worksite by preventing their spread on and off site
a708b7d0-9a62-5b0e-b5d6-839830baa20f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7f217401-a25b-548a-912a-6b2e8d5cba70 | note | Check Item - Check Item
f54e0914-d591-538f-9b4c-b434708bc7cf | note | Reference - MRTS51 Cl. 8.12.2
f2e7a350-18fe-4d6f-aab4-c3679cfab78f | checkpoint | No waste or litter shall be burnt on site. No waste or litter shall be buried on site unless approved by the Administrator and the administering authority.
bdc377de-e604-5836-9b2f-25d665eeafa3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7694d8d9-a362-5517-a7f3-e41cedba7e52 | note | Check Item - Check Item
bc82baf3-2d02-5390-86fa-18b82324904d | note | Reference - MRTS51 Cl. 8.13.2
687b29dd-f2d4-459b-a783-037668419da2 | checkpoint | Fire Ant Inspection Carried out with TMR prior to works commencing. Certificates for applicable imported Items where required.
d4dc401b-9480-5800-a1fe-6702e09edbdd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b05d5922-109c-5ab2-af1c-ad13a8451fa6 | note | Check Item - Check Item
8960e94f-1a28-5a6a-a97e-3fe9c6c9c31c | note | Reference - BCC Supplied Certificate
a2dc6cf8-9157-43d5-94b3-113996fa803a | checkpoint | Monthly reporting requirements up-to-date copies of all monitoring results and tracking registers (including waste registers) within 5 business days of the end of a calendar month and upon request.
1ff7c651-967e-526e-a7bf-63c7456d4b0c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9a477d4d-8e84-5ee1-a190-16fb93897c41 | note | Check Item - Check Item
a9d98b08-6f28-58c7-8be2-6bfb23644663 | note | Reference - MRTS51.1 Cl4.2
5931344a-eda1-4117-b04f-39589ddb396d | checkpoint | Maintan a animal tamping register inline with the SMP
14773cfc-0b9a-5305-8b4f-e26335231be6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5bf07004-4214-5e55-9e7e-02aa3affd2ef | note | Check Item - Check Item
7ccc18fe-9377-5cbc-997e-27a5419b2db2 | note | Reference - SMP requirement
287c8aa0-bd86-498a-ac24-05f330941197 | checkpoint | The contractor shall be responsible for the management of all chemicals and fuels within the worksite so as not to cause environmental nuisance or harm. The contractor shall ensure spill kits response equipment are available on site for use in emergency
772c8226-d074-5cc4-8a62-e1991242239a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
14b12a41-dba7-50fe-b1d1-3f1cb3e9af0c | note | Check Item - Check Item
b723d440-72e5-580e-a2a2-e8a17c5c0413 | note | Reference - MRTS51 Cl. 8.14.1
e9d0a269-08a4-49bb-8af1-51119a71e697 | checkpoint | Final Verification
4fe47a6b-ccc0-51f3-bd97-ea7f8394161a | note | Project Manager Verify that the Above has been Constructed according to Specification
b771cd0e-def9-5fc0-99ee-468f0b289a42 | textbox | Print Name:
1c673abd-fca7-5d33-9694-dfbaf7f58d24 | date | Date:
18024487-9052-5fca-b459-96bf1dd010e3 | note | Client Verify that the Above has been Constructed according to Specification
4bb94b01-9b75-5afc-a64e-9609465eb181 | textbox | Print Name:
660f3d26-d36d-52ef-b5c3-efd05681fabf | date | Date:
27ddf437-2f21-40cb-8605-155b2a6cc103 | signoff | Signature
d234dd6c-b483-4664-b3b3-aa89a97757ab | checklist | 52.01 - Erosion and Sediment Control | itp | 52.01 - Erosion and Sediment Control
46173f10-5524-4541-a93f-416290235736 | section | Details
eca0e38f-612d-4663-a931-ae1921b6db15 | checkpoint | No construction work to commence before an Erosion and Sediment Control Plan has been submitted to the Administrator and assessed as suitable.
61fba314-6a44-5613-bec3-b350daecb10d | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
b70f13ed-c641-5f97-b606-efbe974b6766 | note | Check Item - Hold Point 1
846730bd-a470-54a6-9960-9e2dfed50bbc | note | Reference - MRTS52 Cl. 6.1
9516f898-9a3a-443e-8897-ca0e95ac7112 | signoff | HOLD POINT
747973db-fb3e-48b6-aa01-a921a0628fea | checkpoint | The Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area.
90d34f6e-b904-5dba-9059-c9ea592a4fc9 | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
49f50bca-cd98-5ca4-9302-38e54c280ca5 | note | Check Item - Hold Point 2
b095638b-02a7-569d-87ce-30a34cb8171c | note | Reference - MRTS52 Cl. 7.1
47ac8f47-3f37-486f-8916-bdd96bc6e211 | signoff | HOLD POINT
cae990cb-0dff-48cd-a16d-c9efe0c1f697 | checkpoint | Releases from site must not cause scour at the area of discharge. Water must only be released at the discharge point nominated within the ESCP and as deemed acceptable by the Administrator.
4f89b254-39a7-54e7-a070-f437494e4ccb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a783eb70-4f64-5e1a-bd4d-f1797b0e82e0 | note | Check Item - Records
68aff64f-d2bd-59f0-8018-4f40955c8e55 | note | Reference - MRTS52 Cl. 8.1
48771bec-681f-4a6e-8d8d-333aacf5a0b7 | checkpoint | The Contractor shall install a proprietary rain gauge and keep record of the rainfall depth of each rain event
76ea1729-1eca-5b02-abea-4e34cc5b58c4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fc8cf2a2-2efd-501e-93d7-32d40179495e | note | Check Item - Records
dd67327b-607a-5524-b827-2e980120ccc2 | note | Reference - MRTS51 Cl. 8.2.3.2.1
36da7c68-6cd7-4ee5-9827-6609ca7e5e3b | checkpoint | The Contractor shall maintain all erosion and sediment controls in effective working order including reconfiguring drainage lines as required during the construction process to ensure dirty water is directed into sediment controls at all times. Reuse of the water collected in sediment ponds or basins for dust suppression and roadworks is preferred over release into the environment. Where water is being stored for dust suppression the required design capacity of the basins shall be available.
835815cb-a189-5802-ae91-cc0ece2eda09 | note | ○ Sediment basins and other sediment controls shall be operated and maintained in a manner that minimises the risk of environmental harm. The design capacity of the upper settling volume shall be made available within 120 hours of the most recent rainfall event which causes runoff.
96e60319-c8c8-5844-b406-18ed9788323e | note | ○ The sediment storage zone shall be maintained at all times with the accumulated sediment removed in a manner that does not allow the sediment to be conveyed into a watercourse or offsite.
381cbbca-b06f-58db-b776-c7fb5bb63439 | note | ○ Where coagulants or flocculants are used to treat stormwater, they must not cause harm to the receiving waters or environment. A jar test or streaming current detector (SCV) must be undertaken to estimate volumes of the coagulant or flocculant required and to reduce the risk of overdosing.
238f5eb0-6d6c-5eff-8b30-4c99b939aff6 | note | ○ Coagulants or flocculants containing aluminium (including alum and PAC) shall not be used when water is being discharged to an acidic environment where natural pH is less than 6.0 (such as wallum stream or wetland).
8ad6cc47-35d9-5408-a307-64b91afd2545 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
011b717c-ab47-5455-8ae9-6cbc73e54711 | note | Check Item - Check Item
2d4e106f-514b-5b3d-9cdd-98c2aa5a6ec0 | note | Reference - MRTS51 Cl. 7.2
6f094253-d950-45b1-826e-816e761d876e | checkpoint | The Contractor shall remove temporary controls when permanent measures are in place and/or Site stabilisation has occurred. This should occur prior to the end of the Defects Liability Period or the end of the Landscape and Revegetation Works Monitoring Period whichever is the later. The Contractor will not receive a Final Certificate until these temporary controls have been removed from the Site. Any areas used for erosion and sediment control shall be rehabilitated to the satisfaction of Administrator.
89bd441d-ac76-5b0b-888d-041b738476e1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
536c8db7-9847-532e-93ae-3359040a225b | note | Check Item - Check Item
853f6873-8a54-54e9-99c2-a59d9163a039 | note | Reference - MRTS51 Cl. 7.3
483ba688-ab11-4bec-acc2-0f31114f9e1c | checkpoint | The Contractor is required to conduct daily visual assessments of erosion and sediment control structures to verify their condition and effectiveness. The Contractor shall also conduct weekly site inspections. Where any defect or damage is identified it is required that they be rectified immediately. This information must be recorded at the time of inspection, and both daily and weekly records submitted in the Contractor’s Weekly Site Inspection Reports (refer Clause 7.1 of MRTS51). The Contractor's ESCP’s and EMP(C) shall document detailed response procedures to address any observed or documented sediment release or erosion.
da17d84f-be7b-59b3-8f4f-d9c3ab9c4d17 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
377327bc-e53b-572e-b2c1-3b4c60e61a43 | note | Check Item - Records
89fce38b-b7eb-5a95-95f3-baec455d6ba7 | note | Reference - MRTS51 .1 Cl. 4.1.1
d00a1ca4-3413-4ac1-bf71-46203988d362 | checkpoint | Independent ESC audits shall be undertaken in accordance with Section 9.1 of MRTS52 and includes one audit immediately following clearing and grubbing, one audit during any cut/fill activities and one audit at the end of major earthworks. Reports shall be submitted to the Administrator within three days of the audit.
68306667-c6c2-57f9-8c1d-3a58c1d62ef5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
15d037ef-def0-591f-9cb7-99efaf9125d2 | note | Check Item - Records
ce122a6a-4829-5937-a05c-cc7740408e37 | note | Reference - MRTS51.1 Cl. 4.1.3
3dd5d480-d027-4db4-b0bd-d90011fccca9 | checkpoint | Final Verification
d7a3d9b7-ac32-50ef-acc2-1facc7265c4f | note | Project Manager Verify that the Above has been Constructed according to Specification
5d810ba4-36b0-549b-a4ac-64ca5077e26a | textbox | Print Name:
7281bf1d-2697-5f2e-8705-e46467658d89 | date | Date:
54993ea9-c629-53cf-a804-4ca2a4e93eba | note | Client Verify that the Above has been Constructed according to Specification
52917a2a-07b2-57d7-95c5-5753ee29a445 | textbox | Print Name:
106b424e-4104-5749-8206-a528f38307a8 | date | Date:
092917f2-8bc7-4c3c-b04b-023e05a67030 | signoff | Signature
ed9ad2cd-6372-43b5-b7b7-133e32adaefc | checklist | 63.1A - Piles for Ancillary Structures | itp | 63.1A - Piles for Ancillary Structures
97573197-cfba-4a09-9d9b-c334b6fc5421 | section | Details
0252519d-0412-4b0c-9d1f-c77654ecb0ae | checkpoint | Construction Procedures At least 28 days prior to the date for sinking of pile shafts a detailed construction procedure has been submitted to the Administrator for review. Along with approval of procedure for construction, excavation, inspection, certification and concreting of piles.
f8319256-c979-57f7-87f8-1544ea3a8733 | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
2991cd98-18f5-57d3-96bd-816d57bf4613 | note | Check Item - Hold Point 1
3b51ebe8-56fe-534d-bef7-19871e1c5121 | note | Reference - MRTS63 Cl. 6.2 & 6.3
d960a04b-8741-40ce-95a4-f8a42baf64b1 | signoff | HOLD POINT
af4566f4-c9df-4eb2-9637-e137d630ca47 | checkpoint | Fabrication of liners Welding shall be carried out in accordance with the provisions of AS/NZS 1554.1. A Weld Procedure Sheet shall be submitted to the Administrator for approval prior to welding liners.
c447b8cd-c3dd-5fc5-87e0-1d613f46df49 | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
140c1a7b-2ddd-5474-a368-5fa1ed7eae47 | note | Check Item - Hold Point 2
29f6496f-2921-5d9a-9b22-9891c1aba3ad | note | Reference - MRTS63 Cl. 7
840a7e3b-a27a-4207-be97-54321ac71eea | signoff | HOLD POINT
16674e3b-ebb9-4610-a717-8fe97cf0f092 | checkpoint | Liners driven fom top Liners shall be driven (hammered, oscillated or rotated), open-ended using a driving rig capable of achieving penetration of the liner to the founding level.
9db1342d-5fd2-5abb-8653-f5478f28fa58 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e8e09e12-71b0-5397-a4ca-986f6731e0df | note | Check Item - Visual
c8c20368-b4de-5b9a-9c59-3e743eb02ded | note | Reference - MRTS63 Cl. 8.2
28e14e54-4468-47ed-8dc0-ad4ee61c7e0d | checkpoint | Construction Limitation A pile which is located within 2.5 m clear distance from a newly concreted pile shall not be bored or driven until 18 hours after completion of concreting in the adjacent pile. A pile which is located between 2.5 m and 9 m clear distance from a newly concreted pile shall not be driven in the period between initial set and 12 hours after casting is completed. The top of a newly concreted pile shall not be in contact with the driving platform while another pile is being prebored or driven from that platform.
05ebdc2d-9e0c-5fac-91b2-b1990cf1ec44 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dd56a53a-08dc-5c8a-8dc2-c798b917c2a5 | note | Check Item - Visual
e9ef9829-bf69-52bd-97d3-513678590837 | note | Reference - MRTS63 Cl. 8.5
dcf29099-6680-40e9-8bfa-a72d970d0ecb | checkpoint | Tolerances The completed pile shall be located as shown on the Standard Drawings within the following tolerances: a) Top of pile, in plan 75 mm in any direction b) Top of pile, vertically 5 mm in height c) Variation from vertical or designated rake 20 mm per metre d) Bow of pile 1% of length of pile in any direction, and e) Diameter of liner and socket - 0, + 5% of nominal diameter at any position.
fefa6675-ef2d-5459-b240-0d65fdc37eee | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ecab84d6-a3a0-5ce3-b120-06776a3b2a7e | note | Check Item - Visual
b1abe61e-b601-50e0-86a9-032b87d4d753 | note | Reference - MRTS63 Cl. 9
d7f8cb55-5174-43dc-824f-ea4696bbd7a7 | checkpoint | Excavation of cast-in-place piles When a pile is to terminate above the design level, the concurrence for this change must be obtained from the Designer, it is not just a geotechnical decision.
f1bfdd80-6508-58d2-9db8-5f221483b9ae | note | Acceptance Criteria and Frequency (Project Specific) - Visual
44b1144a-b785-57b7-b012-205f0ddd6638 | note | Check Item - Check Item
07583d46-1054-582a-8ae9-85f5d0cd7765 | note | Reference - MRTS63 Cl. 10.1
8c93fb8e-f239-4751-ac37-e742df6349f2 | checkpoint | Excavation of cast-in-place piles Temporary safety shields shall be used where manual work is carried out in unlined holes and sockets as required by the Workplace Health and Safety Act.
6ac4c95d-7d0c-5cc6-a4ea-083180a788b4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
032601d2-e67d-5c72-a7c5-4972c26c6a46 | note | Check Item - Check Item
2eb44f38-e544-587f-b8d0-000daea4bb94 | note | Reference - MRTS63 Cl. 10.1
cfa20c66-3cfc-4b95-8f37-a6bb6e042aab | checkpoint | Pile Sockets The walls shall be clean and free of smeared material. Smeared walls shall be cleaned and roughened prior to certification and subsequent concreting.
1d7b8a4d-0017-53b6-a5d9-c1a13dba72db | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6b6b0857-3b48-5567-a9ed-f0e66e47f090 | note | Check Item - Visual
e15cefd3-2b09-52f0-9b13-b5277dfc5da8 | note | Reference - MRTS63 Cl. 10.3
19cf76d9-7136-4179-b3a0-242434bfcb71 | checkpoint | Geotechnical Certification The Contractor shall forward a copy of the geotechnical certification of the foundation to the Administrator prior to concreting. Insertion of reinforcement and concreting of the pile shall not proceed prior to the Administrator's approval.
b0cfe055-bf87-5ed9-8de9-dd903289c82b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
791f3908-f6d5-52a3-8f57-d8126da67568 | note | Check Item - Hold Point 3
800a2ddc-e1c7-5452-9ab9-f570da264715 | note | Reference - MRTS63 Cl. 11.1
76ae295f-1d8b-4337-b4d0-5aad8a27775c | signoff | HOLD POINT
81dd1ca7-3a98-42b0-abac-7a55214f727f | checkpoint | Steel Reinforcing Steel reinforcing shall be supplied and placed in accordance with the requirements of MRTS71 Reinforcing Steel and MRTS71A Stainless Steel Reinforcing. Steel reinforcing shall be assembled as detailed on the Standard Drawings to form a rigid cage capable of being lowered into the excavation without any disintegration occurring.
8394c6a0-28fa-5219-a1f7-eaabd354f91f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
abdf9354-5366-52df-a2a3-bd16e783dc35 | note | Check Item - Records
6451d9d1-6a8a-506f-8a2d-3d8fc52fc653 | note | Reference - MRTS71
d0826fef-81db-4016-830e-7800693ab6a2 | checkpoint | Concreting All concrete shall be placed in accordance with MRTS70 Concrete except as otherwise specified in Clauses 13.2 to 13.4. The Contractor shall observe all relevant Milestones and Hold Points in MRTS70 Concrete.
564b97d3-2376-57dc-b200-17b963ddeb53 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c0d4af35-95b1-5d18-94e8-42b48b5a6a15 | note | Check Item - Hold Point 4
be798ea6-d251-5915-9983-9466b0c944a9 | note | Reference - MRTS63 Cl. 11.1
25a6cf45-8129-43ba-9f87-54066c3ccb1c | signoff | HOLD POINT
2a7b4538-1831-458e-b3c9-ced8145fa48b | checkpoint | Where there has been a delay of more than 24 hours between certification and when the Contractor is ready to start concreting or when the foundation has been observed to deteriorate significantly, the foundation shall be re-cleaned (if required) and re-certified.
24d2b8e1-4ca7-5eb5-938c-48d7c0ea7487 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9747468f-862e-5dbc-8b5f-fc19e1904420 | note | Check Item - Records
9501736a-319a-5326-a944-a0f7c1c552b1 | note | Reference - MRTS70
64fe58d7-9240-4f36-97bf-7039f63bc2ce | checkpoint | All concrete shall be placed in accordance with MRTS70 Concrete except as otherwise specified in Clauses 13.2 to 13.4. The Contractor shall observe all relevant milestones and hold points in MRTS70 Concrete. Placement of concrete underwater shall only commence after the tremie and the placing procedure have been accepted for use by the Administrator.
f60a6256-86ef-5168-844a-5cba579dd76b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
eeb5b535-e41a-51d7-b03a-e1a7e2b039de | note | Check Item - Hold Point 5
d9b37ec9-0040-56b0-983b-12ae961293e8 | note | Reference - MRTS63 Cl. 11.1
c5471540-bafd-49ab-bf70-e288642f9230 | signoff | HOLD POINT
db9f1710-ee29-46a2-8a88-4164d2dd9cb9 | checkpoint | The target slump of concrete shall be selected from the range below: a) for concrete placed in dry conditions 150 mm to 180 mm b) for concrete placed by tremie underwater 180 mm Slump tests on delivery shall conform to the target slump and the tolerances given in AS 1379.
4a01446c-a055-5c40-868b-1d7ce5336f42 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d883b9a6-4d28-5b5e-ae30-effc651c19a5 | note | Check Item - Check Item
fa778a52-a0d4-52e9-874f-00c8491aee3a | note | Reference - MRTS63 Cl. 13.3
30673341-ea3d-46be-9db9-a7f2da36da59 | checkpoint | Prior to commencement of concreting the length of the pile from the base to the top of the liner shall be measured and the socket walls and pile base checked for cleanliness.
433a0777-0434-51c3-8af8-0d59ed0dcbcf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
eb43f04b-b4f2-5414-9037-6c6d62b9847e | note | Check Item - Check Item
f073831a-5b3a-5c22-97cd-854c409b1b3a | note | Reference - MRTS63 Cl. 13.4.1
6a5dc9ce-e099-41d0-a3c9-e97054821749 | checkpoint | To assist compaction by hydraulic head, the rate of placing the concrete shall not be less than 10 metres of pile length per hour. Concrete supply shall be effectively continuous with delays between concrete delivery trucks of 15 minutes or less, unless an approved specific retarded mix design has been developed to allow for longer delays, as in remote areas.
fdb6b6f6-44bd-5a3e-a3e9-e186ad40992f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cdd2c732-b82f-5b37-a57c-f50840ef5f37 | note | Check Item - Check Item
2eafe713-04b6-5d67-bf3d-e7d39ddc6e02 | note | Reference - MRTS63 Cl. 13.4.1
c03c97b4-d53b-46b3-9efc-d27a86f4971c | checkpoint | Concreting The base of the pile shall be clean and all water removed immediately prior to placing concrete. This shall be confirmed by direct observation or by using a camera. The method of placement shall allow the following: a) delivery hose or pipe to 2 m above the pile base, and b) ability to lift and/or shorten the delivery hose / pipe quickly with delays no longer than 10 minutes. Concrete shall be dropped 2 to 3 m from the end of the delivery hose / pipe onto the concrete surface to provide compaction or shall be compacted using vibration. The delivery hose / pipe shall be positioned so that the concrete does not fall onto the reinforcement cage. For raked piles, the Contractor shall detail in the procedure for construction of piles the method of delivering concrete down the piles that minimises the risk of segregation. [Refer to Hold Point 1] The top 3 m of concrete shall be well compacted with a concrete vibrator with a minimum diameter of 50 mm.
2882302f-e594-5390-a990-d02742b500af | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d1278ebb-d65f-566a-ab83-4d18e88d03cf | note | Check Item - Check Item
49e1770b-743f-56eb-b19a-a81c5d520c13 | note | Reference - MRTS63 Cl. 13.4.1
44d2d858-d0f3-4691-bb03-3d742bcdc185 | checkpoint | Unless approved otherwise by the Administrator, the Pile Integrity Testing shall be conducted by a company or organisation independent of the pile designer, and piledriving / installation companies or organisations. No further construction above the pile cut off level shall commence until the Pile Integrity Test Reports have been submitted and approved by the Administrator.
f01f4c4e-cdeb-50e2-b0ff-5d5594252865 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0f22d577-5b7c-5c94-8a38-c5148cb55528 | note | Check Item - Hold Point 6
e2d26832-d8a6-5926-a11c-65b22831d771 | note | Reference - MRTS63 Cl. 14
2df3fece-65d7-4e39-ac7e-ba5eb5e99fca | signoff | HOLD POINT
735d029f-f23b-440c-bc8a-3d137c186217 | checkpoint | Final Verification
bb8d9055-29fd-54b0-bd86-630960c6e0f7 | note | Project Manager Verify that the Above has been Constructed according to Specification
765031a6-ffb2-5922-a03f-698e002946f0 | textbox | Print Name:
c27cc258-3305-5284-9b40-24ae6962492c | date | Date:
74eab1a4-400d-54c9-a469-dcc73d05b0df | note | Client Verify that the Above has been Constructed according to Specification
bb0876ff-0839-5783-8b7c-5790f214cde4 | textbox | Print Name:
bb4b53e4-f25a-56f9-9fb7-54fcfa9aba15 | date | Date:
77cefbd5-8b06-4ecd-8b60-c104b7738329 | signoff | Signature
4e009600-b115-480b-8559-f102c96377eb | checklist | 70.01 - Supply of Concrete | itp | 70.01 - Supply of Concrete
b584f8ef-98ba-4369-b70f-4249bf5378cf | section | Details
9888c740-7234-4988-9d54-65caeb467ef4 | checkpoint | The Contractor shall nominate the special class concrete mix to be used in the Works not less than four weeks prior to the commencement of concreting operations.
07accb47-e40a-5da0-ac54-0520134040a9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
45da16da-49e8-57aa-b9d9-bfa7a3a583bc | note | Check Item - Milestone
b949d56b-dc68-56fa-b469-3a111fbc2f70 | note | Reference - MRTS70 Cl 9.2
aa626da5-cf05-47aa-9830-2700f5e22547 | checkpoint | Submission of long distance travel procedure - Where travel times are, by necessity, longer than 90 min as listed in AS 1379, a procedure for longdistance travel or extended placement times shall be submitted to the Administrator
4564e137-900a-5217-a9ca-618029b71f57 | note | Check Item - Milestone
74f1a6c5-2aaa-5d0b-9033-211f3eb9a248 | note | Reference - MRTS70 Cl 17.6.1
28ad3943-da47-4d69-b485-48308fa7ee07 | checkpoint | Procedure for hot weather concreting submitted 2 weeks prior to first concrete pour.
dab9e9a2-8db2-5cc2-b243-f0bf670f3be5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1c6c2f43-2dcb-5ceb-8e7d-786adeaa5b50 | note | Check Item - Milestone
3793cd2d-66c3-5bfe-a74c-f84c6dfd8716 | note | Reference - MRTS70 Cl 13.1
1428fe78-be72-4135-969d-c2f8022567df | checkpoint | Procedure for curing submitted 2 weeks prior to first concrete pour.
aaf4365d-db7b-5ada-8fb5-29662cc41eb4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f4cf490a-5c6f-5904-9a1c-e37e7e71a085 | note | Check Item - Milestone
20e546d5-38af-5e84-a1a0-6c3165c54f0f | note | Reference - MRTS70 Cl 15.11.1
0bcba6f7-917f-458c-8567-7abddfe53ff6 | checkpoint | Procedure for temperature control submitted 4 weeks prior to first concrete pour
7b0cdfa7-25f1-50e1-9295-20f55513b666 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3e03a9cc-13f3-5fe8-adb8-3702b3998acb | note | Check Item - Milestone
1b3fc379-0732-59b9-9166-b26183158abb | note | Reference - MRTS70 Cl15.5
2e466a08-afc3-43a2-a6a9-d4ae29f52115 | checkpoint | When requested by the Adminstrator, mix designs shall have a trial mix completed. each trial mix shall be a Witness Point with a notice peroid of 3 days.
8992ff7b-9a74-51ef-b145-1628a26085c3 | note | Acceptance Criteria and Frequency (Project Specific) - f'c Each Mix
df40d289-0d6d-55e7-b20a-9d1c9dcca6fc | note | Check Item - Witness Point
4e43cd7e-c441-5d10-af21-93aa5f945fcf | note | Reference - MRTS70 Cl 15.1.1
8712eb04-55fe-45e9-95f0-f4b8d07db52d | checkpoint | No concrete shall be placed in the Works until approval of the mix design has been obtained from the Administrator
7f7d1719-7510-5077-b0fe-8d3b47bd6efa | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8b0f6948-316e-533b-965d-e2e6c8e47910 | note | Check Item - Hold Point 1
8f4d19e8-5cf6-5011-ac08-9cccfe31a57a | note | Reference - MRTS70 Cl 15.1
29a2d081-1c84-4f96-9f84-c4ecf1075b4d | signoff | HOLD POINT
c097c36d-be59-4c09-9279-bb54cd357f5f | checkpoint | Final Verification
64ca9654-96dd-503f-8235-05867a0c4c12 | note | Project Manager Verify that the Above has been Constructed according to Specification
bf59d1e3-9d72-567b-bff1-bc969ae46556 | textbox | Print Name:
3db1424c-f89c-5244-8564-676b126d8e88 | date | Date:
f080a5a9-92a1-564e-9d6a-73588cf777a8 | note | Client Verify that the Above has been Constructed according to Specification
b6ee1ee9-06f6-55b0-afa5-afa71d38c2e4 | textbox | Print Name:
76901674-3641-5d5a-8367-544e2fef6e64 | date | Date:
40ba7f9a-fc74-4495-9bba-174cff01aa0f | signoff | Sign ITP
0f69dc13-f14a-45e1-ae04-9cd4e83e384c | checklist | 70.02 - Placement of Concrete | itp | 70.02 - Placement of Concrete
b885d97f-b49c-4a9a-8962-141d2948db45 | section | Details
94d467d1-cac9-4e21-8725-45603bdf9da2 | checkpoint | Concrete placed within 1 hour (conc. Temp<=32 degrees) or 45 mins (32>conc. temp < 35 degrees) from the time of charging the mixer unless a retardant is used and approved by the Administrator. No concrete may be placedthe temperature of the concrete is less than 10°C or exceeds 35°C
7fddac05-14e1-556c-8a5c-15b1d871f432 | note | Acceptance Criteria and Frequency (Project Specific) - 10< Temp <35 Continuous
1ace588e-7677-5364-b3b9-aa053b5704e9 | note | Check Item - Check Item
2afb659b-8fff-5150-a6d5-1be4d699c901 | note | Reference - MRTS70 Cl 13.1
867d39e6-8502-4f38-b0e4-f1c1d3ac04be | checkpoint | Falsework details provided to Administrator at least 4 weeks prior to erection.
b9487029-e624-57df-84ce-7ef2e9221ede | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c6f9aaaf-1363-50fc-a937-56a5a0d29c80 | note | Check Item - Milestone
fd36138e-f6f2-5ebf-8627-c33ca2417a87 | note | Reference - MRTS70 Cl 15.3
aa5bf430-fee3-4e08-b76a-f0ee6af53a38 | checkpoint | Design and erection of falsework, its founding, support and time, order and manner of release approved by the Administrator.
aa656b15-5f95-5dd8-9b26-fd34267a9725 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c4659b17-996c-5555-a19b-f3da97960947 | note | Check Item - Hold Point 2
c57f74fb-b47d-5066-89b9-de3dc705186a | note | Reference - MRTS70 Cl 15.3
30f53a5f-7d4f-4165-9d3e-a2410a6fe789 | signoff | HOLD POINT
2b152cee-e204-4765-abbb-536465662b37 | checkpoint | No concrete placed until falsework, formwork, reinforcement and stressing materials inspected by administrator, foreign material removed from forms and equipment and placement procedures approved.
f271acf2-51e3-557e-86ee-0efc2f6ac685 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
62c6ad53-46cf-50dd-b25b-709e9a79dd98 | note | Check Item - Hold Point 3
3fa3fd17-8123-50c5-a3ea-f0c616404826 | note | Reference - MRTS70 Cl 15.4.1
e95fca83-232b-449b-af3b-ce4417353a70 | signoff | HOLD POINT
810262e4-be0e-43eb-9101-c282c152097a | checkpoint | Concrete operations shall not commence until all relevant procedures, listed in Table 5.2 have been approved by the Administrator.
45b1329a-0519-5b2f-8536-045900ad8942 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
34a503ad-4a36-550e-81d4-e4da70dc264a | note | Check Item - Hold Point 4
24742768-db6f-54df-b844-519c5f164069 | note | Reference - MRTS70 Cl 15.6
4be0833b-6484-4234-b1cc-1e436f0e0343 | signoff | HOLD POINT
db0372d3-0d0d-4efe-82e4-b7dbdb1156f4 | checkpoint | No concrete shall be placed in the Works until:
75813938-8d7c-5d9d-94a7-0abd6ed5b78f | note | a) the formwork and reinforcement have been inspected
40fc50a6-88cc-57aa-a189-bb5860f4ee51 | note | b) all foreign material has been completely removed from the forms
3df8602e-ff2c-54f0-93c4-590563ef5913 | note | c) the mixing, batching, and compaction equipment have been approved by the Administrator.
2a005f0a-dfc1-5cbd-9eaf-85b2d6d556b2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3b04bc3a-b510-5f32-b5eb-e05ae3972634 | note | Check Item - Hold Point 5
690d1fa9-9794-596f-835a-da0cf2138146 | note | Reference - MRTS70 Cl 15.6.1
45e016f3-7bc5-487b-a939-122208970421 | signoff | HOLD POINT
102e11f1-a06d-4555-ac3c-e43511e62fbe | checkpoint | Administrator to be present for placement of concrete, given 24 hours notice.
ad1c8a21-5881-5d07-bf1c-a6f0015c1c0a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dfd5a906-6285-5f1e-8af0-8007d747da1c | note | Check Item - Witness Point
dbd7f48b-951d-5c6d-a33d-bfdd3406be10 | note | Reference - MRTS70 Cl 15.6.1
1104b34b-b45c-4358-8671-f8c8a55e0c50 | checkpoint | Concrete slump is within tolerance (AS 1379 table 6) of approved target slump.
43ee64b8-adf4-5b6c-89b6-cef96effe6a0 | note | Acceptance Criteria and Frequency (Project Specific) -
ec855590-fdd6-54c3-99cf-4c9bc45737ff | note | Slump Test: ¦¦ Spread Test:
cc2b254a-c724-5e1e-9aad-7b6e35d1d97a | note | <60 - ±10 ¦¦ 500 - 600(HWC) ±80
311c5f17-0fa8-5b50-944a-48f9660257f6 | note | 60<80 - ±15 ¦¦ 650 - 700(HWC) ±50
3b1929ad-793b-5cfe-a772-ebc53fde37d2 | note | 80<110 - ±20
8367f83a-0e84-5e20-84c9-0ab679e329aa | note | 110<150 - ±30
f0bf9a57-efa8-5690-bb02-5d209b833004 | note | 150< 200 - ±40
af48f023-6a34-5423-b99c-a4775cb458e0 | note | Every Load
6f4de08a-3868-5d78-8dae-eb6207483082 | note | Check Item - Check Item
04ca7626-306d-5f7b-a934-8d5ea3e710e9 | note | Reference - MRTS70 AS 1379 Table 6
ae4e244a-7ab8-4b39-b3ea-81f47c9086a7 | checkpoint | Samples for testing taken as required in accordance with claus 12. - min 2 cylinders/sample
4ebf7b98-7fb2-5148-b7f6-c003fcb429a8 | note | Acceptance Criteria and Frequency (Project Specific) - 1-3 Loads - Every Load
6d11347e-eeb5-50ec-bd34-a7e84a497adb | note | ○ 4-10 Loads - 4 Samples
c70d397c-b3de-5641-9536-836207f32798 | note | ○ 11-23 Loads - 5 Samples
7acb9083-03ce-57a2-9b91-5139fe66cc16 | note | ○ >24 Loads - n/4
5bbaed61-2dc2-58f0-97d7-c37384ffd851 | note | Check Item - Test Results
0fc73012-9e97-58ef-a5b7-90b23cc65400 | note | Reference - MRTS70 Cl 15.2
81ae6b05-9932-493f-84c0-666788584aea | checkpoint | Compaction of concrete commences immediately after deposition in accordance with approved procedures and equipment - The number of vibrators to be used by the Contractor shall be not less than one for each 10 m³ of concrete placed per hour
d58e6244-d64c-5726-a40c-b98676e97a63 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1c434f07-86f4-5bfb-9344-d4b1b7141e8a | note | Check Item - Check Item
e166f533-3680-5464-a7f6-2000da7e0572 | note | Reference - MRTS70 Cl 16.5.2
f1417d2c-84f8-4e69-9fdc-d72cdbc719b6 | checkpoint | Fresh concrete shall not be placed against concrete which has taken its initial set.If an interruption greater than 45 minutes occurs, a construction joint approved by the Administrator shall be placed.
4b001cc1-0202-5e44-9d86-183ef39468d3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d78da561-7dde-5f23-be47-6805e718c544 | note | Check Item - Check Item
d452fded-ad28-5791-8867-dbde0c78bbae | note | Reference - MRTS70 Cl.16.5.1
a4a78e1f-5377-4e98-8969-a1451454bb47 | checkpoint | Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer
dca126ec-5394-5f11-b3d6-60b54d92fc5c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9c444592-c2f8-58f1-b4f7-de17b3486a91 | note | Check Item - Hold Point 7
131b2dcc-7f8d-5bb2-8c4b-b58b34d1649f | note | Reference - MRTS70 Cl 15.13
cecb511c-2cc1-4a1c-aa66-65de4a84a2a3 | signoff | HOLD POINT
e5481c79-4d21-4a37-990e-3a9dbe06fc9c | checkpoint | Forms, falsework and centring shall remain in position until the times stated in Cl15.8 and table 15.8 have elapsed after completion of concreting
fe5a5961-7d23-514d-a87e-3c3cc890f872 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
290b3aba-4a06-5614-a622-2083f35ad54b | note | Check Item - Hold Point 6
aafb8507-7285-5bc8-b3fc-c84eafc43dc1 | note | Reference - MRTS70 Cl 15.8
6952036c-9581-462a-9715-926879d175d2 | signoff | HOLD POINT
48e4d8c1-34f6-4841-94ee-e37e1b994ac5 | checkpoint | Forms shall be removed with care, without hammering and wedging, and in a manner which shall not injure the concrete or disturb the remaining supports. Centres shall be lowered gradually and uniformly in such a manner as to avoid injurious stress in any part of the structure
eabe55be-cf08-51e2-9361-25d6d9b94ee0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
86fcbd58-022f-5698-a4e6-247728151a01 | note | Check Item - Witness Point
95b88b97-150d-5015-a7fa-f05a1c7f2a73 | note | Reference - MRTS70 Cl 15.8
5e0c1bb8-f611-41e5-8e84-4a080af1c276 | checkpoint | Following removal of forms
8c4b6f3b-d3c1-52ca-b63a-3a9d41934c40 | note | ○ Fins and unwanted projections are ground off
033206b4-5200-5cb6-9e8e-448c9c71ab50 | note | ○ Pockets and honeycombed areas repaired using approved methods
9bbaf314-d828-5543-a56f-ff95a841435f | note | ○ Where required in the drawings surfaces achieve class 1 finish or are bagged within 4 hours of stripping, then cured
319397a8-8fcc-5d00-bd99-70fb1b45e092 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1e9be1a6-ba23-533c-9306-0c23b58cbc26 | note | Check Item - Check Item
f5d7cc8f-d050-598a-b299-737d9da43f4b | note | Reference - MRTS70 Cl 16.8.1
5721f5a5-bde9-4fbc-97a4-303b65cc9a83 | checkpoint | Positional tolerances, listed in Table 15.7.3, refer to the departure of any point, plane or component of a structure from its correct position within the layout of the structure as shown in the Drawings.
968fe958-c48d-5077-9184-bc899a9095c0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual < Specified MRTS70 Cl15.7.3
2ef13947-ed83-5442-9751-917e2d274596 | note | Check Item - Check Item
bcf0a282-8d45-5422-b37c-0b9cd66a93f1 | note | Reference - MRTS70 Cl 15.7.3
27dfa540-fae0-4568-b7a9-c465c8ca58fd | checkpoint | Acceptance or Rejection of Hardened Concrete
84092594-3816-5fbf-8402-577666c8f567 | note | Acceptance Criteria and Frequency (Project Specific) - a) < 0.9 Fc (Any sample)
f22d88b0-f8ef-5331-ab8a-c13fa6887f9d | note | b) < Fc (Ave 3 consective samples from Lot)
a6da30f8-140f-580f-adb9-6223738bff5b | note | c) > 1.4 Fc (Ave 3 consective samples from Lot)
a25b010d-47a5-59db-ba9b-ebeb62a1c530 | note | In addition
24e8db5a-5ac9-5fa3-8236-47f6abdbd4a7 | note | d) < 0.5 (Fc+Ft) (10 or more samples for Class of concrete in 4 consective weeks)
e36ed38f-f4de-544b-9a09-c5b56b955ea3 | note | Check Item - Test Results
3e067cae-0aec-5067-bbb3-d0259d2eb4a5 | note | Reference - MRTS70 Cl 12.5
df754cec-5016-4151-800b-c3d8c8380a82 | checkpoint | Final Verification
d3f6ece4-a919-591a-b5cb-1b44592ca054 | note | Project Manager Verify that the Above has been Constructed according to Specification
8d38c602-1554-53d0-b38e-eaa607f6ccfa | textbox | Print Name:
44b0e2bb-a8e6-5592-9ae9-4c540abde7a6 | date | Date:
1532ebcc-6add-5aca-861a-5b5d30a658f0 | note | Client Verify that the Above has been Constructed according to Specification
1c76d08f-2cd7-52b1-8305-5a9087929194 | textbox | Print Name:
82e113ed-c0e6-5d5c-b73f-2bcc748d0649 | date | Date:
665e0a68-deb0-4b3f-9f90-62c732fcc0de | signoff | Signature
02af5c00-2794-44da-80d1-3684f77628a7 | section | Details: Concrete Record
682f9967-99bb-4ffa-b2b8-b168a54b9cb1 | checkpoint | 1 - Date
1841c4d8-2791-5fa2-a605-3d21b4785a37 | date | Truck 1:
682d4095-5cc8-5742-bdc5-817e6379950e | date | Truck 2:
ce9f4218-0372-5c88-95fb-72c25e389b6a | date | Truck 3:
a1fae970-2f2f-5f20-bd79-6c9a8061e971 | date | Truck 4:
3dc895f1-6b7e-4f36-9717-4a087e3aecb2 | checkpoint | 2 - Docket
52aeb75a-23a6-5a98-9a01-ea531862a108 | textbox | Truck 1:
61664efa-f551-5629-acd8-9d5d853dab39 | textbox | Truck 2:
ac129f29-5ea2-51ac-8b14-4445515c7fc4 | textbox | Truck 3:
fcb2a1f1-d3c5-5ecf-a2ec-65cbc797d37e | textbox | Truck 4:
80643adf-e14d-4efa-a5fd-24d4e63f574f | checkpoint | 3 - Time Batched
dabf4817-0b40-5145-aee3-4481b63f5e17 | textbox | Truck 1:
5b76186a-10e8-5141-995a-da6eb4afcc7c | textbox | Truck 2:
d23c849a-53e3-5f13-8e1f-02f2984c0bf7 | textbox | Truck 3:
511892be-61d9-5601-a0fb-24047b8ab125 | textbox | Truck 4:
cff75ef8-76f9-4720-be2f-02f5a94ce9bc | checkpoint | 4 - Truck Arrival Time
d050493c-5b5a-5cc1-8fa3-822b002b75ae | textbox | Truck 1:
bd8d2d76-ea9e-5d7e-bf20-0abc58721e64 | textbox | Truck 2:
6bb1a93b-a7a0-57ef-9b57-a4b06bbe68b1 | textbox | Truck 3:
84914841-5146-50cb-94cf-9d75e4160a45 | textbox | Truck 4:
5a8158e6-7e0b-47c6-aa3c-584b6ce2d048 | checkpoint | 5 - Load Size (m3)
f1bcb661-36f7-5f3a-bf05-d49c9eb0eb78 | textbox | Truck 1:
62b83ce0-ed54-541f-82fb-7e99005e7b6c | textbox | Truck 2:
1752b8ee-e7c0-54e5-ab67-989ce5a166a8 | textbox | Truck 3:
ef7ef049-b624-5b21-84a8-f43501cfb78d | textbox | Truck 4:
a34ea7bc-850e-47cf-b368-283a84fc1d3d | checkpoint | 6 - Mix
3e359bd8-6180-43f3-8f6b-efc79fda8acf | checkpoint | 7 - Slump (mm)
95b4058f-2177-5b10-a2a2-62adec8ddf8d | textbox | Truck 1:
27603a28-2fb0-5f44-846b-014891a2b18b | textbox | Truck 2:
57e38581-6465-51ea-ad6e-18f5ce207a1b | textbox | Truck 3:
86d71ae5-860a-5f30-8405-8ebbd221b74f | textbox | Truck 4:
903a1fbc-7e3a-4dfb-8683-9fc6bb3992d7 | checkpoint | 8 - Slump Time
39cc6bf4-b92c-5974-9304-aeebf3a2dea7 | textbox | Truck 1:
fa1589b2-0f54-5376-8c4b-e46a3e4e2638 | textbox | Truck 2:
40aa3b43-4a10-56ab-8777-e0efc18f963d | textbox | Truck 3:
68bf7ecb-53cf-558c-9b54-6461f0333a1b | textbox | Truck 4:
76b1f4cc-2d99-4484-ab79-0466010ba0e5 | checkpoint | 9 - Concrete Arrival Temperature (˚C)
698f28a2-2e02-59ae-bd47-2766650b1a37 | textbox | Truck 1:
d52beb15-fdb0-5822-a629-b0113185e347 | textbox | Truck 2:
dba41fc6-b006-5b5e-840d-7091d4b732fb | textbox | Truck 3:
3cec1bb9-8838-5b17-ae57-5be150993acc | textbox | Truck 4:
f3700e15-dcbf-45c2-838c-7d50ea2542af | checkpoint | 10 - Ambient Temperature at time of slump (˚C)
1cbc3768-9934-5ed8-ad44-a79ff11e9026 | textbox | Truck 1:
c5fe2000-bdab-58f8-98ee-c3d50be66315 | textbox | Truck 2:
4ab03209-56ca-56a2-9197-1537ffd1bd85 | textbox | Truck 3:
3ce98d81-627a-565a-bdee-8847abd3aee7 | textbox | Truck 4:
f80e689f-0fbd-4fa5-bd0d-07a1b22211fe | checkpoint | 11 - Time Start delivery
8389bcb5-b076-51d1-9732-98b9a70128d2 | textbox | Truck 1:
82cbc293-2e66-55db-a2ab-6126c775fc7d | textbox | Truck 2:
9f99cbcd-c7e0-5b4c-937e-95729a7a92cc | textbox | Truck 3:
3f923bfb-9d56-56f4-a36b-afcd3fc19aa6 | textbox | Truck 4:
f3cc7347-58de-4531-a392-6b0949ce079d | checkpoint | 12 - Time Finish Delivery
2fab18c7-3e76-571d-acdf-bc65356603fa | textbox | Truck 1:
c4e459e1-7646-508d-83fb-d95df8c7caa8 | textbox | Truck 2:
bd56b393-ba42-570e-91c9-07efb6a8fe34 | textbox | Truck 3:
dfc9aa9c-30a8-5417-9ae0-9af1905c1b5e | textbox | Truck 4:
56084150-1a67-4324-a606-0f656142ae3d | checklist | 71.01 - Reinforcing Steel | itp | 71.01 - Reinforcing Steel
a129c2b0-83ca-445a-b8db-e7429173b8bd | section | Details
a88d5c6c-14b3-430e-83a8-0a200b4104e5 | checkpoint | Submission of proposed supplier of reinforcement with three days notice prior to supply.
19bb4d85-7293-5516-8411-afbd585150e7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e2e206c9-0e23-5ebd-880a-b5aabc76b713 | note | Check Item - Milestone
cb4480e9-fef5-5606-84d2-59b362b805fd | note | Reference - MRTS71 Cl 6.1
ea0869e2-5caf-41e2-94f0-ba8f519cec81 | checkpoint | Acceptance of supplier from Administrator
f528ab67-fb04-5490-8c4a-10487717f242 | note | Check Item - Hold Point 1
8586bfb0-efa6-50db-af8f-6e773221a640 | note | Reference - MRTS71 Cl 6.1
9dca9165-e8ec-46e5-afd5-e8d62b18d9ec | signoff | HOLD POINT
a1f57468-2317-4103-a7fc-d9d00243b55b | checkpoint | Inspection of steel reinforcement before placement of concrete.
d3394765-40e0-5ed8-9f79-fd8a6a5c770b | note | Check Item - Hold Point 3
92d702a0-9dd0-5a39-9270-3526a9576ddb | note | Reference - MRTS71 Cl 10
3b261e22-3088-4201-9f2e-a1bd529edd7a | signoff | HOLD POINT
990bb058-1606-43b0-ba9d-2b3a97c942c2 | checkpoint | The min. clear distance between parallel bars other than lapped bars shall be the greater of: - 1.5 x the diameter of the larger bar - 1.5 x max nominal size of aggregate - or 40mm
841a77af-b980-54f6-bcbb-3ea565698fc0 | note | Check Item - Witness Point
089a697a-b5a8-5e0d-bb3a-eded8675fe86 | note | Reference - MRTS71 Cl 10
d3a486fa-a77b-4835-b38f-6a720fec93b7 | signoff | WITNESS POINT
8134ed63-e99c-420c-9785-06fa9835cccb | checkpoint | Permitted mechanical reinforcing bar splices listed in Clause 1 of MRTS71.1.
662e48f5-b6e1-53bd-a86c-fd3de27a29ec | note | Acceptance Criteria and Frequency (Project Specific) - Visual
32512770-381c-585b-9b0e-e457dec94f35 | note | Check Item - Hold Point 4
d0bedde2-1eb2-5768-84be-c140024570f4 | note | Reference - MRTS71 Cl 11.3
b30b024c-d94f-41b1-97ea-7b6467d4ef8d | signoff | HOLD POINT
e842e4e4-4720-4192-bdab-9d455af5d52c | checkpoint | Installation of mechanical reinforcing bar splices as per provisions in Clause 11.3.2
4b07f869-22f5-5dab-804d-f447c9f504b3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5a0ff869-842d-52be-aa4b-25deebcbb86a | note | Check Item - Witness Point
c508549e-783c-5b5b-bcdc-e8f3882113dc | note | Reference - MRTS71 Cl 11.3.2
51b18d68-b2dc-433f-825d-d0a6cdb2cde0 | signoff | WITNESS POINT
90e09974-0920-4ff2-ae6b-f2f26b348f7e | checkpoint | No substitution of different size, grade or ductility class of steel reinforcement shall be placed unless approved by the Administrator.
1f11f3f3-b3eb-51d1-b0d9-853edc32b4cb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8732b7a8-db26-5ecf-9788-27e37d6badab | note | Check Item - Hold Point 5
db4d219a-4125-57f7-b355-d845ac8b6d49 | note | Reference - MRTS71 Cl 13
4c4b40ab-68d4-4dc4-b45c-95abbb34a638 | signoff | HOLD POINT
a44ed702-a7f0-4431-99a5-f3ba9b5874aa | checkpoint | Application for substitution of reinforcement forwarded to Administrator 3 weeks prior to supply
055fd873-e70a-5303-8cf7-2369ee93ffbc | note | Acceptance Criteria and Frequency (Project Specific) - f'c Each Mix
d6956809-1d55-556e-830a-0aebba4f59a3 | note | Check Item - Milestone
ac911f80-83d5-5ab8-9aa7-0c715a287719 | note | Reference - MRTS71 Cl 13
b7fe9db5-7667-489f-b5a4-926fc92d5e6c | checkpoint | Final Verification
56027c8a-2635-58ea-9854-b8c73b7c8860 | note | Project Manager Verify that the Above has been Constructed according to Specification
f3e34c34-3bad-5554-b10c-30f4a125fca3 | textbox | Print Name:
f7cdc418-41de-5c25-a209-ba9436c761f9 | date | Date:
ac23af12-c825-545b-bd45-4aa00ca36154 | note | Client Verify that the Above has been Constructed according to Specification
538bf01a-b74a-5411-b808-acd326fda47f | textbox | Print Name:
95bb0081-4701-58ba-9afb-937fe7a61d5b | date | Date:
82284705-bee2-4671-9d3c-87e948c5c2c6 | signoff | Sign ITP