## ITP Cover Page
Stormwater Inspection Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - - Rev D
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number:
Project Number: |  |  | DN1205 |  |  |  |  | ITP Status:
ITP Description: |  |  | Impact Basin Structures |  |  |  |  | Revision: | 1000 |  | D
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets:
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification and RITS
Quality Specified: |  |  | NZTA Z/1
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A |  | 2025-04-11 |  | EK |  | Multiple comments |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B |  | 2025-04-14 |  | EK |  | Pipe requirements, handrail/grates, etc. |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
C |  | 2025-04-15 |  | EK |  | Mill certs, cylinder testing |  |  |  | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
D |  | 2025-05-04 |  | EK | [5 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Stormwater Inspection Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - - Rev D
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1.1 | Environmental Protection | ESCP for works have been approved. | ESCP | ITP Sign Off | Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events | M | PE
1.2 | Shop Drawings | Shop Drawings have been approved by the designer. |  | Approved Shop Drawings Record of Approval | Prior to Construction | HP | ENG
1.2 | ITP Approval | Record of approval |  | Record of Approval Approved ITP | Prior to Construction | HP | ENG
SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
2.1 | Pre-cast Structures | Inspect pre-cast elements upon delivery to confirm they match the drawings. Producer statement for each structure. |  | Producer Statement Shop Drawing Approval Shop Drawings | Each Delivery to site | S | PE
2.2 | Bedding/Side & Haunch/Overlay/Backfill Material Compliance | Confirm material grading and density. |  | IANZ Lab Test Report Material Docket | 1 Test per 1000m3 | H | PE
2.3 | Connection Details | Materials used for connections are as per assembly drawings. | Shop Drawings - Connection Details | Dockets | Each item | S | PE
2.4 | Riprap Material | Density - Greater than 2.40t/m3 Crushing Resistance - Not less than 150kN Weathering Classification - AA, BA, AB or BB Abrasion Resistance - Not more than 26% Calcite intrusions - Rock shall be free of calcite intrusions Grading - Rock for riprap shall be the nominal D50 size shown on the drawings and shall be well graded. If riprap product is unavailable, alternative material to be approved by designer. | Project Specification 4.7.1 | Delivery Dockets Lab Reports | Per Truck | H | PE
2.5 | Grate | Webforge grate or similar aproved grate. Fixing detail to be approved. All fixings to be installed as per drawings. | BBO Downer | Dockets PS1 | Prior to delivery | H | PE
2.6 | Handrail | Material and design to be approved. Fixing detail to be approved. All fixings to be installed as per drawings. | BBO Downer | Dockets PS1 Record of Approval | Prior to delivery |  | PE
2.7 | Concrete Mix | Material and design to be approved. Fixing detail to be approved. All fixings to be installed as per drawings. | BBO Downer | Dockets PS1 Record of Approval | Prior to delivery |  | PE
2.8 | Reinforcing | Mill & test certificates for each batch of reinforcement used to be provided to the Engineer. Unless specifically nominated otherwise on the Drawings, only Grade 500E reinforcement manufactured using the micro-alloyed process is acceptable. | SS 2142 - 3, PS - 11.6 | Mill Certs | Each Batch |  | PE
SECTION 3 – CONSTRUCTION ACTIVITY
3 | Installation
3.1 | Impact Basin Foundation | Geotextile laid on base, GAP65/GAP100 compacted to 95% MDD and 20MPa blinding. | Shop Drawings | IANZ Lab Test Report Dockets | Prior to installation | H | PE
3.2 | Impact Basin Assembly | 1. All Panels & Baffle to be delivered to site seperately and assembled in-situ by the contractor. 2. Erect and Place Panels 3 & 4 to Panel 1 and Panel 2 with temporary supports, aligning projecting Reidbars through associated Drossbach ducts. 3. Tighten nuts equally at downstream end, using a socket wrench to a maximum torque of 200Nm, and fill ducts with grout. 4. Place Baffle and fit to Panels 1 & 2 with Reidbar starter bars fixed to couplers cast into Baffle ends. 5. Tie Base Slab reinforcing to projecting steel from Panels. 6. Fix Panel 5 - lid. 7. Fill swiftlift recessess with Sikagrout 212 or equivalent. 8. Remove temporary supports. 9. Contractor to ensure joints are suitably sealed to Engineer's/ Site specified requirements. | Shop Drawings - Site Installation Notes | Photos | Each item | H | PE
3.3 | Riprap Mix | Riprap Mix Materials to be stockpiled separately and mixed in a pre-determined ratio. Soil-riprap will contain 70% riprap mix and 30% topsoil. Voids-filled riprap will contaon 70% riprap mix and 30% GAP40. | Project Specification 4.7.1 | Photographs Riprap Mixing Inspections | Each item | H | PE
3.4 | Reinforcing | Reincorcing to be installed as per drawings. |  | Prepour Inspection Photos Dockets Mill certs | Each item | H | PE
3.5 | In-situ Concrete | Pre-pour inspection. Slump test +-30mm of slump target. UCS testing with 1x7 days and 3x28 days cylinders. U2 Finish | Downer Drawings NZS3114, NZS3109 | Dockets Testing Records Pre-pour record | Each item | HP | ENG
3.6 | Bedding Compaction Testing Pipe Bedding | Minimum Compaction 95%(Average 98%) of MDD or concrete fill beneath pipe. | Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002 | IANZ Lab Test Report or Concrete Dockets | One test | H | QE
3.7 | Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe | NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD | HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007 | IANZ Lab Test Report | One test | H | QE
3.8 | Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe | NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD | HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007 | IANZ Lab Test Report | One test | H | QE
3.9 | Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. One lifts of 300mm to be placed. | NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD | HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007 | IANZ Lab Test Report | One test | H | QE
3.1 | Drainage | Novaflo pipe with filter sock and no-fines concrete behind structure. Riprap surrounding structure as per BBO drawings. | Downer Drawings | Dockets Photos | Each item |  | PE
SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
4.1 | Red pen markup | Markup to cover all changes. | Project Specification | Red-pen markup | Post consutrction | H | SV
4.2 | As-builts | Ensure all items have been surveyed and records are assembled for asbuilting | Downer | Records | Post consutrction | H | SV