## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Impact Basins | itp |  |  |  |  | ITP - Impact Basins Rev D
section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 1.1 - Environmental Protection
label | Acceptance / Conformance Criteria - ESCP for works have been approved.
label | Standard / Specification - ESCP
label | Verifying Document - ITP Sign Off
label | Frequency - Prior to Construction
label | ○ Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
label | Verification Activity: Activity - M
label | Verification Activity: By - PE
checkpoint | 1.2 - Shop Drawings
label | Acceptance / Conformance Criteria - Shop Drawings have been approved by the designer.
label | Verifying Document - Approved Shop Drawings, Record of Approval
label | Frequency - Prior to Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - ITP Approval
label | Acceptance / Conformance Criteria - Record of approval
label | Verifying Document - Record of Approval, Approved ITP
label | Frequency - Prior to Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 2.1 - Pre-cast Structures
label | Acceptance / Conformance Criteria - Inspect pre-cast elements upon delivery to confirm they match the drawings.
label | ○ Producer statement for each structure.
label | Verifying Document - Producer Statement, Shop Drawing Approval, Shop Drawings
label | Frequency - Each Delivery to site
label | Verification Activity: Activity - S
label | Verification Activity: By - PE
checkpoint | 2.2 - Bedding/Side & Haunch/Overlay/Backfill - Material Compliance
label | Acceptance / Conformance Criteria - Confirm material grading and density.
label | Standard / Specification -
label | Verifying Document - IANZ Lab Test Report, Material Docket
label | Frequency - 1 Test per 1000m3
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 2.3 - Connection Details
label | Acceptance / Conformance Criteria - Materials used for connections are as per assembly drawings.
label | Standard / Specification - Shop Drawings - Connection Details
label | Verifying Document - Dockets
label | Frequency - Each item
label | Verification Activity: Activity - S
label | Verification Activity: By - PE
checkpoint | 2.4 - Riprap Material
label | Acceptance / Conformance Criteria - Density - Greater than 2.40t/m3
label | ○ Crushing Resistance - Not less than 150kN
label | ○ Weathering Classification - AA, BA, AB or BB
label | ○ Abrasion Resistance - Not more than 26%
label | ○ Calcite intrusions - Rock shall be free of calcite intrusions
label | ○ Grading - Rock for riprap shall be the nominal D50 size shown on the drawings and shall be well graded.
label | ○ If riprap product is unavailable, alternative material to be approved by designer.
label | Standard / Specification - Project Specification 4.7.1
label | Verifying Document - Delivery Dockets, Lab Reports
label | Frequency - Per Truck
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 2.5 - Grate
label | Acceptance / Conformance Criteria - Webforge grate or similar aproved grate.
label | ○ Fixing detail to be approved.
label | ○ All fixings to be installed as per drawings.
label | Standard / Specification - BBO, Downer
label | Verifying Document - Dockets, PS1
label | Frequency - Prior to delivery
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 2.6 - Handrail
label | Acceptance / Conformance Criteria - Material and design to be approved.
label | ○ Fixing detail to be approved.
label | ○ All fixings to be installed as per drawings.
label | Standard / Specification - BBO, Downer
label | Verifying Document - Dockets, PS1, Record of Approval
label | Frequency - Prior to delivery
label | Verification Activity: By - PE
checkpoint | 2.7 - Concrete Mix
label | Acceptance / Conformance Criteria - Material and design to be approved.
label | ○ Fixing detail to be approved.
label | ○ All fixings to be installed as per drawings.
label | Standard / Specification - BBO, Downer
label | Verifying Document - Dockets, PS1, Record of Approval
label | Frequency - Prior to delivery
label | Verification Activity: By - PE
checkpoint | 2.8 - Reinforcing
label | Acceptance / Conformance Criteria - Mill & test certificates for each batch of reinforcement used to be provided to the Engineer. Unless specifically nominated otherwise on the Drawings, only Grade 500E reinforcement manufactured using the micro-alloyed process is acceptable.
label | Standard / Specification - SS 2142 - 3, PS - 11.6
label | Verifying Document - Mill Certs
label | Frequency - Each Batch
label | Verification Activity: By - PE
section | SECTION 3 – CONSTRUCTION ACTIVITY
checkpoint | 3.1 - Impact Basin Foundation
label | Acceptance / Conformance Criteria - Geotextile laid on base, GAP65/GAP100 compacted to 95% MDD and 20MPa blinding.
label | Standard / Specification - Shop Drawings
label | Verifying Document - IANZ Lab Test Report, Dockets
label | Frequency - Prior to installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.2 - Impact Basin Assembly
label | Acceptance / Conformance Criteria - 1. All Panels & Baffle to be delivered to site seperately and assembled in-situ by the contractor.
label | 2. Erect and Place Panels 3 & 4 to Panel 1 and Panel 2 with temporary supports, aligning projecting Reidbars through associated Drossbach ducts.
label | 3. Tighten nuts equally at downstream end, using a socket wrench to a maximum torque of 200Nm, and fill ducts with grout.
label | 4. Place Baffle and fit to Panels 1 & 2 with Reidbar starter bars fixed to couplers cast into Baffle ends.
label | 5. Tie Base Slab reinforcing to projecting steel from Panels.
label | 6. Fix Panel 5 - lid.
label | 7. Fill swiftlift recessess with Sikagrout 212 or equivalent.
label | 8. Remove temporary supports.
label | 9. Contractor to ensure joints are suitably sealed to Engineer's/ Site specified requirements.
label | Standard / Specification - Shop Drawings - Site Installation Notes
label | Verifying Document - Photos
label | Frequency - Each item
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.3 - Riprap Mix
label | Acceptance / Conformance Criteria - Riprap Mix Materials to be stockpiled separately and mixed in a pre-determined ratio.
label | ○ Soil-riprap will contain 70% riprap mix and 30% topsoil.
label | ○ Voids-filled riprap will contaon 70% riprap mix and 30% GAP40.
label | Standard / Specification - Project Specification 4.7.1
label | Verifying Document - Photographs, Riprap Mixing Inspections
label | Frequency - Each item
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.4 - Reinforcing
label | Acceptance / Conformance Criteria - Reincorcing to be installed as per drawings.
label | Verifying Document - Prepour Inspection, Photos, Dockets, Mill certs
label | Frequency - Each item
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.5 - In-situ Concrete
label | Acceptance / Conformance Criteria - Pre-pour inspection.
label | ○ Slump test +-30mm of slump target.
label | ○ UCS testing with 1x7 days and 3x28 days cylinders.
label | ○ U2 Finish
label | Standard / Specification - Downer Drawings NZS3114, NZS3109
label | Verifying Document - Dockets, Testing Records, Pre-pour record
label | Frequency - Each item
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Bedding Compaction Testing - Pipe Bedding
label | Acceptance / Conformance Criteria - Minimum Compaction 95%(Average 98%) of MDD or concrete fill beneath pipe.
label | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
label | Verifying Document - IANZ Lab Test Report or Concrete Dockets
label | Frequency - One test
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 3.7 - Haunch Zone Compaction Testing - Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
label | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm
label | ○ Minimum Compaction 92% of MDD
label | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
label | Verifying Document - IANZ Lab Test Report
label | Frequency - One test
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 3.8 - Side Zone Compaction Testing - Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
label | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm
label | ○ Minimum Compaction 92% of MDD
label | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
label | Verifying Document - IANZ Lab Test Report
label | Frequency - One test
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 3.9 - Overlay Compaction Testing - Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. One lifts of 300mm to be placed.
label | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm
label | ○ Minimum Compaction 92% of MDD
label | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
label | Verifying Document - IANZ Lab Test Report
label | Frequency - One test
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 3.10 - Drainage
label | Acceptance / Conformance Criteria - Novaflo pipe with filter sock and no-fines concrete behind structure.
label | ○ Riprap surrounding structure as per BBO drawings.
label | Standard / Specification - Downer Drawings
label | Verifying Document - Dockets, Photos
label | Frequency - Each item
label | Verification Activity: Activity -
label | Verification Activity: By - PE
section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 4.1 - Red pen markup
label | Acceptance / Conformance Criteria - Markup to cover all changes.
label | Standard / Specification - Project Specification
label | Verifying Document - Red-pen markup
label | Frequency - Post consutrction
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 4.2 - As-builts
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post consutrction
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature