## ITP Cover Page
[BLANK] Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 129 - Rev B
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 129
Project Number: |  |  | DS1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Pavement Type 6 (Maintenance Track) |  |  |  |  | Revision: | 1000 |  | B
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets:
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification and Appendices.
Quality Specified:
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Draft For Approval | 2023-11-02 |  | Craig Lingard |  | BBO requested requested changes to materials testing requirements and on site testing targets |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Draft for approval | 2023-11-22 |  | Craig Lingard |  | Updated based on BBO comments |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Craig Lingard | [5 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
|  |  |  | Maintenance Track |  |  | [BLANK] Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements
3.01.01 | Construction Pack | Methodology and ITP to be submitted to the Engineer and approved prior to works beginning | Downer | Construction Pack | Submit 10 days prior to commencement of works | HP | ENG
3.01.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
3.01.03 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
3.01.04 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE
3.01.05 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE
3.01.06 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | SUB ACTIVITY
4.01.01 | SIL Maximum Dry Density & Optimum Moisture Content | The GAP65 and GAP40 IANZ Accredited laboratory for Maximum Dry Density & Optimum Moisture Content | PS - 7.2.1 | Lab Reports | 1 test per material type and no less than 1 test every 5,000m³ (in place) | HP | ENG
4.01.02 | GAP Aggregates | PSD, WQI, Crushing resistance, CI, PI, SE. Requirements to RITS 3.1.4.2 GAP aggregates. | PS - 7.2.1 | Lab Reports | 1 test per material type and no less than 1 test every 5,000m³ (in place) | HP | ENG
4.01.03 | Undercut Backill Compliance | Test results for undercut backfill prior to bulk fill commencing, NDM, scala penetrometer, shear vane or cleggs, material dependant. TBC instruction from engineer. Undercut backfill QA to be filed/captured separately from bulk earthworks fill QA. | GWS 2.9.2 | Test Results | Prior to bulk fill commencing | R | SE
SECTION 5 – CONSTRUCTION ACTIVITY
5.01 | Construction
5.01.01 | Subgrade Inspection and Testing | Scalar Pentrometer testing completed at 20m intervals at a depth of 1.0m and proof rolling if deemed pratical as per Geotechnical Works Specification. Failure of either test method will result in a 300mm undercut of the subgrade. Included target of CBR >7% as per DWG notes. | PS 7.1 GWW | Site Record, Scalar Test Results | Prior to Pavement Works | HP | ENG
5.01.02 | Undercut Inspection and Testing | 300mm undercut to be inspected, on cohesive materials shear veins are to be completed with a target of >70KPa. | PS 7.1 GWW | Site Record | Every Undercut and Prior to Undercut Backfill | HP | ENG
5.01.03 | Subgrade Filll Testing | GAP subgrade hard fill shall be tested via back scatter. NDM direct transmission with probe depth of 300mm with granular materials. 98% average MDD, 95% minimium MDD. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. Proof Roll Completed prior to subbase. | GWS 2.9.4 | NDM Test Results / Proof Roll | Every Undercut Prior to Pavement & Proof Roll 100% of layer | I | SE
5.01.04 | Subbase - 200mm GAP65 Compaction Testing | GAP65 subbase shall be tested via back scatter. 95% average and 92% minimium. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number. Proof Roll completed prior to placing basecourse. | BBO | NDM Test Results / Proof Roll | 5 tests per 1000m2 & Proof Roll 100% of layer | I | SE
5.01.05 | Basecourse - 100mm GAP40 Layer Compaction Testing | GAP40 basecourse fill shall be tested by back scatter. 95% average and 92% minimium. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number. Final Proof Roll and inspection. | BBO | NDM Test Results / Proof Roll | 5 tests per 1000m2 & Proof Roll 100% of layer | I | SE
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.01 | Post Construction Activities
8.1.1 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | SE
8.1.2 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level | Downer | Records | Post construction | H | SV
8.1.3 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. | Downer | Redlines | Post construction | H | PE
8.1.4 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | H | PE
8.1.5 | Photos | Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill. | Downer | Photo Records | Post construction | H | SE