## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - AC10 Milling and Filling | itp |  |  |  |  | ITP - AC10 Milling and Filling Rev 0
section | 1.0 Construction
checkpoint | 1.1 - Approved JMF for Asphalt Base or Wearing Course
label | Detail of Activity / Test - JMF reference in here
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
label | Inspection / Test method - Confirm requirements are followed
label | Acceptance Criteria - JMF Validated in accordance with NZTA M/10:2020
label | Record documents (QCP - Quality Control Portal) - Mix Design Report
label | Responsibility - Paving Contractor
label | Project Specific Notes / Instructions - JMF expiry date and validation details in here.
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - A
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Compaction test
label | Detail of Activity / Test - Clegg Test
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - For each site where milling and filling is required
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Project Specific Notes / Instructions -
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.3 - Milling
label | Detail of Activity / Test - Surface strung to ensure milling Depth is achieved
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Before Asphalt placement commences
label | Inspection / Test method - Confirm requirements are followed
label | Acceptance Criteria - Site is suitable for paving
label | Record documents (QCP - Quality Control Portal) - String Sheet
label | Responsibility - Paving Contractor
label | Project Specific Notes / Instructions -
label | Designer -
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.4 - Tack Coat, OR
label | Detail of Activity / Test - Application of Tack Coat
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - For each site where milling and filling is required
label | Inspection / Test method -
label | Acceptance Criteria - Target Between 0.2l/m2 - 0.6l/m2 +/- 0.1l/m2 From Target Application Rate
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Paving Contractor
label | Project Specific Notes / Instructions -
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.5 - Temperature
label | Detail of Activity / Test - Asphalt Delivery temperature
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Every Load on delivery to the Paver Hopper
label | Inspection / Test method - Temperature Probe
label | Acceptance Criteria - Target ≥ 150 deg.C. in the Paver
label | ○ Min. ≥ 130 deg.C in the Paver
label | ○ <130°C to be Rejected
label | Record documents (QCP - Quality Control Portal) - Site Diary
label | Responsibility - Paving Contractor
label | Project Specific Notes / Instructions -
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.6 - Thickness
label | Detail of Activity / Test - Thickness Monitoring
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Continuously
label | Inspection / Test method - Dipping
label | Acceptance Criteria - Target Loose Thickness -0mm / +20%mm
label | Record documents (QCP - Quality Control Portal) - Spray run
label | Responsibility - Paving Contractor
label | Project Specific Notes / Instructions -
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.7 - Post Paving Completion Checks
label | Detail of Activity / Test - Site clear and cleanup
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
label | Inspection / Test method - Visual
label | Acceptance Criteria - Site is cleared of plant (or parked in safe location) cleanup of all waste mix, paper and detritus is complete
label | Record documents (QCP - Quality Control Portal) - Site Diary/Photo
label | Responsibility - Paving Contractor
label | Project Specific Notes / Instructions -
label | Designer -
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.8 - Post Paving Completion Checks
label | Detail of Activity / Test - Pavement Marking (If required)
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
label | Inspection / Test method - Visual
label | Acceptance Criteria - Roadmarking is complete
label | Record documents (QCP - Quality Control Portal) - Site Diary/Photo
label | Responsibility - Paving Contractor
label | Project Specific Notes / Instructions -
label | Designer -
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.9 - Post Paving Completion Checks
label | Detail of Activity / Test - Cold Joint Bandaging (If required)
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
label | Inspection / Test method - Visual
label | Acceptance Criteria - Cold joint bandaging is complete
label | Record documents (QCP - Quality Control Portal) - Site Diary/Photo
label | Responsibility - Paving Contractor
label | Project Specific Notes / Instructions -
label | Designer -
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature