## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-263-RAIL-PSD-Track Formation - Capping Layer
ITP Description: |  | Track Formation - Capping Layer
Project: |  | Progress Street
Discipline (e.g. CIV/STR/RAIL: |  | RAIL
Revision Number: |  | 1
Revision Date: |  | 2025-05-08
ITP created by: |  | Jake Argentaro
ITP approved for use by: |  | Romualdo Magpantay
Special Notes to ConQA Team : |  | ITP to be used at Progress Street Project Only
Inspection & Test Plan - Rail Formation - Capping Material
|  |  | Document Title: ITP-263-RAIL-PSD-Track Formation - Capping Layer | [5 empty] | Revision: | 1
[9 empty] | Date: | 2025-05-08
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Drawing Pack - Rail Track and Civil | MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Metro Engineering Specifications - Earthworks & Formation Specification | L1-CHE-SPE-178 (VERSION 3) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Metro Engineering Specifications - Earthworks & Formation Standard | L1-CHE-STD-029 (VERSION 4) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Australian Standard - Methods of testing soils for engineering purposes | AS 1289 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Capping Material Conformance (1 of 2) | L1-CHE-SPE-178 - Clause 5.12.3. Table 6 | Capping material shall comply with the following grading requirements: • % passing 53.0mm sieve 100% • % passing 37.5mm sieve 100% • % passing 26.5mm sieve 100% • % passing 19.0mm sieve 95-100% • % passing 9.5mm sieve 60-90% • % passing 4.75mm sieve 40-70% • % passing 2.36mm sieve 30-60% • % passing 0.075mm sieve 6-10% Enter: Teambinder Material Approval number | Document Review | Once, for each material type - prior to works commencement | HP | PE/Nominated authority | Material approval in TeamBinder This ITP Signed Off
2.2 | Capping Material Conformance (2 of 2) | L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests | The following tests shall be carried out on samples of the capping layer material: • Soaked CBR - minimum 50% compacted to 98% modified dry density • Liquid Limit - 30% Max • Plastic Limit - 20% Max. • Plasiticity Index - 4-15% • Linear Shrinkage - 4.5% • Dry Density - 2.0t/m³ MIn. Refer to AS 1289 for Tests Enter: Teambinder Material Approval number | Document Review | Once, for each material type - prior to works commencement | HP | PE/Nominated authority | Material approval in TeamBinder This ITP Signed Off
3 | Preliminaries - Procedures & Documentation
3.1 | Pre-Commencement of Fill Works | L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests | The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Responsible Engineer. | Visual Inspection | Prior to commencement of fill works | HP | SE/PE | This ITP Signed Off MTM representative signoff Attach: Site Photos
4 | Pre-Construction Activities
4.1 | Approval of IFC drawings | MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street | Approved IFC Drawings | Document review and approval | Prior to works commencing | HP | SE/PE | This ITP Signed Off
4.2 | Survey Set Out | IFC Drawings | Set out pegs in place and clearly mark out limits of works. | Visual Inspection | Prior to commencement of fill works | HP* | SE/PE/SPE | This ITP Signed Off
5 | Construction Activities
5.1 | Capping Layer Preparation and Installation (1 of 3) | L1-CHE-SPE-178 - Clause 5.12.4. | Capping layer shall be constructed in one layer and compacted to a total compacted thickness of no less than 150mm. | Visual / Measure Review Test | Each Lot | IP | SE/Nominated Authority | Sign ITP Signed Off MTM representative Signoff
5.2 | Capping Layer Preparation and Installation (2 of 3) | L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests | The following tests shall be carried out on samples of the capping layer material: • Soaked CBR - minimum 50% compacted to 98% modified dry density • Liquid Limit - 30% Max • Plastic Limit - 20% Max. • Plasiticity Index - 4-15% • Linear Shrinkage - 4.5% • Dry Density - 2.0t/m³ MIn. | Modified Compaction Test | Each lot | HP | SE/Nominated Authority | This ITP Signed Off Attach: Compaction Test Report
5.3 | Capping Layer Preparation and Installation (3 of 3) | L1-CHE-SPE-178 - Clause 5.12.6. AS 1289 | • 99% Compaction (Modified Compaction Test) | Modified Compaction Test | • 3 tests per 500m³ • atleast 2 tests if < 500m³ | HP | SE/Nominated Authority | This ITP Signed Off Attach: Compaction Test Report
5.4 | Proof rolling | L1-CHE-SPE-178 - Clause 4.6. | Proof roll as per L1-CHE-SPE-178 - Clause 4.6. | Proof roll | Each Lot | HP | SE/Nominated Authority | This ITP Signed Off MTM representative Signoff
6 | Post -Construction Activities
6.1 | Survey Conformance / Capping Layer Finishing and Tolerances | L1-CHE-SPE-178 - Clause 5.12.7. | The finished surface level of capping layer shall: - Be within -25 to +0mm of approved design level - Be within 10mm of algebraic difference of the deviations from the correct level for any two points 20m apart on the centreline - Be within -0mm to +10mm of 3m straightedge laid on final capping layer surface parallel and perpendicular to centreline | Document Review | Each Lot | IP | SE/Surveyor | This ITP Signed Off Attach: Survey Conformance Report
6.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /