## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource ID
checklist | ITP-261-RAIL-PSD-Aluminothermic Welding and Stressing | itp |  |  |  |  | ITP-261-RAIL-PSD-Aluminothermic Welding and Stressing Rev 1
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-261-RAIL-PSD-Aluminothermic Welding and Stressing
label | ITP Description: Aluminothermic Welding and Stressing
label | Discipline (e.g. CIV/STR/RAIL): RAIL
label | Revision Number: 1
label | Revision Date: 8/05/2025
label | ITP created by: Jake Argentaro
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 Drawing Pack - Rail Track and Civil
label | Reference: MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street
label | 1.2 Railway Track Materials – Part 1: Steel Rails
label | Reference: AS 1085.1
label | 1.3 Welding Rail Steels
label | Reference: AS 1085.2
label | 1.4 Flash Butt Welding Specification
label | Reference: A1340
label | 1.5 Hot Works Procedure
label | Reference: A1606
label | 1.6 Welded Track Management Manual Chapter 7 - Requirements For Welding Track Procedure
label | Reference: A4597
label | 1.7 Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure
label | Reference: A4589
label | 1.8 Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure
label | Reference: A4598
label | 1.9 PTDT Form B - Track Certifier Booking Form
label | Reference: A4263
label | 1.10 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure
label | Reference: A4588
label | 1.11 Non-Destructive Hand Testing Of Rail - Track Procedure
label | Reference: A4550
label | 1.12 Track Construction - ITP
label | Reference: ITP-262-RAIL-PSD-Track Construction
section | Preliminaries - Materials
checkpoint | 2.1 Supply of Weld Kits
label | REFERENCE: AS1085.20 Railway Track Material Part 1: Steel Rails
label | ○ A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure
label | ACCEPTANCE CRITERIA: Weld kits supplied are within expiry period and conform to the requirements of applicable standards.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Visual Measure, Document Review
label | FREQUENCY: Upon Delivery
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP Signed Off
label | ○ Attach: Delivery Dockets/Site Photos
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Primary Documentations
label | REFERENCE: A4263 PTDT Form B - Track Certifier Booking Form
label | ○ A1606 Hot Works Procedure
label | ACCEPTANCE CRITERIA: MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street
label | METHOD: Document review and approval
label | FREQUENCY: Prior to works commencing
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Approved PTDT
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.2 Pre-Commencement of Work
label | REFERENCE: ITP, Quality Checklist, SWMS,
label | ACCEPTANCE CRITERIA: All approved by relevant representative.
label | METHOD: Document review and approval
label | FREQUENCY: Once (Prior to Works)
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Approved templates
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.3 Welding Procedures & Quality Documentation
label | REFERENCE: AS1085.20 Railway Track Material Part 1: Steel Rails
label | ○ A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure
label | ACCEPTANCE CRITERIA: WPS (Welding Procedure Specifications), WPQR (Welding Procedure Qualification Records), WQR (Welder Qualification Register)
label | METHOD: Document review and approval
label | FREQUENCY: Once (Prior to Works)
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Pre-Construction Activities
checkpoint | 4.1 Approval of IFC drawings
label | REFERENCE: MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street
label | ACCEPTANCE CRITERIA: Approved IFC Drawings
label | METHOD: Document review and approval
label | FREQUENCY: Prior to works commencing
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Construction Activities
checkpoint | 5.1 Aluminothermic Welding
label | REFERENCE: AS1085.20 Railway Track Material Part 1: Steel Rails
label | ACCEPTANCE CRITERIA: Verify Aluminothermic welding carried out in accordance with AS1085.20
label | METHOD: Visual Inspection
label | FREQUENCY: As Task Progresses
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE, Track Supervisor, Welder
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Site Photos
date | Date Completed:
checkpoint | 5.2 Alignment of Welds
label | REFERENCE: AS1085.20 Railway Track Material Part 1: Steel Rails
label | ○ L2-TRK-PRO-014 Welded Track Management Manual
label | ○ Chapter 11 – Rail Welding Process Section 4.9
label | ACCEPTANCE CRITERIA: Alignment inspection shall be carried out on each weld and record results.
label | ○ Horizontal Alignment ± 0.5mm
label | ○ Vertical Alignment + 0.5mm, - 0.0mm
label | METHOD: Visual Inspection, Test & Measure
label | FREQUENCY: Each Weld
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE, Track Supervisor, Welder
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Inspection Records & site photos
date | Date Completed:
checkpoint | 5.3 Welder's Identification Marks
label | REFERENCE: AS1085.20 Railway Track Material Part 1: Steel Rails
label | ○ A1340 Flash Butt Welding Specification Section 4.3.5
label | ACCEPTANCE CRITERIA: Stamp ID on the field side of the rail head adjacent to the weld.
label | METHOD: Visual Inspection
label | FREQUENCY: Each Weld
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE, Track Supervisor, Welder
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Site Photos
date | Date Completed:
checkpoint | 5.4 Stressing Track Lengths
label | REFERENCE: AS1085.20 Railway Track Material Part 1: Steel Rails
label | ○ A4200 Metro Track - Management Chapter 11
label | ○ Welding Process Procedure Section 5
label | ○ A4598 Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure Table 7.
label | ACCEPTANCE CRITERIA: Ensure track lengths area stressing accordance with Metro Track - Management Chapter 11 Welding Process Procedure (A4200),
label | ○ Minimum Closure Length taken as 13. 7 meters if not Detailed in Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure (A4598) table 7.
label | METHOD: Survey and Visual Inspection
label | FREQUENCY: As Task Progresses
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE, Track Supervisor, Track Surveyor
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Inspection Records & site photos
date | Date Completed:
checkpoint | 5.5 Stress Free Temperature
label | REFERENCE: A4589 Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure Section 5.1.2
label | ACCEPTANCE CRITERIA: The design SFT is 38°C and all stressing is to be carried out to this design SFT.
label | METHOD: Test and Measure
label | FREQUENCY: Each Weld
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE, Track Supervisor, Welder
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Inspection Records & site photos
date | Date Completed:
checkpoint | 5.6 Weld Ultrasonic Testing
label | REFERENCE: A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure
label | ○ AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
label | ○ A4589 Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure Section 6.20
label | ACCEPTANCE CRITERIA: Ultrasonic testing to be carried out within 14 days and in accordance with A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure
label | ○ The cross section of the area of the head and web shall be completely scanned;
label | — The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
label | — Welds shall be scanned to both directions.
label | METHOD: Inspection / Test
label | FREQUENCY: Each Weld within 14 days
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE, Track Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Ultrasonic Weld Test Results
date | Date Completed:
section | Post-Construction Activities
checkpoint | 6.1 Rail Stressing Records
label | REFERENCE: A4589 Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure Section 6.21
label | ACCEPTANCE CRITERIA: Complete Stressing Recorded documentation
label | METHOD: Measure and Document Review
label | FREQUENCY: Each Weld
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE, Track Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Rail Stressing Documentation
date | Date Completed:
checkpoint | 6.2 Track Certification
label | REFERENCE: MTMF020000-1 – Track Form A T
label | ○ MTMF020000-2 – Track Form B
label | ○ A4549: MAINTAINING TRACK INTEGRITY PROCEDURE
label | ACCEPTANCE CRITERIA: - Track Geometry Conformance Certificate
label | - Track System and Component
label | METHOD: Visual Measure, Document Review
label | FREQUENCY: Once (upon completion of occupation works)
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier), Project Cert III Rail Infrastructure
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Relevant Conformance Certs as per acceptance criteria
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 6.3 As-Built Drawings
label | REFERENCE: As-Built Drawing Management Procedure (A8197)
label | ACCEPTANCE CRITERIA: IFC drawings (including cables, patches and labels) are marked up with redlines and supplied the Project and MTM.
label | METHOD: Document review and approval
label | FREQUENCY: Once
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Redline mark-up drawings
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | REFERENCE: MTM Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | ITP-262-RAIL-PSD-Track Construction | itp |  |  |  |  | ITP-262-RAIL-PSD-Track Construction Rev 1
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-262-RAIL-PSD-Track Construction
label | ITP Description: Track Construction
label | Discipline (e.g. CIV/STR/RAIL): RAIL
label | Revision Number: 1
label | Revision Date: 8/05/2025
label | ITP created by: Jake Argentaro
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 Drawing Pack - Rail Track and Civil
label | Reference: MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street
label | 1.2 Railway Track Materials – Part 1: Steel Rails
label | Reference: AS 1085.1
label | 1.3 Welding Rail Steels
label | Reference: AS 1085.2
label | 1.4 Concrete Sleepers Specification
label | Reference: A1504
label | 1.5 Track Geometry Tolerances
label | Reference: A1303
label | 1.6 Ballast Supply Specification
label | Reference: A1341
label | 1.7 Transit Space Clearances
label | Reference: A1536
label | 1.8 Track Design And Construction
label | Reference: A1545
label | 1.9 Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure
label | Reference: A4598
label | 1.10 Welded Track Management Manual Chapter 7 - Requirements For Welding Track Procedure
label | Reference: A4597
label | 1.11 Aluminothermic Weld and Stressing - Inspection and Test Plan Template
label | Reference: A7949
label | 1.12 PTC Heavy Rail Track Construction Standards
label | Reference: N/A - no document reference number
label | 1.13 PTC Heavy Rail Track Construction Standards Drawing
label | Reference: F598
label | 1.14 Earthworks & Formation Specification
label | Reference: L1-CHE-SPE-178 (VERSION 3)
label | 1.15 Earthworks & Formation Standard
label | Reference: L1-CHE-STD-029 (VERSION 4)
label | 1.16 Aluminothermic Welding and Stressing ITP
label | Reference: ITP-261-RAIL-PSD-Aluminothermic Welding and Stressing
section | Preliminaries - Materials
checkpoint | 2.1 Supply of 60mm Ballast
label | REFERENCE: A1341 Ballast Supply Specification Section 4.2.2
label | ACCEPTANCE CRITERIA: The Ballast supplied must be tested and meet requirements in MTM standard Ballast Supply Specification (A1341) Table 3
textbox | Enter: Teambinder Material Approval number
label | METHOD: Visual Measure, Document Review
label | FREQUENCY: Prior to works commencing
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP Signed Off, Delivery Dockets
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 Supply of LPCS Sleepers
label | REFERENCE: A1303 Track Geometry Tolerances Section 8.1.13
label | ○ A1504 Concrete Sleepers Specification Table 2
label | ACCEPTANCE CRITERIA: Sleepers supplied must be type approved by MTM and in accordance with the relevant standard.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Visual Measure, Document Review
label | FREQUENCY: Prior to works commencing
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP Signed Off, Delivery Dockets
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.3 Supply of 53kg/m Rail
label | REFERENCE: One Steel Certificate, Flashbutt Weld Reports
label | ACCEPTANCE CRITERIA: AS 1085.1 Railway Track Materials – Part 1: Steel Rails
label | ○ AS 1085.20 Welding Rail Steels Section 2
textbox | Enter: Teambinder Material Approval number
label | METHOD: Visual Measure, Document Review
label | FREQUENCY: Prior to works commencing
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP Signed Off, Delivery Dockets
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.4 Supply of: Track Jewellery, Geofabric
label | ACCEPTANCE CRITERIA: To be type approved by MTM.
label | ○ To be inspected upon delivery to have no damage or rust.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Visual Measure
label | FREQUENCY: Prior to works commencing
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP Signed Off, Delivery Dockets
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Primary Documentations
label | REFERENCE: A4263 PTDT Form B - Track Certifier Booking Form
label | ○ A1606 Hot Works Procedure
label | ACCEPTANCE CRITERIA: Approved PTDT
label | METHOD: Document review and approval
label | FREQUENCY: Prior to works commencing
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Approved PTDT
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.2 Pre-Commencement of Work
label | REFERENCE: ITP, Quality Checklist, SWMS
label | ACCEPTANCE CRITERIA: All approved by relevant representative.
label | METHOD: Document review and approval
label | FREQUENCY: Once (Prior to Works)
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Approved Templates
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Pre-Construction Activities
checkpoint | 4.1 Approval of IFC drawings
label | REFERENCE: MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street
label | ACCEPTANCE CRITERIA: Approved IFC Drawings
label | METHOD: Document review and approval
label | FREQUENCY: Prior to works commencing
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Construction Activities
checkpoint | 5.1 Survey Track Alignment
label | REFERENCE: IFC Drawings: MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street
label | ACCEPTANCE CRITERIA: Correct line and level established for placement of Sleepers and Ballast as per IFC.
label | METHOD: Visual Inspection, Survey / Measure
label | FREQUENCY: As Task Progresses
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE, Track Supervisor, Track Surveyor
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Survey Records & Photos on site
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.2 Lay Bottom Ballast
label | REFERENCE: PTC Heavy Rail Track Construction Standards Drawing F598
label | ACCEPTANCE CRITERIA: Ballast to be placed in 150mm max layers. Bottom Ballast to be left 20-40mm below final design level – Tolerance (under sleeper) -0mm, +25mm
label | METHOD: Visual Inspection, Survey / Measure
label | FREQUENCY: As Task Progresses
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE, Track Supervisor, Track Surveyor
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Survey Records & Photos on site
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.3 Place Sleepers
label | REFERENCE: A1303 Track Geometry Tolerances Table 1
label | ○ A4597 Welded Track Management Manual Chapter 7 - Requirements For Welding Track Procedure Section 4.8
label | ACCEPTANCE CRITERIA: Sleepers Square at nominal 685mm ±25mm.
label | ○ 2 concrete sleepers either side of welds
label | ○ Up to 50mm variation in spacing to allow for clearance around a thermit weld (only over two sleepers)
label | METHOD: Visual Inspection, Survey / Measure
label | FREQUENCY: As Task Progresses
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE, Track Supervisor, Track Surveyor
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Survey Records & Photos on site
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.4 Rail Installation
label | REFERENCE: A4598 Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure Section 4.1.1, 4.1.2 and Table 7
label | ○ Aluminothermic Weld and Stressing - Inspection and Test Plan
label | ACCEPTANCE CRITERIA: Plain line Aluminothermic welds square and centrally located in beds.
label | ○ Alignment inspection shall be carried out on each weld and record results.
label | ○ Horizontal Alignment ± 0.5mm
label | ○ Vertical Alignment + 0.5mm, - 0.0mm
label | ○ Rail ends identified & clearly marked for visibility of joint.
label | ○ All fastenings must be fully applied.
label | ○ Minimum Closure Length taken as 13. 7meters if not Detailed in A4598 table 7.
label | ○ Complete Aluminothermic Weld and Stressing - Refer to Aluminothermic Weld and Stressing ITP
label | METHOD: Visual Inspection, Measure
label | FREQUENCY: As Task Progresses
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE, Track Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Photos on site
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.5 Sleeper Alignment and Rail Jewellery
label | REFERENCE: PTC Heavy Rail Track Construction Standards Drawing F598
label | ACCEPTANCE CRITERIA: Sleeper alignment complies to square with centreline for tangent track.
label | ○ Rail jewellery secure and installed correctly
label | METHOD: Visual Inspection
label | FREQUENCY: As Task Progresses
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE, Track Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Photos on site
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.6 Tamp New Track
label | REFERENCE: IFC Drawings: MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street
label | ○ A1536 Transit Space Clearances Figure 1 and section 9.2
label | ACCEPTANCE CRITERIA: Tamp track as per IFC design and within below tolerances:
label | — Gauge +3 / -3
label | — Gauge Variation in 2m 4
label | — Line (10m Chord) +4 / -4
label | — Twist (3.5m Chord) +2 / -2
label | — Top (10m Chord) +5 / -5
label | — Cant +5 / -5
label | — General Alignment +15/ -15
label | ○ A minimum horizontal clearance of 3.0m from track centreline to structure.
label | ○ Height and Stagger readings of overhead wire to ensure minimum clearance of 4.61m is not breached
label | METHOD: Visual Inspection, Tamping Geometry Recording, Measure / Survey Pickup
label | FREQUENCY: Once (Post Tamping)
label | CATEGORY: HP
label | RESPONSIBILITY: Tamping Operator, Track Surveyor, Overhead Engineer, Track Supervisor, SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Photos on site
label | ○ Tamping Geometry Report, Survey Records
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.7 Regulate and Check Ballast profile
label | REFERENCE: A1537 Earthworks And Formation Standard Section 9
label | ○ PTC Heavy Rail Track Construction Standards Drawing F598
label | ACCEPTANCE CRITERIA: As per IFC drawings; 405mm from sleeper end tangent track
label | ○ 1 in 1.5 steepest shoulder slope.
label | METHOD: Visual Inspection, Measure
label | FREQUENCY: Once
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE, Track Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Photos on site
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Post-Construction Activities
checkpoint | 6.1 As-Built Survey
label | REFERENCE: As-Built Drawing Management Procedure (A8197)
label | ACCEPTANCE CRITERIA: Track survey to be carried out at completion of works. Track levels compared to IFC and ensure tolerances are met
label | METHOD: Survey and Review
label | FREQUENCY: Once
label | CATEGORY: HP
label | RESPONSIBILITY: Track Surveyor, SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: As-Built survey report
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 6.2 Track Certification
label | REFERENCE: MTMF020000-1 – Track Form A T
label | ○ MTMF020000-2 – Track Form B
label | ○ A4549: MAINTAINING TRACK INTEGRITY PROCEDURE
label | ACCEPTANCE CRITERIA: - Track Geometry Conformance Certificate - Track System and Component
label | METHOD: Visual Measure, Document Review
label | FREQUENCY: Once (upon completion of occupation works)
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier), Project Cert III Rail Infrastructure
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Relevant Conformance Certs as per acceptance criteria
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 6.3 As-Built Drawings
label | REFERENCE: As-Built Drawing Management Procedure (A8197)
label | ACCEPTANCE CRITERIA: IFC drawings (including cables, patches and labels) are marked up with redlines if applicable and supplied the Project and MTM.
label | METHOD: Document review and approval
label | FREQUENCY: Once
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Redline mark-up drawings
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | REFERENCE: MTM Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | ITP-263-RAIL-PSD-Track Formation - Capping Layer | itp |  |  |  |  | ITP-263-RAIL-PSD-Track Formation - Capping Layer Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-263-RAIL-PSD-Track Formation - Capping Layer
label | ITP Description: Track Formation - Capping Layer
label | Discipline (e.g. CIV/STR/RAIL): RAIL
label | Revision Number: 1
label | Revision Date: 8/05/2025
label | ITP created by: Jake Argentaro
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 Drawing Pack - Rail Track and Civil
label | Reference: MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street
label | 1.2 Metro Engineering Specifications - Earthworks & Formation Specification
label | Reference: L1-CHE-SPE-178 (VERSION 3)
label | 1.3 Metro Engineering Specifications - Earthworks & Formation Standard
label | Reference: L1-CHE-STD-029 (VERSION 4)
label | 1.4 Australian Standard - Methods of testing soils for engineering purposes
label | Reference: AS 1289
section | Preliminaries - Materials
checkpoint | 2.1 Capping Material Conformance (1 of 2)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.12.3. Table 6
label | ACCEPTANCE CRITERIA: Capping material shall comply with the following grading requirements:
label | ○ % passing 53.0mm sieve 100%
label | ○ % passing 37.5mm sieve 100%
label | ○ % passing 26.5mm sieve 100%
label | ○ % passing 19.0mm sieve 95-100%
label | ○ % passing 9.5mm sieve 60-90%
label | ○ % passing 4.75mm sieve 40-70%
label | ○ % passing 2.36mm sieve 30-60%
label | ○ % passing 0.075mm sieve 6-10%
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, for each material type - prior to works commencement
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 Capping Material Conformance (2 of 2)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.12.5. Table 7, AS1289 Tests
label | ACCEPTANCE CRITERIA: The following tests shall be carried out on samples of the capping layer material:
label | — Soaked CBR - minimum 50% compacted to 98% modified dry density
label | — Liquid Limit - 30% Max
label | — Plastic Limit - 20% Max.
label | — Plasiticity Index - 4-15%
label | — Linear Shrinkage - 4.5%
label | — Dry Density - 2.0t/m³ MIn.
label | ○ Refer to AS 1289 for Tests
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, for each material type - prior to works commencement
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Pre-Commencement of Fill Works
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.12.5. Table 7, AS1289 Tests
label | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Responsible Engineer.
label | METHOD: Visual Inspection
label | FREQUENCY: Prior to commencement of fill works
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off, MTM representative signoff
label | ○ Attach: Site Photos
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Pre-Construction Activities
checkpoint | 4.1 Approval of IFC drawings
label | REFERENCE: MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street
label | ACCEPTANCE CRITERIA: Approved IFC Drawings
label | METHOD: Document review and approval
label | FREQUENCY: Prior to works commencing
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 4.2 Survey Set Out
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Set out pegs in place and clearly mark out limits of works.
label | METHOD: Visual Inspection
label | FREQUENCY: Prior to commencement of fill works
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Capping Layer Preparation and Installation (1 of 3)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.12.4.
label | ACCEPTANCE CRITERIA: Capping layer shall be constructed in one layer and compacted to a total compacted thickness of no less than 150mm.
label | METHOD: Visual / Measure, Review Test
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Nominated Authority
label | VERIFYING DOCUMENTS: Sign ITP Signed Off, MTM representative Signoff
date | Date Completed:
checkpoint | 5.2 Capping Layer Preparation and Installation (2 of 3)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.12.5. Table 7, AS1289 Tests
label | ACCEPTANCE CRITERIA: The following tests shall be carried out on samples of the capping layer material:
label | ○ Soaked CBR - minimum 50% compacted to 98% modified dry density
label | ○ Liquid Limit - 30% Max
label | ○ Plastic Limit - 20% Max.
label | ○ Plasiticity Index - 4-15%
label | ○ Linear Shrinkage - 4.5%
label | ○ Dry Density - 2.0t/m³ MIn.
label | METHOD: Modified Compaction Test
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/Nominated Authority
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Compaction Test Report
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.3 Capping Layer Preparation and Installation (3 of 3)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.12.6. AS 1289
label | ACCEPTANCE CRITERIA: 99% Compaction (Modified Compaction Test)
label | METHOD: Modified Compaction Test
label | FREQUENCY: 3 tests per 500m³
label | ○ at least 2 tests if < 500m³
label | CATEGORY: HP
label | RESPONSIBILITY: SE/Nominated Authority
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Compaction Test Report
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.4 Proof rolling
label | REFERENCE: L1-CHE-SPE-178 - Clause 4.6.
label | ACCEPTANCE CRITERIA: Proof roll as per L1-CHE-SPE-178 - Clause 4.6.
label | METHOD: Proof roll
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/Nominated Authority
label | VERIFYING DOCUMENTS: This ITP Signed Off, MTM representative Signoff
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Post -Construction Activities
checkpoint | 6.1 Survey Conformance / Capping Layer Finishing and Tolerances
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.12.7.
label | ACCEPTANCE CRITERIA: The finished surface level of capping layer shall:
label | — Be within -25 to +0mm of approved design level
label | — Be within 10mm of algebraic difference of the deviations from the correct level for any two points 20m apart on the centreline
label | — Be within -0mm to +10mm of 3m straightedge laid on final capping layer surface parallel and perpendicular to centreline
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Surveyor
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Survey Conformance Report
date | Date Completed:
checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | ITP-264-RAIL-PSD-Track Formation - General Fill | itp |  |  |  |  | ITP-264-RAIL-PSD-Track Formation - General Fill Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-264-RAIL-PSD-Track Formation - General Fill
label | ITP Description: Track Formation - General Fill
label | Discipline (e.g. CIV/STR/RAIL): RAIL
label | Revision Number: 1
label | Revision Date: 8/05/2025
label | ITP created by: Jake Argentaro
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 Drawing Pack - Rail Track and Civil
label | Reference: MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street
label | 1.2 Metro Engineering Specifications - Earthworks & Formation Specification
label | Reference: L1-CHE-SPE-178 (VERSION 3)
label | 1.3 Metro Engineering Specifications - Earthworks & Formation Standard
label | Reference: L1-CHE-STD-029 (VERSION 4)
label | 1.4 Australian Standard - Methods of testing soils for engineering purposes
label | Reference: AS 1289
section | Preliminaries - Materials
checkpoint | 2.1 General Fill Material Conformance (1 of 2)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.10.1.
label | ○ Australian Standard - AS1289
label | ACCEPTANCE CRITERIA: General Fill shall consist of suitable material that shall be compacted to a minimum characteristic value of density ratio 98%
label | ○ Refer to AS1289 for tests
textbox | Enter: Teambinder Material Approval number
label | METHOD: Visual, Review Test
label | FREQUENCY: Once, for each material type - prior to works commencement
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 General Fill Material Conformance (2 of 2)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.10.4.1. Table 1, AS 1289
label | ACCEPTANCE CRITERIA: General fill shall comply with the criteria listed in
label | ○ Table 1 (L1-CHE-SPE-178 - Clause 5.10.4.1.):
label | — Soaked CBR - 3% min nominal
label | — Plasticity Index 9-20%
label | — Dispersion (pin hole dispersity) - ND1/ND2
label | — Dispersion (Emerson class number of soil) - not to be class 1 or 2
label | — Collapse strain - to be agreed by MTM geotechnical engineer
label | — Free swell index - 2.5% max.
label | — Soil soluble salt content - 3%
label | — Organic content (dry weight) - 2% max.
label | ○ Refer to AS 1289 for Tests
textbox | Enter: Teambinder Material Approval number
label | METHOD: Visual, Review Test
label | FREQUENCY: Once, for each material type - prior to works commencement
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Pre-Commencement of Fill Works
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.12.5. Table 7
label | ○ AS1289 Tests
label | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Responsible Engineer.
label | METHOD: Visual Inspection
label | FREQUENCY: Prior to commencement of fill works
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off, MTM representative signoff
label | ○ Attach: Site Photos
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Pre-Construction Activities
checkpoint | 4.1 Approval of IFC drawings
label | REFERENCE: MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street
label | ACCEPTANCE CRITERIA: Approved IFC Drawings
label | METHOD: Document review and approval
label | FREQUENCY: Prior to works commencing
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 4.2 Survey Set Out
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Set out pegs in place and clearly mark out limits of works.
label | METHOD: Visual Inspection
label | FREQUENCY: Prior to commencement of fill works
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 General Fill Preparation and Installation - For track constructed on embankment (1 of 2)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.10.3.1.
label | ○ Australian Standard - AS1289
label | ○ IFC Drawings.
label | ACCEPTANCE CRITERIA: Any surface on which fills are to be constructed shall be proof rolled.
label | ○ All layers of general fill material shall be compacted to a minimum characteristic value of density ratio of 98% (Standard Compaction)
label | ○ Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose.
label | — One test per 1000m³
label | — Volume < 1000m³ atleast one set of tests shall be carried out
label | METHOD: Standard Compaction
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Compaction Test Report
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.2 General Fill Preparation and Installation - For track constructed on embankment (2 of 2)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.10.3.1.
label | ○ Australian Standard - AS1289
label | ○ IFC Drawings.
label | ACCEPTANCE CRITERIA: General fill shall comply with the criteria listed in
label | ○ Table 1 (L1-CHE-SPE-178 - Clause 5.10.4.1.):
label | — Soaked CBR - 3% min nominal
label | — Plasticity Index 9-20%
label | — Dispersion (pin hole dispersity) - ND1/ND2
label | — Dispersion (Emerson class number of soil) - not to be class 1 or 2
label | — Collapse strain - to be agreed by MTM geotechnical engineer
label | — Free swell index - 2.5% max.
label | — Soil soluble salt content - 3%
label | — Organic content (dry weight) - 2% max.
label | ○ Refer to AS 1289 for Tests
label | — One test per 1000m³
label | — Volume < 1000m³ atleast one set of tests shall be carried out
label | METHOD: Standard Compaction
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Test Report
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.3 Proof rolling
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.4.1. and Clause 5.10.3.1.
label | ACCEPTANCE CRITERIA: Proof roll as per L1-CHE-SPE-178 - Clause 5.10.3.1.
label | METHOD: Proof roll
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off, MTM representative Signoff
label | ○ Attach: Site Photos
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Post-Construction Activities
checkpoint | 6.1 General Fill Finishing and Tolerances - For track constructed on embankment / Survey Conformance
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.10.6.1.
label | ACCEPTANCE CRITERIA: General fill on embankments shall be installed within +/- 40mm of approved design surface level
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Surveyor
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Survey Conformance Report
date | Date Completed:
checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | ITP-265-RAIL-PSD-Track Formation - Structural Fill | itp |  |  |  |  | ITP-265-RAIL-PSD-Track Formation - Structural Fill Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-265-RAIL-PSD-Track Formation - Structural Fill
label | ITP Description: Track Formation - Structural Fill
label | Discipline (e.g. CIV/STR/RAIL): RAIL
label | Revision Number: 1
label | Revision Date: 8/05/2025
label | ITP created by: Jake Argentaro
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 Drawing Pack - Rail Track and Civil
label | Reference: MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street
label | 1.2 Metro Engineering Specifications - Earthworks & Formation Specification
label | Reference: L1-CHE-SPE-178 (VERSION 3)
label | 1.3 Metro Engineering Specifications - Earthworks & Formation Standard
label | Reference: L1-CHE-STD-029 (VERSION 4)
label | 1.4 Australian Standard - Methods of testing soils for engineering purposes
label | Reference: AS 1289
section | Preliminaries - Materials
checkpoint | 2.1 Structural Fill Material Conformance (1 of 2)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.11.2.1. Table 4
label | ACCEPTANCE CRITERIA: Structural fill materias shall have the following properties:
label | ○ % passing 53.0mm sieve 80-100%
label | ○ % passing 2.36mm sieve 15-100%
label | ○ % passing 0.425mm sieve 0-70%
label | ○ % passing0.075mm sieve 0-30%
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, for each material type - prior to works commencement
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 Structural Fill Material Conformance (2 of 2)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.11.4.1. Table 5
label | ○ AS 1289
label | ACCEPTANCE CRITERIA: Structural fill must comply with the following requirements:
label | — Soaked CBR 8% min compacted to 100%
label | ○ Standard dry density
label | — Liquid Limit 40% Max.
label | — Plasticity Index 20% Max.
label | — Dry Density 1.8t/m³ Min.
label | ○ Refer to AS 1289 for Tests
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, for each material type - prior to works commencement
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Pre-Commencement of Fill Works
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.12.5. Table 7
label | ○ AS1289 Tests
label | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Responsible Engineer.
label | METHOD: Visual Inspection
label | FREQUENCY: Prior to commencement of fill works
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off, MTM representative signoff
label | ○ Attach: Site Photos
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Pre-Construction Activities
checkpoint | 4.1 Approval of IFC drawings
label | REFERENCE: MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street
label | ACCEPTANCE CRITERIA: Approved IFC Drawings
label | METHOD: Document review and approval
label | FREQUENCY: Prior to works commencing
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 4.2 Survey Set Out
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Set out pegs in place and clearly mark out limits of works.
label | METHOD: Visual Inspection
label | FREQUENCY: Prior to commencement of fill works
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Structural Fill Preparation and Installation - (1 of 3)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.11.3.
label | ○ L1-CHE-STD-029 - Clause 8.1.
label | ACCEPTANCE CRITERIA: Where Rail Subgrade CBR < 3%:
label | — Required minimum depth of structural fill is 1000mm
label | — 8% min CBR, Compacted to 100% (Standard Compaction Test)
label | ○ Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose.
label | ○ 3 tests per 1000m³
label | ○ 3 tests if 500-1000m³
label | ○ At least 2 tests if < 500m³
label | METHOD: Standard Compaction Test
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Compaction Test Report
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.2 Structural Fill Preparation and Installation - (2 of 3)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.11.3.
label | ○ L1-CHE-STD-029 - Clause 8.1.
label | ACCEPTANCE CRITERIA: Where Rail Subgrade 3% < CBR < 8%:
label | — Required minimum depth of structural fill is 500mm
label | — 8% min CBR, Compacted to 100% (Standard Compaction Test)
label | ○ Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose.
label | ○ 3 tests per 1000m³
label | ○ 3 tests if 500-1000m³
label | ○ At least 2 tests if < 500m³
label | METHOD: Standard Compaction Test
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Compaction Test Report
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.3 Structural Fill Preparation and Installation - (3 of 3)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.11.3.
label | ○ L1-CHE-STD-029 - Clause 8.1.
label | ACCEPTANCE CRITERIA: Where Rail Subgrade CBR > 8%:
label | — Structural fill can directly be placed onto subgrade and compacted to 100%
label | — 8% min CBR, Compacted to 100% (Standard Compaction Test)
label | ○ Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose.
label | ○ 3 tests per 1000m³
label | ○ 3 tests if 500-1000m³
label | ○ At least 2 tests if < 500m³
label | METHOD: Standard Compaction Test
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Compaction Test Report
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.4 Proof rolling
label | REFERENCE: L1-CHE-SPE-178 - Clause 4.6.
label | ACCEPTANCE CRITERIA: Proof roll as per L1-CHE-SPE-178 - Clause 4.6.
label | METHOD: Proof roll
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/Nominated Authority
label | VERIFYING DOCUMENTS: This ITP Signed Off, MTM representative Signoff
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Post -Construction Activities
checkpoint | 6.1 Structural Fill Finishing and Tolerances - For track constructed on embankment / Survey Conformance
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.11.6.
label | ACCEPTANCE CRITERIA: Structural fill shall be within +0 to -35mm of approved design surface level
label | ○ Structural fill shall be within +0 to +50mm of 3m straightedge laid on final structural surface parallel and perpendicular to centreline
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Surveyor
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Survey Conformance Report
date | Date Completed:
checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | ITP-266-RAIL-PSD-Track Formation - Subgrade | itp |  |  |  |  | ITP-266-RAIL-PSD-Track Formation - Subgrade Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-266-RAIL-PSD-Track Formation - Subgrade
label | ITP Description: Track Formation - Subgrade
label | Discipline (e.g. CIV/STR/RAIL): RAIL
label | Revision Number: 1
label | Revision Date: 8/05/2025
label | ITP created by: Jake Argentaro
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 Drawing Pack - Rail Track and Civil
label | Reference: MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street
label | 1.2 Metro Engineering Specifications - Earthworks & Formation Specification
label | Reference: L1-CHE-SPE-178 (VERSION 3)
label | 1.3 Metro Engineering Specifications - Earthworks & Formation Standard
label | Reference: L1-CHE-STD-029 (VERSION 4)
label | 1.4 Australian Standard - Methods of testing soils for engineering purposes
label | Reference: AS 1289
section | Preliminaries - Materials
checkpoint | 2.1 Subgrade Description
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.5.1. Table 1
label | ○ AS1289 Tests 5.1.1 & 5.3.1
label | ACCEPTANCE CRITERIA: Subgrade shall comply with the following criteria:
label | ○ Soaked CBR - 3% min nominal
label | ○ Plasticity Index 9-20%
label | ○ Dispersion (pin hole dispersity) - ND1/ND2
label | ○ Dispersion (Emerson class number of soil) - not to be class 1 or 2
label | ○ Collapse strain - to be agreed by MTM geotechnical engineer
label | ○ Free swell index - 2.5% max.
label | ○ Soil soluble salt content - 3%
label | ○ Organic content (dry weight) - 2% max.
label | ○ Refer to AS 1289 for Tests
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, for each material type - prior to works commencement
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Pre-Commencement of Fill Works
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.12.5. Table 7
label | ○ AS1289 Tests
label | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Responsible Engineer.
label | METHOD: Visual Inspection
label | FREQUENCY: Prior to commencement of fill works
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off, MTM representative signoff
label | ○ Attach: Site Photos
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Pre-Construction Activities
checkpoint | 4.1 Approval of IFC drawings
label | REFERENCE: MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street
label | ACCEPTANCE CRITERIA: Approved IFC Drawings
label | METHOD: Document review and approval
label | FREQUENCY: Prior to works commencing
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 4.2 Survey Set Out
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Set out pegs in place and clearly mark out limits of works.
label | METHOD: Visual Inspection
label | FREQUENCY: Prior to commencement of fill works
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Subgrade Preparation and Installation - For track constructed on embankment (1 of 3)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.4.
label | ACCEPTANCE CRITERIA: If min CBR < 3%:
label | — Install min 1m structural fill
label | If general fill is to be placed directly over subgrade:
label | — Subgrade to be compacted to 98%
label | If structural fill is to be placed directly over subgrade:
label | — Subgrade shall be scarified to 200mm and re-compacted to 100%
label | ○ One test per 1000m³
label | ○ Volume < 1000m³ atleast one set of tests shall be carried out
label | METHOD: Standard Compaction Test
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Compaction Test Report
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.2 Subgrade Preparation and Installation - For track constructed on embankment (2 of 3)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.4.
label | ACCEPTANCE CRITERIA: If min 3%< CBR < 8%:
label | If general fill is to be placed directly over subgrade
label | — Subgrade to be compacted to 98% (Standard Compaction Test)
label | If structural fill is to be placed directly over subgrade
label | — Subgrade shall be scarified to 200mm and re-compacted to 100% (Standard Compaction Test)
label | ○ One test per 1000m³
label | ○ Volume < 1000m³ atleast one set of tests shall be carried out
label | METHOD: Standard Compaction Test
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Compaction Test Report
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.3 Subgrade Preparation and Installation - For track constructed on embankment (3 of 3)
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.4.
label | ACCEPTANCE CRITERIA: If min CBR > 8%
label | — Excavation can be stopped to suit capping layer or at top of section with CBR > 8%
label | — Subgrade shall be scarified to 200mm and re-compacted to 100% (Standard Compaction Test)
label | ○ One test per 1000m³
label | ○ Volume < 1000m³ atleast one set of tests shall be carried out
label | METHOD: Standard Compaction Test
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Compaction Test Report
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.4 Proof rolling
label | REFERENCE: L1-CHE-SPE-178 - Clause 4.6. and 5.4.1.
label | ACCEPTANCE CRITERIA: Proof roll as per L1-CHE-SPE-178 - Clause 4.6.
label | METHOD: Proof roll
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP Signed Off, MTM representative Signoff
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Subgrade Finishing and Tolerances
checkpoint | 6.1 Subgrade Finishing and Tolerances - For track constructed on embankment / Survey Conformance
label | REFERENCE: L1-CHE-SPE-178 - Clause 5.7.
label | ACCEPTANCE CRITERIA: Subgrade on embankments shall be installed within +/- 40mm of approved design surface level
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Surveyor
label | VERIFYING DOCUMENTS: This ITP Signed Off
label | ○ Attach: Survey Conformance Report
date | Date Completed:
checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP