## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
59638ccc-eb0c-41f3-a93b-a0baab414e94 | checklist | ITP001 - CG - Clear & Grub - Rev0 | itp | ITP001 - CG - Clear & Grub
ea9d918a-943e-418b-922f-7430418c3920 | section | Inspection and Test Plan Details
bce562da-c328-431c-813c-b59b5a96e1c3 | checkpoint | 01 - Survey Set Out
ac09d8dc-759a-587c-ace6-c8bf79ff79dc | note | Work By - Contractor
f65d494a-a381-5c3f-b9e3-86611dac42c0 | note | Standard / Spec - Technical Specification
5fa583d9-a92e-5c6f-89b1-bc11656e946f | note | Criteria - The contractor shall be responsible for engaging a licensed surveyor of Australia approved by the Superintendent to set out all works in accordance with the design drawings prior to the commencement of the works
4f4aae7b-7204-5942-8ec8-bfbaa831e766 | note | Frequency - Prior to commencement
abcd17bc-bf23-5614-8909-7436ace0b1f2 | note | Record - ITP Verification Checklist/Site Survey
c910104f-cb18-58a5-bab1-5377f39cc86c | note | Contractor: Resp - RSA
682c971a-360f-5fe2-b4d6-9110c1204be5 | note | Contractor: Type - WP
65270ee4-6ec6-5049-89ed-bf68247035e5 | note | Client: Resp - Senex
a015dd71-0be4-56a1-8630-3bab4c86c763 | note | Client: Type - WP
852e841a-cc8b-4c07-9b05-6d5dd05b6c65 | checkpoint | 02 - Site Services
6ea77bac-f567-5eaa-84b0-1c3ff104be12 | note | Work By - Contractor
6b92d610-a991-50e6-a10d-d97da3ad97b4 | note | Standard / Spec - Technical Specification
28fd8c88-9601-58d9-9ca1-c20043773721 | note | Criteria - Contractor shall take reasonable steps to locate all existing service on the site. Where existing services are identified they shall be clearly marked for the duration of the works.
d7affaa5-7e27-56e5-836e-72670eacb648 | note | Frequency - Prior to commencement
104c0bf5-19de-5755-a094-93022b01e537 | note | Record - Site general layout drawing
5978108f-fd9e-58c9-9d6b-842ebce00e48 | note | Contractor: Resp - RSA
627e231e-cd1a-5a50-9e52-c27ae8a1d60d | note | Contractor: Type - HP
5ff1886e-73a0-5c99-b8d7-a10d45c42848 | note | Client: Resp - Senex
44003065-8e21-5c1b-b3c6-f7528116cf3e | note | Client: Type - Hold Point
dc255fb8-f91e-4334-bd39-fbd5d1cf9abc | signoff | HOLD POINT
3ed1e238-98d2-4573-b436-3283ada11c64 | checkpoint | 03 - Lot Identification
7fd17753-6c2f-5fee-ac19-e1bb988b9b67 | note | Work By - Contractor
9e7cf3bc-9a9f-5f47-bf48-5b1ab4ecb6dc | note | Standard / Spec - Technical Specification
f7d81988-f115-56fd-976f-54dc1f942f8f | note | Criteria - Location of works identified in accordance with the Project Technical Specifications.
4bf722f2-2a28-585e-a3a7-0e22ed305a57 | note | Frequency - 1/Lot
23b11d14-e525-5487-a14c-c382f86d3015 | note | Record - Attached Drawing
af19f709-6461-557d-b407-0f3040f3d103 | note | Contractor: Resp - RSA
828a6673-5f0f-56ee-a352-3f20fa186cd9 | note | Contractor: Type - CHK
9eec80ff-7e3f-5792-9832-faf8cc60a43f | note | Client: Resp - Senex
2dccbe7c-05d5-5ff1-8845-45b4d7d92b48 | note | Client: Type - Check
2eba868c-3e07-4b8a-983f-a612e3c5371d | checkpoint | 04 - Clearing
766bcbe1-850f-5612-97bd-c0c2112de22d | note | Work By - Contractor
5134a310-7d98-56e5-a289-3ab06ccd14c2 | note | Standard / Spec - Technical Specification
87db33e4-ab6c-5745-80de-f8a572fb4c5a | note | Criteria - Clearing shall be performed within the limits of the works indicated on the drawings.
d1c8ffed-a74e-5e98-8657-5ff5360a6624 | note | ○ Trees, shrubs, logs, debris, perishable material, organic matter, fallen trees, overhanging branches and surface obstructions shall be removed from the stripping area.
6d993666-069f-543f-9787-cb0b4dc6484b | note | Frequency - 1/Lot
c57ad858-3284-5326-87dc-4d996e7b47b5 | note | Record - ITP Verification Checklist
f504c316-429c-5a7a-a316-13a26d095484 | note | Contractor: Resp - RSA
fe2e9a91-b624-50e0-9308-3c648d610e4d | note | Contractor: Type - HP
5e4613ee-fa15-553d-b146-461c6e11961f | note | Client: Resp - Senex
7f8da501-0592-596b-8891-96ae451a5ff3 | note | Client: Type - Hold Point
ef253173-f92b-4630-a365-a9b956705b8e | signoff | HOLD POINT
4f070dd8-faf7-466d-a939-ddf831907342 | checkpoint | 05 - Grubbing
a75e076b-47f8-57d7-91af-e7706bc5eb2f | note | Work By - Contractor
cb4858b5-5655-58d4-a697-042726351659 | note | Standard / Spec - Technical Specification
67f748d0-9de7-514f-920f-963f74bf6915 | note | Criteria - Roots from trees and large shrubs shall be excavated to the extent to be agreed with the Superintendent.
9ce113f2-fec4-5581-8420-6d5f4b85d850 | note | Frequency - 1/Lot
9dcfe725-ef88-59ae-b805-7374967acf22 | note | Record - ITP Verification Checklist/Lot Map
062d116f-5bac-53d2-9cc3-68199d41e8f5 | note | Contractor: Resp - RSA
fcc94613-5752-58a6-8c7e-ab186bf4e196 | note | Contractor: Type - CHK
8088cb36-a2d9-59be-83a6-2a1e6a436850 | note | Client: Resp - Senex
41584a74-5dc7-5ee9-8b92-3837ecdf5a09 | note | Client: Type - Check
e6fb1d72-8cdf-4a65-8fca-c1741cf914d1 | checkpoint | 06 - Stockpile of Materials
6131b2f0-5508-5de7-b447-e764c8b6cc81 | note | Work By - Contractor
0ab65781-6401-5e75-af2f-192b82120851 | note | Standard / Spec - Technical Specification
0549f203-5098-5324-b3bf-54ea041b5d6c | note | Criteria - Cleared and grubbed materials shall be stockpiled or disposed of as directed by the superintendent
c74260dc-9293-5701-9456-b08e86b77dc7 | note | Frequency - 1/Lot
fbd207f1-3b9f-57ca-aa98-66cd9960594a | note | Record - ITP Verification Checklist/Lot Map
f699ad98-40e5-536c-a392-252fc328c409 | note | Contractor: Resp - RSA
65f7dcdc-46ad-5912-8a7f-c34a2eb3547c | note | Contractor: Type - CHK
c2528cf3-89d1-5b0a-bbfc-9c2af716cc21 | note | Client: Resp - Senex
972979f5-4131-555e-9a5d-ca7bc4f35839 | note | Client: Type - Check
ab762826-cfdc-4a52-9f41-6860fd446b5a | checkpoint | Built in accordance with this document:
645fbfee-d6bd-5e32-9fe0-da1235523e3e | date | Date
ccd477a7-638f-4b30-9d38-ae12d77fee52 | signoff | Signed
a029d8bc-cd07-4c6a-8090-960a94c6de2a | checkpoint | Test results received. Lot conforms to Specification:
94584718-365f-5166-a240-d0763bc7d5b3 | date | Date
f10ee1e9-a282-4ac5-a1f8-83df9ac31d9e | signoff | Signed
2dc4d38d-c006-4e6c-a4fa-15e02a281d26 | checklist | ITP002 - Topsoil Stripping - Rev0 | itp | ITP002 - Topsoil Stripping
416520b3-aeee-4cfa-86f1-048913cfd312 | section | Inspection and Test Plan Details
5fe59956-12e6-42fd-8ac4-3d310a716d23 | checkpoint | 01 - Survey Set Out
57f28395-56b7-53fd-886d-e198f88810fb | note | Work By - Contractor
b56b08de-5e7b-5e40-8ea9-8ffc17f8e665 | note | Standard / Spec - Technical Specification
82dd8e2a-0235-5289-b347-1f318268aafe | note | Criteria - The contractor shall be responsible for engaging a licensed surveyor of Australia approved by the Superintendent to set out all works in accordance with the design drawings prior to the commencement of the works
c2b8f35b-55e3-5b2e-9096-35694a432c58 | note | Frequency - Prior to commencement
42fe79e3-3d75-5c98-aa50-82f3fb57b0fc | note | Record - ITP Verification Checklist/Site Survey
94e309d3-de7b-5148-ba75-96051e1244c9 | note | Contractor: Resp - RSA
05933466-e4ce-5c64-bc68-76518e8214fe | note | Contractor: Type - WP
70d15bbf-5877-5580-b143-fa2b188dfe94 | note | Client: Resp - Senex
e8c6ad04-efe2-531e-8b47-821b93254549 | note | Client: Type - WP
715b6f73-eb70-47e4-acd1-d939f4c52bf5 | checkpoint | 02 - Lot Identification
d0c749ac-b984-5f27-b127-ac3aec9a2db7 | note | Work By - Contractor
236c0e9d-4b99-5cb5-b727-b054b7c63062 | note | Standard / Spec - Technical Specification
b4f3d768-01c7-561a-a302-ae0c28b03ca7 | note | Criteria - Location of works identified in accordance with the Project Technical Specifications.
8014c830-25d3-56b0-b619-69c3feca2198 | note | Frequency - 1/Lot
4c272972-5616-5f1e-98ff-579297eefc3b | note | Record - Attached Drawing
cafc242e-a839-57c0-bc99-fb28020c37bd | note | Contractor: Resp - RSA
313bf202-206c-5b42-b24e-a0070edbbe8f | note | Contractor: Type - CHK
41a2dbf3-9beb-5b71-b320-78461fefafdd | note | Client: Resp - Senex
28767938-e526-523a-adbc-cb8201aab8c2 | note | Client: Type - CHK
eaf56a90-538d-44ec-a0b0-a17e3f1f0e67 | checkpoint | 03 - Topsoil Stripping
b754f6e7-c15b-5fc2-a9d0-0c5f1375ef85 | note | Work By - Contractor
e5f424a4-576f-55fb-9c0d-d1c0d6717420 | note | Standard / Spec - Technical Specification
c7ecb81c-5eee-5fcc-bdd8-8805787e6d8e | note | Criteria - Topsoil shall be stripped such that all organic rich soil and roots/rootlets has been removed from the foundation of the embankment and internal borrow areas
dbce238e-63c2-5e83-94f2-921c38ded01a | note | ○ Topsoil shall be stripped to the depth(s) 200mm indicated on BOQ. Any areas with depth greater than 200mm should be notified to the superintendent.
89d61994-c799-5d02-b999-7f724f1ce052 | note | Frequency - Confirm with survey
6b45d1dd-80dc-5a15-8018-d68f10439fb5 | note | Record - ITP Verification Checklist/Site Survey
c6333406-51f1-5d75-a11a-a4aadd21fabb | note | Contractor: Resp - RSA
08a34b57-85b1-5d60-a934-20a62200fd93 | note | Contractor: Type - HP
e96f135e-8bfb-5b77-963f-906ecada8324 | note | Client: Resp - Senex
0c09753f-b5ac-508e-9098-e4ab8d9a0e30 | note | Client: Type - HP
0524ed0c-02fe-49e3-ac41-bda9041bd229 | signoff | HOLD POINT
93dc99ec-4c96-47b4-aa0b-635ebd4b9474 | checkpoint | 04 - Stockpile of Materials
007f22ee-b2c8-56e7-8161-32fd213c7d7f | note | Work By - Contractor
f6dc2b06-79c3-5e6a-bb9d-e20be8b0001e | note | Standard / Spec - Technical Specification
ae094ef3-baee-575d-a44f-26dee22cb821 | note | Criteria - Stripped topsoil shall be stockpiled where directed by the Superintendent, for reuse.
53c5532b-cbf5-511a-a998-dd54dd639e62 | note | ○ Topsoil is to be placed in a loose, non- compacted state, to a maximum height of 3 metres
38a2ad6a-7d21-5483-8ddc-22f8ca47b83a | note | Frequency - 1/lot
36e12fbb-afa5-5378-a8c6-15b8d7dd08a3 | note | Record - ITP Verification Checklist/ Lot Map
3278544c-06d9-5458-b56f-2b69c9a58177 | note | Contractor: Resp - RSA
8b1ac109-bd33-5367-8a8a-7ac3eaba9dcb | note | Contractor: Type - HP
dc4e21d3-9930-5434-bc7e-594ac88bb752 | note | Client: Resp - Senex
7197cfa9-03d2-5677-b0a4-c3caa9f33e9b | note | Client: Type - HP
4124393b-c9a4-4467-a3cf-cc05500a214d | signoff | HOLD POINT
1ed2c005-1041-4f12-a6f5-1c0be75623bd | checkpoint | 05 - Survey after topsoil removal
f0f5b2ed-4020-518d-9ff8-fca946b6c4d0 | note | Work By - Contractor
88972782-6282-59b3-92ab-63b47df4f9c3 | note | Standard / Spec - Technical Specification
46cfbd7c-bede-5b37-89ac-447f2c837dd4 | note | Criteria - As-constructed survey has been completed to record the surface levels on completion of topsoil stripping.
8d4273d8-9c16-5489-903b-89660a0743af | note | ○ The Contractor shall submit results of each survey to the superintendent within 48hours of undertaking the Survey.
9ee23373-2715-52b6-bb89-cb97f30a4600 | note | Frequency - As required
c59cbc9e-1c81-5e8b-99c4-6dd3ff4aaf1b | note | Record - ITP Verification Checklist/Lot Map
363cfe54-3883-5cc7-b13c-59e451b85fcb | note | Contractor: Resp - RSA
9f4b98f1-42fa-5d45-880b-15100ff83f13 | note | Contractor: Type - HP
331cc477-4ee2-5efb-8581-b0dd2ddc8271 | note | Client: Resp - Senex
789ea673-b53d-5279-9f93-acd71bf99169 | note | Client: Type - HP
6950c2f5-9a87-4553-b789-659a32bb3480 | signoff | HOLD POINT
3b12f239-2c2c-4e1e-a5aa-58c5d50ce15f | checkpoint | Built in accordance with this document:
1c766f27-3757-5a18-b1e7-b8a134b4cb86 | date | Date
133df39e-f007-4a4b-a019-245f32c9cae2 | signoff | Signed
71def67f-2548-49ea-8e77-9359debf17bc | checkpoint | Test results received. Lot conforms to Specification:
d0c10b4b-c1db-5f48-9bab-a87d5e11c06d | date | Date
06b4b41c-e715-45f0-88f3-f12320ffc596 | signoff | Signed
ca03677c-23ee-4cc7-9146-5d80ce88aba5 | checklist | ITP003 - FP - Foundation Preparation - Rev0 | itp | ITP003 - FP - Foundation Preparation
bbd933bc-8115-4be8-a9bc-ec63ae0f3679 | section | Inspection and Test Plan Details
36eafe1d-451d-4aa9-9666-0fdb833b014b | checkpoint | 01 - Lot Identification
a650c655-6d1b-5521-977a-564a2ceec696 | note | Work By - Contractor
0155519a-e8e9-504e-95f7-fdd56181c521 | note | Standard / Spec - Technical Specification
e4b4f01f-50b6-5bb3-b865-9bec0c41daab | note | Criteria - Location of Works identified in accordance with project technical specification
119a179d-373d-5e00-bd9b-8ec17f380b92 | note | Frequency - 1/Lot
0f2e1d6f-48fb-5295-ad28-49d1370873de | note | Record - ITP Verification Checklist/Lot Map
d26b590d-fe8e-5685-ac18-4a946b396f82 | note | Contractor: Resp - RSA
8e9f8986-f490-5a29-ad22-24491079404d | note | Contractor: Type - CHK
cd851d72-e10a-53cc-b8de-02763cd8e805 | note | Client: Resp - Senex
2765a829-d9a6-5712-953c-df5c0b69593a | note | Client: Type - CHK
57d6aaa5-abb5-4689-a467-f72cb9825f00 | checkpoint | 02 - Foundation Preparation
cba9bebb-96b7-5c18-ae3a-c9882df08ee8 | note | Work By - Contractor
53326770-4382-5819-a564-11d3a8985dc2 | note | Standard / Spec - Technical Specification
4d4cdc18-3c1a-57ba-a8aa-d772f0b59f3b | note | Criteria - Foundation preparation of Lot will be visually inspected for material type, moisture and organic material prior to foundation preparation works.
08fe6ab7-5161-5344-bf57-9b7f30504633 | note | Frequency - 1/Lot
56154109-e612-50b7-8c20-f587a0c58fc3 | note | Record - ITP Verification Checklist/Lot Map
166d2549-c6e2-5fdf-bb0b-075789840bb7 | note | Contractor: Resp - RSA
7c777ce5-7ace-562a-ba66-fe0dbbf204cf | note | Contractor: Type - VIS
74099af5-0ac2-52fc-a7e9-301745cecf14 | note | Client: Resp - Senex
c826d89e-4f30-5108-9a82-8bee1c4bcf04 | note | Client: Type - VIS
d8204a73-d1e2-4be4-9f3a-b15abaa953bf | checkpoint | 03 - Foundation Preparation – Proof Rolling
57be7faa-b43a-5c4f-82fb-c70d555fc32d | note | Work By - Contractor
6a3aaf69-d6e3-5d50-ba1b-9a4fad53da3e | note | Standard / Spec - Technical Specification
85bbf005-103b-5c34-bbc7-d4eda2cc8d8a | note | Criteria - Subgrade shall be Proof Rolled in accordance with Queensland Department of Main Roads Technical Specification (MRTS) 04 General Earthworks Section 18.3.2 or similar method as approved by the Superintendent while in the presence of the Client.
499eb8be-05f1-5f01-a1ce-dd8cc334853a | note | ○ Areas of subgrade identified by the superintendent as unsuitable material shall be excavated and replaced with material conforming to the requirements of the overlying fill zone
12033f7f-1c5a-577a-a668-3dd7ad475cf0 | note | Frequency - 1/Lot
9d5083b2-e53b-5380-824c-10cb0db7c5cd | note | Record - ITP Verification Checklist/Lot Map
b9589bfa-6a25-52ac-9168-5bb07b77203e | note | Contractor: Resp - RSA
d9206cbc-707f-52aa-a64b-012a9e0c0f50 | note | Contractor: Type - WP
16cf8f3b-851e-5a61-8654-51809f3578e3 | note | Client: Resp - Senex
ce02eb1b-68b9-5eed-aea6-9eb4f2368837 | note | Client: Type - WP
e0e4ec4f-3d69-4aed-abfb-4206f21d94ed | checkpoint | 04 - Foundation Preparation – Ground Surface Treatment
288b7a68-700f-5785-906a-c2a4ad7cc372 | note | Work By - Contractor
f37fdd30-a0b7-59eb-820f-135e8cd86b9a | note | Standard / Spec - Technical Specification
1e421a93-f06e-5238-9f41-5d183fe88c85 | note | Criteria - Scarify minimum 150mm, moisture condition and compact.
4dd5714b-d8fd-55d6-ab45-66332dbb0ee7 | note | ○ The Superintendent shall inspect the subgrade for conformance with the specification prior to placement of overlying fill.
027f88cc-bfb7-5af4-bf87-272aa0ea56c4 | note | Frequency - 1/Lot
af0bcb55-c78f-5d84-abe7-e5eeb4cb3744 | note | Record - ITP Verification Checklist/Lot Map
11edef3d-0e7d-5595-a1d1-1e73dbe424cf | note | Contractor: Resp - RSA
5835b52c-f695-58fe-83a2-ff25d3d7b93b | note | Contractor: Type - HP
c543818b-fc47-50dc-93f1-276d94260188 | note | Client: Resp - Senex
98d8b51e-173f-5d35-9268-bd2eb0165dbd | note | Client: Type - HP
8104ac23-29eb-4379-98ea-9b9134c6523b | signoff | HOLD POINT
c2d9432c-2120-4257-930f-f69001e49950 | checkpoint | 05 - Foundation Preparation – Smooth drum rolling of material
e4863d0a-1ba1-50a0-ba7a-86cf0c6aa719 | note | Work By - Contractor
92fe32a2-967c-571b-a8e0-946acdc3f240 | note | Standard / Spec - Technical Specification
38e626f3-7ea3-506b-b36c-13575bd8b11b | note | Criteria - Prior to the placemat of construction materials, the subgrade shall be rolled using a smooth drum roller to form a hard-smooth surface and approved by the superintendent
5e15eed5-08ec-5389-a5dc-40c3e1e7fc87 | note | Frequency - 1/Lot
e9f5593a-1c01-5897-932b-52d5d00c0bda | note | Record - ITP Verification Checklist/Lot Map
d6ae3156-f944-55f2-b019-b8fc659558c4 | note | Contractor: Resp - RSA
3ec4eae1-8117-5194-abba-f1af44e145ad | note | Contractor: Type - HP
27059c5b-d66c-55da-b208-d4cfe1522b14 | note | Client: Resp - Senex
18d0d358-9ab3-56fb-9996-e1863aa23d25 | note | Client: Type - HP
4d9636b3-392c-45ff-9add-774064a61275 | signoff | HOLD POINT
df4ec570-5b1f-4483-a6f4-cae4d6d6f20e | checkpoint | 06 - Ground Surface Treatment Testing
f8d05244-d34c-5e37-b9a6-ce3c5cb23a0f | note | Work By - Contractor
5063cbaa-9c62-5bc4-86a9-37f653fbab1f | note | Standard / Spec - Technical Specification
ec1d5237-9a32-5266-9004-ec59a735df04 | note | Criteria - The foundation surface level shall be scarified, watered and compacted to a density ratio of no less than 96% of standard MDD and -+2 % of OMC
3980a8ad-bba5-5706-adc6-251282cf0b66 | note | Frequency - 2/100m2
1c835798-dd9d-5ff8-a8c4-7b7165ffa015 | note | Record - NATA certificate
129d1440-14f8-5d22-8aae-5ed30d7cf298 | note | Contractor: Resp - RSA
25d39a57-9550-56c1-91b1-496bce8e8bc7 | note | Contractor: Type - HP
f9eb2b3d-468d-5601-b8c5-c1f0e77c0682 | note | Client: Resp - Senex
197ba358-aad0-5994-9fd7-c9995d0b5101 | note | Client: Type - HP
8409d0ac-5cb4-421d-97f5-f10e5a2bc41d | signoff | HOLD POINT
c4091b93-cfa6-49a7-9381-fd3d559cba37 | checkpoint | 07 - As built Survey
98c1af6c-0f59-5938-abb7-674f2e1cb8ae | note | Work By - Contractor
e501f5ca-baca-5531-aa56-70f87145d5da | note | Standard / Spec - Technical Specification
dd6f583c-cb6c-5356-819c-f89c6b7c4a2d | note | Criteria - Finished levels checked for Vertical and horizontal tolerances as required.
885b2715-e886-541c-90f2-6da7cb123489 | note | Frequency - 1/Lot
adb51827-7242-5a7a-98b2-f4ba7c6091ca | note | Record - Survey as Built
6c40876b-f541-55b3-a2d1-95854956f796 | note | Contractor: Resp - RSA
2b0ec34e-7736-5fc6-ba09-b1e7ae6c7b51 | note | Contractor: Type - HP
c5f5b1b2-f112-53b4-8349-a7f24a80a6a5 | note | Client: Resp - Senex
55820247-0285-5de6-b234-b658c69c5021 | note | Client: Type - HP
863717e2-d574-4573-a5c9-b7483e0644e2 | signoff | HOLD POINT
b165553e-6766-4735-80fb-518b21525d71 | section | Test Details
801cfb64-39ad-4f80-a93b-bdeb4d2abe60 | checkpoint | 01 - AS 1289 5.1.1
28a848e4-ac87-539c-a377-bfbab9be1538 | note | Description - Standard Moisture Content, Dry density ratio
f6a17436-bfa7-5447-8695-b37863000894 | note | Normal Testing Level:
be1844ab-cc66-50bc-aa0c-2d0686f7d0de | textbox | Max Lot Size -
eadf9bd5-9fff-5e14-969f-1c3573ebd7aa | note | Min Test Frequency - 1/2500m2
26dcaab7-57b2-5ce6-a482-aa7063750b0f | textbox | Min No of tests -
3666e6c4-e798-510f-a7b2-0ff89ba9a70b | note | Required Result(s):
ed390bbf-37d5-5652-8ae9-bb423aef4aaa | note | Criteria - -2% dry to +2% wet OMC SDDR 96%
196c9664-7c37-47ed-a952-2f1ca4da1e12 | checkpoint | Built in accordance with this document:
bc39018d-89a2-5b79-9a42-95205c9ab86b | date | Date
4653c28e-084a-4925-b634-f0c29f1708ba | signoff | Signed
e31d0164-60ae-4a81-8020-a029d9f99f29 | checkpoint | Test results received. Lot conforms to Specification:
a3912065-e68e-5cc4-9c06-637f46c8c222 | date | Date
6c02f05f-089f-4cda-a4f7-7182913fc64c | signoff | Signed
d8a6cd9d-2ae2-44d3-9757-424210d155e3 | checklist | ITP004 - EC - Embankment Construction - Rev0 | itp | ITP004 - EC - Embankment Construction
4af47b2a-5ea6-4ac3-a7fe-248f5483e26e | section | Inspection and Test Plan Details
583b076a-a7b2-4783-a7e6-352d04b4be68 | checkpoint | 01 - Lot Identification
d3f9c7ad-f942-522f-be73-ea4cefdd589a | note | Work By - Contractor
19044299-d780-518a-97da-6a260c5ba563 | note | Standard / Spec - Technical Specification
33e4990c-472d-530b-8d4a-5662b4f6108d | note | Criteria - Location of Works identified in accordance with project technical specification
55b140c1-e5ab-5acb-9d53-a5d51f8ff6d7 | note | Frequency - 1/Lot
0e03c2cc-2045-51aa-b7ae-2b102db9267a | note | Record - ITP Verification Checklist/Lot Map
29f4c618-0a9e-5238-9452-d61735e82866 | note | Contractor: Resp - RSA
2ce21187-deb4-5aa4-be89-6b8caff83dab | note | Contractor: Type - CHK
e86a69e5-534e-52a8-ab93-dabdd4cb4c13 | note | Client: Resp - Senex
afbae5c0-859b-5826-aa46-c2646ba15aa2 | note | Client: Type - CHK
bbc6b2f5-32af-488c-b111-3675d0ebde28 | checkpoint | 02 - Underlying Lot Conforms
65990888-3c7d-5510-ac46-eb6f69814eb8 | note | Work By - Contractor
43cbc18b-e8a6-513f-a33b-2ccf58cd69d9 | note | Standard / Spec - Technical Specification
2ea49c1c-6c5c-5e25-a6dc-7d7175b3a2de | note | Criteria - Foundation preparation works completed in underlying lot.
8f8af63a-264e-5fb6-a75c-5e2cf9377653 | note | Frequency - 1/Lot
e76b2790-35f3-5a32-87d3-d111b679cb6c | note | Record - ITP Verification Checklist/Lot Map
49ddf531-0720-567d-bcdb-8f23b216b9d4 | note | Contractor: Resp - RSA
9c294d7d-4728-56bb-a0c5-3d1e21aa0989 | note | Contractor: Type - CHK
e8d9db84-d6b8-53b9-8770-8052dec4e2f5 | note | Client: Resp - Senex
b32dcaa2-3175-5392-b30a-9e1bbf37e306 | note | Client: Type - CHK
089f1aa8-1bac-4520-94ee-5538388e2572 | checkpoint | 03 - General Fill Material Requirement
e702809c-68b2-5a2b-84ba-1e18f072a1a4 | note | Work By - Contractor
b72460f7-9d7c-5db1-8ec3-7aa2d8bfefa1 | note | Standard / Spec - Technical Specification
473f8e26-3e00-5093-8a33-31b41583c7cd | note | Criteria - Grading Requirements
2a7dd6f3-7ad3-545e-bbf1-c053c70047db | note | ○ 75mm sieve –100% passing 19mm Sieve - 80 to 100% passing
00af160b-b4b9-5b99-b23f-e0c4f19783c6 | note | ○ 2.36mm sieve - 30 to 100 % passing 0.075mm Sieve –15-90% passing Indicator requirements
e4c34281-aa6f-5019-9e4f-9e205fa90324 | note | ○ Plasticity Index – 10 to 40%
5c97a4e1-4abf-54e2-bcfd-e626cbc0014f | note | ○ Liquid Limit – 20 to 60% Emerson Class 2 (minimum) Organic content 2% (maximum)
4a44eb14-92ea-5cff-9011-8b7511f29b85 | note | Frequency - 1/Lot
9c8374cf-1e41-503f-a028-0ceb8f2292ca | note | Record - Laboratory test Certificate
a4234883-7cf6-5866-af72-8524af0c8be1 | note | Contractor: Resp - RSA
3925113e-fa6e-5990-bd02-77813c42ab69 | note | Contractor: Type - WP
4a3f1369-0a98-5bc2-9c14-c5ffc4f3af6d | note | Client: Resp - Senex
6440bd48-bcd9-57e3-9e9d-e8a3dee905f9 | note | Client: Type - WP
ab92751a-e33e-4c68-a8dd-cb6ee678ae84 | checkpoint | 03 - Fill placement
b7839fb8-dd81-59d2-8754-932fc941ea94 | note | Work By - Contractor
22015c91-29e2-5222-b086-6e632ef29107 | note | Standard / Spec - Technical Specification
8d1a6427-33d4-5bda-ad95-26609a7904a8 | note | Criteria - General Fill
cdebb70a-1c83-5c14-aff3-3a7e7e39529a | note | ○ Placed in continuous, approximately horizontal layers for the full width of the area, having a compacted thickness of not more than 300 mm or less than 75 mm. If the surface of any layer is smooth, it must be scarified to a depth of approximately 30 to 50 mm prior to the placement of the next layer.
98359f30-e8f3-55c5-81c0-f904cb1abe50 | note | ○ ≥ 96 % standard MDD.
1c42892c-8a55-50da-b602-e9ce231cacca | note | ○ NOTE: ≥ 98% standard MDD for the Earthen Ring Beam General Fill Section.
d92327f7-22e4-5c35-a267-c679f079491c | note | ○ -2% to +2% of OMC
72b65249-ecf2-5971-a206-fb20adecd047 | note | Frequency - Each Lot
230a353e-e750-5e5f-8e40-adb9689dba7a | note | Record - ITP Verification Checklist/Lot Map, Laboratory test Certificate
c3d4ab39-bcf5-5024-a739-ce86cad2bae0 | note | Contractor: Resp - RSA
9fc95c5d-0530-5b5c-91df-9b89b1ce4f2a | note | Contractor: Type - WP
961813c8-dec9-58a6-b187-226ae109b20d | note | Client: Resp - Senex
3d3bc5b2-8081-52b7-afd9-b5e029b464d2 | note | Client: Type - WP
4242dbb5-8303-49f8-9f44-d4a671d6aadc | checkpoint | 04 - Testing
b9b72cc5-21f1-5f6a-8d5a-98f19df521e1 | note | Work By - Contractor
bc279baf-5115-5605-b1ee-7407053e0bdb | note | Standard / Spec - Technical Specification
d4f1ec3b-d28e-57a7-bdcd-6d18db5de486 | note | Criteria - General Fill
efcfa735-e106-53d3-9c02-7b66497b4ac1 | note | ○ SDDR – 3 per 2500m3 PSD – 2 per 2500m3
0c4643f6-d715-585f-96b1-f2a56c7d02fd | note | ○ Atterberg – 2 per 2500m3 Emerson – 2 per 2500m3
5e8d2e24-7af2-5181-bb44-b53369da45a2 | note | ○ General fill – Earth Ring Beam
2252ffa7-15ba-5737-af28-3b435422b076 | note | ○ SDDR – 1 every 50 m(lineal)
648078f6-62b9-5829-b3d6-a327ed8281b8 | note | Frequency - 1/Lot
049b999a-46b5-5f9a-8a67-c372eb8945b5 | note | Record - Laboratory test Certificate
387880a9-2240-553d-b907-ddc8a93638a5 | note | Contractor: Resp - RSA
c9248ea2-6889-5b12-aef7-571546dfac6d | note | Contractor: Type - HP
77851d7f-3837-5b88-b4dc-da92e29603de | note | Client: Resp - Senex
df4d778d-1e5f-5186-a055-b86567ae72f5 | note | Client: Type - WP
fb4c3f7f-2304-4320-9164-2d39d5407550 | signoff | HOLD POINT
f7c0cc63-04d7-49c4-a298-78d1bfc4b278 | checkpoint | 05 - Survey
ea8474fe-57ad-546c-8015-22ec14b5d8ee | note | Work By - Contractor
855cc2ce-af0b-5316-9663-ff819f72fa19 | note | Standard / Spec - Technical Specification
da3d0ccb-2e53-530c-8f78-294538225f8f | note | Criteria - RSA shall submit 50%, 100% tank pad foundation fill placement completion survey to the superintendent within 48 hours of each milestone achievement
1d9995b6-de59-5b2c-9efa-5a953f78b442 | note | Frequency - 1/Lot
a2a22a64-6818-56c8-aa2e-23f1990c84b8 | note | Record - ITP Verification Checklist/Lot Map
37383b2a-1e13-507d-b0e4-68a07c23efa4 | note | Contractor: Resp - RSA
4d7f29fb-5fad-5163-95e1-009ad1be2231 | note | Contractor: Type - HP
737682b4-38c5-57d0-ad9a-3228d53ef105 | note | Client: Resp - Senex
5ee60f94-60db-51b4-8fca-8178f66f6820 | note | Client: Type - HP
d7b0d952-03e1-486a-815d-9cf57953c6e9 | signoff | HOLD POINT
54f9f864-5e60-430a-9ddb-012d302d82cc | checkpoint | Built in accordance with this document:
5a8bd20c-d1b4-56fb-ade5-a9aa09ca9e36 | date | Date
ffef2fd0-fd0d-46f0-8d9e-f397309530d4 | signoff | Signed
aa3dbad7-9512-4366-971c-534cf6a423cf | checkpoint | Test results received. Lot conforms to Specification:
23ba4615-6d05-5e7b-9a19-b1d182e6482c | date | Date
12fb571c-da02-4fb5-a0f2-433da907af20 | signoff | Signed
88ed0f52-ce18-422e-ad48-5114def0c04a | checklist | ITP005 - CL - Capping Layer - Rev0 | itp | ITP005 - CL - Capping Layer
b772e71c-926e-4f72-97c2-b2a01c0fe6a0 | section | Inspection and Test Plan Details
825d36cb-9076-4be6-8ccb-9efb59351292 | checkpoint | 01 - Lot Identification
2414ce71-1a3a-5a7a-bb95-113afe34f687 | note | Work By - Contractor
7bd2afb9-3282-5a33-87b8-a79e28e1529d | note | Standard / Spec - Technical Specification
fa78e961-333c-5942-aca8-23707002f0c7 | note | Criteria - Location of Works identified in accordance with project technical specification
793608a0-aac0-53a1-8483-df294e7d8fa0 | note | Frequency - 1/Lot
bb6971ec-a75c-5a52-be98-a2104364f889 | note | Record - ITP Verification Checklist/Lot Map
4327f3e1-c5d1-587a-8d3a-14f30fb7ade8 | note | Contractor: Resp - RSA
e0b226b5-75c6-52a8-a594-237e5ae28b5a | note | Contractor: Type - CHK
cc81480d-9b9b-51d8-a451-79c2a40aa8dd | note | Client: Resp - Senex
8064a623-7acf-51d0-b802-06028d1430d7 | note | Client: Type - CHK
74ac5ade-16a9-4cb4-adeb-1758089a73e6 | checkpoint | 02 - Material Approval
a7fd1190-1ce5-58ac-9beb-448aea77ab2e | note | Work By - Contractor
be0742e2-ec3f-5647-b0c6-27074ffd55c1 | note | Standard / Spec - Technical Specification
e29f605e-73ae-5293-8e7a-4f2e15324d7a | note | Criteria - Material shall meet the requirements under Queensland Department of Main Roads Technical Specification (MRTS)05 Type 2.5.
08fcee04-3b37-5c2d-b7b1-2a51cf45354c | note | Frequency - 1/Stockpile
c92470e2-1296-5727-82bf-17340074927f | note | Record - Laboratory test Certificate
088a9e96-c596-5b90-aa8c-8439a478f777 | note | Contractor: Resp - RSA
efa08dce-4a86-5ff3-8dc1-7228772d7e6a | note | Contractor: Type - CHK
fdee91a8-e97c-5072-9d77-6da0c5682cc5 | note | Client: Resp - Senex
2ee1e70e-ab29-563c-80c1-f16c45f50ac9 | note | Client: Type - CHK
dff69b11-a0a7-4829-8b2c-7ad9b8d4e5b2 | checkpoint | 03 - Proof Rolling Subgrade acceptance
9e159732-5ff3-542f-a220-6c5ae5a1a8d8 | note | Work By - Contractor
d160faee-cf1d-5c58-9b44-e2c4bc519941 | note | Standard / Spec - Technical Specification
21272107-b921-5f3c-90e3-a8a9fd5a919b | note | Criteria - Main Roads Technical Specification (MRTS) 04 General Earthworks Section 18.3.2 or similar method as approved by the Superintendent while in the presence of the Client
42ccca67-10ff-5a3a-92d8-c3744b279a53 | note | Frequency - 1/Lot
2a885ef4-ce0a-5e02-b77c-1f70c2929890 | note | Record - ITP Verification Checklist/Lot Map
142a2aab-9c16-5e13-992a-edbd6c283adb | note | Contractor: Resp - RSA
e799d354-d5d8-5e87-a9d1-1adf14dddba8 | note | Contractor: Type - WP
df51b116-da13-5251-bb9d-27562ef58ba9 | note | Client: Resp - Senex
fab5ff21-8204-59d3-aef2-2c6217680a62 | note | Client: Type - WP
fc8f3830-45cd-40dc-b9e2-e995a1a72b3a | checkpoint | 04 - Placement of material
67a6c4b8-5b8d-59de-b2d3-4ac854fad497 | note | Work By - Contractor
83d837eb-034d-55a6-b225-b7272ce5ff76 | note | Standard / Spec - Technical Specification
7ffb9a81-5f77-5726-8810-83ea77a62561 | note | Criteria - Access track and ring road capped with 200 mm depth gravel. Placed in continuous, approximately horizontal layers having a compacted thickness of not less than 75 mm and not more than 200 mm. If the surface of any layer is smooth it must be lightly scarified to a depth of approximately 30 to 50 mm prior to the placement of the next layer.
4c70cd47-8ae6-5da6-b54f-99cac6737b7a | note | Frequency - 1/Lot
056d08fa-06d3-598a-8916-7fd810c6be5c | note | Record - ITP Verification Checklist/Lot Map
251308d0-56c2-508f-8fd8-b847a403293e | note | Contractor: Resp - RSA
0dfb374d-423d-5a28-a876-6434ddaaeb0f | note | Contractor: Type - CHK
020f723d-c86a-5f7e-aee5-45bb0cd16965 | note | Client: Resp - Senex
92af9c20-2ba3-5be4-82ef-f54a7bd0a47b | note | Client: Type - CHK
2e98482a-fc2f-45d9-ba55-cba6f1b4e468 | checkpoint | 05 - Material Testing
bed2d00e-f159-5aac-a3ee-0bbbbbc26aa3 | note | Work By - Contractor
f1f37fa7-580a-5023-9d71-275aaf8db71a | note | Standard / Spec - Technical Specification
bba8e20d-5cba-5df9-a978-7ba29128d315 | note | Criteria - Capping Material shall be tested for material characteristics, moisture, and compaction.
c24b80ee-de7c-56d5-b920-f9f58ceb1ce2 | note | ○ >98% SDDR
1a53e9b5-6cbd-54e3-87e8-cf1ad069a104 | note | ○ -2% dry to +2% wet OMC
4a03d383-0cf0-59c8-afb4-b67f96f7d822 | note | Capping Material:
c03f076c-e88f-507a-8fad-ffa3a0ed0c87 | note | ○ SDDR – 3 per 500m3
6d457d31-84cc-524a-9986-506bd42fd0a6 | note | ○ PSD – 2 per 500m3 Atterberg – 2 per 500m3 CBR – 2 per 500m3
2c557f57-9a78-5be0-b11b-0f4291935c6f | note | Frequency - 1/Lot
5641b691-1ad2-5d3d-95f3-3efc15624241 | note | Record - Laboratory test Certificate
44ba39fa-10df-5b7f-95f0-6c4c79e70174 | note | Contractor: Resp - RSA
1403f3a8-74c2-528b-8394-0d450bbf6dd9 | note | Contractor: Type - HP
579e0b36-c504-57e3-a3a8-238095b7d95b | note | Client: Resp - Senex
088d2470-76dc-556e-b386-43b8ac1155e9 | note | Client: Type - HP
df1e78c9-fdaf-4763-967e-a57fcdb56051 | signoff | HOLD POINT
8c885399-0662-4e8f-bdad-af5ce68e1d9a | checkpoint | 06 - As built Survey
b300836b-e4c5-5259-b2a2-16c0040321e3 | note | Work By - Contractor
2737c29a-eeb8-5a16-abdd-ebf1d981fe4e | note | Standard / Spec - Technical Specification
f356163d-4292-5305-bbef-2c24aba0363c | note | Criteria - Finished levels checked for Vertical and horizontal tolerances as required.
17c0fc1e-11b0-57c7-a8e8-e28afe20079d | note | Frequency - 1/Lot
f06d79ca-d211-50d7-b87d-c3bd4514bdde | note | Record - Survey as Built
c5cdaa2f-097e-5dc8-a8e6-b63c5746531a | note | Contractor: Resp - RSA
413fcffc-f0c1-5c68-aa89-245cbb2147d0 | note | Contractor: Type - HP
7f694e92-7bb0-5570-959a-c62f4ff861b4 | note | Client: Resp - Senex
fb8834d7-2d52-5367-a851-0a1ad188f36e | note | Client: Type - HP
d692dcc3-6baf-48e3-8350-bc9a30bb5f33 | signoff | HOLD POINT
b970b9c9-a127-44bd-b266-b72f8a3c6f24 | checkpoint | Built in accordance with this document:
0e73905f-f337-589e-9cff-7d1f3f1edeef | date | Date
e5c457d6-8451-46a7-983e-6d7e6a26e346 | signoff | Signed
ac75599e-5c66-44de-989a-01a7f0731a9a | checkpoint | Test results received. Lot conforms to Specification:
e7711ad8-2889-50a4-9193-6640be034311 | date | Date
455af85a-7cae-4f34-aac4-7fe74eac32e0 | signoff | Signed
7c4eecc3-935f-460c-b6c7-ae0e14d8ae09 | checklist | ITP006 - Surface Water Runoff Management - Rev0 | itp | ITP006 - Surface Water Runoff Management
952038c7-9867-4966-bed5-0000c3a5b4a8 | section | Inspection and Test Plan Details
05f05bc2-f03b-44b5-af98-25b2f261d8b3 | checkpoint | 01 - Lot Identification
227a2130-d686-5ccd-ac40-8e9af049d468 | note | Work By - Contractor
37824f10-dd8e-52ff-945a-22baf5491f4c | note | Standard / Spec - Technical Specification
beaba2e5-f369-5d4d-ba92-dc501c4e4324 | note | Criteria - Location of works identify as per IFC drawings
32ee798b-53f7-56c8-96b6-73eb0a2d0bfb | note | Frequency - 1/Lot
c1651ea9-c95c-5c4a-af87-8d9e2ea73c19 | note | Record - ITP Verification Checklist/Lot drawing
43f43366-038b-50e3-93ff-176be6aa348a | note | Contractor: Resp - RSA
74744cd8-1e8f-5da7-9eff-b4b00581b379 | note | Contractor: Type - CHK
fa5102d7-99bb-55a9-9e53-6c04e9ddea30 | note | Client: Resp - Senex
b75ebfe8-f638-592a-88a8-975bf43c11e3 | note | Client: Type - CHK
3bee91de-eec4-423a-a7ec-33fce61ad6f0 | checkpoint | 02 - Gypsum Application
486867d3-8e15-581d-a54f-70ac284009b0 | note | Work By - Contractor
2b4a3a77-0957-5bd8-9477-d384cb5f7b12 | note | Standard / Spec - Technical Specification
61d3aa1c-eb67-5fc7-bdea-6f32b04e51c6 | note | Criteria - Apply gypsum to batters and table drains at rate of 2t/ha, scarify subsoil to a minimum depth of 150mm and apply water at 10mm/m2 to create adequate topsoil bond with the subgrade
8d9a3966-0688-5afb-a05f-ecd148d159e3 | note | Frequency - 1/Lot
16b76a24-63cf-5d22-a562-5370c7debc48 | note | Record - ITP Verification Checklist/Lot drawing
2deead41-0a7a-5970-a2e7-8ff40c0a0b8b | note | Contractor: Resp - RSA
75d97032-49d1-5e53-ac3e-1547eeb7a61b | note | Contractor: Type - CHK
254bc0ba-6d71-5b89-b266-a9e467501d4a | note | Client: Resp - Senex
5c5e4c67-359f-5b1f-ac51-9ce38f2a50e9 | note | Client: Type - CHK
e20245e6-f375-4a26-a2df-daeefdf5246a | checkpoint | 03 - Topsoil Amelioration
06eaf150-b076-567c-9fc0-053cb709fcac | note | Work By - Contractor
d675ffaa-7aab-5f8a-a203-905e23e86e52 | note | Standard / Spec - Technical Specification
86c31dfa-b7f3-59dd-a591-b607b5a83e48 | note | Criteria - Topsoil to be ameliorated with DAP Fertilizer at the rate of 150kg per Ha.
d36c6683-db85-53e7-ac42-6c100cce17c0 | note | Frequency - 1/Lot
fc432e48-784e-5b7c-969f-5f78cfbbf94c | note | Record - ITP Verification Checklist/Lot drawing
ce70bee9-7640-50d6-8fe6-64ffbed2e06c | note | Contractor: Resp - RSA
a9925371-cd64-5eff-85c1-b750b2bcbbd1 | note | Contractor: Type - CHK
7f722cea-9d62-53e1-aa27-793200dce67c | note | Client: Resp - Senex
855008c1-d361-54b2-a797-109df63f46e4 | note | Client: Type - CHK
a2b8deb0-f169-45c9-9351-4468aa3c161f | checkpoint | 04 - Respreading of Topsoil
8a6b9938-2554-5f0d-a86c-3d59ce7039c3 | note | Work By - Contractor
9aa44442-659b-5fea-b1d3-1c294ab8cc99 | note | Standard / Spec - Technical Specification
59e1172d-53c3-583b-bad2-7d385f733696 | note | Criteria - Topsoil is to be placed 300mm thick and trim with grader and scarify to a depth of 100mm.Surface left in a roughened state with horizontal rills running across the slopes to minimise potential erosion.
c1edfa41-fa02-572c-aafe-e40cf97b6d52 | note | Frequency - 1/Lot
d734e0ad-2c7f-5357-b448-873fa7c9e619 | note | Record - ITP Verification Checklist/Lot drawing
31c2ee60-d1b0-5b8e-be56-025f2e44e46a | note | Contractor: Resp - RSA
f8d3215a-dfac-577c-9ca4-7032ac704975 | note | Contractor: Type - CHK
564487b3-e4a6-5a62-8262-83638658e153 | note | Client: Resp - Senex
52f6a0fa-c6c6-52ba-bd7c-f21b2011c7e9 | note | Client: Type - CHK
ced06a03-ee42-4129-8b44-d51076c79b14 | checkpoint | 05 - Seeding/Hydro mulch
db61ed44-a11c-5b9c-87f7-a814ff777b1c | note | Work By - Contractor
0a5475fe-f33a-5517-93f8-e37fdf89e09c | note | Standard / Spec - Technical Specification
1fd2fc41-78b9-51f5-9023-fe3d7b57de19 | note | Criteria - The Contractor shall submit a proposed seed mix and hydro mulch / growth medium specifications for approval by the Company’s Representative
2fac2757-4fb4-578e-9248-5d19421ba1ad | note | Frequency - 1/Lot
187f941c-f110-564c-a9ef-27938f1cb11d | note | Record - ITP Verification Checklist/Lot drawing
4f65140b-b1ee-506c-ad0b-0d12e2536d9f | note | Contractor: Resp - RSA
69160f6a-8434-526e-95fd-55bb7e8944d1 | note | Contractor: Type - HP
5bb24130-d246-52ef-8759-831ee7a9619f | note | Client: Resp - Senex
b96e1974-ebdd-5aaf-92ca-e8ca5d85101c | note | Client: Type - HP
c80ca1c0-f50d-4968-af2b-4f18528ae323 | signoff | HOLD POINT
99bf5854-ada6-4e7d-b1a5-38b2e94e60c3 | checkpoint | 06 - Watering of Topsoil
c3577514-ff08-5713-bad9-ecf04ebe7b6c | note | Work By - Contractor
3d542f1f-a925-5ca9-8a09-f4b7b6916a2b | note | Standard / Spec - Technical Specification
78d85f18-6c4e-50d6-a230-b42c34c141c0 | note | Criteria - Watering 10mm/m2 every day for first 8 days, then every second day to get to a total of 14 irrigation days.
7a6b093b-c22d-57a2-b74c-64dbe5b6c4c2 | note | Frequency - 1/Lot
b284f548-4213-5371-81d5-90698b259cca | note | Record - ITP Verification Checklist/Lot drawing
9cd1c0d4-85a3-5d8c-9411-c7ec476cdfe2 | note | Contractor: Resp - RSA
b51059b0-c2c8-5d67-864e-266ea26c1cba | note | Contractor: Type - WP
6a01891b-00b8-5922-8571-5822ec19ceff | note | Client: Resp - Senex
cc853dce-aae6-50f4-911b-85f6aeef594d | note | Client: Type - WP
6e1469d6-1aa3-4b59-b364-59434e43a0b8 | checkpoint | 07 - Survey
d6d3e20a-eebc-514c-a674-158a1933d318 | note | Work By - Contractor
7cb261bc-5522-5212-b4f7-229c29d32d44 | note | Standard / Spec - Technical Specification
c2e5808a-1409-530e-a5e6-aee9cefcc7a1 | note | Criteria - As-constructed survey has been completed to record the surface levels on completion.
c9c1026c-7bb9-50f6-87c4-d02b55e1357d | note | ○ The Contractor shall submit results of each survey to the superintendent within 48hours of undertaking the Survey.
d23a9bcc-5d94-5b2f-a066-4b75ba15b3e5 | note | Frequency - 1/Lot
5b65881d-b8a3-51df-922f-7f49d471e110 | note | Record - ITP Verification Checklist/Lot drawing
a7415ff9-13fb-5a76-80f3-f9ff5b97c327 | note | Contractor: Resp - RSA
5b2eafef-ea80-5698-b438-0c9db36abd32 | note | Contractor: Type - HP
39882035-5095-5e44-b742-3588d27cf814 | note | Client: Resp - Senex
27a47c88-8a8d-52b0-bbe2-83eff543f5e6 | note | Client: Type - HP
675ffd9d-4812-4330-93a5-960e8942bbbb | signoff | HOLD POINT
fa1c0df9-ae98-424c-82e5-5e8e414b6f56 | checkpoint | Built in accordance with this document:
2d17e4d3-abd7-56f2-8569-fb223b3d2747 | date | Date
6bdd659b-2935-4c12-9870-d63de2c72e1e | signoff | Signed
2d709997-b9d8-4827-b250-9f977c7fc07c | checkpoint | Test results received. Lot conforms to Specification:
a49b7505-8396-5708-a223-6de17e8f85ba | date | Date
d2351e4f-5d14-462a-a1b2-e72d0381ae7b | signoff | Signed
10a11565-f588-42b3-a57e-7e9b7b2c1ace | checklist | ITP007 - Erosion and Sediment Control Installation - Rev0 | itp | ITP007 - Erosion and Sediment Control Installation
40374a26-b3a9-43e2-a61b-ef9589edc9e0 | section | Inspection and Test Plan Details
9b64cb52-06d8-488d-9367-09bf7a6b30df | checkpoint | 01 - Lot Identification
625f5c46-ed65-5475-b803-dacb5e503fc5 | note | Work By - Contractor
80fc6e75-6437-52d3-81c0-917cf1922839 | note | Standard / Spec - Technical Specification
21dc6a1e-7cc3-5b14-9b66-ef54a8bc6cd7 | note | Criteria - Location of works identified as per IFC drawings
4acdaa46-5d71-5d54-b7ac-ba4ac8dab03e | note | Frequency - 1/Lot
86eaa512-47be-585f-817c-f9d42be6139a | note | Record - ITP Verification Checklist/Lot drawing
8f6930c3-468c-5a36-933c-6aabfb0e69ee | note | Contractor: Resp - RSA
0f9848c2-bb4c-5c8f-aa99-4354f9cb2ead | note | Contractor: Type - CHK
d1d1e6ed-5048-58b3-832c-230eca8fa959 | note | Client: Resp - Senex
09d4f959-b425-5f3c-aebb-dbec7486dc98 | note | Client: Type - CHK
402c66ec-8f61-4a3f-9988-fcad0feb2d77 | section | Temporary Sediment and Erosion Control
9cd21c0d-4474-4f05-956c-d99c59044925 | checkpoint | 02 - Clear identification and demarcation of ‘no go zones’ (where required)
32fff6d9-85d8-58ee-9a8e-be96d8871be0 | note | Work By - Contractor
4e0c4b73-2330-5b66-9213-a096903e38f5 | note | Standard / Spec - Technical Specification
5dab19ac-8554-5d87-84f3-401fa57f5a64 | note | Criteria - Remove vegetation and disturb soil only in those areas approved for construction work to occur
21d0f23b-b31a-59b6-9485-8b1cb70c0938 | note | Frequency - 1/Lot
b29c59f0-56c3-59fb-aa7a-7c69e551c645 | note | Record - ITP Verification Checklist
1d33e313-8c4a-5232-b40a-527f3ce71503 | note | Contractor: Resp - RSA
c7397414-0677-5e8d-b526-ebe3e45910a5 | note | Contractor: Type - CHK
79b135c3-fbe4-5076-9a1b-86191cac3780 | note | Client: Resp - Senex
397e4225-3468-5bc6-83e8-3bd5df447fd9 | note | Client: Type - CHK
c563a316-a5a2-4c08-8232-a704d65c595a | checkpoint | 03 - Installation of temporary sediment and erosion control devices
8bf9493a-946e-5013-bfea-af936b3ccd33 | note | Work By - Contractor
1d0ed901-40a7-5bfe-af27-71d890b09523 | note | Standard / Spec - Technical Specification
5b2dafcb-cb7c-5c0c-aad5-64b40314a531 | note | Criteria - Construction of earth bunds Installation of coir logs and Silt Fence Excavation of sediment catch sumps
6b389d7b-80b3-520f-95e0-8c2bae2b94c6 | note | Frequency - 1/Lot
c6947320-515d-55a9-aa80-e9c2b4e05620 | note | Record - ITP Verification Checklist
ef41f9d9-45c8-5c4a-9b6e-fc1fa288e0d0 | note | Contractor: Resp - RSA
9887bd8c-1fcd-5208-8abd-bc456afbbbf7 | note | Contractor: Type - HP
dcf767b7-03d9-52fa-a877-bdbcc8189b8f | note | Client: Resp - Senex
1f655a1a-cc9e-5d84-b645-2ddae7391fe9 | note | Client: Type - HP
7ffd68ba-a4a5-4ce6-bd1a-62ec59605598 | signoff | HOLD POINT
b874cd81-eb6e-44ed-b3df-c4f1346a89fc | checkpoint | 04 - Sediment and erosion control device ongoing inspections
884c58ef-5716-54b1-9773-6e351f031095 | note | Work By - Contractor
e5ed7983-4e7f-5eb3-bffd-3a1214ce40b9 | note | Standard / Spec - Technical Specification
4983b70c-7012-5624-9396-7b54ccdff6c4 | note | Criteria - Inspection of sediment and erosion control devices completed to be completed at the below frequencies
29cd8996-53d8-50d9-af48-b7376b48b83f | note | ○ Rain: >50mm in on day or >100mm over 4 days Prior to shift breaks
dd33b01b-cccb-5903-ad4c-57ef9366530f | note | Frequency - Ongoing
53a0cf61-ee40-5fde-adee-9e90166ea6a7 | note | Record - Environmental Routine Checklist
551b19f3-5e12-5866-aac7-65bd6fcc88db | note | Contractor: Resp - RSA
15f43598-265f-56aa-8b28-ef9eedb2a3c7 | note | Contractor: Type - WP
3f51176e-fe0e-5ec9-80db-256e9e39ecd0 | note | Client: Resp - Senex
7b9adadc-0d21-5ea3-a120-42210b269112 | note | Client: Type - WP
479472ad-73f4-4bfa-9468-ae8ed502e692 | section | Permanent Sediment and Erosion Control – Rip Rap (Rock Protection)
6c5d428f-7e2a-4f5e-b550-cce107a027a9 | checkpoint | 05 - Underlying Lot conformance - Subgrade
e60de8c6-425e-505b-8036-b859ab79abea | note | Work By - Contractor
51100a55-2c7b-5776-b3be-64c5ebc41682 | note | Standard / Spec - Technical Specification
f48aba21-b47a-5a8f-9470-8a66e1f3cc50 | note | Criteria - The Superintendent must have a visual inspection of the subgrade, prior to the placement of the Separation Geotextile.
082f3b68-7634-54e0-b34f-96172c97f2a8 | note | Frequency - 1/Lot
2f492392-b95c-53b0-8f45-f7ca0d54d33f | note | Record - ITP Verification Checklist
3dff62c0-5c8b-5351-94b3-c98d1b195ea7 | note | Contractor: Resp - RSA
60002f33-7a7e-5dda-a546-833a0308fa04 | note | Contractor: Type - HP
473f2363-8024-5c2a-b082-2ca73c071295 | note | Client: Resp - Senex
666940df-1ed4-5627-8940-8264dd4ca027 | note | Client: Type - HP
3637775b-943a-4162-9087-357931b10142 | signoff | HOLD POINT
2935addf-0f88-4ef5-9247-e1bc9fc14b3a | checkpoint | 06 - Conformance Separation Geotextile Material
b85ba4a8-c44d-5f12-92b7-73ceb3a652a7 | note | Work By - Contractor
e27513c0-c271-59a1-967a-5eb348e29078 | note | Standard / Spec - Technical Specification
fc408cff-ac4c-5dfa-93d6-933fb48d7634 | note | Criteria - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data Certificates.
dc579bfb-8081-5047-b97a-40ee4226ff4b | note | Frequency - 1/Lot
ed488c77-2590-5200-a6d3-94cfee0ca4a7 | note | Record - ITP Verification Checklist
46714528-c5be-5783-ab2e-a4b91bdfa7ca | note | Contractor: Resp - RSA
252790df-3679-50d5-bb81-8a8de081303d | note | Contractor: Type - HP
0669cf2d-fc4a-5ce4-955e-87804d8cfdc6 | note | Client: Resp - Senex
0ef0796c-deb9-56e7-9698-9b76fa4e401e | note | Client: Type - HP
1e6dc465-61eb-4a94-93ab-216c6dd6e315 | signoff | HOLD POINT
dcdd2dc6-a395-4c5f-8dac-df663aad1a66 | checkpoint | 07 - Conformance Rip Rap
92042e88-1946-590a-a0fb-01964821da8a | note | Work By - Contractor
09799edd-9a19-5388-a171-fdd5547ffcc6 | note | Standard / Spec - Technical Specification
dc91e458-c536-54d2-876a-25f9d94975ee | note | Criteria - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data certificates.
99a9f893-112b-5178-9055-725041f4e2b3 | note | Frequency - 1/Lot
10f7514b-b1b7-52bf-9457-fbada5b9b3a9 | note | Record - ITP Verification Checklist
7c1520df-2a41-5019-af3f-591f19af32fc | note | Contractor: Resp - RSA
604e1c67-d350-5004-a3bc-7905fbd49b23 | note | Contractor: Type - HP
1cfacb5b-7ac2-5328-8c2d-377fb3807e5a | note | Client: Resp - Senex
3f6ffabb-a70b-5ca5-8442-b1c1aebff3f9 | note | Client: Type - HP
48fd7be4-19a6-4124-b49a-cb5c3bcc6e70 | signoff | HOLD POINT
04ccb9c6-2f76-459b-8fc1-a127062f8abc | checkpoint | 08 - Separation geotextile placement
3f06ec25-fcd0-5bd5-9966-5555f8363bd5 | note | Work By - Contractor
6b21f5f8-9fd3-5198-a40c-ce3d1e58b823 | note | Standard / Spec - Technical Specification
92f48ed3-f82d-53e0-a4f6-ee93b609c575 | note | Criteria - Installation method comply with the requirements of the technical specification and the IFC drawings. Laps to geotextiles shall be a minimum 0.6m
9f976e5e-0dc7-511b-9614-09186d6df8f9 | note | ○ The Superintendent shall inspect the placement of Geotextile for conformance with this Technical Specification prior to placement of overlying layers.
e5af29dc-84c4-578f-a35d-37428af2ec7e | note | Frequency - 1/Lot
b6dd7e8c-1d8b-5bde-b59a-b236160ac22c | note | Record - ITP Verification Checklist
6980fc21-e60f-50ff-a6f9-99b5565ceab1 | note | Contractor: Resp - RSA
b94d2894-3a9e-517e-91f7-f1380ccc2071 | note | Contractor: Type - HP
946abca8-0ecb-577b-abe2-f763939f81b9 | note | Client: Resp - Senex
c5c63691-ddaf-5123-9071-36429e3a24e1 | note | Client: Type - HP
f119a928-f4f2-4bbb-8ecf-663f2954a71a | signoff | HOLD POINT
00222a64-d783-4f51-b60e-d8de22b5b5da | checkpoint | 09 - Rip Rap Placement
bb7ac0bf-8260-5ec5-a4a7-5d0792f24616 | note | Work By - Contractor
e81ee234-ab7a-5a29-a4f1-3cd2a8ac3a9c | note | Standard / Spec - Technical Specification
a8ab4187-07c6-5193-b1b2-df843b13e750 | note | Criteria - A Safe Work Method Statement for the placement of Rip Rap shall be provided to superintendent.
6b481d50-6c78-5c38-91a4-b933c19550df | note | ○ Rip rap to be placed by excavator over the separation geotextile.
d61cd4ed-6a0a-5468-b371-6980ed12fc43 | note | ○ Rock finished smoothed to the final lines and levels.
c6828696-774e-5883-9c97-75c9ba2b48a6 | note | Frequency - 1/Lot
54c48b8c-74df-5b4f-ac00-1025e6758e46 | note | Record - ITP Verification Checklist
371f0f8c-9717-591c-b2f0-de6e42440b02 | note | Contractor: Resp - RSA
48b8e13f-c2a3-53f0-b556-c29ca7617883 | note | Contractor: Type - CHK
c4c59264-867b-56bf-9c80-14b25ee03819 | note | Client: Resp - Senex
e0f29202-284a-51c8-ac26-b841fc6874f2 | note | Client: Type - HP
01f17fb4-d91e-4bc7-ad33-9d78f1aeb0b7 | signoff | HOLD POINT
0764fe0c-215b-4535-b8de-cf5ab2c6821f | checkpoint | 10 - Acceptance of works (Rip rap)
be8c3a20-4ed4-5f8e-b615-fe6ab824c0c0 | note | Work By - Contractor
0099089f-3755-5196-bee3-5f88df8ee875 | note | Standard / Spec - Technical Specification
25bbe0cc-b539-55eb-a125-b8ab7b1536c7 | note | Criteria - The Superintendent must approve the finish surface and underlying separation geotextile installation of the Rip Rap prior to completion of works.
c8bf0333-aeb8-5020-b9bc-67d0effdf841 | note | Frequency - 1/Lot
8fb6c548-ea12-515d-9246-485fdf68d0c7 | note | Record - ITP Verification Checklist / MDR
54088595-8110-58e3-8b0e-0f96ea239019 | note | Contractor: Resp - RSA
7fb1c9eb-51b3-5bd9-be4f-282bea473e0a | note | Contractor: Type - CHK
5f75f598-66f4-531a-82b8-7a182f771688 | note | Client: Resp - Senex
5da0cb75-c6ec-5433-a51a-5a513e1c4d7e | note | Client: Type - HP
0840aa3b-c968-4d5b-92a9-4d40c7a5cd68 | signoff | HOLD POINT
99047714-f929-4020-a890-2fabb4e2267c | section | Permanent Sediment and Erosion Control – RCP and Headwall
24fc39d7-874a-4563-a830-c64f79d9ec5c | checkpoint | 11 - RCP Installation
a7810a85-f81a-5ecf-bff5-7af56787474f | note | Work By - Contractor
47c5215d-e5af-533b-8ab0-265182033a9b | note | Standard / Spec - Technical Specification
e036da22-6200-53b7-b4e5-724319ff20ac | note | Criteria - Excavation to design invert levels allowing for 100-250mm bedding sand (or equivalent)
7917b472-b73f-5e9f-b6f6-c897a6f6b174 | note | ○ 600 Rubber ring joint Class 4 RCP installed with barrels laid straight free from damage.
79d99366-bf79-556b-9f73-e3c93e0ce3d5 | note | ○ Sand (or equivalent) haunching and overlay to approximately 150mm above pipe
4bdeec93-427e-5c7c-8d97-0d493b7dde1a | note | Frequency - 1/Lot
930c36dd-eb45-5191-884b-780515ee5fe1 | note | Record - ITP Verification Checklist
f40e5857-abca-5728-aeed-e2bd6f48f27b | note | Contractor: Resp - RSA
22963a3c-f362-51bd-b957-41a8fe9983ba | note | Contractor: Type - CHK
ae8554e5-7fcb-5a2a-9239-0cd3490178e9 | note | Client: Resp - Senex
e47ef24a-fda8-556e-be67-d0695c742092 | note | Client: Type - CHK
55ebdf6c-3830-4814-98d8-60282ffd83f9 | checkpoint | 12 - Backfilling
b1b9d5a5-5c27-5aae-b31a-cead6e1de0be | note | Work By - Contractor
444c22f9-d212-5fcf-a653-9163bfa2d467 | note | Standard / Spec - Technical Specification
33d601e6-0156-57a8-ada1-69545c7be7ac | note | Criteria - Trench backfilled and tested in line with requirements for Fill
6acfe025-7b19-5041-8e40-ededcfa8cbca | note | ○ 96% +/-2% moisture
2294a334-24fa-5f16-9ced-e2bd6bc42587 | note | Frequency - Min 2 test per Lot
47db56f3-fc93-5319-86df-23a4a49f2987 | note | Record - Test Reports
65f208e1-59df-5efd-83c7-de7c4d0f390a | note | Contractor: Resp - RSA
b46348ae-1420-5a10-bb32-361fd829d18c | note | Contractor: Type - CHK
5fda399b-77de-5253-b9e4-280a5694094d | note | Client: Resp - Senex
5449d41b-33f9-551e-a811-12729b998aa4 | note | Client: Type - CHK
48f7a3e1-81f8-4123-92f9-ea4702edf3e0 | checkpoint | 13 - Headwall
bb7c58e6-4191-5b8f-8f29-a992eeb1432a | note | Work By - Contractor
5443bf2e-feae-5950-b0b4-ff288feb839e | note | Standard / Spec - Technical Specification
6b8856ab-3612-5d89-9eca-bec100217dc0 | note | Criteria - 2 x 600DN Headwalls installed on 100-250mm sand bedding to required invert levels
63998ce5-7e99-5079-bc79-953a1daf736f | note | ○ Headwall installed flush with RCP pipe and grouted neat.
0e89694c-0869-5b8c-9327-73f5937a8fd6 | note | Frequency - 1/Lot
8bd4a963-8e9d-5ff9-9297-fbaa7eb932a1 | note | Record - ITP Verification Checklist
964f7c42-78cc-5852-a6de-afde608e30e4 | note | Contractor: Resp - RSA
00bedcf8-b0cc-5b0c-95ba-e3aa54c33134 | note | Contractor: Type - CHK
f041d5f8-2943-577e-b696-6ccd56df65d2 | note | Client: Resp - Senex
3544b6ea-6296-5730-aa68-d43ba9b211ef | note | Client: Type - CHK
ffcf2ea3-3b63-485c-ac4f-60a2a625014c | checkpoint | 14 - Acceptance of works (RCP and Headwalls)
a33974fb-7bdb-5db2-9711-ae49f5392388 | note | Work By - Contractor
4f8018f3-bd4f-5252-bfd0-d84fe888fbdb | note | Standard / Spec - Technical Specification
17783560-c67d-5b09-b651-a91538d46e36 | note | Criteria - Conformance certificates supplied by manufacturer
e4d3aff1-d046-554d-8c6b-fb35d4c1502e | note | ○ All required test reports provided to client As-constructed survey data obtained
09d8b95d-e1f6-5a11-b04d-934f006fbc39 | note | Frequency - 1/Lot
1e8ec437-654f-5c75-8945-2769dfd34972 | note | Record - ITP Verification Checklist / MDR
356a35d8-ac0c-599a-a867-99981015b776 | note | Contractor: Resp - RSA
45fc8972-ecdf-50e4-b678-265b9d7ed7e4 | note | Contractor: Type - CHK
2b1ceaa3-32d8-586e-89b6-38ae36e8f8db | note | Client: Resp - Senex
8463216e-b36d-5c74-9f77-c9ab7c48d273 | note | Client: Type - HP
b59c9d20-9eb7-43a4-9fe7-a600aefe1ebf | signoff | HOLD POINT
d0e4a9d1-9dd3-47c5-92b7-68739d3fc828 | checkpoint | Built in accordance with this document:
2358a29c-c727-5a30-ae20-1c56bf9832fa | date | Date
936fec08-1e3a-4f2b-a805-a947cecff859 | signoff | Signed
45920bc5-b6c6-4053-a7e2-5a72ed90f448 | checkpoint | Test results received. Lot conforms to Specification:
27137127-c756-599c-abfb-b78521a3a2e4 | date | Date
473252cc-66d8-4d1a-94bf-35d3e4f0ea3e | signoff | Signed
23816b61-3f05-40d5-a439-3614468d84d6 | checklist | ITP008 - LD - Installation of Leak Detection Pipe and Sump - Rev0 | itp | ITP008 - LD - Installation of Leak Detection Pipe and Sump
74d3ac93-eae9-45a0-8dfc-2f33ec92939a | section | Inspection and Test Plan Details
7771e73d-e59d-4e13-8547-c4d93ec51db4 | checkpoint | 01 - Lot Identification
89fc30bc-fe4e-5d6f-a1cc-6ecd7771754d | note | Work By - Contractor
f052cd8b-cbb0-5e94-ba84-72603edd38b8 | note | Standard / Spec - Technical Specification
99f434a0-faa4-5e55-9ea3-130e64f37786 | note | Criteria - Location of works identified as per IFC drawings
84d1cc76-81af-567b-9d7f-7c5d8f564fc1 | note | Frequency - 1/Lot
2aa8da33-9a5d-5419-a96e-73afbe5c53ee | note | Record - ITP Verification Checklist/Lot drawing
a891025e-dc46-5eb6-90b5-ca0f6f5a7641 | note | Contractor: Resp - RSA
b759bf22-e24e-580f-8651-22eee29c7754 | note | Contractor: Type - CHK
6606d91e-aca6-5b23-87b3-8ef175634b88 | note | Client: Resp - Senex
58e9320d-462a-512f-bc81-7a2b3f0c2039 | note | Client: Type - CHK
ffc5063c-662d-46b3-a707-f23ad50a89cd | checkpoint | 02 - Survey control and Setout
54ba90dc-be18-53e4-9bf0-233774af2375 | note | Work By - Contractor
9f2ba57a-52fc-5588-a0da-13bd793702d3 | note | Standard / Spec - Technical Specification
3639cdeb-0055-54ab-9cc5-d82281b20fb9 | note | Criteria - Confirm centres of both sump and tank locations
22c93ecf-dfaf-54a9-9786-ed237eeda515 | note | Frequency - 1/Lot
67449306-aadc-5fc8-a396-2969b92ca7b3 | note | Record - ITP Verification Checklist
f15121fc-dd28-57a1-8efb-d5dc1402a75c | note | Contractor: Resp - RSA
a9404649-ee04-5ea3-bb90-ade67c551423 | note | Contractor: Type - HP
41ebb80a-8a87-5cd3-a1cb-c1580c3ba452 | note | Client: Resp - Senex
9f97fb9e-0a34-5185-b409-555cf1b11413 | note | Client: Type - HP
1edd004c-ca05-4b20-8082-4de0232d10d1 | signoff | HOLD POINT
1082b116-d89b-470d-9726-827553d4ec34 | checkpoint | 03 - Excavation of sump
1b3a93fc-a43c-5723-9f99-9484a5502dbc | note | Work By - Contractor
be094ef6-83a5-5549-86f0-4464c8e85c3d | note | Standard / Spec - Technical Specification
79d3f1cd-34db-5fb1-a833-1e8f2622f9ee | note | Criteria - Located at 3m outside from the hinge point of the tank pad. To be trenched to a depth of 3.17 m (to be confirmed on site)
6e8b5ee3-86a0-5d44-b7da-646f547bb847 | note | ○ Sump excavated to correct dimensions in line with Concept Tanks (CT) OPS-ATLW- PE-GAR-004
0571edf4-6e4c-5bb4-bbde-206971b810d3 | note | ○ 0.8m diameter excavation to design depth. Sump pit depth to be determined onsite ensuring sufficient fall from tank centre to sump
3fbf2e9e-1a78-5dbb-91b0-89a1a02d4594 | note | Frequency - 1/Lot
de08f8d1-406b-5161-b960-c356c2626572 | note | Record - ITP Verification Checklist
45e8ac7a-8b83-584e-938f-eed77d0f07e8 | note | Contractor: Resp - RSA
0f430e4b-7cb6-5342-a387-6ef5f6a2531a | note | Contractor: Type - CHK
ac1ee677-1840-589b-b9ca-88326ca5db95 | note | Client: Resp - Senex
845db8aa-13e3-5eec-933d-f2d215088d41 | note | Client: Type - WP
8d7a0ad9-d42d-4f20-86d2-b5000383dd2e | checkpoint | 04 - Installation of HDPE sump base and chamber at correct height and level
99c11f57-6d9e-5cc8-9684-6116a0c85b2a | note | Work By - Contractor
deea2a4d-d5af-5cf3-91ec-666396f9d479 | note | Standard / Spec - Technical Specification
fb37d06a-e283-55c6-b895-df0256b65d5b | note | Criteria - Poly sump base to be installed at 200mm below leak detection pipe.
5956de95-6784-5b82-8122-ea179bc2c452 | note | ○ Sump chamber installed plumb to correct height minimum 150mm above top of tank
64ae9479-6b70-5c4f-9541-33c0a61e3b46 | note | Frequency - 1/Lot
6b750498-cbb9-501e-8f90-18ce355a7f5f | note | Record - ITP Verification Checklist
58c9dfa2-58b4-5313-95f1-a038dcbdb87d | note | Contractor: Resp - RSA
0a51b361-ce5c-56fd-aa72-c67bb339c137 | note | Contractor: Type - CHK
330b64c8-4322-5a63-8200-9e7d364d0d8e | note | Client: Resp - Senex
8bc3e3f6-4b71-590a-840a-5de2b111702e | note | Client: Type - WP
7f6a81af-b662-4ec0-a83e-946379558b89 | checkpoint | 05 - Backfill - Sump
aea541b0-fd95-58b4-8c03-8e6894942c79 | note | Work By - Contractor
567db715-1a71-5c34-a654-c69afc2a1a86 | note | Standard / Spec - Technical Specification
348ca8c5-1834-5491-b35a-7d83edd1e9d0 | note | Criteria - Backfill in accordance with CT requirements. Compaction testing in line with Earthworks specification
fc796905-aab8-56d1-b779-5c8ea4e5a147 | note | Frequency - 1/Lot
19fbd615-f8ae-59e5-944c-a795b3b83789 | note | Record - ITP Verification Checklist / Test
2c43f89b-2a62-57d4-905f-554068adcca5 | note | Contractor: Resp - RSA
4f8bf14e-6370-5910-b031-673b409036e5 | note | Contractor: Type - CHK
657e4027-0dc7-5369-8432-8015e7c6fd95 | note | Client: Resp - Senex
e1c07119-f891-5f6e-b19d-b7794bb2a284 | note | Client: Type - HP
f52b165c-5b9a-4f00-aa54-b59b660f6a8e | signoff | HOLD POINT
a9c5d1b7-d26a-44ac-b93b-922ccd880778 | checkpoint | 06 - Leakage pipe trench excavation
903f8893-332a-513a-a0db-d4e9f687b9bd | note | Work By - Contractor
ea8362cc-368e-5056-833a-f1d1619249da | note | Standard / Spec - Technical Specification
3a1d617c-7453-5e3b-bb21-6ba0fb44f37a | note | Criteria - Trench excavated to correct lines and levels in line with CES drawings.
565e18fd-8fea-524d-a0dd-fad1d7e91601 | note | ○ 1:100 fall to sump
f00207be-6dc5-5ab6-bd05-77c0efb6f2cb | note | ○ Sufficient excavation width to facilitate installation.
9ea9e39d-fc76-552d-a3ac-3951eb934c96 | note | Frequency - 1/Lot
7e0ec3a2-5f7a-58ef-9fab-abc65d16ea56 | note | Record - ITP Verification Checklist
4d33987d-0418-5f94-8dac-756b7c3feb8f | note | Contractor: Resp - RSA
b015f78f-3338-50f6-8c8b-4651501a040a | note | Contractor: Type - CHK
71c99b1e-39f9-5a64-8c29-a289d336093e | note | Client: Resp - Senex
f3c3f270-5a32-5226-aaf5-647ea50c8408 | note | Client: Type - WP
8ffe5a13-0246-4592-84bc-6d08c073dee3 | checkpoint | 07 - Installation of 50mm HDPE leakage pipe
b1a85353-56f1-5805-8b03-70e8d69ca58c | note | Work By - Contractor
c42ebcba-adb0-5b20-9ca8-3a0bf44c7778 | note | Standard / Spec - Technical Specification
661bdd1e-91c2-5bbe-b366-fd6682663ad6 | note | Criteria - 50mm HDPE pipe and bends installed in accordance with CT and manufacturer requirements.
65b6eb34-2b27-5aa9-9ced-df66df431f2a | note | ○ Minimum 150mm cover at centre of tank Pipe installed on 50mm sand bedding (optional) as per CT recommendations
3e655d60-d3d8-59ea-9a71-be5ee3c168ba | note | ○ HDPE pipe riser installed 300mm above FSL at centre of tank, temporary seal to prevent sediment ingress.
e32318a8-f36a-5d40-aff7-94cc68f6cb78 | note | ○ Pipe to be left exposed at centre of sump pit
19e14739-447d-5205-98c3-8eb49437af82 | note | Frequency - 1/Lot
16e15158-ead9-532b-a7bd-97d7346e3d88 | note | Record - ITP Verification Checklist
a64ec667-af27-503a-9968-e5a0aac66cd8 | note | Contractor: Resp - RSA
8a4d3fcf-c999-53cc-9775-293ea7a3a794 | note | Contractor: Type - CHK
8fe93426-1d00-5639-9660-8c87b08f5298 | note | Client: Resp - Senex
b5ecce18-22b1-54c6-9b52-124a73cc101e | note | Client: Type - WP
70a3f2a9-9b42-41ba-b331-762ed4ec1ab4 | checkpoint | 08 - Surface Water Runoff
3941b493-61e3-5ebc-90ca-bb9a9521cae5 | note | Work By - Contractor
a08f4684-ffb3-5d7f-ac2e-a95ef1b5af11 | note | Standard / Spec - Technical Specification
c565900d-4f63-5aca-a04c-266315d71ad6 | note | Criteria - DN110 HDPE pipe for construction surface water runoff to be installed 1:100 fall to swale drain
cd15d8fc-b2a1-52ff-9fd5-ec80bd83a4dc | note | Frequency - 1/Lot
6f59bfb6-8830-5bf6-9940-b623ad33f7a5 | note | Record - ITP Verification Checklist
40ec2b2d-c216-5232-a7bf-cf1e5ca530a1 | note | Contractor: Resp - RSA
362b1d64-b86d-56cb-9086-34f83864b31f | note | Contractor: Type - CHK
b30c4202-d943-57b6-8cbe-7ec87c88b7ce | note | Client: Resp - Senex
0febc477-5656-59b3-9934-668d86647ea7 | note | Client: Type - WP
98e1ab92-f1ed-49b8-83c8-debd63cd13dd | checkpoint | 09 - Backfill - Trench
b501b653-d08f-5ea2-9de2-4a06049aeefd | note | Work By - Contractor
311d4b4e-98f3-5e0a-88c7-1d89bf7876ef | note | Standard / Spec - Technical Specification
46b3a24c-7697-571a-9be0-166d4ba19ce1 | note | Criteria - Backfill in accordance with CES requirements and general earthworks specifications
a81091f6-7e3d-59d3-9a9f-917463adc399 | note | ○ 98% +/-2% moisture (Ring beam area) 96% +/-2% moisture (All other areas)
d15e4433-255a-5749-838f-022da5657b37 | note | Frequency - Min 2 tests per lot
a0908c5d-6b40-51fa-8ea9-d35073756c38 | note | Record - ITP Verification Checklist / Test Report
1a121b23-fda4-5760-9ab1-01ad893749c5 | note | Contractor: Resp - RSA
da542c80-23ca-58f2-bb9c-a6dda2f672ca | note | Contractor: Type - CHK
b8a09166-e44b-55af-9377-8254b4f977f4 | note | Client: Resp - Senex
3426d827-0121-5fc0-abee-fc80aa96b034 | note | Client: Type - WP
757f060e-3f20-4eb8-9392-d53376a3a9b6 | checkpoint | 10 - Acceptance of work
db63b03f-eb74-5682-8513-a6fcc863605a | note | Work By - Contractor
a2ca1720-fa0a-579e-93d4-1bb32f724f80 | note | Standard / Spec - Technical Specification
f26f87b8-0773-5295-8857-3d33eee4d6a1 | note | Criteria - Work completed in accordance with CES requirements.
3a99c983-8509-5348-a89c-3fa5ec24b796 | note | Compaction reports received and meeting specification
8207ae4a-4d5e-5b59-9a4a-62e581b2120f | note | As-constructed survey data obtained
ce1bf48e-c465-5fec-8a18-b48fa59e1a13 | note | Frequency - Once per lot
b0685795-4b44-5eb7-bb26-7af3bd080570 | note | Record - ITP Verification Checklist
160768ba-a7e9-5661-9dd7-808e75a7f6d8 | note | Contractor: Resp - RSA
20ccf25c-fe23-54e3-b185-01d5b04a51ec | note | Contractor: Type - CHK
ba199b9f-17ee-5d6c-8938-f03d3ba6642a | note | Client: Resp - Senex
73122f2b-44b7-5cda-9226-8c9ef236272d | note | Client: Type - HP
521d0e1c-0795-4ac5-8507-d8bbdef49c67 | signoff | HOLD POINT
542ce5f2-1f3d-428b-9252-7b5e57986ba0 | checkpoint | Built in accordance with this document:
089671f6-0ede-5c6a-9187-1741f909bab5 | date | Date
c80459f2-8f18-4393-9f73-3b06e46d567a | signoff | Signed
27b7e197-db41-456d-aa42-fb3c713a1f90 | checkpoint | Test results received. Lot conforms to Specification:
c214869c-ed1e-5d2f-99b3-e8b1629acad3 | date | Date
af2ee744-335d-4b75-ab32-18989a30c564 | signoff | Signed