## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Checklist - ITP001 - CG - Clear and Grub | [5 empty] | Checklist - ITP001 - CG - Clear and Grub - Rev1
section | Details
checkpoint | Survey Set Out
label | Specifications - The contractor shall be responsible for engaging a licensed surveyor of Australia approved by the Superintendent to set out all works in accordance with the design drawings prior to the commencement of the works.
label | Type - WP
checkpoint | Site Services
label | Specifications - Contractor shall take reasonable steps to locate all existing service on the Site. Where existing services are identified they shall be clearly marked for the duration of the works.
label | Type - HP
holdpoint | HOLD POINT
checkpoint | Lot Identification
label | Specifications - Location of works identified in accordance with the Project Technical Specifications.
label | Type - CHK
checkpoint | Clearing
label | Specifications - Clearing shall be performed within the limits of the works indicated on the drawings.
label | ○ Trees, shrubs, logs, debris, perishable material, organic matter, fallen trees, overhanging branches and surface obstructions shall be removed from the stripping area.
label | Type - HP
holdpoint | HOLD POINT
checkpoint | Grubbing
label | Specifications - Roots from trees and large shrubs shall be excavated to the extent to be agreed with the Superintendent.
label | Type - CHK
checkpoint | Stockpile of Materials
label | Specifications - Cleared and grubbed materials shall be stockpiled or disposed of as directed by the superintendent
label | Type - CHK
checkpoint | Localised Holes
label | Specifications - Holes created by grubbing shall be filled with materials approved by the Company’s Representative and compacted to a density approved by the Company’s Representative
label | Type - CHK
checkpoint | Inspection and Verification Statement
label | Inspection: I declare that the above work has been inspected, and the recorded results of the inspections are correct.
textbox | Inspection - Inspected by:
label | Verification: I verify that the recorded results of the above inspections are correct.
textbox | Verification - Inspected by:
holdpoint | (Signed)
checklist | Checklist - ITP002 - Top Soil Stripping | [5 empty] | Checklist - ITP002 - Top Soil Stripping - Rev1
section | Details
checkpoint | Survey Set Out
label | Specifications - The contractor shall be responsible for engaging a licensed surveyor of Australia approved by the Superintendent to set out all works in accordance with the design drawings prior to the commencement of the works.
label | Type - WP
checkpoint | Lot Identification
label | Specifications - Location of works identified in accordance with the Project Technical Specifications
label | Type - CHK
checkpoint | Topsoil Stripping
label | Specifications - Topsoil shall be stripped such that all organic rich soil and roots/rootlets has been removed from the foundation of the embankment and internal borrow areas
label | ○ Topsoil shall be stripped to the depth(s) 200mm indicated on BOQ. Any areas with depth greater than 200mm should be notified to the superintendent.
label | Type - HP
holdpoint | HOLD POINT
checkpoint | Stockpile of Materials
label | Specifications - Stripped topsoil shall be stockpiled where directed by the Superintendent, for reuse. Topsoil Stockpiles to be ameliorated and treated as per company’s directions.
label | ○ Topsoil is to be placed in a loose, non-compacted state, to a maximum height of 3 metres
label | Type - HP
holdpoint | HOLD POINT
checkpoint | Survey after topsoil removal
label | Specifications - As-constructed survey has been completed to record the surface levels on completion of topsoil stripping.
label | ○ The Contractor shall submit results of each survey to the superintendent within 48hours of undertaking the Survey.
label | Type - HP
holdpoint | HOLD POINT
checkpoint | Inspection and Verification Statement
label | Inspection: I declare that the above work has been inspected, and the recorded results of the inspections are correct.
textbox | Inspection - Inspected by:
label | Verification: I verify that the recorded results of the above inspections are correct.
textbox | Verification - Inspected by:
holdpoint | (Signed)
checklist | Checklist - ITP003 - FP - Foundation Preparation | [5 empty] | Checklist - ITP003 - FP - Foundation Preparation - Rev1
section | Details
checkpoint | Lot Identification
label | Specifications - Location of work identified in accordance with project technical specification
label | Type - CHK
checkpoint | Compaction Trial
label | Specifications - Compaction trial for general fill will be completed and approved by the client
label | Type - CHK
checkpoint | Foundation Preparation Inspection
label | Specifications - Foundation preparation of Lot will be inspected for material type, moisture and organic material prior to foundation preparation works.
label | Type - VIS
checkpoint | Foundation Preparation – Proof Rolling
label | Specifications - Subgrade shall be Proof Rolled in accordance with Queensland Department of Main Roads Technical Specification (MRTS) 04 General Earthworks Section 18.3.2 or similar method as approved by the Superintendent while in the presence of the Client.
label | ○ Areas of subgrade identified by the superintendent as unsuitable material shall be excavated and replaced with material conforming to the requirements of the overlying fill zone
label | Type - WP
checkpoint | Foundation Preparation – Ground Surface Treatment
label | Specifications - Scarify minimum 150mm, moisture condition and compact.
label | ○ The Superintendent shall inspect the subgrade for conformance with the specification prior to placement of overlying fill.
label | Type - HP
holdpoint | HOLD POINT
checkpoint | Foundation Preparation – Smooth drum rolling of material
label | Specifications - Prior to the placemat of construction materials, the subgrade shall be rolled using a smooth drum roller to form a hard-smooth surface and approved by the superintendent.
label | Type - HP
holdpoint | HOLD POINT
checkpoint | Ground Surface Treatment Testing
label | Specifications - The foundation surface level shall be scarified, watered and compacted to a density ratio of no less than 96% of standard MDD and -+2 % of OMC
label | Type - HP
holdpoint | HOLD POINT
checkpoint | As built Survey
label | Specifications - Finished levels checked for Vertical and horizontal tolerances as required.
label | Type - HP
holdpoint | HOLD POINT
checkpoint | Inspection and Verification Statement
label | Inspection: I declare that the above work has been inspected, and the recorded results of the inspections are correct.
textbox | Inspection - Inspected by:
label | Verification: I verify that the recorded results of the above inspections are correct.
textbox | Verification - Inspected by:
holdpoint | (Signed)
checklist | Checklist - ITP004 - EC - Embankment Construction | [5 empty] | Checklist - ITP004 - EC - Embankment Construction - Rev1
section | Details
checkpoint | Lot Identification
label | Specifications - Location of Works identified in accordance with project technical specification
label | Type - CHK
checkpoint | Underlying Lot Conforms
label | Specifications - Foundation preparation works completed in underlying lot
label | Type - CHK
checkpoint | General Fill Material Requirement
label | Specifications - Grading Requirements
label | ○ 75mm sieve –100% passing
label | ○ 19mm Sieve - 70 to 100% passing
label | ○ 2.36mm sieve - 30 to 100 % passing
label | ○ 0.075mm Sieve –15-90% passing
label | Indicator requirements
label | ○ Plasticity Index – 10 to 40%
label | ○ Liquid Limit – 20 to 60%
label | ○ Emerson Class 2 (minimum)
label | ○ Organic content 2% (maximum)
label | Type - WP
checkpoint | Fill placement
label | Specifications - Placed in continuous, approximately horizontal layers for the full width of the area, having a compacted thickness of not more than 300 mm or less than 150 mm. If the surface of any layer is smooth, it must be scarified to a depth of approximately 30 to 50 mm prior to the placement of the next layer.
label | ○ ≥ 96 % standard MDD.
label | ○ NOTE: 98% standard MDD for the Earthen Ring Beam General Fill Section.
label | ○ -2% to +2% of OMC
label | Type - WP
checkpoint | Testing
label | Specifications - SDDR – 3 per 2500m3
label | ○ PSD – 2 per 2500m3
label | ○ Atterberg – 2 per 2500m3
label | ○ Emerson – 2 per 2500m3
label | ○ General fill – Earth Ring Beam
label | ○ SDDR – 1 every 50 m(lineal)
label | Type - HP
holdpoint | HOLD POINT
checkpoint | Survey
label | Specifications - RSA shall submit 0% and 100% tank pad foundation fill placement completion survey to the superintendent within 48 hours of each milestone achievement
label | Type - HP
holdpoint | HOLD POINT
checkpoint | Inspection and Verification Statement
label | Inspection: I declare that the above work has been inspected, and the recorded results of the inspections are correct.
textbox | Inspection - Inspected by:
label | Verification: I verify that the recorded results of the above inspections are correct.
textbox | Verification - Inspected by:
holdpoint | (Signed)
checklist | Checklist - ITP005 - CL - Capping Layer | [5 empty] | Checklist - ITP005 - CL - Capping Layer - Rev1
section | Details
checkpoint | Lot Identification
label | Specifications - Location of work identified in accordance with project technical specification
label | Type - CHK
checkpoint | Compaction Trial
label | Specifications - Compaction Trial to be completed and approved
label | Type - CHK
checkpoint | Material Approval
label | Specifications - Material shall meet the requirements under Queensland Department of Main Roads Technical Specification (MRTS)05 Type 2.5
label | Type - check
checkpoint | Proof Rolling Subgrade acceptance
label | Specifications - Main Roads Technical Specification (MRTS) 04 General Earthworks Section 18.3.2 or similar method as approved by the Superintendent while in the presence of the Client
label | Type - WP
checkpoint | Placement of material
label | Specifications - Access track and ring road capped with 200 mm depth gravel. Placed in continuous, approximately horizontal layers having a compacted thickness of not less than 75 mm and not more than 200 mm. If the surface of any layer is smooth it must be lightly scarified to a depth of approximately 30 to 50 mm prior to the placement of the next layer.
label | Type - CHK
checkpoint | Material Testing
label | Specifications - Capping Material shall be tested for material characteristics, moisture, and compaction.
label | ○ >98% SDDR
label | ○ -2% dry to +2% wet OMC
label | Capping Material:
label | ○ SDDR – 3 per 500m3
label | ○ PSD – 2 per 500m3
label | ○ Atterberg – 2 per 500m3
label | ○ CBR – 2 per 500m3
label | Type - HP
holdpoint | HOLD POINT
checkpoint | As built Survey
label | Specifications - Finished levels checked for Vertical and horizontal tolerances as required.
label | Type - HP
holdpoint | HOLD POINT
checkpoint | Inspection and Verification Statement
label | Inspection: I declare that the above work has been inspected, and the recorded results of the inspections are correct.
textbox | Inspection - Inspected by:
label | Verification: I verify that the recorded results of the above inspections are correct.
textbox | Verification - Inspected by:
holdpoint | (Signed)
checklist | Checklist - ITP006 - Surface Water Runoff Management | [5 empty] | Checklist - ITP006 - Surface Water Runoff Management - Rev1
section | Details
checkpoint | Lot Identification
label | Specifications - Location of works identify as per IFC drawings
label | Type - CHK
checkpoint | Gypsum Application
label | Specifications - Apply gypsum to batters and table drains at rate of 5t/ha, scarify subsoil to a minimum depth of 150mm and apply 10mm/m2 to create adequate topsoil bond with the subgrade.
label | Type - CHK
checkpoint | Topsoil Amelioration
label | Specifications - Topsoil to be ameliorated with DAP Fertilizer at the rate of 150kg per Ha. If required.
label | Type - CHK
checkpoint | Respreading of Topsoil
label | Specifications - Topsoil is to be placed 300mm thick and trim with grader and scarify to a depth of 100mm.Surface left in a roughened state with horizontal rills running across the slopes to minimise potential erosion.
label | Type - CHK
checkpoint | Seeding
label | Specifications - Topsoil to be seeded at sowing rate as per client requirements. If Required
label | Type - CHK
checkpoint | Watering of Topsoil
label | Specifications - Watering 10mm/m2 every day for first 8 days, then every second day to get to a total of 14 irrigation days. If required
label | Type - CHK
checkpoint | Inspection and Verification Statement
label | Inspection: I declare that the above work has been inspected, and the recorded results of the inspections are correct.
textbox | Inspection - Inspected by:
label | Verification: I verify that the recorded results of the above inspections are correct.
textbox | Verification - Inspected by:
holdpoint | (Signed)
checklist | Checklist - ITP007 - Erosion and Sediment Control Installation | [5 empty] | Checklist - ITP007 - Erosion and Sediment Control Installation - RevA
section | Details
checkpoint | Lot Identification
label | Specifications - Location of works identify as per IFC drawings
label | Type - Check
checkpoint | Clear identification and demarcation of ‘no go zones’ (where required)
label | Specifications - Remove vegetation and disturb soil only in those areas approved for construction work to occur.
label | Type - Check
checkpoint | Installation of temporary sediment and erosion control devices.
label | Specifications - Construction of earth bunds
label | ○ Installation of coir logs and
label | ○ Excavation of sediment catch sumps
label | ○ Generally in accordance with DWG 1484.00.010 and as agreed onsite.
label | Type - Check
checkpoint | Sediment and erosion control device ongoing inspections.
label | Specifications - Inspection of sediment and erosion control devices completed to be completed at the below frequencies
label | ○ Rain: >50mm in on day or >100mm over 4 days
label | ○ Prior to shift breaks
label | Type - Check
checkpoint | Underlying Lot conformance – Subgrade
label | Specifications - The Superintendent must have a visual inspection of the subgrade, prior to the placement of the Separation Geotextile
label | Type - Check
checkpoint | Conformance Separation Geotextile Material.
label | Specifications - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data
label | ○ Certificates
label | Type - Hold Point
holdpoint | HOLD POINT
checkpoint | Conformance Rip Rap
label | Specifications - The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data certificates.
label | Type - Hold Point
holdpoint | HOLD POINT
checkpoint | Separation geotextile placement.
label | Specifications - Installation method comply with the requirements of the technical specification and the IFC drawings.
label | ○ Separation Geotextile shall be weighted with sandbags or equivalent until covered with overlying materials.
label | ○ Laps to geotextiles shall be a minimum 0.6m
label | ○ The Superintendent shall inspect the placement of Geotextile for conformance with this Technical Specification prior to placement of overlying layers.
label | ○ Separation Geotextile must be covered by overlying construction activities within one week of being rolled out.
label | Type - Hold Point
holdpoint | HOLD POINT
checkpoint | Geotextile Repairs (if required).
label | Specifications - Area cleared of soil or other deleterious materials.
label | ○ A patch placed from the same Geotextile of minimum 0.6 m lap to intact Geotextile on all sides and final patch approved by the Superintendent.
label | Type - Hold Point
holdpoint | HOLD POINT
checkpoint | Rip Rap Placement
label | Specifications - Rip Rap shall be provided to superintendent.
label | ○ Rip rap to be placed by excavator over the separation geotextile.
label | ○ Rock finished smoothed to the final lines and levels
label | Type - Hold Point
holdpoint | HOLD POINT
checkpoint | Acceptance of works (Rip rap).
label | Specifications - The Superintendent must approve the finish surface and underlying separation geotextile installation of the Rip Rap prior to completion of works.
label | Type - Hold Point
holdpoint | HOLD POINT
checkpoint | RCP Installation
label | Specifications - Excavation to design invert levels allowing for 100mm bedding sand (or equivalent)
label | ○ Rubber ring joint Class 2 RCP installed with barrels laid straight free from damage.
label | ○ Sand (or equivalent) haunching and overlay to approximately 150mm above pipe
label | ○ Foundation to be tested for bearing capacity of 100kPa
label | Type - Check
checkpoint | Backfilling
label | Specifications - Trench backfilled and tested in line with requirements for Fill
label | ○ 95% +/-2% moisture
label | Type - Check
checkpoint | Headwall
label | Specifications - Headwalls installed on 100mm sand bedding to required invert levels
label | ○ Headwall installed flush with RCP pipe and grouted neat.
label | Type - Check
checkpoint | Acceptance of works (RCP and Headwalls)
label | Specifications - Conformance certificates supplied by manufacturer
label | ○ All required test reports provided to client
label | ○ As-constructed survey data obtained
label | Type - Hold Point
holdpoint | HOLD POINT
checkpoint | Inspection and Verification Statement
label | Inspection: I declare that the above work has been inspected, and the recorded results of the inspections are correct.
textbox | Inspection - Inspected by:
label | Verification: I verify that the recorded results of the above inspections are correct.
textbox | Verification - Inspected by:
holdpoint | (Signed)
checklist | Checklist - ITP008 - LD - Installation of Leak Detection Pipe and Sump | [5 empty] | Checklist - ITP008 - LD - Installation of Leak Detection Pipe and Sump - Rev0
section | Details
checkpoint | Lot Identification
label | Specifications - Location of works identified as per IFC drawings
label | Type - Check
checkpoint | Survey control and Setout
label | Specifications - Confirm centres of both sump and tank locations
label | Type - Hold Point
holdpoint | HOLD POINT
checkpoint | Excavation of sump
label | Specifications - Location Minimum 3m from outside edge of ring beam (to be confirmed)
label | ○ Sump excavated to correct dimensions in line with Concept Environmental Services (CES) DWG 221212-DR-004.
label | ○ 0.8m diameter excavation to design depth. Sump pit depth to be determined onsite ensuring sufficient fall from tank centre to sump
label | Type - Check
checkpoint | Installation of HDPE sump base and chamber at correct height and level
label | Specifications - Poly sump base to be installed at 200mm below leak detection pipe.
label | ○ Sump chamber installed plumb to correct height minimum 150mm above top of tank
label | Type - Witness point
checkpoint | Backfill – Sump
label | Specifications - Backfill in accordance with CES requirements. Compaction testing in line with Earthworks specification.
label | Type - Hold Point
holdpoint | HOLD POINT
checkpoint | Leakage pipe trench excavation
label | Specifications - Trench excavated to correct lines and levels inline with CES drawings.
label | ○ 1:50 (2%) fall to sump (TBC)
label | ○ Sufficient excavation width to facilitate installation.
label | Type - Witness point
checkpoint | Installation of 50mm HDPE leakage pipe
label | Specifications - 50mm HDPE pipe and bends installed in accordance with CES and manufacturer requirements.
label | ○ Minimum 150mm cover at centre of tank
label | ○ Pipe installed on 50mm sand bedding (optional) as per CES recommendations
label | ○ HDPE pipe riser installed 300mm above FSL at centre of tank, temporary seal to prevent sediment ingress.
label | ○ Pipe to be left exposed at centre of sump pit
label | Type - Witness point
checkpoint | Backfill – Trench
label | Specifications - Backfill in accordance with CES requirements and general earthworks specifications
label | ○ 98% +/-2% moisture (Ring beam area)
label | ○ 95% +/-2% moisture (All other areas)
label | Type - Witness point
checkpoint | Acceptance of work
label | Specifications - Work completed in accordance with CES requirements.
label | ○ Compaction reports received and meeting specification
label | ○ As-constructed survey data obtained
label | Type - Hold Point
holdpoint | HOLD POINT
checkpoint | Inspection and Verification Statement
label | Inspection: I declare that the above work has been inspected, and the recorded results of the inspections are correct.
textbox | Inspection - Inspected by:
label | Verification: I verify that the recorded results of the above inspections are correct.
textbox | Verification - Inspected by:
holdpoint | (Signed)