## Sheet1
1 | Documen Submission As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan | Check that proper safety procedures are being followed and environmental controls are in place, including traffic management | Check Item | 1 - Documen Submission As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan | Acceptance Criteria CHAR(AMP) Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management | Check Item - Check Item | Reference - | 1 - Documen Submission As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
Acceptance Criteria CHAR(AMP) Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management
2 | Traffic and Safety Controls Traffic and safety controls are in place (eg. PPE, daily plant check) | Check traffic CHAR(AMP) safety controls have been implemented as per plan | Check Item | 2 - Traffic and Safety Controls Traffic and safety controls are in place (eg. PPE, daily plant check) | Acceptance Criteria CHAR(AMP) Frequency (Project Specific) - Check traffic CHAR(AMP) safety controls have been implemented as per plan | Check Item - Check Item | Reference - | Check Item - Check Item
Reference -
3 | Asphalt Quality Plan The Contractor must develop an Asphalt Quality Plan (AQP). The AQP must be submitted to the Administrator for consideration at least seven days prior to work commencing and must be implemented. | Approval | MILESTONE | 3 - Asphalt Quality Plan The Contractor must develop an Asphalt Quality Plan (AQP). The AQP must be submitted to the Administrator for consideration at least seven days prior to work commencing and must be implemented. | Acceptance Criteria CHAR(AMP) Frequency (Project Specific) - Approval | Check Item - MILESTONE | Reference - Clause 5.2 MRTS30 | 2 - Traffic and Safety Controls Traffic and safety controls are in place (eg. PPE, daily plant check)
|  |  | Clause 5.2 MRTS30 |  |  |  |  | Acceptance Criteria CHAR(AMP) Frequency (Project Specific) - Check traffic CHAR(AMP) safety controls have been implemented as per plan
4 | Compliance Testing Compliance Testing shall be carried out for each lot. The Testing Frequencies shall not be less than those listed in Tables 5.4.1-A, 5.4.1-B and 5.4.1-D | Check CHAR(AMP) Verify | Check Item | 4 - Compliance Testing Compliance Testing shall be carried out for each lot. The Testing Frequencies shall not be less than those listed in Tables 5.4.1-A, 5.4.1-B and 5.4.1-D | Acceptance Criteria CHAR(AMP) Frequency (Project Specific) - Check CHAR(AMP) Verify | Check Item - Check Item | Reference - Clause 5.4.1 MRTS30 | Check Item - Check Item
|  |  | Clause 5.4.1 MRTS30 |  |  |  |  | Reference -
5 | Binder Class Contractor shall provide evidence of the binder conformance and compliance with MRTS17 Bitumen or MRTS18 Polymer Modified Binder The Binder Class are specified in Clause 1 of Annexure MRTS30.1 and are: | Check CHAR(AMP) Verify | Check Item | 5 - Binder Class Contractor shall provide evidence of the binder conformance and compliance with MRTS17 Bitumen or MRTS18 Polymer Modified Binder The Binder Class are specified in Clause 1 of Annexure MRTS30.1 and are: | Acceptance Criteria CHAR(AMP) Frequency (Project Specific) - Check CHAR(AMP) Verify | Check Item - Check Item | Reference - Clause 7.1.6 MRTS30 | 3 - Asphalt Quality Plan The Contractor must develop an Asphalt Quality Plan (AQP). The AQP must be submitted to the Administrator for consideration at least seven days prior to work commencing and must be implemented.
|  |  | Clause 7.1.6 MRTS30 |  |  |  |  | Acceptance Criteria CHAR(AMP) Frequency (Project Specific) - Approval
6 | Moisture Sensitivity For dense graded asphalt, the tensile strength ratio (TSR) must be ≥ 80% and the average tensile strength of the freeze/thaw group must be 500 kPa for polymer modified binders and 600kPa for mixes containing all other binders. Table 7.2.5 is a list of accepted non-conformance strength ratio for 70% ≥ Where a Hold Point is required to be observed, the Contractor shall investigate the causes of the nonconformance and propose corrective action to prevent recurrence of the nonconformance. The Contractor shall submit: a) test results covering the same Lot for insitu air voids and all characteristics specified in Clause 9.2, and b) the proposed corrective action to achieve conformance. The Administrator shall consider the submitted documents prior to authorising the release of the Hold Point allowing recommencement of asphalt production. | Approval | HOLD POINT | 6 - Moisture Sensitivity For dense graded asphalt, the tensile strength ratio (TSR) must be ≥ 80% and the average tensile strength of the freeze/thaw group must be 500 kPa for polymer modified binders and 600kPa for mixes containing all other binders. Table 7.2.5 is a list of accepted non-conformance strength ratio for 70% ≥ Where a Hold Point is required to be observed, the Contractor shall investigate the causes of the nonconformance and propose corrective action to prevent recurrence of the nonconformance. The Contractor shall submit: a) test results covering the same Lot for insitu air voids and all characteristics specified in Clause 9.2, and b) the proposed corrective action to achieve conformance. The Administrator shall consider the submitted documents prior to authorising the release of the Hold Point allowing recommencement of asphalt production. | Acceptance Criteria CHAR(AMP) Frequency (Project Specific) - Approval | Check Item - HOLD POINT | Reference - Clause 7.2.5 MRTS30 | Check Item - MILESTONE
|  |  | Clause 7.2.5 MRTS30 |  |  |  |  | Reference - Clause 5.2 MRTS30
7 | Asphalt Contractor Prequalification CHAR(AMP) Operation Procedures At least 7days before asphalt is incorporated the Contractor shall notify the Administrator in writing of the identify and address of the PAC (Prequalified Asphalt Contractor) and their operation procedures. Operation procedures a) laying program and rolling pattern b) details of any required placement trial and Technical Standard, MRTS30 Dense Graded and Open Graded Asphalt Main Roads Specifications and Technical Standards c) Inspection and test plan. | Approval | Check Item | 7 - Asphalt Contractor Prequalification CHAR(AMP) Operation Procedures At least 7days before asphalt is incorporated the Contractor shall notify the Administrator in writing of the identify and address of the PAC (Prequalified Asphalt Contractor) and their operation procedures. Operation procedures a) laying program and rolling pattern b) details of any required placement trial and Technical Standard, MRTS30 Dense Graded and Open Graded Asphalt Main Roads Specifications and Technical Standards c) Inspection and test plan. | Acceptance Criteria CHAR(AMP) Frequency (Project Specific) - Approval | Check Item - Check Item | Reference - Clause 6 MRTS30 | 4 - Compliance Testing Compliance Testing shall be carried out for each lot. The Testing Frequencies shall not be less than those listed in Tables 5.4.1-A, 5.4.1-B and 5.4.1-D
|  |  | Clause 6 MRTS30 |  |  |  |  | Acceptance Criteria CHAR(AMP) Frequency (Project Specific) - Check CHAR(AMP) Verify
Check Item - Check Item
Reference - Clause 5.4.1 MRTS30
5 - Binder Class Contractor shall provide evidence of the binder conformance and compliance with MRTS17 Bitumen or MRTS18 Polymer Modified Binder The Binder Class are specified in Clause 1 of Annexure MRTS30.1 and are:
Acceptance Criteria CHAR(AMP) Frequency (Project Specific) - Check CHAR(AMP) Verify
Check Item - Check Item
Reference - Clause 7.1.6 MRTS30
6 - Moisture Sensitivity For dense graded asphalt, the tensile strength ratio (TSR) must be ≥ 80% and the average tensile strength of the freeze/thaw group must be 500 kPa for polymer modified binders and 600kPa for mixes containing all other binders. Table 7.2.5 is a list of accepted non-conformance strength ratio for 70% ≥ Where a Hold Point is required to be observed, the Contractor shall investigate the causes of the nonconformance and propose corrective action to prevent recurrence of the nonconformance. The Contractor shall submit: a) test results covering the same Lot for insitu air voids and all characteristics specified in Clause 9.2, and b) the proposed corrective action to achieve conformance. The Administrator shall consider the submitted documents prior to authorising the release of the Hold Point allowing recommencement of asphalt production.
Acceptance Criteria CHAR(AMP) Frequency (Project Specific) - Approval
Check Item - HOLD POINT
Reference - Clause 7.2.5 MRTS30
7 - Asphalt Contractor Prequalification CHAR(AMP) Operation Procedures At least 7days before asphalt is incorporated the Contractor shall notify the Administrator in writing of the identify and address of the PAC (Prequalified Asphalt Contractor) and their operation procedures. Operation procedures a) laying program and rolling pattern b) details of any required placement trial and Technical Standard, MRTS30 Dense Graded and Open Graded Asphalt Main Roads Specifications and Technical Standards c) Inspection and test plan.
Acceptance Criteria CHAR(AMP) Frequency (Project Specific) - Approval
Check Item - Check Item
Reference - Clause 6 MRTS30