## Structure
Job Name: 106661 - Bert Sutcliffe Dementia fence
Main area/First click | Level/2nd click | Apartment/3rd click | checklist needed
Main Building
Dementia Ward
|  | Outdoor Dementia area | Framed and Semi-Framed Glass Checklist

## Checklists
type | name | values
checklist | Frameless Glass Checklist
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install Spacers, Backing Channel and Clamps
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Glass, wedges and glazing rubbers as per PS1
checkpoint | Install Front covers, Inner and Top Rail and End Caps
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Framed Baluster Checklist
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install posts and Panels
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Inner and Top Rail and Endcaps
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Postless Baluster Checklist
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install Spacers and Backing Channel
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Panels
checkpoint | Install Inner and Top Rail and Endcaps
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Frameless Glass arena point Checklist
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install Spacers,
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Glass, wedges and glazing rubbers as per PS1
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Framed and Semi-Framed Glass Checklist
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install posts
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Glass, wedges and glazing rubbers as per PS1
checkpoint | Install Inner and Top Rail and Endcaps
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Uni-Rail Checklist
checkpoint | Work area acceptable & approval to start work
label | Latest drawings available, checked and referenced
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Install posts and Panels
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Rail Brackets, Leada Rail and End Caps
checkpoint | Silicone gaps, Confirm not bigger than 2mm
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
checklist | Stairs (add to previous if required)
checkpoint | Install J-Mounts, Leada Rail and End Caps
checkpoint | Silicone gaps, Confirm not bigger than 2mm
checkpoint | All work completed, reviewed and approved
checklist | Arena point hand rails
checkpoint | Install J-Mounts, Leada Rail and End Caps
checkpoint | Ends fixed to wall and polished
checkpoint | All work completed, reviewed and approved

## Checklist word meaning
checkpoint = | pass/fail/N/A
label = | additional text on a checkpoint
text = | empty text box
button = | up to 3 boxes you can select
select = | drop down with multiple options to select
bool = | tick box