## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2672-ITP-S123 - CFA Piling Overarching - Rev 1 | itp |  |  |  |  | DS2672-ITP-S123 - CFA Piling Overarching - Rev 1
section | 7.01 Piling General
checkpoint | 7.01.01 - Method Statements
label | Acceptance / Conformance Criteria - A detailed method statement shall be prepared by the Constructor for the Designer’s review for each piling operation undertaken on the site.
label | Standard / Specification - 51/33669 - 3.2, 4
label | Verifying Document - Method Statement
label | Frequency - 3 weeks prior to the commencement of each piling operation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.01.02 - Change of piling supervisor, crew of excavation method
label | Acceptance / Conformance Criteria - When a change is made to the piling crew, excavation method or other change (e.g. variations in ground conditions) that could influence the quality of the works, the Designer may adjust the inspection requirement and frequency to suit the revised risk profile of the works.
label | Standard / Specification - 51/33669 - 6.3.2
label | Verifying Document - Notice
label | Frequency - When a change is made
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 7.01.03 - Non-conformances
label | Acceptance / Conformance Criteria - Non-conformance "make good" measure agreed with Engineer and subsequently completed.
label | Standard / Specification - 3.8.1
label | Verifying Document - NCR
label | Frequency - As required
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checklist | DS2672-ITP-S123 - CFA Piling Materials - Rev 1 | itp |  |  |  |  | DS2672-ITP-S123 - CFA Piling Materials - Rev 1
section | 4.07 Piling Materials
checkpoint | 4.07.01 - Piling Supervisor
label | Acceptance / Conformance Criteria - A suitably qualified and experienced person shall be nominated by the Constructor as the ‘Piling Supervisor’.
label | Standard / Specification - 51/33669 - 3.9
label | Verifying Document - Supervisor Approval
label | Frequency - Prior to any piling works commencing.
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 4.07.02 - Pile Mix Design
label | Acceptance / Conformance Criteria - The Designer shall be provided with the proposed concrete mix design for review, prior to any piling works commencing.
label | Standard / Specification - 51/33669 - 5.1
label | Verifying Document - Mix Design
label | Frequency - Prior to any piling works commencing.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.07.03 - Reinforcement Cage Fabrication Inspection
label | Acceptance / Conformance Criteria - Designer inspection of reinforcement cage fabrication process for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure)
label | Standard / Specification - 51/33669 - 9.4
label | Verifying Document - Hold Point Release
label | Frequency - First pile at every structure
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.07.04 - CFA Pile Construction Record Card Template
label | Acceptance / Conformance Criteria - Supply a template for the CFA pile construction record card a minimum of 3 weeks prior to the commencement of any piling works.
label | Standard / Specification - 51/33669 - 9.1
label | Verifying Document - Construction Record Card Template
label | Frequency - 3 weeks prior to the commencement of any piling
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checklist | DS2672-ITP-S123 - CFA Trial Pile Hold Points - Rev 1 | itp |  |  |  |  | DS2672-ITP-S123 - CFA Trial Pile Hold Points - Rev 1
section | 7.07 First Pile at Every Structure
checkpoint | 7.07.01 - Inspection of Reinforcement Cages Prior to Installation
label | Acceptance / Conformance Criteria - Designer inspection of the reinforcement cage for the reinforced trial pile.
label | Standard / Specification - 51/33669 - 9.4
label | Verifying Document - Reinforcement Cage Inspection Record
label | Frequency - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.07.02 - Concreting of Piles
label | Acceptance / Conformance Criteria - Designer inspection of concreting for the reinforced and unreinforced trial piles.
label | Standard / Specification - 51/33669 - 9.4
label | Verifying Document - Pile Construction Record Card
label | Frequency - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.07.03 - Compression Testing
label | Acceptance / Conformance Criteria - A set of specimens for concrete tests shall be taken for each trial pile at the following intervals:
label | a. Unreinforced trial pile: 24hrs (3no), 3 days (3no)
label | b. Reinforced trial pile: 3 days (1no), 7 days (2no), 14 days (2no), 21 days (2no) and 28 days (2no).
label | Standard / Specification - GHD-Piling Specs 2.1-3.7.1
label | Verifying Document - Test results
label | Frequency - Per pile
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.07.04 - Pile integrity testing (PIT)
label | Acceptance / Conformance Criteria - PIT completed on each pile after the concrete has achieved 75% of it's design strength (75% of 25MPa = 18.75MPa). Preliminary PIT results to be submitted to Designer within 24 hrs of testing being done. Final report to be submitted within 10 days of completion of testing for Designer's review.
label | Standard / Specification - GHD-Piling Specs 2.1-3.7.2 & 8.1
label | Verifying Document - Test results
label | Frequency - Per pile
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.07.05 - Pile Excavation
label | Acceptance / Conformance Criteria - Unreinforced pile only to be to be exhumed to a minimum of 3m after PIT testing. To be photographed over the full length exposed and measurement of pile dimensions to be recorded at max. 500mm intervals. Results to be provided to GHD.
label | Standard / Specification - GHD-Piling Specs 2.1-3.7 & 3.7.3
label | Verifying Document - Photos
label | Frequency - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checklist | DS2672-ITP-S123 - CFA Piling First Pile Hold Points - Rev 1 | itp |  |  |  |  | DS2672-ITP-S123 - CFA Piling First Pile Hold Points - Rev 1
section | 7.07 First Pile at Every Structure
checkpoint | 7.07.01 - Inspection of any Reinforcement Cage Extension
label | Acceptance / Conformance Criteria - Designer inspection of reinforcement cage extensions for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure).
label | Standard / Specification - 51/33669 - 9.4
label | Verifying Document - Reinforcement Cage Inspection Record
label | Frequency - First pile at every structure with the Opportunity to inspect remainder
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.07.02 - Inspection of Reinforcement Cages Prior to Installation
label | Acceptance / Conformance Criteria - Designer inspection of the reinforcement cage for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure).
label | Standard / Specification - 51/33669 - 9.4
label | Verifying Document - Photos
label | Frequency - First pile at every structure with the Opportunity to inspect remainder
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.07.03 - Concreting of Piles
label | Acceptance / Conformance Criteria - Designer inspection of concreting for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure).
label | Standard / Specification - 51/33669 - 9.4
label | Verifying Document - Pile Construction Record Card
label | Frequency - First pile at every structure with the Opportunity to inspect remainder
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.07.08 - Pile Head Preparation
label | Acceptance / Conformance Criteria - Designer inspection of the pile head prior to incorporation into the connecting structure for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure)
label | Standard / Specification - 51/33669 - 9.4
label | Verifying Document - Hold Point Release
label | Frequency - First pile at every structure
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checklist | DS2672-ITP-S123 - CFA Piling Logging Hold Points - Rev 1 | itp |  |  |  |  | DS2672-ITP-S123 - CFA Piling Logging Hold Points - Rev 1
section | 7.06 Class 2 Pile Inspection Requirements
checkpoint | 7.06.01 - Logging of Spoil Excavation
label | Acceptance / Conformance Criteria - Class 2 – 25% of piles, First 2 No. piles constructed and then at random as advised by the Designer, Geological conditions match ground model and design assumptions. Designer to complete material logging for the first pile for all structures with the Opportunity to complete (at random) for subsequent piles.
label | Standard / Specification - 51/33669 - 6.3.2
label | Verifying Document - Pile Construction Record Card
label | Frequency - First 2 No. piles constructed and then 25% at random as advised by the Designer
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checklist | DS2672-ITP-S123 - CFA Pile Construction Card - Rev 1 | itp |  |  |  |  | DS2672-ITP-S123 - CFA Pile Construction Card - Rev 1
section | 7.02 Setout and Excavation
checkpoint | 7.02.01 - Nature of Ground and Subsurface Conditions
label | Acceptance / Conformance Criteria - The Constructor shall inform the Designer where circumstances indicate that ground and / or groundwater conditions differ from those presented in the reports, indicated on the Drawings or interpreted from proof bores.
label | Standard / Specification - 51/33669 - 3.5
label | Verifying Document - Notice
label | Frequency - Ongoing
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 7.02.02 - Pile Logging Inspection
label | Acceptance / Conformance Criteria - The logging of selected piles shall also be undertaken by the Designer to agree with the Constructor in identifying the founding stratum.
label | Standard / Specification - 51/33669 - 6.2.2
label | Verifying Document - Site Log
label | Frequency - Each Pour
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 7.02.03 - CFA Column Construction Control
label | Acceptance / Conformance Criteria - Digital records from the on board Jean Lutz system containing all information specified in 7.1 of the GHD Specification.
label | Standard / Specification - 51/33669 - 3.8.1
label | Verifying Document - Jean-Lutz output
label | Frequency - Each Pile
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 7.02.04 - Instrument Calibration
label | Acceptance / Conformance Criteria - Equipment used for monitoring shall be calibrated at the start of the Works and calibration certificates issued to the Designer prior to commencement. Depth tolerance = +/-50mm; concrete volume = +/-5%
label | Standard / Specification - 3.9.2
label | Verifying Document - Calibration certificates, record of depth measurement and concrete volume
label | Frequency - Depth = Prior to commencing
label | ○ Concrete = Varies; see 3.9.2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | 7.03 Pile Concreting
checkpoint | 7.03.01 - Reinforcement Cage Cover
label | Acceptance / Conformance Criteria - Pile reinforcement cages shall be located centrally within the pile excavation, such that final concrete cover to the extremities of the reinforcement cages is not less than 75 mm at any location.
label | Standard / Specification - 51/33669 - 3.8.2
label | Verifying Document - Site Record
label | Frequency - Each Pile
label | Verification Activity: Activity - D
label | Verification Activity: By - SV / SE
section | 7.04 Concrete Pour
checkpoint | 7.04.01 - Delivery Dockets
label | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
label | Standard / Specification - RSV - CS - 1.9
label | Verifying Document - Dockets
label | Frequency - Each Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 7.04.02 - Compression Testing
label | Acceptance / Conformance Criteria - A set of specimens for concrete tests shall consist of four specimens from each major pour of concrete, one of which shall be tested at 7 days and the remaining three at 28 days after casting.
label | Standard / Specification - RSV - CS - 1.12
label | Verifying Document - Test Results
label | Frequency - Each Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
section | 7.05 Pile Post Pour
checkpoint | 7.05.01 - Pile Head Break Back
label | Acceptance / Conformance Criteria - Pile heads shall be broken back to achieve A slightly convex profile so that the middle of the pile is nominally 25 mm above the average level at the perimeter of the pile and a Type B construction joint in accordance with standard NZS3109:1997.
label | Standard / Specification - 51/33669 - 3.8.3
label | Verifying Document - Site Record
label | Frequency - Each Pile
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 7.05.02 - Pile As-builting
label | Acceptance / Conformance Criteria - On completion of pile installation and prior to incorporating any piles into the permanent works, the actual pile locations and verticality shall be confirmed by a suitably experienced surveyor.
label | Standard / Specification - 51/33669 - 3.7
label | Verifying Document - Survey Records
label | Frequency - 5 working days prior to incorporating any piles into the permanent works.
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | 7.05.03 - CFA Pile Construction Record Card
label | Acceptance / Conformance Criteria - Pile construction records shall be submitted to the Designer within 24 hours of completion of any particular pile. Copies of the records shall be retained on site and made available for inspection by the Designer as required.
label | Standard / Specification - 51/33669 - 7
label | Verifying Document - Pile Construction Record Card
label | Frequency - Within 24 hours of completion of any particular pile
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 7.05.04 - Pile integrity testing (PIT)
label | Acceptance / Conformance Criteria - PIT completed on each pile after the concrete has achieved 75% of it's design strength (75% of 25MPa = 18.75MPa). Preliminary PIT results to be submitted to Designer within 24 hrs of testing being done. Final report to be submitted within 10 days of completion of testing for Designer's review.
label | Standard / Specification - GHD-Piling Specs 2.1-3.7.2 & 8.1
label | Verifying Document - Test results
label | Frequency - First 3 No. piles constructed and then 10 % of piles selected by the Designer, following receipt of the construction record cards.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT