## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 558020-DOW-ITP-PC-0031_v3 (WIM South) | itp |  |  |  |  | 558020-DOW-ITP-PC-0031_v3 (WIM South)
section | 3.1 General Preliminary
checkpoint | 3.1.1 - Survey Setout
label | Standard/Specification - Downer
label | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - SV
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Service Location
label | Standard/Specification - Downer
label | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
label | Verifying Document - Service location documents
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.3 - Internal Permits
label | Standard/Specification - Downer
label | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.4 - External Permits
label | Standard/Specification - Downer
label | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.1.5 - Approved Construction Drawings
label | Standard/Specification - Downer
label | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 3.2 Receiving Materials/Parts - ANPR + Cabinet Pad Foundation
checkpoint | 3.2.1 - Concrete mix design
label | Standard/Specification - As per Design Specification 30Mpa
label | Acceptance Criteria - Concrete Mix design for each mix comply with the requirements of the Project Specification
label | Verifying Document - Concrete supplier mix designs
label | Frequency - Submitted to Client Engineer for approval before construction
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - Reinforcement
label | Standard/Specification - As per Design Specification
label | Acceptance Criteria - Reinforcing bars and mesh shall comply with AS/NZS4671:2001.
label | Verifying Document - Mill Certs
label | Frequency - Each Lot
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
section | 3.3 Receiving Materials/Parts - WIM plates + Ducts + Chamber
checkpoint | 3.3.1 - Galvansied Ducts
label | Standard/Specification - As per Design Specification
label | Acceptance Criteria - Galvanised steel pipe larger than DN 80 must be Schedule 40 Seamless Line Pipe to ASTM A106 and hot dip galvanised following fabrication
label | Verifying Document - Product data sheet/Docket
label | Frequency - Per Delivery/Batch
label | Inspection Type (Visual, other) - Visual, Document Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.3.2 - Concrete Chamber
label | Standard/Specification - As per Design Specification
label | Acceptance Criteria - Manholes or Precast Structures to be cast to NZS 3109 with surface finish to NZS 3114 standard
label | Verifying Document - Product data sheet/Docket
label | Frequency - Per Item/Batch
label | Inspection Type (Visual, other) - Visual, Document Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.3.3 - Embedment / Bedding
label | Standard/Specification - As per Design Specification
label | Acceptance Criteria - Free draining river cobble or similar bedding material
label | Verifying Document - IANZ Test Reports
label | Frequency - Prior to Works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.3.4 - Concrete mix design
label | Standard/Specification - As per Design Specification Minimum of 20Mpa
label | Acceptance Criteria - Concrete Mix design for each mix comply with the requirements of the Project Specification
label | Verifying Document - Concrete supplier mix designs
label | Frequency - Submitted to Client Engineer for approval before construction
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
section | 3.4 Receiving Materials - Pavement Materials
checkpoint | 3.4.1 - Mix Design Approval AC20
label | Standard/Specification - NZTA M10:2020 - 3.1 , 3.6
label | Acceptance Criteria - The Contractor’s mix design shall be assessed by the Engineer for compliance with the requirements of this specification including a production trial, job mix formula, and be currently Validated. The Engineer’s approval of the mix design is a prerequisite for its use.
label | Verifying Document - Approved Mix Design
label | Frequency - Prior to Use
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.2 - Mix Design Approval SMA10/12.5
label | Standard/Specification - NZTA M27:2020 - 3.1 , 3.6
label | Acceptance Criteria - The Contractor’s mix design shall be assessed by the Engineer for compliance with the requirements of this specification including a production trial, job mix formula, and be currently Validated. The Engineer’s approval of the mix design is a prerequisite for its use.
label | Verifying Document - Approved Mix Design
label | Frequency - Prior to Use
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.2 - Bitumen
label | Standard/Specification - NZTA P11: 2007
label | Acceptance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to Use
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
section | 3.5 Receiving Materials/Parts - Shoulder Widening and Sealing
checkpoint | 3.5.1 - AP65 - Source Property Tests and Sampling
label | Standard/Specification - TNZ M/3 Notes : 1986, TNZ M/4: 2006, NZS 4407 : 1991, NZS 4402 : 1986
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m3
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.2 - AP65 - Production Property Tests and Sampling
label | Standard/Specification - TNZ M/3 Notes : 1986, TNZ M/4: 2006, NZS 4407 : 1991
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 3 per source initially, then 1/1000m³
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.3 - AP65 - Testing for Layer Compaction - MDD
label | Standard/Specification - TNZ B/02: 2005 - 7.5, NZS 4402:1986 - 4.1.3
label | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.4 - AP40 - Source Property Tests and Sampling
label | Standard/Specification - TNZ M/4: 2006 - 3, NZS 4407 : 1991, NZS 4402 : 1986
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m4
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.5 - AP40 - Production Property Tests and Sampling
label | Standard/Specification - TNZ M/4: 2006 - 4, NZS 4407 : 1991
label | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 3 per source initially, then 1/1000m³
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.6 - AP40 - Testing for Layer Compaction - MDD
label | Standard/Specification - TNZ B/02: 2005 - 7.5, NZS 4402:1986 - 4.1.3
label | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.7 - Sealing Chip - Source Property Tests and Sampling
label | Standard/Specification - TNZ M/6: 2019 - 4
label | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
label | Verifying Document - IANZ Lab Reports
label | Frequency - Before Supply and Every 10,000m3 Thereafter
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.8 - Sealing Chip - Production Property Test Sampling
label | Standard/Specification - TNZ M/6: 2019 - 5
label | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 500m3
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.9 - Bitumen - Quality Testing
label | Standard/Specification - NZTA M01: 2022 - 6
label | Acceptance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test per grade supplied
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.10 - Bitumen - Supply Testing
label | Standard/Specification - NZTA Q05: 2022 - 6.2
label | Acceptance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 200 tonnes supplied.
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
section | 3.6 Receiving Materials/Parts - Safety Barrier
checkpoint | 3.6.1 - Barrier Mill Certs
label | Standard/Specification - NZTA M23, AS/NZS 3845
label | Acceptance Criteria - Compliance documentation
label | Verifying Document - Mill Certs
label | Frequency - Prior to commencement of works
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 3.6.2 - Concrete mix design
label | Standard/Specification - As per Design Specification
label | Acceptance Criteria - Concrete Mix design for each mix comply with the requirements of the Project Specification
label | Verifying Document - Concrete supplier mix designs
label | Frequency - Submitted to Client Engineer for approval before construction
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6.3 - Guard Rail
label | Standard/Specification - As per Design Specification, Appendix E, Section 2.1.2
label | Acceptance Criteria - The Contractor will in advance nominate type of compliant system and manufacturer they propose to use and agree this with the Engineer.
label | Verifying Document - Concrete supplier mix designs
label | Frequency - Engineer for approve before construction
label | Inspection Type (Visual, other) - Document review
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
section | 4.1 ANPR + Cabinet Foundation - Construction
checkpoint | 4.1.1 - Construction Location
label | Standard/Specification - Design Location
label | Acceptance Criteria - Proposed location of construction to be staked out to the engineer for review prior to construction
label | Verifying Document - Approval letter, Photos
label | Frequency - Prior to each foundation build
label | Inspection Type (Visual, other) - Survey Setout
label | Inspection: Key - V
label | Inspection: By - CR
checkpoint | 4.1.2 - Ground Compaction Test
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Compaction shall achieve a minimum Clegg Impact Value (CIV) of 20 on the first layer and 25 on subsequent layers
label | Verifying Document - Test reults, Location of Test
label | Frequency - For each Foundation
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.1.3 - Reinforcement and Hold Down Bolt Inspection
label | Standard/Specification - As per Design Specification
label | Acceptance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
label | Verifying Document - Pre pour, Photos
label | Frequency - Prior to each foundation pour
label | Inspection Type (Visual, other) - Visual Inspection, Dimensional Inspection
label | Inspection: Key - H
label | Inspection: By - CR,SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.4 - Electrical & Comms Ducts Placement
label | Standard/Specification - As per Design Specification
label | Acceptance Criteria - Compliant with the construction drawings
label | Verifying Document - Pre pour, Photos
label | Frequency - Prior to each foundation pour
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - H
label | Inspection: By - CR,SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.5 - Pre-Pour Inspection
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
label | Verifying Document - Pre pour, Photos
label | Frequency - Prior to each foundation pour
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - H
label | Inspection: By - CR,SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.6 - Delivery Dockets
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
label | Verifying Document - Dockets
label | Frequency - Each Pour
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.1.7 - Compression Testing
label | Standard/Specification - As per Design Specification
label | Acceptance Criteria - Three specimen from each batch or upto 50m3 and shall be tested 1 at 7 days and remaining 2 at 28 days.
label | Verifying Document - Test Results
label | Frequency - 3 samples per 50m³/per batch
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.1.8 - Post Pour Inspection
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
label | Verifying Document - Post Pour, Photos
label | Frequency - Each Pour
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.1.9 - Defective Concrete Finishes
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
label | Verifying Document - NCR
label | Frequency - Prior to minor repair
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - A
label | Inspection: By - SE
section | 4.2 WIM plates and Ducts Installation
checkpoint | 4.2.1 - WIM plate location
label | Standard/Specification - Design Location
label | Acceptance Criteria - Set-out to be completed by Surveyor
label | Verifying Document - Approval letter, Photos
label | Frequency - Each
label | Inspection Type (Visual, other) - Survey Setout
label | Inspection: Key - D,W
label | Inspection: By - SV,CR
checkpoint | 4.2.2 - WIM plate installation
label | Standard/Specification - Design Location
label | Acceptance Criteria - To be completed as per the design and technical requirements, under supervision of PAT NZ
label | Verifying Document - ITP Sign off/Photos
label | Frequency - Each
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.2.3 - Supply and installation galvanised pipe
label | Standard/Specification - As per design drawing/notes Sheet No: C 8102
label | Acceptance Criteria - 100mm Galvansied pipes, one each to the line of WIM plate location from concrete chamber, one connecting the chamber to cabinet
label | Verifying Document - ITP Sign off, As-built and Photos
label | Frequency - Before backfill
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.2.4 - Supply and installation concrete chamber
label | Standard/Specification - As per design drawing/notes Sheet No: C 8103
label | Acceptance Criteria - To be completed as per the design and technical requirements
label | Verifying Document - Photos, Checkcheet
label | Frequency - Each
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
section | 4.3.1 Preliminary
checkpoint | 4.3.1.1 - Service Location
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
label | Verifying Document - ITP Sign off/Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SP
checkpoint | 4.3.1.2 - Pre-Construction Test Pits
label | Standard/Specification - Scala test as per specification
label | Acceptance Criteria - Minimum CBR 3.5% as per design notes, Drawing/Notes Sheet No :C 8103
label | Verifying Document - Test report
label | Frequency - 3 test pits per site
label | Inspection Type (Visual, other) - Report review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 4.3.1.3 - Proofroll - Exisiting pavement(Minimum 350mm)
label | Standard/Specification - Visual Inspection
label | Acceptance Criteria - No signs of excessive deformation or springing
label | ○ As per project specified proof roll procedure
label | Verifying Document - Check sheet, DN-QC-05, Video
label | Frequency - Entire length of pavement
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.3.1.4 - Undercut - If needed
label | Standard/Specification - Visual Inspection
label | Acceptance Criteria - Undercut to be treated as per specific Note: Drawing/Notes Sheet No : TD0002
label | Verifying Document - Undercut need to reproof roll after backfill and NDM comapction, Check sheet, DN-QC-05, Phtos
label | Frequency - Area of undercut needed
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
section | 4.3.2 Type B Asphalt
checkpoint | 4.3.2.1 - Preparation of Area to be Paved
label | Standard/Specification - NZTA M27:2020 - 9
label | Acceptance Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected.
label | Verifying Document - Site Notes/Photos
label | Frequency - Pre Seal
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - PS
checkpoint | 4.3.2.2 - Ambient Conditions for Placing
label | Standard/Specification - NZTA M27:2020 - 9
label | Acceptance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C,
label | Verifying Document - Site Notes/ Weather report
label | Frequency - Pre Seal
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - R
label | Inspection: By - PS
checkpoint | 4.3.2.3 - Subbase check
label | Standard/Specification - as per project specification 3.7.7
label | Acceptance Criteria - Visual inspection by engineer's representative
label | Verifying Document - ITP Sign off
label | Frequency - All
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - H
label | Inspection: By - CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3.2.4 - Benkelman Beaming on Subbase
label | Standard/Specification - Contract Specification, Section 3.5.5
label | Acceptance Criteria - 90th percentile deflection ≤ 1.4mm.
label | ○ No single deflection > 1.5mm.
label | Verifying Document - Test report
label | Frequency - 1 per 10m each traffic lane (alternating wheel paths)
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.3.2.5 - Heavy Tack & Blind
label | Standard/Specification - Minimum Residual Bitumen of 1.2 L/m2, As per project based pavement specification
label | Acceptance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat. Where SMA is to be spread over clean, freshly placed asphalt, the Engineer can direct the Contractor to omit the tack coat.
label | Verifying Document - Run sheet, QA from Sub
label | Frequency - Entire length of pavement
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.3.2.6 - Asphaltic Concrete - Base
label | Standard/Specification - NZTA M27
label | Acceptance Criteria - 210mm of AC20 (PG58-V) Lifts of 105/105mm, As per project based pavement specification
label | Verifying Document - Run sheet, QA from Sub
label | Frequency - Entire length of pavement
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SE
checkpoint | 4.3.2.7 - Asphaltic Concrete - Surfacing
label | Standard/Specification - NZTA M27
label | Acceptance Criteria - 40mm of SMA10 (PG58-V), As per project based pavement specification
label | Verifying Document - Run sheet, QA from Sub
label | Frequency - Entire length of pavement
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SE
checkpoint | 4.3.2.8 - Thickness
label | Standard/Specification - Contract Specification, Section 3.7.15
label | Acceptance Criteria - Thickness as per design lift with +/-10mm (AC20), Thickness of 40mm with +/-5mm (SMA10)
label | Verifying Document - ITP Sign off
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.3.2.9 - Finished surface at joints
label | Standard/Specification - Contract Specification, Section 3.7.16
label | Acceptance Criteria - No more than 5 mm variation under a 3 m stright edge
label | Verifying Document - ITP Sign off
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.3.2.10 - Air Voids
label | Standard/Specification - NZTA M/10
label | Acceptance Criteria - The maximum and minimum air voids for each core shall be +3%/-2% from the mix design air voids.
label | Verifying Document - Test results
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.3.2.11 - Level checks
label | Standard/Specification - Survey
label | Acceptance Criteria - Thickness as per design lift with +/-10mm (AC20), Thickness of 40mm with +/-5mm (SMA10)
label | Verifying Document - As-built drawing
label | Frequency - 1/20m full width
label | Inspection Type (Visual, other) - As-built
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.3.2.12 - Line marking
label | Standard/Specification - Set out
label | Acceptance Criteria - 1. All signs and markings are to comply with waka kotahi nz transportagency manuals
label | A. Manual of traffic signs and markings.
label | ○ part 1: signs
label | ○ part 2: markings
label | B. Traffic control devices manual
label | 4. All reflectorised markings to meet standards specified in waka kotahi nzta P30 document.
label | 5. Raised pavement markers not shown, refer to motsam for locations and requirements
label | Verifying Document - ITP sign off/ Photos
label | Frequency - All
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
section | 4.4 Shoulder Widening and Sealing - Construction
checkpoint | 4.4.1 - Material Placement
label | Standard/Specification - Downer Standard
label | Acceptance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored thoughout
label | Verifying Document - Survey / Level Checks
label | Frequency - Continuous monitoring.
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SV, PS
checkpoint | 4.4.2 - Sub-basecourse Pavement Layer Compaction (NDM)
label | Standard/Specification - TNZ B/02: 2005 - 7.6
label | Acceptance Criteria - Mean Value ≥ 95 % of MDD Minimum Value ≥ 92 of MDD
label | Verifying Document - NDM Report
label | Frequency - 1/10m
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4.3 - Sub-basecourse Layer thickness
label | Standard/Specification - TNZ B/02: 2005 - 5.1
label | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –25 mm +5 mm
label | Verifying Document - Survey / Level Checks
label | Frequency - 1/20m Full width
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SV or SE
checkpoint | 4.4.4 - Basecourse Pavement Layer Compaction
label | Standard/Specification - TNZ B/02: 2005 - 7.6
label | Acceptance Criteria - Mean Value ≥ 98 % of MDD Minimum Value ≥ 95 of MDD
label | Verifying Document - NDM Report
label | Frequency - 1/10m
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4.5 - Basecourse Layer thickness
label | Standard/Specification - TNZ B/02: 2005 - 5.1
label | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –5 mm +15 mm
label | Verifying Document - Survey / Level Checks
label | Frequency - 1/20m Full width
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SV or SE
checkpoint | 4.4.6 - Surface Shape
label | Standard/Specification - TNZ B/02: 2005 - 7.7
label | Acceptance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual. No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%.
label | Verifying Document - Survey / Straight edge Report
label | Frequency - 1/20m Full width prior to sealing
label | Inspection Type (Visual, other) - Dimensional Inspection
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.4.7 - Surface Finish post sweeping
label | Standard/Specification - TNZ B/02: 2005 - 7.8
label | Acceptance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
label | Verifying Document - Photos
label | Frequency - Prior to sealing
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.4.8 - Preselling Requirements
label | Standard/Specification - TNZ B/02: 2005 - 12
label | Acceptance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 80%.
label | Verifying Document - NDM Report
label | Frequency - 1/10m
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.4.9 - PreSeal inspection
label | Standard/Specification - TNZ P3 TNZ B02
label | Acceptance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site.
label | Verifying Document - Hold point Release, ITP Sign off
label | Frequency - Prior to sealing
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.4.10 - Spray Temperature
label | Standard/Specification - TNZ P3
label | Acceptance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
label | Verifying Document - Sealing statement
label | Frequency - Prior to sealing
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.4.11 - Chip Application
label | Standard/Specification - TNZ P3
label | Acceptance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
label | Verifying Document - Sealing statement
label | Frequency - For every spray run
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.4.12 - Post Seal Inspections
label | Standard/Specification - TNZ P3
label | Acceptance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
label | Verifying Document - Engineers Acceptance
label | Frequency - Prior to TM Removal and After Final Sweeping
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - H
label | Inspection: By - SE,CR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4.13 - Chipseal Repairs
label | Standard/Specification - TNZ P3
label | Acceptance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
label | Verifying Document - Approved Repair Methodology
label | Frequency - Prior to Repairs
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - A
label | Inspection: By - SE
section | 4.5 Guardrail - Installation
checkpoint | 4.5.1 - Guard rails - Installation
label | Standard/Specification - Appendix E, Section 2.1.3
label | Acceptance Criteria - The Contractor will set out the guardrail location with the Engineer on site.
label | Verifying Document - Hold Point
label | Frequency - For each guard rail
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - CR & SE
checkpoint | 4.5.2 - Guard rails - Checklist
label | Standard/Specification - As per the Contract Specification
label | Acceptance Criteria - To complete the check list along with the guard rail installer after the construction
label | Verifying Document - Check Sheet DN-QC-06 Photos
label | Frequency - For each guard rail
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 4.5.3 - Guard rail completion
label | Standard/Specification - NZTA M/23
label | Acceptance Criteria - All road safety barrier systems (including end treatments and crash cushions):
label | ○ System checklists to be completed and co-signed by qualified contractor (who has completed the Waka Kotahi IMI workshop) and Waka Kotahi representative.
label | Note: All faults to be rectified before acceptance into network operations (maintenance manual) and network assets register (and RAMM).
label | Verifying Document - Hold Point
label | Frequency - For each guard rail
label | Inspection Type (Visual, other) - Visual Inspection
label | Inspection: Key - V
label | Inspection: By - CR & SE
section | Final Inspection and Handover
checkpoint | 5.1 - Construction Record Compilation
label | Standard/Specification - Upon completion of works
label | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Verifying Document - Closed-out NCR/Defects
label | Frequency - Post construction
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - SE
checkpoint | 5.2 - As-built Survey
label | Standard/Specification - Upon completion of works
label | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Verifying Document - As built survey record completed
label | Frequency - Post construction
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - SV
checkpoint | 5.3 - Red-line As-built Drawings
label | Standard/Specification - Upon completion of works
label | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
label | Verifying Document - Signed As-built Drawings
label | Frequency - Post construction
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - SE,SV
checkpoint | 5.4 - Defect, Snag and Punch List
label | Standard/Specification - Upon completion of works
label | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
label | Verifying Document - Register
label | Frequency - Post construction
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - PE
checkpoint | 5.5 - All QA documentation collated & signed-off
label | Standard/Specification - Upon completion of works
label | Acceptance Criteria - All signed and closed out
label | Verifying Document - Signed off Documents
label | Frequency - Post construction
label | Inspection Type (Visual, other) - Review
label | Inspection: Key - R
label | Inspection: By - QM