## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 558020-DOW-ITP-PC-0024_v1 Ducting (Open Trench) | itp |  |  |  |  | 558020-DOW-ITP-PC-0024_v1 Ducting (Open Trench)
section | Receiving Inspection
checkpoint | 3.1 - Design
label | Inspection Point: Quality Control Activity - Pre-construction
label | Acceptance Criteria - Ensure that you are working with the latest IFC drawings.
label | Verifying Document - Drawings
label | Frequency - Continously
label | Inspection Type - Document review
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Permits
label | Inspection Point: Quality Control Activity - Prior to Construction
label | Acceptance Criteria - Please ensure that the permit to work is the latest and approved, and that Existing Services have been positively identified.
label | Verifying Document - Permit Register
label | Frequency - Prior to works.
label | Inspection Type - Document review
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - The survey set out of ducting alignment.
label | Inspection Point: Quality Control Activity - Prior to Construction
label | Acceptance Criteria - Consistent with the IFC construction drawings.
label | Note: All positions to be confirmed on site prior to construction
label | ○ If trenching needs to intersect or traverse existing services, appropriate temporary protection must be implemented.
label | Verifying Document - Survey set out records
label | Frequency - Continuous
label | Inspection Type - Document review
label | Inspection: Key - H
label | Inspection: By - SV
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Marking out of existing services. Confirm there are no clashes with design and existing services
label | Inspection Point: Quality Control Activity - Prior to Construction
label | Acceptance Criteria - Consistent with the IFC construction drawings.
label | Verifying Document - Photos
label | Frequency - Continuous
label | Inspection Type - Document review
label | Inspection: Key - R
label | Inspection: By - SV
checkpoint | 3.5 - Material Compliance - 50mm or 100mm or 150mm uPVC Ducts
label | Inspection Point: Quality Control Activity - Prior to Construction
label | Acceptance Criteria - Ducts shall comply with AS/NZS 61386:2015 or AS/NZS 2053.2:2001. Orange for Power & Salmon for Fibre, green for telecom. Also required print marking details of the configuration
label | Verifying Document - Product Technical Datasheet, Delivery Dockets
label | Frequency - Prior to work starting on site and upond delivery to site.
label | Inspection Type - Visual, Document Review
label | Inspection: Key - H
label | Inspection: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Warning Tape
label | Inspection Point: Quality Control Activity - Prior to construction.
label | Acceptance Criteria - Consistent with the ICF drawings
label | Verifying Document - Photos
label | Frequency - Prior to work starting on site
label | Inspection Type - Visual, Document Review
label | Inspection: Key - V, R
label | Inspection: By - PS
checkpoint | 3.7 - Incoming Material Inspection for all products and good delivered onto the project site
label | Inspection Point: Quality Control Activity - Material Delivery
label | Acceptance Criteria - Material inspected apon arrival for defects, material handling and storage is suitable and follows manufactures guidelines.
label | Verifying Document - DN-QUA-QC-10
label | Frequency - Prior to works.
label | Inspection Type - Visual, Document Review
label | Inspection: Key - R, V
label | Inspection: By - PS
section | 4.1 Trench Works
checkpoint | 4.1.1 - Ensure all sevice in conflict with placement of ducting area exposed
label | Inspection Point: Quality Control Activity - Potholing
label | Acceptance Criteria - All existing services have been identified and confirmed. If trenching needs to intersect or traverse existing services, appropriate temporary protection must be implemented.
label | Verifying Document - Visual inspection and documented.
label | Frequency - Prior to the works starting
label | Inspection Type - Visual
label | Inspection: Key - V
label | Inspection: By - PS
checkpoint | 4.1.2 - Excavations
label | Inspection Point: Quality Control Activity - During construction
label | Acceptance Criteria - Alignment and elevation consistent with the IFC drawings. Where excavation depth exceeds 1.5m the trench shields will be used if the excavations exceed 1.5 meters in depth to Work Safe NZ requirements, All works will be undertaken using hydraulic excavators operated by a competent operator, and all waste material will be removed from the site, and taken to a clean fill site
label | Verifying Document - Photo Records.
label | Frequency - Continuous
label | Inspection Type - Visual Inspections, Measure
label | Inspection: Key - V, M
label | Inspection: By - SE
section | 5.1 ITS Ducts Installation
checkpoint | 5.1.1 - Placement of Bedding Material
label | Inspection Point: Quality Control Activity - During construction
label | Acceptance Criteria - 100mm thick or as shown in the IFC drawings
label | Verifying Document - Delievry Dockets, Photos
label | Frequency - Continuous
label | Inspection Type - Visual Inspections, Measure
label | Inspection: Key - V, M
label | Inspection: By - PS
checkpoint | 5.1.2 - Laying Ducts for Power and Fibre
label | Inspection Point: Quality Control Activity - During construction
label | Acceptance Criteria - As shown in the IFC drawings.
label | Verifying Document - Photos
label | Frequency - Continuous
label | Inspection Type - Visual Inspections,
label | Inspection: Key - V
label | Inspection: By - SE
checkpoint | 5.1.3 - Clearances
label | Inspection Point: Quality Control Activity - During construction
label | Acceptance Criteria - Check with the as-built data if any services coming close then work to the standard clearance to each services as detailed in project spec
label | Verifying Document - As-built
label | Frequency - Continuous
label | Inspection Type - Visual Inspection and verification
label | Inspection: Key - V, M
label | Inspection: By - SE
checkpoint | 5.1.4 - Placement of Sand Surround Material
label | Inspection Point: Quality Control Activity - During construction
label | Acceptance Criteria - Dimensions as shown in the IFC drawings
label | Verifying Document - Ducting Installation Checksheet, Photos
label | Frequency - Continuous
label | Inspection Type - Visual Inspections, Measure
label | Inspection: Key - V, M
label | Inspection: By - SE
checkpoint | 5.1.5 - As Built Survey of the laid ducts
label | Inspection Point: Quality Control Activity - During construction
label | Acceptance Criteria - Consistent with Issued For Construction drawings
label | Verifying Document - As Built Survey Records
label | Frequency - After ducts and chambers are installed
label | Inspection Type - Survey
label | Inspection: Key - C
label | Inspection: By - SV
checkpoint | 5.1.6 - Backfill ducts with Sand Material or approved material.
label | Inspection Point: Quality Control Activity - During construction
label | Acceptance Criteria - Consistent with Issued For Construction drawings
label | Verifying Document - Photos, Delivery Dockets
label | Frequency - After ducts are installed
label | Inspection Type - Visual Inspections, Measure
label | Inspection: Key - V, M
label | Inspection: By - SE
section | Final Inspection and Handover
checkpoint | 7.1 - NCR/Defect/RFI Closed out
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Construction within a tolerance of drawings & specifications
label | Verifying Document - Closed-out NCR/Defects
label | Frequency - Review
label | Inspection Type - Review
label | Inspection: Key - I/R
label | Inspection: By - SE
label | Customer Requirements Verification Records/Location- M-DNZ
checkpoint | 7.1.1 - As-built Survey
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Comply with the project specification and drawings
label | Verifying Document - As built survey record completed
label | Frequency - Review
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE
label | Customer Requirements Verification Records/Location- M
checkpoint | 7.1.2 - Red-line As-built Drawings
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Consistent with the IFC drawings.
label | Verifying Document - Signed As-built Drawings
label | Frequency - Action
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - SE/SV
checkpoint | 7.1.3 - PS3 & Warranties Completed
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - Contractual requirement
label | Verifying Document - PS3 & Warranty
label | Frequency - Review
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PE
label | Customer Requirements Verification Records/Location- DNZ
checkpoint | 7.1.4 - All QA documentation collated & signed-off
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Acceptance Criteria - All signed and closed out
label | Verifying Document - Signed off Documents
label | Frequency - Final Internal Review
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - QM
label | Customer Requirements Verification Records/Location- M-DNZ