## ITP Cover Page
[SWD04] Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - 131 - Rev E
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 131
Project Number: |  |  | DN1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | SWD04 Eastern Gully Works |  |  |  |  | Revision: | 1000 |  | E
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | Stormwater Attenuation (146000-002A-2221 to 2224)
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification, EMMP, FMP, ESCP.
Quality Specified: |  |  | NZTA Z/1
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Draft for Approval | 2024-02-09 |  | Emil Karlsson |  | Various comments to be added, SW ITP lines to be added, description of requirements for bulkfill added. |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Draft for Approval | 2024-02-16 |  | NA |  | NA |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
C | Draft for Approval | 2024-04-17 |  | Emil Karlsson |  | Comments added |  |  |  | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
D | Draft for Approval | 2024-05-14 |  | Emil Karlsson |  | Two minor comments to adjust. |  |  |  | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
E | Draft for Approval | 2024-05-15 |  | Emil Karlsson | [5 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
[SWD04] Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - 131 - Rev E
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements
3.01.01 | Construction Pack | Methodology and ITP to be submitted to the Engineer and approved prior to works beginning | Downer | Construction Pack | Submit 10 days prior to commencement of works | HP | ENG
3.01.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
3.01.03 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
3.01.04 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE
3.01.05 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE
3.01.06 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | Earthworks
4.01.01 | Fish Relocation | In-Streams works to be carried out between Jan to April. Fish relocation to be carried out by Ecology NZ as per FMP requirements. | Fish Management Plan | Ecologist Memo | Prior to in-stream works | H | SE
4.01.02 | Tree Clearance | EcologyNZ to inspect trees for fauna prior to removal. | Bat Management Plan, Lizard Management Plan | Ecologist Memo | Within 24hrs of tree felling | H | SE
4.01.03 | Weir Clay Fill Material Testing | Standard Compaction Minimum 30% fines content. Plasticity Index 16-30, Liquid Limit 30%-60%. | GWS Table 1 | Test Results | 3 initial tests per source of fill | HP | ENG
4.01.04 | Grouted Boulders | Boulders to have specific gravity >2.1, be clean and crack-free. The grout shall meet NZS 3109 and be kept wet 12 hours post pour. Grout should be recessed 1/3 the diameter of the boulders' side facing the channel. 48 hrs before grouting, placement must be inspeted by Engineer. 20MPa concrete. | Project Specification 4.7.6 | Material Certs Concrete Docket | Before Delivery to Site | HP | ENG
4.01.05 | Riprap Material | Density - Greater than 2.40t/m3 Crushing Resistance - Not less than 150kN Weathering Classification - AA, BA, AB or BB Abrasion Resistance - Not more than 26% Calcite intrusions - Rock shall be free of calcite intrusions Grading - Rock for riprap shall be the nominal D50 size shown on the drawings and shall be well graded. If riprap product is unavailable, alternative material to be approved by designer. | Project Specification 4.7.1 | Delivery Dockets Lab Reports | Per Truck | HP | ENG
4.01.06 | Bulk Fill below Clay Fill | Maximum 10% fines Blue/brown run of pit material (not too weathered) Wrapped in a geotextile (strength class determined by the clast size of aggregate) Maximum clast size 200mm. All larger blasts to be broken up. | Desiger | Delivery Dockets Proof Roll Testing | Per Truck | HP | ENG
4.01.07 | Grout | 20MPa Grout mix design to be deemed suitable by designer. | Designer | Record of Approval | Prior to use. | HP | ENG
4.01.08 | Geotextile (Base of Undercut) | NZTA F/07 Strength Class C geotextile installed at the base of undercut. | Designer | Dockets | Per Delivery | C | PE
4.01.09 | Geotextile (Top of Rockfill) | NZTA F/07 Strength Class E geotextile installed on top of finished rockfill surface. Only required if GCL is installed. | Designer | Dockets | Per Delivery | HP | ENG
4.01.10 | Geosynthetic Clay Liner | Elcoseal GCL to be deemed suitable by designer. X800 grade to be used unless otherwise advised by designer. | Designer | RFI | Prior to use. | HP | ENG
4.02 | Stormwater/Fish Passage
4.02.01 | Pipes, Fittings and Pre-cast Structures | Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/manholes/catchpits are correct and in good condition and compliant. | As per design | Delivery Dockets | Per Deliver | S | SE
4.02.02 | Bedding/Side & Haunch/Overlay/Backfill Material Compliance | Pit sand, PAP 5 or an equivalent material approved by Engineer. | Project Specification | IANZ Lab Test Report | 1 Test per 1000m3 | H | SE
4.02.03 | Quick Mix Concrete (Haunching) | Mixed as per manufacturer's requirements | Minimum 20MPa concrete mix | Photographs | Per Application | C | PE
SECTION 5 – CONSTRUCTION ACTIVITY
5.01 | Pre-Construction
5.01.01 | Erosion and Sediment Control | Super Silt Fencing and Silt Fencing in place as per ESCP Silt Buster to provide sediment control for weir. | ESCP WRC TR0902 | Enviro As-Built | Prior | H | SE
5.01.02 | Upstream and Downstream Bunds | Temporary dam constructed via 1m sand bags, stacked up to max 2m height. 600mm rigid pipe at stream level to connect to 600mm flexible flume. | ESCP | Enviro As-Built | Prior | H | SE
5.01.03 | Dewatering | Water from downstream bund to be pumped to Lamella Clarifier and discharged under into the stream further down.. Treated discharge into stream to be between pH 5.5-8.5. TSS limit 150mg/l. Turbidity limit 50NTU or 100mm clarity. Non-compliant discharge notified to WRC within 24 hours. | ESCP / DMP | Enviro As-Built | As required | M | SE
5.02 | Construction - Earthworks
5.02.01 | Preparation for Filling | Preparation of the firm to stiff / medium dense subgrade beneath the proposed fill areas should comprise stripping of all vegetation, topsoil, any pre-existing fill materials or weak alluvium followed by benching of the exposed subgrade where natural slopes beneath the fill exceed gradients of nominally 1:5 (vertical to horizontal). CMW to inspect subgrade prior to placement of rockfill. Benching in accordance with CMW sketch detail. | GWS 2.9.2 | Subgrade Inspection | Prior to placement and compaction of fill | HP | SE
5.02.02 | Settlement Pin Installation (Only if pre-loading is required) | Protective waratahs and coloured flagging shall be installed around all settlement pins for protection. Settlement pins shall be installed within 24 hours of reaching design subgrade level. | GWS 6.3 | Checksheet | within 24 hours of reaching design subgrade level. | HP | ENG
5.02.03 | Settlement Survey (Only if pre-loading is required) | Survey measurements are to be undertaken regularly by the Contractor as specified on the drawings, to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading. | GWS 6.3 | Both paper and electronic formats | within 24 hours of each reading. | H | SV/SE
5.02.04 | Weir Fill Shear Strength Testing | Weir clay fill shall be tested for Vane Shear Strength to: Minimum average 120kPa over 10 tests, minimum single value 110kPa. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm. | GWS 2.9.4 | Test Results | 1 set / 500m3 (1 set to include 5 x shear vanes and 1 x air voids within a 3m radius) | R | SE
5.02.05 | Weir Fill Air Voids Testing | Weir clay fill shall be tested for Air Voids to: Maximum average 10% over 10 tests, maximum single value 12%. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm. | GWS 2.9.4 | Test Results | 1 set / 500m3 (1 set to include 5 x shear vanes and 1 x air voids within a 3m radius) | R | SE
5.02.06 | Rockfill Installation | Proof rolls at 500mm lifts, to be observed by CMW. Rockfill to be fully wrapped in geotextile filter fabric, strength class c. Wrapping to be inspected by CMW. Upon completion of rock fill instalation, inspection by CMW. Sharp edges of rock (protrusions) to be minimised. | Designer | Proof Roll Record | per 500mm lift | HP | ENG
5.02.07 | Geotextile (Base of Undercut) | Class C Geotextile to cover the entire base of excavation and be fully wrapped around the rockfill material. Minimum 500mm overlap required. | Designer | Photographs | every overlap | HP | ENG
5.02.08 | Geotextile (Top of Rockfill) | Class E Geotextile to cover the entire surface of rockfill material between rockfill – GCL interface. CMW to inspect prior once installed. | Designer | Photographs | upon installation | HP | ENG
5.02.09 | GCL | GCL to cover entire surface of rockfill material. Installed as per manufacturer's requirements. CMW to inspect once installed. | Designer | Photographs | upon installation | HP | ENG
5.02.10 | Topsoil | Topsoil to cover entire surface of GCL. Minimum 300mm of coverage. | Designer | Photographs | upon installation | HP | ENG
5.03 | Construction - Stormwater/Fish Passage Pipe
5.03.01 | Foundation Compliance | Clegg Testing to be carried out on pipe foundation. Clegg Test to correlate to minimum CBR of 15. Foundation for Manholes/structures to only be measured with Clegg CIV of where there is a rockfill foundation. Other MH's and impact basin structures are to meet the foundation requirement. Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa | Project Specification 4.3 | Test Results | 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m | H | SE
5.02.02 | Undercut Backfill Compliance | NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD | Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002 | IANZ Lab Test Report | Based on Undercut Section | H | QE
5.03.03 | Bedding Compaction Testing | HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD | Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002 | IANZ Lab Test Report | 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m | H | QE
5.03.04 | Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe | NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD | HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007 | IANZ Lab Test Report | 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m | H | QE
5.03.05 | Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe | NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD | HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007 | IANZ Lab Test Report | 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m | H | QE
5.03.06 | Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed. | NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD | HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007 | IANZ Lab Test Report | 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m | H | QE
5.03.07 | Backfill Inspection | Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline. | Project Specification 4.3 | Photographs | Continous | S | SE
5.03.08 | Survey | Invert Levels The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified. Horizontal Alignment The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm. Gradient For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point. | Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm | Survey Data | Continous | C | SV
5.03.09 | Backfill Compaction Testing | NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 300mm lifts of backfill - 95% of MDD at OMC (98% Average) | PS 4.3 NZS 4402 Test 4.1.2 | IANZ Lab Test Report | 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m | H | QE
5.03.10 | Riprap Mix | Riprap Mix Materials to be stockpiled separately and mixed in a pre-determined ratio to make a suitable riprap product | Designer | Photographs | Prior to Use | HP | ENG
5.03.11 | Riprap Embedment (Fish Passage) | Riprap layer within 1200mm fish passage to be 400mm high. Pipe laser to be used to ensure compliance. | Drawings | Photographs | During Placement | H | SV
5.03.12 | CCTV | CCTV inspection of 750mm stormwater and wastewaterline. CCTV soft copy to be provided to designer. | Project Specification 4.4 | Soft Copy | Post Installation | H | ITP
5.04 | Construction - Manhole & Wingwalls
5.03.01 | Foundation Compliance | Clegg Testing to be carried out on stormwater manhole foundation. Clegg Test to correlate to minimum CBR of 15. | Project Specification 4.3 | Test Results | 1 Test/Manhole | H | QE
5.03.02 | Undercut Backfill Compliance | NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD | Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002 | IANZ Lab Test Report | 1 Test/Manhole if Undercut required | H | QE
5.03.03 | Bedding Compaction Testing | HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD | Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002 | IANZ Lab Test Report | 1 Test/Manhole | H | QE
5.03.04 | Backfill Inspection | Inspection of manhole prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the manhole | Project Specification 4.3 | Photographs | Continous | S | SE
5.03.05 | Survey | Invert Levels The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified. Horizontal Alignment The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm. Gradient For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point. | Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm | Survey Data | Continous | C | SV
5.03.06 | Backfill Compaction Testing | NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 300mm lifts of backfill - 95% of MDD at OMC. | Project Specification 4.3 | IANZ Lab Test Report | 4 Density test per layer at Quarter Points around the Structure | H | QE
5.03.07 | Haunching | All the MH's needs to be haunched as per the specifications | RITS | Photographs | Continous | S | PE
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.01 | General
6.01.01 | As-Builts Critical Elements | Undercut/topsoil clearance. Any placed fill. Any drainage undercuts/structures. | Downer | Survey Records | After Completion | H | SV
6.01.02 | Red-line Markup |  | Downer | Red-line Markup | After Completion | H | SE