## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - 131 - SWD04 Eastern Gully Works Rev E | itp |  |  |  |  | ITP - 131 - SWD04 Eastern Gully Works Rev E
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Submit 10 days prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.01.03 - Service Location
label | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard / Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.04 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.05 - External Permits
label | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard / Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.06 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Fish Relocation
label | Acceptance / Conformance Criteria - In-Streams works to be carried out between Jan to April. Fish relocation to be carried out by Ecology NZ as per FMP requirements.
label | Standard / Specification - Fish Management Plan
label | Verifying Document - Ecologist Memo
label | Frequency - Prior to in-stream works
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.02 - Tree Clearance
label | Acceptance / Conformance Criteria - EcologyNZ to inspect trees for fauna prior to removal.
label | Standard / Specification - Bat Management Plan, Lizard Management Plan
label | Verifying Document - Ecologist Memo
label | Frequency - Within 24hrs of tree felling
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.03 - Weir Clay Fill Material Testing
label | Acceptance / Conformance Criteria - Standard Compaction
label | ○ Minimum 30% fines content.
label | ○ Plasticity Index 16-30, Liquid Limit 30%-60%.
label | Standard / Specification - GWS Table 1
label | Verifying Document - Test Results
label | Frequency - 3 initial tests per source of fill
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.04 - Grouted Boulders
label | Acceptance / Conformance Criteria - Boulders to have specific gravity >2.1, be clean and crack-free.
label | ○ The grout shall meet NZS 3109 and be kept wet 12 hours post pour.
label | ○ Grout should be recessed 1/3 the diameter of the boulders' side facing the channel.
label | ○ 48 hrs before grouting, placement must be inspeted by Engineer.
label | ○ 20MPa concrete.
label | Standard / Specification - Project Specification 4.7.6
label | Verifying Document - Material Certs, Concrete Docket
label | Frequency - Before Delivery to Site
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.05 - Riprap Material
label | Acceptance / Conformance Criteria - Density - Greater than 2.40t/m3
label | ○ Crushing Resistance - Not less than 150kN
label | ○ Weathering Classification - AA, BA, AB or BB
label | ○ Abrasion Resistance - Not more than 26%
label | ○ Calcite intrusions - Rock shall be free of calcite intrusions
label | ○ Grading - Rock for riprap shall be the nominal D50 size shown on the drawings and shall be well graded.
label | ○ If riprap product is unavailable, alternative material to be approved by designer.
label | Standard / Specification - Project Specification 4.7.1
label | Verifying Document - Delivery Dockets, Lab Reports
label | Frequency - Per Truck
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.06 - Bulk Fill below Clay Fill
label | Acceptance / Conformance Criteria - Maximum 10% fines
label | ○ Blue/brown run of pit material (not too weathered)
label | ○ Wrapped in a geotextile (strength class determined by the clast size of aggregate)
label | ○ Maximum clast size 200mm. All larger blasts to be broken up.
label | Standard / Specification - Desiger
label | Verifying Document - Delivery Dockets, Proof Roll Testing
label | Frequency - Per Truck
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.07 - Grout
label | Acceptance / Conformance Criteria - 20MPa Grout mix design to be deemed suitable by designer.
label | Standard / Specification - Designer
label | Verifying Document - Record of Approval
label | Frequency - Prior to use.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.08 - Geotextile (Base of Undercut)
label | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C geotextile installed at the base of undercut.
label | Standard / Specification - Designer
label | Verifying Document - Dockets
label | Frequency - Per Delivery
label | Verification Activity: Activity - C
label | Verification Activity: By - PE
checkpoint | 4.01.09 - Geotextile (Top of Rockfill)
label | Acceptance / Conformance Criteria - NZTA F/07 Strength Class E geotextile installed on top of finished rockfill surface. Only required if GCL is installed.
label | Standard / Specification - Designer
label | Verifying Document - Dockets
label | Frequency - Per Delivery
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.10 - Geosynthetic Clay Liner
label | Acceptance / Conformance Criteria - Elcoseal GCL to be deemed suitable by designer. X800 grade to be used unless otherwise advised by designer.
label | Standard / Specification - Designer
label | Verifying Document - RFI
label | Frequency - Prior to use.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02.01 - Pipes, Fittings and Pre-cast Structures
label | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/manholes/catchpits are correct and in good condition and compliant.
label | Standard / Specification - As per design
label | Verifying Document - Delivery Dockets
label | Frequency - Per Deliver
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 4.02.02 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
label | Acceptance / Conformance Criteria - Pit sand, PAP 5 or an equivalent material approved by Engineer.
label | Standard / Specification - Project Specification
label | Verifying Document - IANZ Lab Test Report
label | Frequency - 1 Test per 1000m3
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.02.03 - Quick Mix Concrete (Haunching)
label | Acceptance / Conformance Criteria - Mixed as per manufacturer's requirements
label | Standard / Specification - Minimum 20MPa concrete mix
label | Verifying Document - Photographs
label | Frequency - Per Application
label | Verification Activity: Activity - C
label | Verification Activity: By - PE
section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint | 5.01.01 - Erosion and Sediment Control
label | Acceptance / Conformance Criteria - Super Silt Fencing and Silt Fencing in place as per ESCP Silt Buster to provide sediment control for weir.
label | Standard / Specification - ESCP WRC TR0902
label | Verifying Document - Enviro As-Built
label | Frequency - Prior
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.02 - Upstream and Downstream Bunds
label | Acceptance / Conformance Criteria - Temporary dam constructed via 1m sand bags, stacked up to max 2m height. 600mm rigid pipe at stream level to connect to 600mm flexible flume.
label | Standard / Specification - ESCP
label | Verifying Document - Enviro As-Built
label | Frequency - Prior
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.03 - Dewatering
label | Acceptance / Conformance Criteria - Water from downstream bund to be pumped to Lamella Clarifier and discharged under into the stream further down.
label | ○ Treated discharge into stream to be between pH 5.5-8.5. TSS limit 150mg/l. Turbidity limit 50NTU or 100mm clarity. Non-compliant discharge notified to WRC within 24 hours.
label | Standard / Specification - ESCP / DMP
label | Verifying Document - Enviro As-Built
label | Frequency - As required
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 5.02.01 - Preparation for Filling
label | Acceptance / Conformance Criteria - Preparation of the firm to stiff / medium dense subgrade beneath the proposed fill areas should comprise stripping of all vegetation, topsoil, any pre-existing fill materials or weak alluvium followed by benching of the exposed subgrade where natural slopes beneath the fill exceed gradients of nominally 1:5 (vertical to horizontal). CMW to inspect subgrade prior to placement of rockfill.
label | ○ Benching in accordance with CMW sketch detail.
label | Standard / Specification - GWS 2.9.2
label | Verifying Document - Subgrade Inspection
label | Frequency - Prior to placement and compaction of fill
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.06 - Rockfill Installation
label | Acceptance / Conformance Criteria - Proof rolls at 500mm lifts, to be observed by CMW.
label | ○ Rockfill to be fully wrapped in geotextile filter fabric, strength class c.
label | ○ Wrapping to be inspected by CMW.
label | ○ Upon completion of rock fill instalation, inspection by CMW.
label | ○ Sharp edges of rock (protrusions) to be minimised.
label | Standard / Specification - Designer
label | Verifying Document - Proof Roll Record
label | Frequency - per 500mm lift
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.07 - Geotextile (Base of Undercut)
label | Acceptance / Conformance Criteria - Class C Geotextile to cover the entire base of excavation and be fully wrapped around the rockfill material. Minimum 500mm overlap required.
label | Standard / Specification - Designer
label | Verifying Document - Photographs
label | Frequency - every overlap
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.08 - Geotextile (Top of Rockfill)
label | Acceptance / Conformance Criteria - Class E Geotextile to cover the entire surface of rockfill material between rockfill – GCL interface.
label | ○ CMW to inspect prior once installed.
label | Standard / Specification - Designer
label | Verifying Document - Photographs
label | Frequency - upon installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.09 - GCL
label | Acceptance / Conformance Criteria - GCL to cover entire surface of rockfill material.
label | ○ Installed as per manufacturer's requirements.
label | ○ CMW to inspect once installed.
label | Standard / Specification - Designer
label | Verifying Document - Photographs
label | Frequency - upon installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.10 - Topsoil
label | Acceptance / Conformance Criteria - Topsoil to cover entire surface of GCL. Minimum 300mm of coverage.
label | Standard / Specification - Designer
label | Verifying Document - Photographs
label | Frequency - upon installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.01 - Foundation Compliance
label | Acceptance / Conformance Criteria - Clegg Testing to be carried out on pipe foundation.
label | ○ Clegg Test to correlate to minimum CBR of 15.
label | ○ Foundation for Manholes/structures to only be measured with Clegg CIV of where there is a rockfill foundation.
label | ○ Other MH's and impact basin structures are to meet the foundation requirement.
label | ○ Granular Material: Scala 3 blows/100mm
label | ○ Cohesive Material: Vane Shear Strength 70kPa
label | Standard / Specification - Project Specification 4.3
label | Verifying Document - Test Results
label | Frequency - 0-5m: 2 Tests
label | ○ 5m-10m: 3 Tests
label | ○ 10m-40m: 4 Tests
label | ○ 40m-100m: 5 Tests
label | ○ 100m: 1 test per 20m
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.03.03 - Bedding Compaction Testing
label | Acceptance / Conformance Criteria - HS2 Bedding under pavement
label | ○ H2 Bedding outside pavement
label | ○ NDM Back Scatter
label | ○ Minimum Compaction 95%(Average98%) of MDD
label | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD, AS/NZS 2566.2/2002
label | Verifying Document - IANZ Lab Test Report
label | Frequency - 0-5m: 2 Tests
label | ○ 5m-10m: 3 Tests
label | ○ 10m-40m: 4 Tests
label | ○ 40m-100m: 5 Tests
label | ○ 100m: 1 test per 20m
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 5.03.04 - Haunch Zone Compaction Testing - Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
label | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Minimum Compaction 92% of MDD
label | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD, AS/NZS 3725:2007
label | Verifying Document - IANZ Lab Test Report
label | Frequency - 0-5m: 2 Tests
label | ○ 5m-10m: 3 Tests
label | ○ 10m-40m: 4 Tests
label | ○ 40m-100m: 5 Tests
label | ○ 100m: 1 test per 20m
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 5.03.05 - Side Zone Compaction Testing - Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
label | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Minimum Compaction 92% of MDD
label | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD, AS/NZS 3725:2007
label | Verifying Document - IANZ Lab Test Report
label | Frequency - 0-5m: 2 Tests
label | ○ 5m-10m: 3 Tests
label | ○ 10m-40m: 4 Tests
label | ○ 40m-100m: 5 Tests
label | ○ 100m: 1 test per 20m
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 5.03.06 - Overlay Compaction Testing - Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
label | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Minimum Compaction 92% of MDD
label | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD, AS/NZS 3725:2007
label | Verifying Document - IANZ Lab Test Report
label | Frequency - 0-5m: 2 Tests
label | ○ 5m-10m: 3 Tests
label | ○ 10m-40m: 4 Tests
label | ○ 40m-100m: 5 Tests
label | ○ 100m: 1 test per 20m
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 5.03.07 - Backfill Inspection
label | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
label | Standard / Specification - Project Specification 4.3
label | Verifying Document - Photographs
label | Frequency - Continous
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 5.03.08 - Survey
label | Acceptance / Conformance Criteria - Invert Levels: The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified.
label | ○ Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm.
label | ○ Gradient: For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
label | Standard / Specification - Vertical tolerance +/- 50mm, Horizontal Between Structures +/- 100mm
label | Verifying Document - Survey Data
label | Frequency - Continous
label | Verification Activity: Activity - C
label | Verification Activity: By - SV
checkpoint | 5.03.09 - Backfill Compaction Testing
label | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Testing to be completed on 300mm lifts of backfill - 95% of MDD at OMC (98% Average)
label | Standard / Specification - PS 4.3 NZS 4402 Test 4.1.2
label | Verifying Document - IANZ Lab Test Report
label | Frequency - 0-5m: 2 Tests
label | ○ 5m-10m: 3 Tests
label | ○ 10m-40m: 4 Tests
label | ○ 40m-100m: 5 Tests
label | ○ 100m: 1 test per 20m
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 5.03.10 - Riprap Mix
label | Acceptance / Conformance Criteria - Riprap Mix Materials to be stockpiled separately and mixed in a pre-determined ratio to make a suitable riprap product
label | Standard / Specification - Designer
label | Verifying Document - Photographs
label | Frequency - Prior to Use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.11 - Riprap Embedment (Fish Passage)
label | Acceptance / Conformance Criteria - Riprap layer within 1200mm fish passage to be 400mm high. Pipe laser to be used to ensure compliance.
label | Standard / Specification - Drawings
label | Verifying Document - Photographs
label | Frequency - During Placement
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 5.03.12 - CCTV
label | Acceptance / Conformance Criteria - CCTV inspection of 750mm stormwater and wastewaterline. CCTV soft copy to be provided to designer.
label | Standard / Specification - Project Specification 4.4
label | Verifying Document - Soft Copy
label | Frequency - Post Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - ITP
checkpoint | 5.03.01 - Foundation Compliance
label | Acceptance / Conformance Criteria - Clegg Testing to be carried out on stormwater manhole foundation. Clegg Test to correlate to minimum CBR of 15.
label | Standard / Specification - Project Specification 4.3
label | Verifying Document - Test Results
label | Frequency - 1 Test/Manhole
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 5.03.02 - Undercut Backfill Compliance
label | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Minimum Compaction 95%(Average98%) of MDD
label | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD, AS/NZS 2566.2/2002
label | Verifying Document - IANZ Lab Test Report
label | Frequency - 1 Test/Manhole if Undercut required
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 5.03.03 - Bedding Compaction Testing
label | Acceptance / Conformance Criteria - HS2 Bedding under pavement
label | ○ H2 Bedding outside pavement
label | ○ NDM Back Scatter
label | ○ Minimum Compaction 95%(Average98%) of MDD
label | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD, AS/NZS 2566.2/2002
label | Verifying Document - IANZ Lab Test Report
label | Frequency - 1 Test/Manhole
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 5.03.04 - Backfill Inspection
label | Acceptance / Conformance Criteria - Inspection of manhole prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the manhole
label | Standard / Specification - Project Specification 4.3
label | Verifying Document - Photographs
label | Frequency - Continous
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 5.03.05 - Survey
label | Acceptance / Conformance Criteria - Invert Levels: The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified.
label | Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm.
label | Gradient: For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
label | Standard / Specification - Vertical tolerance +/- 50mm, Horizontal Between Structures +/- 100mm
label | Verifying Document - Survey Data
label | Frequency - Continous
label | Verification Activity: Activity - C
label | Verification Activity: By - SV
checkpoint | 5.03.06 - Backfill Compaction Testing
label | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Testing to be completed on 300mm lifts of backfill - 95% of MDD at OMC.
label | Standard / Specification - Project Specification 4.3
label | Verifying Document - IANZ Lab Test Report
label | Frequency - 4 Density test per layer at Quarter Points around the Structure
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 5.03.07 - Haunching
label | Acceptance / Conformance Criteria - All the MH's needs to be haunched as per the specifications
label | Standard / Specification - RITS
label | Verifying Document - Photographs
label | Frequency - Continous
label | Verification Activity: Activity - S
label | Verification Activity: By - PE
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.01 - As-Builts Critical Elements
label | Acceptance / Conformance Criteria - Undercut/topsoil clearance. Any placed fill. Any drainage undercuts/structures.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - After Completion
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 6.01.02 - Red-line Markup
label | Standard / Specification - Downer
label | Verifying Document - Red-line Markup
label | Frequency - After Completion
label | Verification Activity: Activity - H
label | Verification Activity: By - SE