## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | ITP-0045
Revision : 1 17/06/2022
Client: |  | Surf Coast Shire |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Fischer St Road Saftey Project |  | PIPE TO PIPE CONNECTION TO MAIN DRAINS |  | Name: | Jackson Kay | Name: |  |  | Name:
Contract No: |  | T24-015 |  | Specifications: VicRoads Specification Section 701
|  |  |  | Structure / Component: Drainage |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Fischer St / Puebela St |  | Date : | 2024-05-02 | Date : |  |  | Date :
Lot No: | 1 |  | Lot Details: | Puebela St |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Project Engineer / Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP | QMP, TMP, JSEA, SWMS, ITP | Visual Inspection | This ITP signed off | HP* | Project Engineer / Site Foreman | N/A |  | N/A
1.3 | Precast Materials Inspection |  | Each Delivery | Precast materials have been inspected and fit for purpose and free of defects | 701.04b | Visual Inspection | This ITP signed Receival and Inspection Checklist | IP | Project Engineer | N/A |  | N/A
1.4 | Precast Pipe |  | Prior to Commencing | Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058 | VicRoads Spec. Cl.619 Cl. 701.04(a) Cl. 701.04(b)(i) Cl. 705.04(d) Cl. 705.11 AS4058 AS4680 | Document review & Site inspection | Receival & Inspection Checklist Manufacturer cetificate or accreditation | IP | Project Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Excavation Permit |  | Each lot | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation permit | Verify | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.2 | Set out drainage |  | Prior to excavation | The position of all drainage lines are to be confirmed with the superintendent | Drawings 701.10 | Visual Inspection | ITP Signed | HP | Engineer / Forman & Superintendent |  |  | N/A
2.3 | Excavation (pipes) |  | Each Trench | Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical Depth of trench: • > 100mm below underside of pipe (for pipe width < 1500 mm) • > 200mm below underside of pipe (for pipe width > 1500 mm) | 701.15 Table 701.151 | Visual Inspection | ITP Signed | IP | Site Foreman | N/A |  | N/A
2.4 | Bedding & Support |  | Each Lot | Provide mass Concrete support around branch pipe minimum 150mm thick. Concrete shall be grade S40 with a maximum water cement ratio of 0.50. | MELBOURNE WATER CORPORATION 7251/08/425 | Visual Inspection | ITP Signed | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.5 | Break Into main drain |  | Each Lot | Reinforment in main drain to be cut and formed into collar. Care should be taken to prevent damage to pipe and to enshore opening is kept to a minimum. | MELBOURNE WATER CORPORATION 7251/08/425 | Visual Inspection | ITP Signed | HP | Site Engineer / Site Foreman, Superintendent |  |  | N/A
2.6 | Pipe to Pipe Conection |  | Each Lot | Where connection cannot be rendered from inside main drain, connection to consists of 300mm long stub to allow rendering from outside. Bonding of new to old concrete shall be sufficent to ensure no cracks or leaks form. Concrete surfaces to be scabbled, cleaned primed with parchem nitobond SBR. All reinforcement without adequite cover to be sealed with epoxy or similar. | MELBOURNE WATER CORPORATION 7251/08/425 | Visual Inspection | ITP Signed | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.7 | Place & compact backfill material over pipes |  | each lot | Ordinary earth from excavation which contains no rock fragments compacted in layers no greater than 150mm. Compaction to be minimum 92% modified A.A.S.H.O. using handheld mechanical equipment. Top 100mm to be topsoil and seeded | RFI.01 | Visual Inspection + Testing | ITP Signed | IP | Site Engineer / Site Foreman | N/A |  | N/A
3 | Testing & Completion
3.1 | Compaction and moisture content of backfill & bedding material |  | as required/requested | Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort. Bedding material shall be compacted using a compaction plated to refusal. | 701.2 | Verify | Test Reports | TP | Project Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent