## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-008
Revision : 1
Client: |  | Surf Coast Shire |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Fischer St Road Saftey Project |  | Line Marking |  | Name: | Jackson Kay | Name: |  |  | Name: | Simon Jawoski
Contract No: |  | T24-015 |  | Specifications: VicRoads Standard Specification – Section 721
|  |  |  | Structure / Component: Road |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Fischer St / Inshore Drive |  | Date : |  | Date : |  |  | Date :
Lot No: | 1 |  | Lot Details: | Inshore Dr |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Line marking Conformance |  | Prior to commencing any activity | Materials to be used conform with specification | Review Materials Sheet | Visual inspection | ITP Signed | WP | Project Engineer/ Site Foreman | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP | QMP, TMP, JSEA, SWMS, WP | Visual inspection | ITP Signed | WP | Project Engineer/ Site Foreman | N/A |  | N/A
1.3 | Site preparation |  | Prior to commencing any activity | Removal of any existing unsound,obsolete or redundant pavement markings. Removal of any foreign material or debris. | 721.A06 | Visual inspection | ITP Signed | WP | Project Engineer/ Site Foreman | N/A
1.4 | Set-out of Pavement Markings |  | Prior to commencing any activity | Pavement markings to set-out in accordance with IFC Drawings. | 721.A09 | Visual inspection | ITP Signed | HP | Project Engineer/ Site Foreman | N/A
2 | Construction Works
2.2 | Line marking Installation |  | During Construction | Line marking installed as per IFC Drawings | 721.E01 | Visual inspection | ITP Signed | WP | Project Engineer/ Site Foreman | N/A
2.3 | Glass bead Install |  | During line marking works | Glass beads sprinkled/sprayed on to line marking while in a fluid state to ensure embedment. Glass beads to have uniform distribution | 721.E02 | Visual inspection | ITP Signed | WP | Project Engineer/ Superintendent | N/A
3 | Completion
3.1 | Completion Inspection |  | Each lot | Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, streats, overlaps, unbeaded areas, tyre marks or other defects. Edges and cuts-offs shall be neat and sharp, and there shall be no visible run-off, overspray, dribbles,splash or spiliage on to the surrounding area, or on to parked or passing vehicles. | 721.E01 | Visual inspection | ITP Signed | WP | Project Engineer/ Superintendent | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.