## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-50
[11 empty] | Revision : 0 | Date :
Client: |  | Surf Coast Shire |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Fischer St Road Saftey Project |  | Application of Omnigrip Road Surfacing |  | Name: Jackson Kay |  | Name: |  |  | Name:
Contract No: |  | T24-015 |  | Specifications: Omnigrip CST Technical Data Sheet
|  |  |  | Structure / Component: Omnigrip CST |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Inshore Dr / Fischer St |  | Date : 07/05/2024 |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for Correct Documentation |  | Prior to Commencing Activity | •Ensure that employees and sub-contractors are using the most current and complete set of drawings | Contract Drawings and Registers | Visual Inspection | This ITP Signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to Commencing Activity | •All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP | EMP, TMP, SWMS, WP | Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Check Materials |  | Each Delivery | •Ensure the correct materials have been received including: - Part A Epoxy Compound - Part B Epoxy Harderner - Coloured Aggregate Dressing | Receivable Inspection Checklist | Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Setting out |  | Each Lot | •Alignment and location of Omnigrip road sufracing shall be marked in accordace with the appropriate design drawings. | Work Procedure | Inspection | This ITP Signed off | WP | Fulton Hogan Engineer, Client |  |  | N/A
2 | Construction Works
2.1 | Monitoring Conditions |  | Prior to start | Omnigrip CST must not be applied to wet pavements under any circumstances and suspension of application should be considered: - During periods of dew, drizzle or rain - If the surface temperature exceeds 60°C - If the surface temperature drops below 10°C and is in decline. | Omnigrip Technical Data Sheet | Verify | This ITP signed off | IP | Fulton Hogan Engineer / YT Superintendent | N/A |  | N/A
2.2 | Asphalt Surface Preperation |  | Each Lot | •Ensure that the substrate is dry and clean of all contaminates. Asphalt pavements shall be virgourously brushed or treated with compressed air to remove dust and loose aggregate. | Omnigrip Technical Data Sheet | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Material Mixing and Installation |  | Each Lot | •The Epoxy Part A should be added to Epoxy Part B at a ratio of 1:1 and mixed using a slow speed for 90 to 120 seconds to obtain a homegenous mix. Add pigment colouring throughout the mixing process. •Once mixed the resin should be immediately applied & spread evenly using a serrated squeegee or notched trowel at an average rate of 1.35 - 1.7 kg/m2. •The resion should self-level, however, the use of a 20mm find nap roller should be used to back roll and level the resin. •The applied resin should receive the aggregate dressing within 10-15 minutes of application ensuring no wet resin is left exposed. | Omnigrip Technical Data Sheet | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Curing |  | Each Lot | •For any surface works on asphalt there must be a minimum curing period of 7-10 days. | Omnigrip Technical Data Sheet | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.