## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-008 - Line Marking | itp |  |  |  |  | ITP-008 - Line Marking
section | 1 - Preliminary Works
checkpoint | 1.1 - Line marking Conformance
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Materials to be used conform with specification
label | REFERENCE DOCUMENTS: Review Materials Sheet
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.3 - Site preparation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Removal of any existing unsound,obsolete or redundant pavement markings. Removal of any foreign material or debris.
label | REFERENCE DOCUMENTS: 721.A06
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.4 - Set-out of Pavement Markings
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings.
label | REFERENCE DOCUMENTS: 721.A09
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.2 - Line marking Installation
label | FREQUENCY: During Construction
label | ACCEPTANCE CRITERIA: Line marking installed as per IFC Drawings
label | REFERENCE DOCUMENTS: 7210
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Glass bead Install
label | FREQUENCY: During line marking works
label | ACCEPTANCE CRITERIA: Glass beads sprinkled/sprayed on to line marking while in a fluid state to ensure embedment. Glass beads to have uniform distribution
label | REFERENCE DOCUMENTS: 72100
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Completion Inspection
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, streats, overlaps, unbeaded areas, tyre marks or other defects. Edges and cuts-offs shall be neat and sharp, and there shall be no visible run-off, overspray, dribbles,splash or spiliage on to the surrounding area, or on to parked or passing vehicles.
label | REFERENCE DOCUMENTS: 7210
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: