## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-050 - Omnigrip Road Surfacing | itp |  |  |  |  | ITP-050 - Omnigrip Road Surfacing
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for Correct Documentation
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.3 - Check Materials
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: Ensure the correct materials have been received including:
label | – Part A Epoxy Compound
label | – Part B Epoxy Harderner
label | – Coloured Aggregate Dressing
label | REFERENCE DOCUMENTS: Receivable Inspection Checklist
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.4 - Setting out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Alignment and location of Omnigrip road sufracing shall be marked in accordace with the appropriate design drawings.
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer, Client
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Monitoring Conditions
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Omnigrip CST must not be applied to wet pavements under any circumstances and suspension of application should be considered:
label | – During periods of dew, drizzle or rain
label | – If the surface temperature exceeds 60°C
label | – If the surface temperature drops below 10°C and is in decline.
label | REFERENCE DOCUMENTS: Omnigrip Technical Data Sheet
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
date | Date Completed:
checkpoint | 2.2 - Asphalt Surface Preperation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure that the substrate is dry and clean of all contaminates. Asphalt pavements shall be virgourously brushed or treated with compressed air to remove dust and loose aggregate.
label | REFERENCE DOCUMENTS: Omnigrip Technical Data Sheet
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.3 - Material Mixing and Installation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The Epoxy Part A should be added to Epoxy Part B at a ratio of 1:1 and mixed using a slow speed for 90 to 120 seconds to obtain a homegenous mix. Add pigment colouring throughout the mixing process.
label | ○ Once mixed the resin should be immediately applied & spread evenly using a serrated squeegee or notched trowel at an average rate of 1.35 - 1.7 kg/m2.
label | ○ The resion should self-level, however, the use of a 20mm find nap roller should be used to back roll and level the resin.
label | ○ The applied resin should receive the aggregate dressing within 10-15 minutes of application ensuring no wet resin is left exposed.
label | REFERENCE DOCUMENTS: Omnigrip Technical Data Sheet
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.3 - Curing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: For any surface works on asphalt there must be a minimum curing period of 7-10 days.
label | REFERENCE DOCUMENTS: Omnigrip Technical Data Sheet
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: