## zres_siteapp
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-015-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0015 - Structural Grout (Pedestals, Bearings, Base-plates & Pockets) | 207a7c00-f02c-48e6-a023-e8b8074b7dd5
checkpoint-group |  |  | section | 1 - Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 1.1 - Product Selection
label | 96a8db7e-a9b1-5449-a208-682005d79168 |  | note | Frequency: Once, for each product, prior to placement of product
label | 1d1ee971-2fb3-56e6-a5e5-1231cf5123c8 |  | note | - - - - - - - - -
label | f5556270-a9e0-5ae8-a209-e996158df961 |  | note | Acceptance Criteria: Product to be selected based on the following criteria:
label | 33277c81-21c4-529a-b867-6557337634c1 |  | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout OR a single component low shrinkage mortar
label | bc845ed2-df37-5a0b-8ba0-8cf20c215ae1 |  | note | ii. have the required strength at 28 days as noted on the IFC drawings.
label | 171c204c-be5d-5f1b-869f-6e8b14decbd6 |  | note | iii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
label | 48c340dd-180d-5468-b623-9f5c1aca0f89 |  | note | Note: Pedestals 200mm or greater shall be constructed from concrete - use the Structural Concrete ITP instead
text | bb93c581-2766-5096-9d49-97c9ea624072 |  | textbox | Enter: Teambinder Material Approval number
label | ea7f6a2e-f25a-5067-abc4-2c4c6c710dff |  | note | - - - - - - - - -
label | 307d1e60-d6ad-5b6d-9c96-2d03bb39c130 |  | note | Reference Documents: IFC Drawings 610.28, 610.33
label | e8f0f788-b333-53ae-b860-02a642b7cae3 |  | note | - - - - - - - - -
label | c85d4eed-c667-5571-801f-9731a48d334c |  | note | Inspection / Test Method: Document Review
label | 34e486f0-6dc9-5975-99dc-4c021977e51e |  | note | - - - - - - - - -
label | b2cff1ad-b261-5da0-b012-dd4e0253a055 |  | note | Record of Conformity: This ITP
label | 9fbf4a19-490c-56eb-a205-3a6725bf5cf3 |  | note | - - - - - - - - -
label | 463acfa1-71b9-5c97-95be-dea72adf8b04 |  | note | AP
label | ef3e09a6-2473-5e62-a0f9-c16155b09842 |  | note | - - - - - - - - -
label | def7dfe7-38f7-51e6-96d9-144a662c50f5 |  | note | Responsibility: Superintendent
checkpoint-status |  |  | checkpoint | 1.2 - Curing Compound
label | ce213761-b024-53ca-a93a-e87b90e85295 |  | note | Frequency: Once, for each product, prior to placement of product
label | f8fcc1d4-36dd-5477-9fc0-8832076691f4 |  | note | - - - - - - - - -
label | c8de2979-eefa-55f8-8b43-83dc485175e2 |  | note | Acceptance Criteria: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | 95f05a9c-b090-51d1-8a09-a1fc10dc3fed |  | note | Note: This may be the same product used for the concrete curing
text | f42c7cf6-46e0-535b-8b81-4d446ca4296f |  | textbox | Enter: Teambinder Material Approval number
label | d99e23f1-5784-5932-a9e0-f4f3582bc843 |  | note | - - - - - - - - -
label | e5579792-77ed-5b1a-b2dd-b98d901fc5d1 |  | note | Reference Documents: 610.23 (d)
label | 7f0add1f-c004-5dfd-a153-f889abb9cf1b |  | note | - - - - - - - - -
label | 42a1a9e6-04b5-52af-b168-342ff5aac380 |  | note | Inspection / Test Method: Document Review
label | f95f60f4-9a74-5063-a66f-125e9cad05cf |  | note | - - - - - - - - -
label | 0c70af3d-788b-53fc-b388-cbb7ecd01b11 |  | note | Record of Conformity: This ITP
label | 67c3e403-0c7f-58c6-9813-bfa7172c50e8 |  | note | - - - - - - - - -
label | 175c7ebf-0ee0-589d-b1c0-da8cf06fdb69 |  | note | AP
label | 8962b859-83ae-55ad-9b6e-9193a0293d32 |  | note | - - - - - - - - -
label | d70c67df-01d3-51d7-9d68-61fe02c91c7f |  | note | Responsibility: Superintendent
checkpoint-group |  |  | section | 2 - Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 2.1 - Curing Methodology (for Concrete, Grout and Mortar)
label | 9408c48b-0c59-58e5-921c-a34fe9951bab |  | note | Frequency: Once, 4 weeks prior to placement of product
label | 32e4c7d7-47d3-5a78-a6b5-a6f8a424477b |  | note | - - - - - - - - -
label | f2d67743-6ade-5d30-93cf-193295610812 |  | note | Acceptance Criteria: Curing methodology/procedure to be submitted for review to the Nominated Authority.
label | 5b1ab5f3-41b5-55d8-bb2a-d003bda207b9 |  | note | Note: This may be the same document used for the concrete curing.
text | c2d4fac6-31b7-512c-9292-3572f468356c |  | textbox | Enter: Teambinder Correspondence Approval number
label | 98789ab3-dd6c-56a6-9e29-727bb12b6dfc |  | note | - - - - - - - - -
label | fdd19a9f-0d17-5f0c-b0fb-26449ee0b549 |  | note | Reference Documents: 610.23 (a)
label | 470608c6-b0b1-5fbd-8291-b2ab9886f82f |  | note | - - - - - - - - -
label | 6a097766-d871-54f8-b2bc-5b8cac2abf6d |  | note | Inspection / Test Method: Document Review
label | eb25ad97-c2c7-5969-ad7d-07b8a5ebac6c |  | note | - - - - - - - - -
label | 82c41bf6-b920-57bf-b722-c6c83bc9f7f1 |  | note | Record of Conformity: ConQA Hold Point Release
label | ee298e7b-750e-537f-989b-e148cbf4bf4b |  | note | - - - - - - - - -
label | bd2e0e24-0ca1-5375-9fa3-9989b887e6b7 |  | note | HP
label | 00fd64f0-de70-5099-a92e-5636bc3dad60 |  | note | - - - - - - - - -
label | c4d9d95e-f7d4-5eae-b93e-089e781175a0 |  | note | Responsibility: Superintendent
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Pre-construction Activities
checkpoint-status |  |  | checkpoint | 3.1 - IFC Drawings
label | 8fa4f507-79d3-5ce9-ab35-d471122c3fbb |  | note | Frequency: Prior to starting Works and at regular intervals
label | c53298ab-1707-5259-8129-72bf8b81db8a |  | note | - - - - - - - - -
label | 3673ce84-1a7d-582f-bd17-4747cbe08deb |  | note | Acceptance Criteria: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 4121c005-4aa6-5a7c-85c5-369a9d441f0b |  | note | - - - - - - - - -
label | d54e5912-23fe-5456-a0e0-001ccef14d53 |  | note | Reference Documents: FH Quality Management Plan
label | 81df0fe4-0c13-5e0d-936b-6552abdc0fa3 |  | note | - - - - - - - - -
label | 4e903f05-46b9-5057-9a3e-8511b808c362 |  | note | Inspection / Test Method: Document Review
label | 0912681b-556d-50c0-af38-b9abcb7639b3 |  | note | - - - - - - - - -
label | 3dcbaa96-5296-5475-904e-0f8b7866a949 |  | note | Record of Conformity: This ITP
label | 621544b2-1884-5dd2-8021-cd423060dc1c |  | note | - - - - - - - - -
label | c93edfd7-c40c-58dd-a954-028751dc51bf |  | note | HP*
label | a5fa3195-d3d1-5274-ba20-6f23c70206e2 |  | note | - - - - - - - - -
label | 4a3b7f40-d2cb-5964-974e-2bb987f8a6fb |  | note | Responsibility: All
checkpoint-status |  |  | checkpoint | 3.2 - Survey Set-out
label | cc5bea48-ed33-5591-b191-bbc6096eabbe |  | note | Frequency: Each element
label | 05b2ef95-a6d3-5540-86dd-880ac9449cde |  | note | - - - - - - - - -
label | a63d0a0b-8fa3-59e3-a22e-ab892e751ce1 |  | note | Acceptance Criteria: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.472 as applicable to the element.
label | 345c10e4-627b-588d-ab6b-e578a11b3093 |  | note | - - - - - - - - -
label | 9c6be423-a1df-5a0a-b985-3722a1affb08 |  | note | Reference Documents: IFC Drawings 610.47 (a) Table 610.472
label | c8e5d3f2-0069-581c-bc64-d48e2817bccc |  | note | - - - - - - - - -
label | d26e3ac3-d60c-5d9a-86ff-f0fd9cc116a8 |  | note | Inspection / Test Method: Measure, Visual
label | 5930283f-b0ed-551c-b20b-9d7c5a621f06 |  | note | - - - - - - - - -
label | d00f2ea1-0ed3-5abe-ad3b-4cc0b1af54e7 |  | note | Record of Conformity: This ITP
label | 52ede7b8-ec8a-5ddc-abbf-4406f725d76d |  | note | - - - - - - - - -
label | d1be0c47-d93d-5722-9f6a-9c6f423d3b29 |  | note | SCP
label | 2263e638-38c1-5a72-84ca-20afd208ebc9 |  | note | - - - - - - - - -
label | 212f5d93-b8d7-5803-b490-608ff56698ac |  | note | Responsibility: Surveyor, SE/PE/SPE
checkpoint-status |  |  | checkpoint | 3.3 - Construction Joint
label | 66ba4577-cc84-5203-afa1-9a1457b7b505 |  | note | Frequency: Each element
label | fd4def8b-9e1a-5347-8ac5-7ffa413be882 |  | note | - - - - - - - - -
label | 1420be8d-40bf-561e-b81b-d0a83ac37fc6 |  | note | Acceptance Criteria: Where required, the concrete substrate is to be roughened / scabbled in accordance with the drawings and or Product TDS.
label | 66916310-514b-57d0-a90b-83b06e4855f1 |  | note | Pedestals shall be rebated to 20mm minimum below top of the crosshead / abutment.
label | 6ad803cb-9782-55e3-874e-165002b4222e |  | note | Where required, any reinforcement shall be adjusted to suit the depth of the pedestal and nominated cover.
label | 92a4d353-4634-5019-8e00-6bc1248c6e73 |  | note | Concrete substrate surface saturated with water for several hours in accordance with the selected product TDS prior to pouring product.
label | e9c695ce-6211-56c5-a5ac-3113fd0ec451 |  | note | - - - - - - - - -
label | 48c1275d-d96d-5d5b-af6b-4654336ecb55 |  | note | Reference Documents: IFC Drawings, Product TDS 610.20 BTN 024 Note 4
label | c51381a6-2764-5a9f-8e17-056968870625 |  | note | - - - - - - - - -
label | 7d9b6a40-1a3a-5f25-afba-9f362e319d23 |  | note | Inspection / Test Method: Measure, Visual
label | f48966e9-7897-50d4-b8e2-15c0d3b87b43 |  | note | - - - - - - - - -
label | 336b2506-1dcc-583e-95dd-aba57993f1c3 |  | note | Record of Conformity: This ITP
label | 0c81e753-90c5-5539-bbdd-922bd8a38719 |  | note | - - - - - - - - -
label | 0055041d-4a73-5521-a150-6b44dac3379b |  | note | IP
label | bd5f43e3-4386-57a6-b4b7-c2e38dffb90c |  | note | - - - - - - - - -
label | a6a234d8-dd9a-584a-b5fc-79b8dc0dad4d |  | note | Responsibility: SE/PE/SPE
checkpoint-group |  |  | section | 4 - Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Formwork Construction & Placement
label | f8cadb90-fa39-50a0-bda1-e72e38d751de |  | note | Frequency: Each element
label | aa0fccd9-cdf4-5f04-9172-95b09de9a8f6 |  | note | - - - - - - - - -
label | 2fd68635-149a-527b-b544-07f32d8626a3 |  | note | Acceptance Criteria: Dimensions in plan as per drawings to achieve the desired grout profile.
label | 1a3bf5ae-60d9-5728-b670-7dfc96437cef |  | note | Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
label | 459b691b-ca08-5a2d-bb12-8c29009dc00f |  | note | Where applicable, any cast in componentry (ferrules, conduit etc.) secure.
label | 0a87c0fd-d6ec-5d33-b1f3-3c941794132d |  | note | - - - - - - - - -
label | 06e32726-3867-50fe-9815-71280647652d |  | note | Reference Documents: IFC Drawings
label | 2c3d27b6-7814-5185-9381-f9fa59bd93f8 |  | note | - - - - - - - - -
label | 0c41ccd5-b6c2-5d0d-bad2-a6d854063511 |  | note | Inspection / Test Method: Measure, Visual
label | 2f3eb685-2be4-5632-96bd-d73a42d21871 |  | note | - - - - - - - - -
label | 98cec6a2-65e0-5956-a73a-bd1dd699715a |  | note | Record of Conformity: This ITP
label | 9a0001a5-a02b-5298-871b-d00c6d401aae |  | note | - - - - - - - - -
label | aa9c7eee-cab9-5671-babb-bdc35b0f83bd |  | note | IP
label | a74683f8-c0e0-573a-8272-0a60ed70df3f |  | note | - - - - - - - - -
label | e9c6ac08-6a4b-50a1-a7ba-209dba15bcc0 |  | note | Responsibility: SE/PE/SPE
checkpoint-status |  |  | checkpoint | 4.2 - Pre-pour Inspection
label | 3e56031f-aa37-5309-8105-442ac634dae6 |  | note | Frequency: Each element
label | 20571963-8eb0-52c5-b202-2be59ce6a07c |  | note | - - - - - - - - -
label | 6fc53705-b0db-55e9-b7b1-4b81177fa6bf |  | note | Acceptance Criteria: Concrete substrate surface moisture condition as per the Product's TDS, with no ponding of water.
label | 3c14f78e-01f4-5e3b-9317-01501e9f8832 |  | note | Formwork location and RLs comply.
label | 7c72790d-382e-57b9-92c8-8abcad7da0bc |  | note | Where applicable, any reinforcement is clean and has the required cover.
label | 746d59b0-2ae2-5d68-9f82-0fed14c22ef4 |  | note | - - - - - - - - -
label | ea41c7d6-2d72-5c15-9527-ecf16baed542 |  | note | Reference Documents: IFC Drawings, Product TDS 610.20
label | 93c52d92-5563-52cb-92ff-a0db520ff57f |  | note | - - - - - - - - -
label | a2ec8553-c7d1-5f95-a68c-81bca6736061 |  | note | Inspection / Test Method: Measure, Visual
label | bc083cf4-3e49-5a70-a395-13bbd695bd2f |  | note | - - - - - - - - -
label | 510b25ed-0609-5ec1-bf4f-1a3b0dcb2729 |  | note | Record of Conformity: This ITP
label | f0471237-1716-5cc3-a18b-bee739deb544 |  | note | - - - - - - - - -
label | 61c92bba-56de-5963-8043-9f7c7681b67d |  | note | IP
label | e49862ee-4992-549f-90b2-41a6ebbf0d03 |  | note | - - - - - - - - -
label | 549c4fb7-ca6a-5d90-9c34-e170aaa5e7f1 |  | note | Responsibility: SE/PE/SPE
checkpoint-status |  |  | checkpoint | 4.3 - Weather Conditions
label | f53bd107-a65e-5231-9ec8-0d4e85e9a3c1 |  | note | Frequency: Each element
label | 18990355-abd1-5550-8922-5bcd9ad88f44 |  | note | - - - - - - - - -
label | 27d7f645-e56e-56c6-adbf-b198808a061b |  | note | Acceptance Criteria: All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | ae07df73-d5ad-5874-8ff2-5b59bb46ef83 |  | note | The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | fa286591-360e-5215-ac24-64cb672b1c37 |  | note | Record: Required information on the Grout Pour Record.
label | 082e482c-d75e-5b41-ba67-57880f8601fa |  | note | - - - - - - - - -
label | fe2ee8eb-d403-591e-8580-7aae4e2ddd08 |  | note | Reference Documents: 610.17, 610.17 (a) & (e) Table 610.171
label | 8ae50c65-f70d-5edf-b933-fc5f908da584 |  | note | - - - - - - - - -
label | 25129b16-d29e-585b-9ba0-d899fbc83ec5 |  | note | Inspection / Test Method: Measure, Visual
label | a1fe6d5d-c084-5fa3-bbe8-807fa7bddbaa |  | note | - - - - - - - - -
label | 25f85d97-9009-5f1a-9cf0-5bf23a7fb355 |  | note | Record of Conformity: This ITP
label | b7c5fe68-37a1-5d28-a45d-6361066a6e8f |  | note | - - - - - - - - -
label | d77fef3e-1e60-531d-9dda-5019ad463a63 |  | note | IP
label | 287d2abe-d58a-5467-a35f-2fdbbdfc9a25 |  | note | - - - - - - - - -
label | de094134-b7e1-5ffc-b7ad-574a03eedced |  | note | Responsibility: Foreman, SE/PE/SPE
checkpoint-status |  |  | checkpoint | 4.4 - Mixing Product
label | aa6c85e3-ee3f-535f-91b3-eefe6042644f |  | note | Frequency: Each batch
label | 29f7f6c2-2bd3-5c8f-8eb6-06bfb1dadbca |  | note | - - - - - - - - -
label | b8206124-6ba2-52c1-918f-1392ca153aa5 |  | note | Acceptance Criteria: Size of mixer should match the application.
label | d1568823-58e5-56c9-b992-9694acbae1df |  | note | Only whole bags to be mixed with potable water.
label | 418c0f33-d1df-5020-a4fa-d9b629a17112 |  | note | Volume of water matches the required amount for flowable consistency and accurately measured.
label | c74832d4-fc75-5dbc-863b-cb18cbf58185 |  | note | Product poured into the mixer slowly.
label | 488bd572-6cbd-5963-99a2-47897a24ad41 |  | note | Mixing time as per TDS so that a smooth, even consistency is obtained.
label | a90a207d-be81-51e3-81bc-82eb6e52f7a7 |  | note | Enter: Required information on the Grout Pour Record.
label | cc05c78f-bffa-5524-b174-a5027e7c4f5c |  | note | - - - - - - - - -
label | 0c5177b7-d773-59d1-9018-5a177e9bb28b |  | note | Reference Documents: Product TDS 610.28
label | 0a7aefaf-0acd-5d9a-95b5-5717f2d70292 |  | note | - - - - - - - - -
label | aab3ee36-c743-5bbd-895a-524aac245dfe |  | note | Inspection / Test Method: Measure, Visual
label | 56b7edf1-956a-5300-8f08-6682fcab717a |  | note | - - - - - - - - -
label | 66b7eb89-356c-5895-b7e9-5a30a89c840c |  | note | Record of Conformity: This ITP
label | 5dae6d46-a8eb-5cb5-8ed9-8b34969678e4 |  | note | - - - - - - - - -
label | 48e498b0-1d6c-5d20-933a-141609eee6c5 |  | note | IP
label | 8ac1d01f-21c2-56ac-b778-e3165b190287 |  | note | - - - - - - - - -
label | cf92efab-c191-5b8a-986d-5460ce73fa0c |  | note | Responsibility: SE/PE/SPE
checkpoint-status |  |  | checkpoint | 4.5 - Product Testing - Compressive Strength Cubes
label | 4c0f60c0-b0be-5a41-b0f5-9a5cd9121f6e |  | note | Frequency: Each element
label | f84669fc-eec5-5ab1-85e3-48991bef3d62 |  | note | - - - - - - - - -
label | 747fa074-c97b-537f-831c-fd546b4dea85 |  | note | Acceptance Criteria: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | 594fd0a8-ef40-5a5e-8eb7-80152fe95b1f |  | note | Testing is be in accordance with the following frequencies:
label | 2daa7c93-676a-54b8-ba4a-c1d93eec4dcd |  | note | First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | 6549e62d-67a9-52db-a84d-363f964d002f |  | note | Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | 68ff6541-9e74-528e-a7e3-ecb693ddf52a |  | note | Enter: Required information on the Grout Pour Record.
label | 6a077721-88dd-5549-9e8d-4c9586d6af45 |  | note | - - - - - - - - -
label | ebcf4191-a92d-5637-8248-2223afa525ea |  | note | Reference Documents: 610.28, 610.33
label | 6380dfaf-6340-5956-9467-961ea7a6db9c |  | note | - - - - - - - - -
label | 86808098-df39-5d44-9d72-96823e737858 |  | note | Inspection / Test Method: Test
label | 78b5ec90-575e-5ebc-b414-652469f2f8dc |  | note | - - - - - - - - -
label | a06ccb25-0a96-5e19-b743-2c18a77a3903 |  | note | Record of Conformity: This ITP
label | b7c921c1-b68b-5465-b73c-9cf3f424573b |  | note | - - - - - - - - -
label | 34abd21f-4648-5e60-b884-3102a7e4e5c4 |  | note | IP
label | 9559e8b4-d576-59a0-b82f-0bfa6aa09df6 |  | note | - - - - - - - - -
label | 5fcfe6d3-5d02-5898-88f8-87237b1d0f15 |  | note | Responsibility: Tester, Sub-contractor, SE/PE/SPE
checkpoint-status |  |  | checkpoint | 4.6 - Placement & Compaction
label | 415e796d-e32e-5bcb-85f3-ddd2fcf9fde0 |  | note | Frequency: Each element
label | 5125887b-dbcd-5eaf-b8b6-0bcdca10d3b4 |  | note | - - - - - - - - -
label | ca2bb08e-4072-521a-869b-e6583f9535ac |  | note | Acceptance Criteria: All batches are traceable.
label | 1c8cff4d-8ac5-5ae2-9688-45b210e73875 |  | note | Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | acf6caea-c295-5b24-9190-e6e34159f3ca |  | note | Product should flow to all areas and self consolidate.
label | a17e4575-b5e2-5e76-be60-6cdf4891bbbc |  | note | Product that stiffens or is showing signs of stiffening shall not be used.
label | 2e65fb4a-c27f-5363-99ba-c9a7509ee913 |  | note | Enter: Required information on the Grout Pour Record
label | 0f8ff846-635c-590b-94c2-d473e1459582 |  | note | - - - - - - - - -
label | dcc68ade-69ca-5ddf-a1e9-e34028944ed2 |  | note | Reference Documents: Product TDS
label | b2a447f5-1302-5c2d-b733-38641a85c382 |  | note | - - - - - - - - -
label | 09643902-136e-50b0-bedf-9b9710c7594f |  | note | Inspection / Test Method: Visual
label | 1dea3499-0033-54aa-a8c4-51a3d77d6f1e |  | note | - - - - - - - - -
label | e84a71d8-d452-525d-b232-7319155b0770 |  | note | Record of Conformity: This ITP
label | e964ce07-0385-5cb6-91d3-27245cfbe178 |  | note | - - - - - - - - -
label | ea03971b-6c6a-5bdf-a2fd-7ca0e1badbfa |  | note | IP
label | abda90f9-c6d0-594c-9ac0-3d381c2338be |  | note | - - - - - - - - -
label | 2e98874a-af7e-5a12-b370-7df8fb4926cb |  | note | Responsibility: Foreman, SE/PE/SPE
checkpoint-status |  |  | checkpoint | 4.7 - Surface Finishes
label | 3dca5697-cbaf-5d4a-a874-6c51f2f3b2bb |  | note | Frequency: Each element
label | c97b4a3c-91b4-55f2-a2a5-800b4e4ee61a |  | note | - - - - - - - - -
label | 6b34bb36-d313-528a-8bc9-d2c73115c6d5 |  | note | Acceptance Criteria: Surface to match the IFC drawings.
label | 671c17b2-c50f-5729-8062-ba6b03ccf1c4 |  | note | Where not shown:
label | ab0a9037-89a9-5ce1-9a63-3655dd62ee1b |  | note | Pedestals:
label | bafcff9e-d3f8-5360-a848-6ea4031d7762 |  | note | Surface to be finished flat with a surface roughness of an amplitude of approximately 0.5mm - 1.5mm, likened to 40 grit sandpaper.
label | 8f6e5b50-379c-56e5-9ac4-0cad8a35fa6c |  | note | Bearings, base-plates and pockets:
label | 8dd71918-5a06-5780-a914-ff1dca5bdb19 |  | note | Surface to match the the surrounding surfaces using a smooth trowel finish where exposed.
label | f8e8517d-b23a-59a9-a62e-3f0ca0b4959a |  | note | - - - - - - - - -
label | a75e8e56-ded6-5846-8935-b6e6e4d4c691 |  | note | Reference Documents: 610.28
label | 60fe69ee-80ae-551c-baa0-b3a159c4b31f |  | note | - - - - - - - - -
label | 9584907f-3ae2-5c7d-8f4c-4a2e4bf4a8a6 |  | note | Inspection / Test Method: Visual
label | b4712f42-5730-55ef-8914-4079784dcf61 |  | note | - - - - - - - - -
label | 01be13c9-084d-581c-885a-ad0bda61e3e0 |  | note | Record of Conformity: This ITP
label | 4e25f484-94e8-56df-a5b9-e9e8e25b639e |  | note | - - - - - - - - -
label | 36c8c8c4-06d2-57af-b5f1-7bc09236da61 |  | note | IP
label | d9b9ad9f-d8ef-5910-9e3a-fd9051a37a63 |  | note | - - - - - - - - -
label | da168fe5-2335-507b-82f8-bc6e899f6761 |  | note | Responsibility: Foreman, SE/PE/SPE
checkpoint-status |  |  | checkpoint | 4.8 - Curing
label | aedb6d39-9c31-5928-87f9-cbd10e966a82 |  | note | Frequency: Each element
label | bb4dcbad-ecf5-5ef9-a22a-0cac8d98d751 |  | note | - - - - - - - - -
label | 34620ff7-4804-54a0-840b-a17deec160a7 |  | note | Acceptance Criteria: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | faead20a-0be2-5d5e-86b8-9db32b08ee24 |  | note | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | 638b5d70-c927-579b-9717-1244d3439dd9 |  | note | - - - - - - - - -
label | c96b68c7-9e96-51d4-ac61-eeb6f05dab6f |  | note | Reference Documents: Curing Methodology 610.23 Table 610.231
label | aeab0905-a7f1-52a8-96ad-558417cba41d |  | note | - - - - - - - - -
label | 46d2240a-5093-5142-8dbe-a1c586cd9298 |  | note | Inspection / Test Method: Visual
label | ca63ed8d-87c0-5f1f-8e32-de31fb4a184b |  | note | - - - - - - - - -
label | 69f75438-5a10-5018-b012-89130908a1f6 |  | note | Record of Conformity: This ITP
label | e31f6940-bfeb-534f-9547-06d19eaf2d15 |  | note | - - - - - - - - -
label | 209d8fd4-b418-5343-af15-978ccdd4b1e3 |  | note | IP
label | 9c1ab900-7210-5b80-a35e-49cc117cf5ef |  | note | - - - - - - - - -
label | 02e00457-a118-5ab1-837d-fde303dbc88c |  | note | Responsibility: Foreman, SE/PE/SPE
checkpoint-group |  |  | section | 5 - Post-construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Compressive Strength Test Results
label | e8eafaba-8c45-5f54-817f-dd843cd4e71e |  | note | Frequency: Each cube
label | 87a8e040-5133-5808-a1f7-9ba80e285225 |  | note | - - - - - - - - -
label | 3b5c52d8-a4c8-569e-81a0-7ba0748f7f83 |  | note | Acceptance Criteria: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | 656b523f-4d50-5184-bd15-c0556fa3f01e |  | note | 28 day compressive strength per sample comply with the design strength.
label | dd35e463-8321-583c-85d1-93caeea05dc1 |  | note | Attach: Compressive Strength Test Results
label | a2d0f152-8e2e-514d-936c-67386cc1e857 |  | note | - - - - - - - - -
label | b385398e-9330-5102-aa5c-2244e8d6bd28 |  | note | Reference Documents: IFC Drawings, Product TDS 610.28, 610.33
label | 6717a42f-7a75-5af8-bfc5-8c102ef3bbd5 |  | note | - - - - - - - - -
label | ee716392-da84-5629-b822-a2a297e0237e |  | note | Inspection / Test Method: Document Review
label | 566475fd-adce-5723-8b71-35babf826884 |  | note | - - - - - - - - -
label | 1b126051-4380-52ec-81cf-443f7b464024 |  | note | Record of Conformity: This ITP
label | 20aeb793-2f8c-5561-b898-b25d3b47053c |  | note | - - - - - - - - -
label | a6877787-8958-5512-9fb9-c23965bf7398 |  | note | TP
label | d644b832-5856-5fe7-8341-d073e8c5499e |  | note | - - - - - - - - -
label | e55b69fe-05a1-59b6-82a5-4d944cac2c05 |  | note | Responsibility: SE/PE/SPE
checkpoint-status |  |  | checkpoint | 5.2 - As-built Survey
label | c254772a-5f17-5fb2-917a-702059acf0fc |  | note | Frequency: Each element
label | 7fb1427d-9e71-50bf-8ed2-a2769ba9e84b |  | note | - - - - - - - - -
label | 393bf89a-c88b-5869-8b23-f10d2c789506 |  | note | Acceptance Criteria: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances below:
label | 617d5422-0e55-511e-b6d6-607ab0108e7f |  | note | Reduced level ±2.5mm
label | 2b936f5f-dd59-5513-bcf5-2629074413ad |  | note | Variation from grade across the width of individual pedestals shall not exceed 1 in 200
label | 0b4554c9-9400-54c2-a087-d1e70f20ed9c |  | note | Deviation from flat surface ±1mm
label | 79d1498c-47be-50fb-90fb-ca478c64297b |  | note | Attach: Survey As-builts / Survey Report
label | 104adeef-b1a0-56e1-9482-81e3ef6c9561 |  | note | - - - - - - - - -
label | e2c7fd4f-fcbf-5d3b-a78c-381f50499b76 |  | note | Reference Documents: IFC Drawings 610.47 (a) Table 610.472
label | 212b6ec1-4b1f-5157-87c7-d627845fe7c7 |  | note | - - - - - - - - -
label | 3f4d9721-1cdc-5ffc-82ad-6624c2c04a52 |  | note | Inspection / Test Method: Document Review
label | 6b2794a6-b395-5bf5-bcf3-2c04a27a7e29 |  | note | - - - - - - - - -
label | fb050edd-6968-5723-9488-a7ce1a5dc55d |  | note | Record of Conformity: This ITP
label | 023882ba-4d99-55fc-a19d-e435c0020d76 |  | note | - - - - - - - - -
label | 4e0d7c7e-f0c9-5027-9e4f-cca13ebe535a |  | note | SCP
label | fa9292cc-de26-5387-ae03-e9f1f359d22c |  | note | - - - - - - - - -
label | 8b3a2bca-ef3a-5724-8018-e76284189e34 |  | note | Responsibility: Surveyor, PE/SE/SPE
checkpoint-status |  |  | checkpoint | 5.3 - Non-conformance Report (NCR) Closure
label | 4333a2f0-6dcf-53fd-a89c-29bd5203b2e2 |  | note | Frequency: Once, prior to closure of this lot / element / Work area
label | 06de9df4-a380-58c2-889f-5f89001e17b6 |  | note | - - - - - - - - -
label | 0a2dfd73-a3a1-584a-ac74-01c9e137abe6 |  | note | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | f0376ff8-11d8-5ab9-90a3-a60a99a7b383 |  | note | - - - - - - - - -
label | 531e15e8-17a2-53e1-9c82-00d2267f9a89 |  | note | Reference Documents: FH Quality Management Plan
label | 6ad508df-a604-5e7b-aced-554ee92c4acf |  | note | - - - - - - - - -
label | 4b347384-425a-52d3-905f-509ba64bc14a |  | note | Inspection / Test Method: Document Review
label | be43b404-4db1-5098-9878-e04fbc251ed2 |  | note | - - - - - - - - -
label | 28e6dd18-356c-5e60-af9d-29385933b700 |  | note | Record of Conformity: This ITP
label | fae66785-2a87-5c80-84aa-7d0824b3d98e |  | note | - - - - - - - - -
label | 25a19040-85b6-5f23-aa82-7e4c9374ef1d |  | note | HP*
label | fc6a91c6-9e10-5d5d-9b55-bb14f8d6b460 |  | note | - - - - - - - - -
label | 089c5a6e-6670-5930-a4ce-a67eb1ea2694 |  | note | Responsibility: PE/SE/SPE
checkpoint-status |  |  | checkpoint | Final Inspection
label | 4a100126-b016-580c-b085-9a54fde1061a |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | fb3e7cb5-feb9-5a02-ac6f-ddcb25f7dabc |  | textbox | Print Name:
text | d6b35da7-c0fe-5465-9118-c15828dd35f2 |  | textbox | Position:
date | 6f87a7d7-aac4-5658-ac6b-a1ea6add2d95 |  | date | Date:
date | 155fc95b-79dc-5ee3-8f2c-2ed4ba79d181 |  | date | Work Completed On